## Week 37-38
Report covers outages commencing/returning/spanning the period: 12/09/2022 - 25/09/2022
Outages commencing/returning in Week 37
OUTAGE ID | PLANT |  | Week 37 | [6 empty] | Week 38
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
TO-22-SNU-110SA1-2CB-02 | SNUGBOROUGH 110SA1-2CB | bar: Week 37 Mo 12
TO-22-AD-RAF-1-02 | AGHADA RAFFEEN | bar: Week 37 Mo 12 to Week 37 Fr 16
TO-22-110 kV A1 @ ARV-02 | ARVA 110 kV A1 | bar: Week 37 Mo 12
TO-22-110 kV B1 @ ARV-02 | ARVA 110 kV B1 | bar: Week 37 Mo 12
TO-22-ARV-SKL-1-03 | ARVA SHANKILL 1 | bar: Week 37 Mo 12
TO-22-110 kV A2 @ BYH-05 | BALLYNAHULLA 110 kV A2 | bar: Week 37 Mo 12
TO-22-110 kV B2 @ BYH-05 | BALLYNAHULLA 110 kV B2 | bar: Week 37 Mo 12
TO-22-220 kV A2 @ BYH-02 | BALLYNAHULLA 220 kV A2 | bar: Week 37 Mo 12
TO-22-220 kV B2 @ BYH-02 | BALLYNAHULLA 220 kV B2 | bar: Week 37 Mo 12
TO-22-BYH-T2102-03 | BALLYNAHULLA T2102 | bar: Week 37 Mo 12
TO-22-CF-CL-1-01 | CATHALEENS FALL CLIFF | bar: Week 37 Mo 12
TO-22-CL-T101-02 | CLIFF T101 | bar: Week 37 Mo 12
TO-22-CL-T102-03 | CLIFF T102 | bar: Week 37 Mo 12
TO-22-CRO-110SA1-01 | COOLROE 110SA1 | bar: Week 37 Mo 12
TO-22-CRO-110SA2-01 | COOLROE 110SA2 | bar: Week 37 Mo 12
TO-22-CRO-T121-01 | COOLROE T121 | bar: Week 37 Mo 12
TO-22-110 kV A2 @ FIN GIS-06 | FINGLAS GIS 110 kV A2 | bar: Week 37 Mo 12
TO-22-110 kV A4 @ FIN GIS-01 | FINGLAS GIS 110 kV A4 | bar: Week 37 Mo 12
TO-22-FIN GIS-110SA2-4CB-07 | FINGLAS GIS 110SA2-4CB | bar: Week 37 Mo 12
TO-22-KRA-RAF-1-05 | KNOCKRAHA RAFFEEN | bar: Week 37 Mo 12 to Week 37 Fr 16
TO-22-KUR-NAV-1-01 | KNOCKUMBER NAVAN | bar: Week 37 Mo 12
TO-22-KUR-T3-01 | KNOCKUMBER T3 | bar: Week 37 Mo 12
TO-22-KUR-T4-01 | KNOCKUMBER T4 | bar: Week 37 Mo 12
TO-22-SKL-110SA1-02 | SHANKILL 110SA1 | bar: Week 37 Mo 12
TO-22-SKL-110SA2-02 | SHANKILL 110SA2 | bar: Week 37 Mo 12
TO-22-SKL-M/CAP2-02 | SHANKILL M/CAP2 | bar: Week 37 Mo 12
TO-22-WHI-CKB-T101-01 | WHITEGATE CKB-T101 | bar: Week 37 Mo 12
TO-22-TB-220K1-2-01 | TARBERT 220K1-2 | bar: Week 37 Mo 12; Week 37 Sa 17 to Week 37 Su 18
TO-22-TB-T2004-01 | TARBERT T2004 | bar: Week 37 Mo 12; Week 37 Sa 17 to Week 37 Su 18
TO-22-TB-T2101-02 | TARBERT T2101 | bar: Week 37 Mo 12; Week 37 Sa 17 to Week 37 Su 18
TO-22-110 kV A2 @ KPG-02 | KILPADDOGE 110 kV A2 | bar: Week 37 Mo 12; Week 37 Sa 17 to Week 38 Mo 19
TO-22-110 kV B2 @ KPG-01 | KILPADDOGE 110 kV B2 | bar: Week 37 Mo 12; Week 37 Sa 17 to Week 38 Mo 19
TO-22-220 kV A2 @ KPG-02 | KILPADDOGE 220 kV A2 | bar: Week 37 Mo 12; Week 37 Sa 17 to Week 38 Mo 19
TO-22-220 kV B2 @ KPG-02 | KILPADDOGE 220 kV B2 | bar: Week 37 Mo 12; Week 37 Sa 17 to Week 38 Mo 19
TO-22-KPG-T2102-02 | KILPADDOGE T2102 | bar: Week 37 Mo 12; Week 37 Sa 17 to Week 38 Mo 19
TO-22-ATY-CLW-1-01 | ATHY CARLOW | bar: Week 37 Mo 12; Week 37 Sa 17 to Week 38 Mo 26
TO-22-DSN-T4201-02 | DUNSTOWN T4201 | bar: Week 37 Mo 12; Week 37 Sa 17 to Week 38 Mo 26
TO-22-110 kV B1 @ MAY-02 | MAYNOOTH 110 kV B1 | bar: Week 37 Mo 12; Week 37 Sa 17 to Week 38 Mo 26
TO-22-MAY-TH-1-01 | MAYNOOTH TURLOUGH HILL | bar: Week 37 Mo 12; Week 37 Sa 17 to Week 38 Mo 26
TO-22-CAH-TIP-1-02 | CAHIR TIPPERARY | bar: Su 11 to Week 37 Mo 12
TO-22-GGO-RAF-1-02 | GLANAGOW RAFFEEN | bar: Su 11 to Week 37 Mo 12
TO-22-CLA-DMY-1-01 | CLASHAVOON DUNMANWAY
TO-22-110 kV B1 @ CBT-03 | CASTLEBAGOT 110 kV B1
TO-22-110 kV B2 @ CBT-01 | CASTLEBAGOT 110 kV B2
TO-22-CBT-110SB1-2CB-03 | CASTLEBAGOT 110SB1-2CB
TO-22-LSN-THU-1-03 | LISHEEN THURLES
TO-22-110 kV B1/B2 @ FLA-02 | FLAGFORD 110 kV B1/B2 | bar: Week 37 Sa 17 to Week 38 Mo 26
TO-22-FLA-110K1-2-01 | FLAGFORD 110K1-2 | bar: Week 37 Sa 17 to Week 38 Mo 26
TO-22-IKE,T-THU-1-01 | IKERRIN tee THURLES | bar: Week 37 Sa 17 to Week 38 Mo 26
TO-22-LSN-110SA1-2-01 | LISHEEN 110SA1-2 | bar: Week 37 Sa 17 to Week 38 Mo 26
TO-22-LSN-110SA2-4-01 | LISHEEN 110SA2-4 | bar: Week 37 Sa 17 to Week 38 Mo 26
TO-22-LSN-T122-01 | LISHEEN T122 | bar: Week 37 Sa 17 to Week 38 Mo 26
TO-22-LSN-T142-01 | LISHEEN T142 | bar: Week 37 Sa 17 to Week 38 Mo 26
TO-22-LSN-THU-1-01 | LISHEEN THURLES | bar: Week 37 Sa 17 to Week 38 Mo 26
TO-22-THU-110SA1-2CB-01 | THURLES 110SA1-2CB | bar: Week 37 Sa 17 to Week 38 Mo 26
TO-22-THU-CAP2-01 | THURLES CAP2 | bar: Week 37 Sa 17 to Week 38 Mo 26
TO-22-THU-T142-01 | THURLES T142 | bar: Week 37 Sa 17 to Week 38 Mo 26
TO-22-GOR-110K1-2-01 | GORMAN 110K1-2 | bar: Su 11 to Week 37 Mo 12
TO-22-DMY-110SA1-2CB-01 | DUNMANWAY 110SA1-2CB | bar: Week 37 We 14
TO-22-110 kV A2 @ PA-01 | POLLAPHUCA 110 kV A2
TO-22-PA-T101-04 | POLLAPHUCA T101
Report covers outages commencing/returning/spanning the period: 12/09/2022 - 25/09/2022
Outages commencing/returning in Week 37
OUTAGE ID | PLANT | Week 37 Mo 12: Week 37; Week 38 Mo 19: Week 38
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
TO-22-110 kV A1/A2 @ SH-01 | SHANNONBRIDGE 110 kV A1/A2 | bar: Week 37 We 14
TO-22-110 kV B1/B2 @ SH-01 | SHANNONBRIDGE 110 kV B1/B2 | bar: Week 37 We 14
TO-22-220 kV A1/A2 @ SH-01 | SHANNONBRIDGE 220 kV A1/A2 | bar: Week 37 We 14
TO-22-220 kV B1/B2 @ SH-01 | SHANNONBRIDGE 220 kV B1/B2 | bar: Week 37 We 14
TO-22-KTN-T102-01 | KILLOTERAN T102 | bar: Week 37 Th 15 to Week 37 Fr 16
TO-22-SLI-110SA1-2CB-01 | SLIGO 110SA1-2CB | bar: Week 37 Fr 16
TO-22-SLI-CAP1-01 | SLIGO CAP1 | bar: Week 37 Fr 16
TO-22-SLI-SRA-1-02 | SLIGO SRANANAGH 1 | bar: Week 37 Fr 16
TO-22-110 kV A2 @ GI-01 | GREAT ISLAND 110 kV A2 | bar: Week 37 Fr 16 to Week 37 Su 18
TO-22-GI-WAT-2-01 | GREAT ISLAND WATERFORD 2 | bar: Week 37 Fr 16 to Week 37 Su 18
TO-22-SLI-CAP1-02 | SLIGO CAP1 | bar: Week 37 Fr 16 to Week 38 Th 22
TO-22-SKL-T142-01 | SHANKILL T142 | bar: Su 11 to Week 37 Fr 16
TO-22-SLI-T141-01 | SLIGO T141 | bar: Su 11 to Week 37 Fr 16
TO-22-GI-WEX-1-01 | GREAT ISLAND WEXFORD | bar: Su 11 to Week 37 Su 18
Outages commencing/returning in Week 38
OUTAGE ID | PLANT | Week 37 Mo 12: Week 37; Week 38 Mo 19: Week 38
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
TO-22-AUG-CFM-2-01 | AUGHINISH CASTLEFARM 2 | bar: Week 38 Mo 19
TO-22-CFM-T102-02 | CASTLEFARM T102 | bar: Week 38 Mo 19
TO-22-KRA-MID-1-04 | KNOCKRAHA MIDLETON | bar: Week 38 Mo 19 to Week 38 Th 22
TO-22-ARK-BOG-1-01 | ARKLOW BANOGE | bar: Week 38 Mo 19 to Week 38 Fr 23
TO-22-BOG-110SA1-02 | BANOGE 110SA1 | bar: Week 38 Mo 19 to Week 38 Fr 23
TO-22-BOG-110SA2-01 | BANOGE 110SA2 | bar: Week 38 Mo 19 to Week 38 Fr 23
TO-22-BOG-T122-01 | BANOGE T122 | bar: Week 38 Mo 19 to Week 38 Fr 23
TO-22-CFM-T102-01 | CASTLEFARM T102 | bar: Week 38 Mo 19 to Week 38 Fr 23
TO-22-110 kV A2 @ CDU-03 | CORDUFF 110 kV A2 | bar: Week 38 Mo 19 to Week 38 Fr 23
TO-22-110 kV B2 @ CDU-03 | CORDUFF 110 kV B2 | bar: Week 38 Mo 19 to Week 38 Fr 23
TO-22-220 kV A1 @ DSN-01 | DUNSTOWN 220 kV A1 | bar: Week 38 Mo 19 to Week 38 Fr 23
TO-22-220 kV B1 @ DSN-01 | DUNSTOWN 220 kV B1 | bar: Week 38 Mo 19 to Week 38 Fr 23
TO-22-110 kV A3 @ FIN GIS-02 | FINGLAS GIS 110 kV A3 | bar: Week 38 Mo 19 to Week 38 Fr 23
TO-22-110 kV A5 @ FIN GIS-03 | FINGLAS GIS 110 kV A5 | bar: Week 38 Mo 19 to Week 38 Fr 23
TO-22-FIN GIS-110SA3-5CB-02 | FINGLAS GIS 110SA3-5CB | bar: Week 38 Mo 19 to Week 38 Fr 23
TO-22-CLG-CDU-1-02 | CLOGHRAN CORDUFF | bar: Week 38 Mo 19 to Week 38 Mo 26
TO-22-110 kV A4 @ CBT-01 | CASTLEBAGOT 110 kV A4 | bar: Su 11 to Week 38 Mo 19
TO-22-110 kV B4 @ CBT-02 | CASTLEBAGOT 110 kV B4 | bar: Su 11 to Week 38 Mo 19
TO-22-CBT-110K1-01 | CASTLEBAGOT 110K1 | bar: Su 11 to Week 38 Mo 19
TO-22-CBT-110K4-01 | CASTLEBAGOT 110K4 | bar: Su 11 to Week 38 Mo 19
TO-22-CBT-110SA2-4CB-02 | CASTLEBAGOT 110SA2-4CB | bar: Su 11 to Week 38 Mo 19
TO-22-CBT-110SB2-4CB-02 | CASTLEBAGOT 110SB2-4CB | bar: Su 11 to Week 38 Mo 19
TO-22-GAL-SAL-1-01 | GALWAY SALTHILL | bar: Su 11 to Week 38 Mo 19
TO-22-ISH-T2001-03 | IRISHTOWN T2001 | bar: Su 11 to Week 38 Mo 19
TO-22-KPG-TB-1-01 | KILPADDOGE TARBERT 1 | bar: Su 11 to Week 38 Mo 19
TO-22-220 kV A1 @ TB-01 | TARBERT 220 kV A1 | bar: Su 11 to Week 38 Mo 19
TO-22-220 kV B1 @ TB-01 | TARBERT 220 kV B1 | bar: Su 11 to Week 38 Mo 19
TO-22-BRT-T224-01 | BRACETOWN T224 | bar: Week 38 Tu 20
TO-22-110 kV A1 @ KPG-01 | KILPADDOGE 110 kV A1 | bar: Week 38 Tu 20 to Week 38 Fr 23
TO-22-110 kV A2 @ KPG-01 | KILPADDOGE 110 kV A2 | bar: Week 38 Tu 20 to Week 38 Fr 23
TO-22-KPG-110SA1-2CB-01 | KILPADDOGE 110SA1-2CB | bar: Week 38 Tu 20 to Week 38 Fr 23
TO-22-WEX-CAP2-01 | WEXFORD CAP2 | bar: Week 38 Tu 20 to Week 38 Fr 23
TO-22-WEX-CAP4-01 | WEXFORD CAP4 | bar: Week 38 Tu 20 to Week 38 Fr 23
TO-22-GAL-KNY-1-01 | GALWAY KNOCKRANNY | bar: Week 38 Tu 20 to Week 38 Mo 26
TO-22-GAL-T141-01 | GALWAY T141 | bar: Week 38 Tu 20 to Week 38 Mo 26
TO-22-TB-T2004-02 | TARBERT T2004 | bar: Week 38 Tu 20 to Week 38 Mo 26
TO-22-CRO-KBY-1-04 | COOLROE KILBARRY | bar: Su 11 to Week 38 Tu 20
TO-22-110 kV A1 @ KRA-01 | KNOCKRAHA 110 kV A1 | bar: Su 11 to Week 38 Tu 20
TO-22-KRA-T2101-01 | KNOCKRAHA T2101 | bar: Su 11 to Week 38 Tu 20
TO-22-110 kV A1/A2 @ BYH-01 | BALLYNAHULLA 110 kV A1/A2 | bar: Week 38 We 21
TO-22-110 kV B1/B2 @ BYH-01 | BALLYNAHULLA 110 kV B1/B2 | bar: Week 38 We 21
TO-22-220 kV A1/A2 @ BYH-01 | BALLYNAHULLA 220 kV A1/A2 | bar: Week 38 We 21
Report covers outages commencing/returning/spanning the period: 12/09/2022 - 25/09/2022
Outages commencing/returning in Week 38
OUTAGE ID | PLANT | Week 37 Mo 12: Week 37; Week 38 Mo 19: Week 38
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
TO-22-220 kV B1/B2 @ BYH-01 | BALLYNAHULLA 220 kV B1/B2
TO-22-CRO-T122-01 | COOLROE T122
TO-22-CHA-MAL-1-01 | CHARLEVILLE MALLOW
TO-22-AUG-110SA1-2CB-01 | AUGHINISH 110SA1-2CB
TO-22-BK-MOY-1-02 | BELLACORICK MOY
TO-22-MOY-110SA1-2CB-01 | MOY 110SA1-2CB
TO-22-MOY-CAP2-01 | MOY CAP2
TO-22-MOY-TAW-2-02 | MOY TAWNAGHMORE 2
TO-22-DER-T1/T2-01 | DERRYIRON RHODE T1/T2
TO-22-SLI-T142-01 | SLIGO T142 | bar: Week 38 Fr 23 to Week 38 Mo 26
TO-22-CKM-CKM GIS-1-01 | CARRICKMINES CARRICKMINES GIS
TO-22-CKM-PB-1-01 | CARRICKMINES POOLBEG
TO-22-CKM-PST2201-01 | CARRICKMINES PST2201
TO-22-CF-COR-1-01 | CATHALEENS FALL CORRACLASSY
TO-22-KLS-220K1-2-03 | KELLIS 220K1-2
TO-22-LOU-T2103-01 | LOUTH T2103
TO-22-MOY-T142-01 | MOY T142
TO-22-CBT-MAY-1-06 | CASTLEBAGOT MAYNOOTH 1
Outages spanning Weeks 37-38
OUTAGE ID | PLANT | Week 37 Mo 12: Week 37; Week 38 Mo 19: Week 38
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
TO-22-BYH-BVK-1-01 | BALLYNAHULLA BALLYVOUSKILL
TO-22-CLE-T224-01 | CLONEE T224
TO-22-220 kV A2 @ CDU-01 | CORDUFF 220 kV A2
TO-22-220 kV B2 @ CDU-01 | CORDUFF 220 kV B2
TO-22-CDU-MUL-1-01 | CORDUFF MULLINGAR
TO-22-CKG-KUD-1-01 | CORKAGH KILMAHUD
TO-22-CUL-T2101-01 | CULLENAGH T2101
TO-22-110 kV A2 @ DEY-02 | DERRYCARNEY 110 kV A2
TO-22-110 kV B2 @ DEY-03 | DERRYCARNEY 110 kV B2
TO-22-DEY-110K2-02 | DERRYCARNEY 110K2
TO-22-DSN-400K1-2-01 | DUNSTOWN 400K1-2
TO-22-FIN GIS-110K6-02 | FINGLAS GIS 110K6
TO-22-GGO-220K1-2-02 | GLANAGOW 220K1-2
TO-22-GOR-PLA-1-01 | GORMAN PLATIN
TO-22-INC-220K1-2-03 | INCHICORE 220K1-2
TO-22-ISH-T2001-01 | IRISHTOWN T2001
TO-22-KNR-TRI-2-01 | KNOCKANURE TRIEN 2
TO-22-LET-M/CAP1-01 | LETTERKENNY M/CAP1
TO-22-MAY-WOO-1-15 | MAYNOOTH WOODLAND
TO-22-MUL-CAP2-03 | MULLINGAR CAP2
TO-22-PB-R2002-01 | POOLBEG R2002
TO-22-TB-T101-02 | TARBERT T101
TO-22-TIP-T141-02 | TIPPERARY T141
TO-22-TRI-110SA1-2CB-02 | TRIEN 110SA1-2CB
TO-22-TRI-T142-01 | TRIEN T142
TO-22-WOO-T4201-05 | WOODLAND T4201