## Wks 16 - 17
Report covers outages commencing/returning/spanning the period: 15/04/2024 - 28/04/2024
Outages commencing/returning in Week 16
OUTAGE ID | PLANT |  | Week 16 | [6 empty] | Week 17
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
TO-24-PRN-T4301-01 | PORTAN T4301 | bar: Week 16 Mo 15
TO-24-PRN-WOO-1-04 | PORTAN WOODLAND | bar: Week 16 Mo 15
TO-24-400 kV A1 @ WOO-01 | WOODLAND 400 kV A1 | bar: Week 16 Mo 15
TO-24-BGH-T132-02 | BOGGERAGH T132 | bar: Week 16 Mo 15 to Week 16 Tu 16
TO-24-KLN-SH-1-02 | KILLONAN SHANNONBRIDGE | bar: Week 16 Mo 15 to Week 16 Tu 16
TO-24-BGT-110K1-01 | BALLYRAGGET 110K1 | bar: Week 16 Mo 15 to Week 16 We 17
TO-24-BGT-110SA1-2CB-01 | BALLYRAGGET 110SA1-2CB | bar: Week 16 Mo 15 to Week 16 We 17
TO-24-BGT-110SB1-2CB-01 | BALLYRAGGET 110SB1-2CB | bar: Week 16 Mo 15 to Week 16 We 17
TO-24-BGT-KKY-1-01 | BALLYRAGGET KILKENNY | bar: Week 16 Mo 15 to Week 16 We 17
TO-24-BGT-141-01 | BALLYRAGGET T141 | bar: Week 16 Mo 15 to Week 16 We 17
TO-24-CTN-TIP-1-01 | CAUTEEN TIPPERARY | bar: Week 16 Mo 15 to Week 16 Fr 19
TO-24-CRO-110SA1-02 | COOLROE 110SA1 | bar: Week 16 Mo 15 to Week 16 Fr 19
TO-24-CRO-110SA2-01 | COOLROE 110SA2 | bar: Week 16 Mo 15 to Week 16 Fr 19
TO-24-CRO-IA-1-01 | COOLROE INNISCARRA | bar: Week 16 Mo 15 to Week 16 Fr 19
TO-24-CRO-T122-01 | COOLROE T122 | bar: Week 16 Mo 15 to Week 16 Fr 19
TO-24-CDU-220SA2-4-01 | CORDUFF 220SA2-4 | bar: Week 16 Mo 15 to Week 16 Fr 19
TO-24-CDU-220SB2-4-01 | CORDUFF 220SB2-4 | bar: Week 16 Mo 15 to Week 16 Fr 19
TO-24-CRA-110SA1-02 | CRANE 110SA1 | bar: Week 16 Mo 15 to Week 16 Fr 19
TO-24-CRA-110SA2-04 | CRANE 110SA2 | bar: Week 16 Mo 15 to Week 16 Fr 19
TO-24-CRA-T141-01 | CRANE T141 | bar: Week 16 Mo 15 to Week 16 Fr 19
TO-24-CRA-TTU-1-01 | CRANE TULLABEG | bar: Week 16 Mo 15 to Week 16 Fr 19
TO-24-KPG-T2101-01 | KILPADDOGE T2101 | bar: Week 16 Mo 15 to Week 16 Fr 19
TO-24-220 kV B2 @ CKM GIS-01 | CARRICKMINES GIS 220 kV B2 | bar: Week 16 Mo 15 to Week 17 Tu 23
TO-24-220 kV B4 @ CKM GIS-02 | CARRICKMINES GIS 220 kV B4 | bar: Week 16 Mo 15 to Week 17 Tu 23
TO-24-CKM GIS-220SB2-4CB-02 | CARRICKMINES GIS 220SB2-4CB | bar: Week 16 Mo 15 to Week 17 Tu 23
TO-24-MP GIS-220K1-01 | MONEYPOINT GIS 220K1 | bar: Week 16 Tu 16
TO-24-PRN-WOO-1-01 | PORTAN WOODLAND | bar: Week 16 Tu 16 to Week 16 Fr 19
TO-24-BGH-T121-02 | BOGGERAGH T121 | bar: Week 16 We 17
TO-24-MP GIS-220K2-01 | MONEYPOINT GIS 220K2 | bar: Week 16 We 17
TO-24-SH-220K1-2-02 | SHANNONBRIDGE 220K1-2 | bar: Week 16 We 17 to Week 16 Th 18
TO-24-110 kV A2 @ FIN GIS-02 | FINGLAS GIS 110 kV A2 | bar: Su 14 to Week 16 We 17
TO-24-110 kV B2 @ FIN GIS-02 | FINGLAS GIS 110 kV B2 | bar: Su 14 to Week 16 We 17
TO-24-FIN GIS-110K2-03 | FINGLAS GIS 110K2 | bar: Su 14 to Week 16 We 17
TO-24-FIN GIS-110SA1-2CB-03 | FINGLAS GIS 110SA1-2CB | bar: Su 14 to Week 16 We 17
TO-24-FIN GIS-110SA2-4CB-04 | FINGLAS GIS 110SA2-4CB | bar: Su 14 to Week 16 We 17
TO-24-FIN GIS-110SB1-2CB-03 | FINGLAS GIS 110SB1-2CB | bar: Su 14 to Week 16 We 17
TO-24-FIN GIS-110SB2-4CB-05 | FINGLAS GIS 110SB2-4CB | bar: Su 14 to Week 16 We 17
TO-24-AA GIS-T104-04 | ARDNACRUSHA GIS T104 | bar: Week 16 Th 18
TO-24-FIN GIS-110SB1-2CB-04 | FINGLAS GIS 110SB1-2CB | bar: Week 16 Th 18
TO-24-MP GIS-220SA1-2CB-01 | MONEYPOINT GIS 220SA1-2CB | bar: Week 16 Th 18
TO-24-110 kV A1 @ FIN GIS-01 | FINGLAS GIS 110 kV A1 | bar: Week 16 Th 18 to Week 16 Fr 19
TO-24-110 kV A2 @ FIN GIS-03 | FINGLAS GIS 110 kV A2 | bar: Week 16 Th 18 to Week 16 Fr 19
TO-24-110 kV A3 @ FIN GIS-01 | FINGLAS GIS 110 kV A3 | bar: Week 16 Th 18 to Week 16 Fr 19
TO-24-110 kV B1 @ FIN GIS-01 | FINGLAS GIS 110 kV B1 | bar: Week 16 Th 18 to Week 16 Fr 19
TO-24-110 kV B2 @ FIN GIS-03 | FINGLAS GIS 110 kV B2 | bar: Week 16 Th 18 to Week 16 Fr 19
TO-24-110 kV B3 @ FIN GIS-01 | FINGLAS GIS 110 kV B3 | bar: Week 16 Th 18 to Week 16 Fr 19
TO-24-FIN GIS-110K1-03 | FINGLAS GIS 110K1 | bar: Week 16 Th 18 to Week 16 Fr 19
TO-24-FIN GIS-110K2-04 | FINGLAS GIS 110K2 | bar: Week 16 Th 18 to Week 16 Fr 19
TO-24-FIN GIS-110SA1-2CB-04 | FINGLAS GIS 110SA1-2CB | bar: Week 16 Th 18 to Week 16 Fr 19
TO-24-FIN GIS-110SA1-3CB-02 | FINGLAS GIS 110SA1-3CB | bar: Week 16 Th 18 to Week 16 Fr 19
TO-24-FIN GIS-110SA2-4CB-05 | FINGLAS GIS 110SA2-4CB | bar: Week 16 Th 18 to Week 16 Fr 19
TO-24-FIN GIS-110SA3-5CB-02 | FINGLAS GIS 110SA3-5CB | bar: Week 16 Th 18 to Week 16 Fr 19
TO-24-FIN GIS-110SB1-3CB-02 | FINGLAS GIS 110SB1-3CB | bar: Week 16 Th 18 to Week 16 Fr 19
TO-24-FIN GIS-110SB2-4CB-06 | FINGLAS GIS 110SB2-4CB | bar: Week 16 Th 18 to Week 16 Fr 19
TO-24-FIN GIS-110SB3-5CB-02 | FINGLAS GIS 110SB3-5CB | bar: Week 16 Th 18 to Week 16 Fr 19
TO-24-FIN GIS-T2106-04 | FINGLAS GIS T2106 | bar: Week 16 Th 18 to Week 16 Fr 19
TO-24-MP GIS-220SB1-2CB-01 | MONEYPOINT GIS 220SB1-2CB | bar: Week 16 Fr 19
TO-24-TB-T2102-03 | TARBERT T2102 | bar: Week 16 Fr 19 to Week 16 Su 21
TO-24-SH-110K1-2-02 | SHANNONBRIDGE 110K1-2 | bar: Week 16 Fr 19 to Week 17 Mo 22
TO-24-BAL-CDU-1-05 | BALTRASNA CORDUFF | bar: Su 14 to Week 16 Fr 19
TO-24-BK-CBR-1-01 | BELLACORICK CASTLEBAR | bar: Su 14 to Week 16 Fr 19
Report covers outages commencing/returning/spanning the period: 15/04/2024 - 28/04/2024
Outages commencing/returning in Week 16
OUTAGE ID | PLANT | Week 16 Mo 15: Week 16; Week 17 Mo 22: Week 17
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
TO-24-CDU-110SA2-4-01 | CORDUFF 110SA2-4 | bar: Su 14 to Week 16 Fr 19
TO-24-CDU-110SB2-4-01 | CORDUFF 110SB2-4 | bar: Su 14 to Week 16 Fr 19
TO-24-CDU-MCE-1-02 | CORDUFF MACETOWN | bar: Su 14 to Week 16 Fr 19
TO-24-CDU-T102-01 | CORDUFF T102 | bar: Su 14 to Week 16 Fr 19
TO-24-CDU-WOO-1-03 | CORDUFF WOODLAND | bar: Su 14 to Week 16 Fr 19
TO-24-FLA-SLB-1-04 | FLAGFORD SLIABH BAWN | bar: Su 14 to Week 16 Fr 19
Outages commencing/returning in Week 17
OUTAGE ID | PLANT | Week 16 Mo 15: Week 16; Week 17 Mo 22: Week 17
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
TO-24-BIN-110SA1-2CB-01 | BINBANE 110SA1-2CB | bar: Week 17 Mo 22
TO-24-BIN-T142-02 | BINBANE T142 | bar: Week 17 Mo 22
TO-24-UGL-T132-03 | UGGOOL T132 | bar: Week 17 Mo 22
TO-24-UGL-T134-02 | UGGOOL T134 | bar: Week 17 Mo 22
TO-24-AD-ST101-01 | AGHADA ST101 | bar: Week 17 Mo 22
TO-24-220 kV A2 @ CRU-01 | CRUISERATH 220 kV A2 | bar: Week 17 Mo 22
TO-24-220 kV B2 @ CRU-01 | CRUISERATH 220 kV B2 | bar: Week 17 Mo 22
TO-24-CRU-220K2-01 | CRUISERATH 220K2 | bar: Week 17 Mo 22
TO-24-CRU-SA1-2CB-01 | CRUISERATH 220SA1-2CB | bar: Week 17 Mo 22
TO-24-CRU-SB1-2CB-01 | CRUISERATH 220SB1-2CB | bar: Week 17 Mo 22
TO-24-110 kV A1 @ DND-01 | DARNDALE 110 kV A1 | bar: Week 17 Mo 22
TO-24-110 kV B1 @ DND-01 | DARNDALE 110 kV B1 | bar: Week 17 Mo 22
TO-24-DND-110K1-01 | DARNDALE 110K1 | bar: Week 17 Mo 22
TO-24-DND-110SA1-2CB-01 | DARNDALE 110SA1-2CB | bar: Week 17 Mo 22
TO-24-DND-110SB1-2CB-01 | DARNDALE 110SB1-2CB | bar: Week 17 Mo 22
TO-24-KTN-WAT-1-01 | KILLOTERAN WATERFORD | bar: Week 17 Mo 22
TO-24-LIM-RAT-1-01 | LIMERICK RATHKEALE | bar: Week 17 Mo 22
TO-24-ROP-WEX-1-02 | ROSSPILE WEXFORD | bar: Week 17 Mo 22
TO-24-WEX-110SA1-2CB-01 | WEXFORD 110SA1-2CB | bar: Week 17 Mo 22
TO-24-WEX-T121-01 | WEXFORD T121 | bar: Week 17 Mo 22
TO-24-WEX-T141-01 | WEXFORD T141 | bar: Week 17 Mo 22
TO-24-BAL-DRY-1-05 | BALTRASNA DRYBRIDGE | bar: Week 17 Mo 22; Week 17 Sa 27 to Week 17 Mo 29
TO-24-BIN-CF-1-01 | BINBANE CATHALEENS FALL | bar: Week 17 Mo 22; Week 17 Sa 27 to Week 17 Mo 29
TO-24-COS-FLA-1-03 | CARRICK ON SHANNON FLAGFORD 1 | bar: Week 17 Mo 22; Week 17 Sa 27 to Week 17 Mo 29
TO-24-CD-KBY-1-01 | CARRIGADROHID KILBARRY | bar: Week 17 Mo 22; Week 17 Sa 27 to Week 17 Mo 29
TO-24-110 kV A2 @ CF-01 | CATHALEENS FALL 110 kV A2 | bar: Week 17 Mo 22; Week 17 Sa 27 to Week 17 Mo 29
TO-24-110 kV A2 @ CLO-02 | CLOGHER 110 kV A2 | bar: Week 17 Mo 22; Week 17 Sa 27 to Week 17 Mo 29
TO-24-110 kV B2 @ CLO-02 | CLOGHER 110 kV B2 | bar: Week 17 Mo 22; Week 17 Sa 27 to Week 17 Mo 29
TO-24-CLO-MRY-1-01 | CLOGHER MULREAVY | bar: Week 17 Mo 22; Week 17 Sa 27 to Week 17 Mo 29
TO-24-110 kV A1 @ FLA-04 | FLAGFORD 110 kV A1 | bar: Week 17 Mo 22; Week 17 Sa 27 to Week 17 Mo 29
TO-24-110 kV B1 @ FLA-05 | FLAGFORD 110 kV B1 | bar: Week 17 Mo 22; Week 17 Sa 27 to Week 17 Mo 29
TO-24-MRY-T131-01 | MULREAVY T131 | bar: Week 17 Mo 22; Week 17 Sa 27 to Week 17 Mo 29
TO-24-110 kV A1 @ ARV-01 | ARVA 110 kV A1
TO-24-ARV-NAV-1-01 | ARVA NAVAN
TO-24-GAE-T121-02 | GLANLEE T121
TO-24-KPG-220SB1-3CB-01 | KILPADDOGE 220SB1-3CB
TO-24-SH-T2101-03 | SHANNONBRIDGE T2101
TO-24-ARV-SKL-1-02 | ARVA SHANKILL 1 | bar: Su 14 to Week 17 Mo 22
TO-24-BNK-T122-02 | BARNAKYLE T122 | bar: Week 17 Sa 27 to Week 17 Mo 29
TO-24-110 kV A1 @ LOU-01 | LOUTH 110 kV A1 | bar: Week 17 Sa 27 to Week 17 Mo 29
TO-24-110 kV B1 @ LOU-01 | LOUTH 110 kV B1 | bar: Week 17 Sa 27 to Week 17 Mo 29
TO-24-LOU-RRU-1-01 | LOUTH RATRUSSAN | bar: Week 17 Sa 27 to Week 17 Mo 29
TO-24-RRU-110SA1-05 | RATRUSSAN 110SA1 | bar: Week 17 Sa 27 to Week 17 Mo 29
TO-24-RRU-SKL-1-03 | RATRUSSAN SHANKILL | bar: Week 17 Sa 27 to Week 17 Mo 29
TO-24-RRU-T121-05 | RATRUSSAN T121 | bar: Week 17 Sa 27 to Week 17 Mo 29
TO-24-RRU-T122-05 | RATRUSSAN T122 | bar: Week 17 Sa 27 to Week 17 Mo 29
TO-24-110 kV A3 @ AA GIS-01 | ARDNACRUSHA GIS 110 kV A3
TO-24-AA GIS-T104-02 | ARDNACRUSHA GIS T104
TO-24-AGL-SH-1-02 | AGANNYGAL SHANNONBRIDGE
TO-24-BK-SKY-1-01 | BELLACORICK SRAHNAKILLY | bar: Su 14 to Week 17 Mo 22
Report covers outages commencing/returning/spanning the period: 15/04/2024 - 28/04/2024
Outages commencing/returning in Week 17
OUTAGE ID | PLANT | Week 16 Mo 15: Week 16; Week 17 Mo 22: Week 17
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
TO-24-220 kV A2 @ CDU-03 | CORDUFF 220 kV A2
TO-24-220 kV B2 @ CDU-03 | CORDUFF 220 kV B2
TO-24-SKY-110SA1-01 | SRAHNAKILLY 110SA1
TO-24-SKY-110SA2-01 | SRAHNAKILLY 110SA2
TO-24-SKY-T131-02 | SRAHNAKILLY T131
TO-24-SKY-T132-02 | SRAHNAKILLY T132
TO-24-220 kV A1 @ FIN-02 | FINGLAS 220 kV A1
TO-24-220 kV B1 @ FIN-02 | FINGLAS 220 kV B1
TO-24-FIN-HN-1-01 | FINGLAS HUNTSTOWN
TO-24-HN-T2010/11-01 | HUNTSTOWN T2010/11
Outages spanning Weeks 16-17
OUTAGE ID | PLANT | Week 16 Mo 15: Week 16; Week 17 Mo 22: Week 17
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
TO-24-AD-LPT-1-01 | AGHADA LONG POINT
TO-24-BOL-T141-01 | BOOLTIAGH T141
TO-24-CSH-CAP2-01 | CASHLA CAP2
TO-24-CSH-T2104-02 | CASHLA T2104
TO-24-CLG-110K1-02 | CLOGHRAN 110K1
TO-24-CLN-T142-01 | CLOON T142
TO-24-220 kV A2 @ CUL-02 | CULLENAGH 220 kV A2
TO-24-220 kV B2 @ CUL-02 | CULLENAGH 220 kV B2
TO-24-CUL-KRA-1-01 | CULLENAGH KNOCKRAHA
TO-24-DAL,T-SH-1-02 | DALLOW tee SHANNONBRIDGE
TO-24-DND-T121-01 | DARNDALE T121
TO-24-GAL-T102-01 | GALWAY T102
TO-24-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-24-GI-T141-01 | GREAT ISLAND T141
TO-24-INC-220K1-2-02 | INCHICORE 220K1-2
TO-24-INC-PB-1-03 | INCHICORE POOLBEG 1
TO-24-KPG-TB-1-02 | KILPADDOGE TARBERT 1
TO-24-220 kV A2 @ KRA-01 | KNOCKRAHA 220 kV A2
TO-24-220 kV B2 @ KRA-01 | KNOCKRAHA 220 kV B2
TO-24-KRA-220K4-02 | KNOCKRAHA 220K4
TO-24-KRA-220SA1-2CB-01 | KNOCKRAHA 220SA1-2CB
TO-24-KRA-220SA2-4CB-02 | KNOCKRAHA 220SA2-4CB
TO-24-KRA-220SB1-2CB-01 | KNOCKRAHA 220SB1-2CB
TO-24-KRA-220SB2-4CB-01 | KNOCKRAHA 220SB2-4CB
TO-24-KRA-RAF-1-01 | KNOCKRAHA RAFFEEN
TO-24-LET-M/CAP1-02 | LETTERKENNY M/CAP1
TO-24-LPT-T2002-02 | LONG POINT T2002
TO-24-220 kV B1/B2 @ LOU-01 | LOUTH 220 kV B1/B2
TO-24-LOU-220K1-2-01 | LOUTH 220K1-2
TO-24-MUL-CAP1-01 | MULLINGAR CAP1
TO-24-NAV-T141-01 | NAVAN T141
TO-24-PB-R2002-02 | POOLBEG R2002
TO-24-PRO-TB-1-01 | PROSPECT TARBERT
TO-24-TB-220K1-2-02 | TARBERT 220K1-2
TO-24-TB-T2003-01 | TARBERT T2003
TO-24-TB-T2004-01 | TARBERT T2004
TO-24-TB-T2004-02
TO-24-TB-T2101-02 | TARBERT T2101
TO-24-TB-T2101-01
TO-24-TRL-CAP2-01 | TRALEE CAP2
TO-24-UGL-T132-01 | UGGOOL T132