## Wks 18 - 19
Report covers outages commencing/returning/spanning the period: 29/04/2024 - 12/05/2024
Outages commencing/returning in Week 18
OUTAGE ID | PLANT |  | Week 18 | [6 empty] | Week 19
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
TO-24-MCE-T124-03 | MACETOWN T124 | bar: Week 18 Mo 29 to Week 18 We 1
TO-24-220 kV A1 @ AD-04 | AGHADA 220 kV A1 | bar: Week 18 Mo 29 to Week 18 Fr 3
TO-24-220 kV A2 @ AD-07 | AGHADA 220 kV A2 | bar: Week 18 Mo 29 to Week 18 Fr 3
TO-24-AD-220K1-05 | AGHADA 220K1 | bar: Week 18 Mo 29 to Week 18 Fr 3
TO-24-AD-SA1-2CB-04 | AGHADA 220SA1-2CB | bar: Week 18 Mo 29 to Week 18 Fr 3
TO-24-110 kV A3 @ AA GIS-02 | ARDNACRUSHA GIS 110 kV A3 | bar: Week 18 Mo 29 to Week 18 Fr 3
TO-24-110 kV B3 @ AA GIS-01 | ARDNACRUSHA GIS 110 kV B3 | bar: Week 18 Mo 29 to Week 18 Fr 3
TO-23-AA GIS-110K3-01 | ARDNACRUSHA GIS 110K3 | bar: Week 18 Mo 29 to Week 18 Fr 3
TO-24-AA GIS-110SA1-3CB-01 | ARDNACRUSHA GIS 110SA1-3CB | bar: Week 18 Mo 29 to Week 18 Fr 3
TO-24-AA GIS-110SB1-3CB-01 | ARDNACRUSHA GIS 110SB1-3CB | bar: Week 18 Mo 29 to Week 18 Fr 3
TO-24-AA GIS-CAP1-01 | ARDNACRUSHA GIS CAP1 | bar: Week 18 Mo 29 to Week 18 Fr 3
TO-24-ARK-T2102-01 | ARKLOW T2102 | bar: Week 18 Mo 29 to Week 18 Fr 3
TO-24-CL-T102-05 | CLIFF T102 | bar: Week 18 Mo 29 to Week 18 Fr 3
TO-24-ATH-LA-1-02 | ATHLONE LANESBORO
TO-24-110 kV A2 @ RAF-02 | RAFFEEN 110 kV A2
TO-24-110 kV B2 @ RAF-02 | RAFFEEN 110 kV B2
TO-24-110 kV A2 @ CLO-02 | CLOGHER 110 kV A2 | bar: Su 28 to Week 18 Mo 29
TO-24-110 kV B2 @ CLO-02 | CLOGHER 110 kV B2 | bar: Su 28 to Week 18 Mo 29
TO-24-CLO-MRY-1-01 | CLOGHER MULREAVY | bar: Su 28 to Week 18 Mo 29
TO-24-MRY-T131-01 | MULREAVY T131 | bar: Su 28 to Week 18 Mo 29
TO-24-CRO-IA-1-04 | COOLROE INNISCARRA | bar: Week 18 Tu 30
TO-24-GOR-T122-01 | GORMAN T122 | bar: Week 18 Tu 30
TO-24-110 kV A1 @ IA-02 | INNISCARRA 110 kV A1 | bar: Week 18 Tu 30
TO-24-IA-MAC-1-04 | INNISCARRA MACROOM | bar: Week 18 Tu 30
TO-24-IA-T101-04 | INNISCARRA T101 | bar: Week 18 Tu 30
TO-24-CHA-GLE-1-01 | CHARLEVILLE GLENLARA | bar: Week 18 Tu 30 to Week 18 Th 2
TO-24-220 kV A2 @ CRU-01 | CRUISERATH 220 kV A2 | bar: Su 28 to Week 18 Tu 30
TO-24-220 kV B2 @ CRU-01 | CRUISERATH 220 kV B2 | bar: Su 28 to Week 18 Tu 30
TO-24-CRU-220K2-01 | CRUISERATH 220K2 | bar: Su 28 to Week 18 Tu 30
TO-24-CRU-SA1-2CB-01 | CRUISERATH 220SA1-2CB | bar: Su 28 to Week 18 Tu 30
TO-24-CRU-SB1-2CB-01 | CRUISERATH 220SB1-2CB | bar: Su 28 to Week 18 Tu 30
TO-24-220 kV A2 @ CRU-02 | CRUISERATH 220 kV A2 | bar: Week 18 We 1 to Week 18 Th 2
TO-24-220 kV B2 @ CRU-02 | CRUISERATH 220 kV B2 | bar: Week 18 We 1 to Week 18 Th 2
TO-24-CRU-220K2-02 | CRUISERATH 220K2 | bar: Week 18 We 1 to Week 18 Th 2
TO-24-CRU-SA1-2CB-02 | CRUISERATH 220SA1-2CB | bar: Week 18 We 1 to Week 18 Th 2
TO-24-CRU-SB1-2CB-02 | CRUISERATH 220SB1-2CB | bar: Week 18 We 1 to Week 18 Th 2
TO-24-CRU-CDU-2-02 | CRUISERATH CORDUFF 2 | bar: Week 18 We 1 to Week 18 Th 2
TO-24-AA GIS-T101-01 | ARDNACRUSHA GIS T101 | bar: Week 18 We 1 to Week 19 Mo 13
TO-24-BNK-T122-02 | BARNAKYLE T122 | bar: Su 28 to Week 18 We 1
TO-24-CSH-T2104-02 | CASHLA T2104 | bar: Su 28 to Week 18 We 1
TO-24-110 kV A2 @ CSH-04 | CASHLA 110 kV A2 | bar: Week 18 Th 2 to Week 19 Mo 13
TO-24-110 kV B2 @ CSH-04 | CASHLA 110 kV B2 | bar: Week 18 Th 2 to Week 19 Mo 13
TO-24-220 kV B2 @ CSH-01 | CASHLA 220 kV B2 | bar: Week 18 Th 2 to Week 19 Mo 13
TO-24-CSH-220K2-4-03 | CASHLA 220K2-4 | bar: Week 18 Th 2 to Week 19 Mo 13
TO-24-CSH-T2102-01 | CASHLA T2102 | bar: Week 18 Th 2 to Week 19 Mo 13
TO-24-MAY-TSB-1-02 | MAYNOOTH THORNSBERRY | bar: Week 18 Th 2 to Week 19 Mo 13
TO-24-CD-KBY-1-01 | CARRIGADROHID KILBARRY | bar: Su 28 to Week 18 Fr 3
TO-24-COR-PST-03 | CORRACLASSY ENNISKILLEN PST | bar: Su 28 to Week 18 Fr 3
Outages commencing/returning in Week 19
OUTAGE ID | PLANT | Week 18 Mo 29: Week 18; Week 19 Mo 6: Week 19
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
TO-24-110 kV A1 @ DND-01 | DARNDALE 110 kV A1 | bar: Week 19 Mo 6 to Week 19 Tu 7; Week 19 Th 9 to Week 19 Fr 10
TO-24-110 kV B1 @ DND-01 | DARNDALE 110 kV B1 | bar: Week 19 Mo 6 to Week 19 Tu 7; Week 19 Th 9 to Week 19 Fr 10
TO-24-DND-110K1-01 | DARNDALE 110K1 | bar: Week 19 Mo 6 to Week 19 Tu 7; Week 19 Th 9 to Week 19 Fr 10
TO-24-DND-110SA1-2CB-01 | DARNDALE 110SA1-2CB | bar: Week 19 Mo 6 to Week 19 Tu 7; Week 19 Th 9 to Week 19 Fr 10
TO-24-DND-110SB1-2CB-01 | DARNDALE 110SB1-2CB | bar: Week 19 Mo 6 to Week 19 Tu 7; Week 19 Th 9 to Week 19 Fr 10
TO-24-110 kV A2/A3 @ MAY-01 | MAYNOOTH 110 kV A2/A3 | bar: Week 19 Mo 6 to Week 19 Tu 7; Week 19 Th 9 to Week 19 Mo 13
TO-24-110 kV B2/B3 @ MAY-01 | MAYNOOTH 110 kV B2/B3 | bar: Week 19 Mo 6 to Week 19 Tu 7; Week 19 Th 9 to Week 19 Mo 13
Report covers outages commencing/returning/spanning the period: 29/04/2024 - 12/05/2024
Outages commencing/returning in Week 19
OUTAGE ID | PLANT | Week 18 Mo 29: Week 18; Week 19 Mo 6: Week 19
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
TO-24-BLC-110K1-01 | BELCAMP 110K1 | bar: Week 19 Tu 7
TO-24-KTL-T131-01 | KILTEEL T131 | bar: Week 19 Tu 7
TO-24-BUT-CUL-1-01 | BUTLERSTOWN CULLENAGH | bar: Week 19 Tu 7; Week 19 Th 9
TO-24-CBR-CAP2-01 | CASTLEBAR CAP2 | bar: Week 19 Tu 7; Week 19 Th 9 to Week 19 Fr 10
TO-24-110 kV A2 @ AA GIS-01 | ARDNACRUSHA GIS 110 kV A2 | bar: Week 19 Tu 7; Week 19 Th 9 to Week 19 Mo 13
TO-24-110 kV B2 @ AA GIS-01 | ARDNACRUSHA GIS 110 kV B2 | bar: Week 19 Tu 7; Week 19 Th 9 to Week 19 Mo 13
TO-24-AA GIS-110K2-01 | ARDNACRUSHA GIS 110K2 | bar: Week 19 Tu 7; Week 19 Th 9 to Week 19 Mo 13
TO-24-AA GIS-110SA1-2CB-01 | ARDNACRUSHA GIS 110SA1-2CB | bar: Week 19 Tu 7; Week 19 Th 9 to Week 19 Mo 13
TO-24-AA GIS-110SB1-2CB-01 | ARDNACRUSHA GIS 110SB1-2CB | bar: Week 19 Tu 7; Week 19 Th 9 to Week 19 Mo 13
TO-24-AA GIS-ENN-1-04 | ARDNACRUSHA GIS ENNIS | bar: Week 19 Tu 7; Week 19 Th 9 to Week 19 Mo 13
TO-24-AD-220K1-02 | AGHADA 220K1
TO-24-BLC-110K3-01 | BELCAMP 110K3
TO-24-CSH-GAL GIS-2-02 | CASHLA GALWAY GIS 2
TO-24-GOR-LOU-1-01 | GORMAN LOUTH
TO-24-LIS-T131-01 | LISDRUM T131
TO-24-ROP-110K1-01 | ROSSPILE 110K1
TO-24-110 kV A1 @ GAL GIS-01 | GALWAY GIS 110 kV A1 | bar: Week 19 Th 9 to Week 19 Mo 13
TO-24-110 kV B1 @ GAL GIS-01 | GALWAY GIS 110 kV B1 | bar: Week 19 Th 9 to Week 19 Mo 13
TO-24-GAL GIS-110SA1-2CB-01 | GALWAY GIS 110SA1-2CB | bar: Week 19 Th 9 to Week 19 Mo 13
TO-24-GAL GIS-110SA1-3CB-01 | GALWAY GIS 110SA1-3CB | bar: Week 19 Th 9 to Week 19 Mo 13
TO-24-GAL GIS-110SB1-2CB-01 | GALWAY GIS 110SB1-2CB | bar: Week 19 Th 9 to Week 19 Mo 13
TO-24-GAL GIS-110SB1-3CB-01 | GALWAY GIS 110SB1-3CB | bar: Week 19 Th 9 to Week 19 Mo 13
TO-24-220 kV A1 @ FIN-02 | FINGLAS 220 kV A1 | bar: Su 28 to Week 19 Tu 7
TO-24-220 kV B1 @ FIN-02 | FINGLAS 220 kV B1 | bar: Su 28 to Week 19 Tu 7
TO-24-FIN-220K1-03 | FINGLAS 220K1 | bar: Su 28 to Week 19 Tu 7
TO-24-FIN-220SA1-2CB-02 | FINGLAS 220SA1-2CB | bar: Su 28 to Week 19 Tu 7
TO-24-FIN-220SB1-2CB-03 | FINGLAS 220SB1-2CB | bar: Su 28 to Week 19 Tu 7
TO-24-FIN-HN-1-01 | FINGLAS HUNTSTOWN | bar: Su 28 to Week 19 Tu 7
TO-24-HN-T2010/11-01 | HUNTSTOWN T2010/11 | bar: Su 28 to Week 19 Tu 7
TO-24-220 kV B1/B2 @ LOU-01 | LOUTH 220 kV B1/B2 | bar: Su 28 to Week 19 Tu 7
TO-24-LOU-220K1-2-01 | LOUTH 220K1-2 | bar: Su 28 to Week 19 Tu 7
TO-24-BLC-110SA1-3CB-01 | BELCAMP 110SA1-3CB | bar: Week 19 Th 9
TO-24-ARK-T101-01 | ARKLOW T101 | bar: Week 19 Th 9 to Week 19 Fr 10
TO-24-WOH-T122-01 | WOODHOUSE T122 | bar: Week 19 Th 9 to Week 19 Fr 10
TO-24-AA GIS-T104-01 | ARDNACRUSHA GIS T104 | bar: Week 19 Th 9 to Week 19 Mo 13
TO-24-DAL,T-SH-1-02 | DALLOW tee SHANNONBRIDGE | bar: Su 28 to Week 19 Tu 7; Week 19 Th 9
TO-24-110 kV A2 @ SH-03 | SHANNONBRIDGE 110 kV A2 | bar: Su 28 to Week 19 Tu 7; Week 19 Th 9
TO-24-110 kV B2 @ SH-03 | SHANNONBRIDGE 110 kV B2 | bar: Su 28 to Week 19 Tu 7; Week 19 Th 9
TO-24-BLC-110SB1-3CB-01 | BELCAMP 110SB1-3CB | bar: Week 19 Fr 10
TO-24-BK-SKY-1-01 | BELLACORICK SRAHNAKILLY | bar: Su 28 to Week 19 Tu 7; Week 19 Th 9 to Week 19 Fr 10
TO-24-SKY-110SA1-01 | SRAHNAKILLY 110SA1 | bar: Su 28 to Week 19 Tu 7; Week 19 Th 9 to Week 19 Fr 10
TO-24-SKY-110SA2-01 | SRAHNAKILLY 110SA2 | bar: Su 28 to Week 19 Tu 7; Week 19 Th 9 to Week 19 Fr 10
TO-24-SKY-T131-02 | SRAHNAKILLY T131 | bar: Su 28 to Week 19 Tu 7; Week 19 Th 9 to Week 19 Fr 10
TO-24-SKY-T132-02 | SRAHNAKILLY T132 | bar: Su 28 to Week 19 Tu 7; Week 19 Th 9 to Week 19 Fr 10
Outages spanning Weeks 18-19
OUTAGE ID | PLANT | Week 18 Mo 29: Week 18; Week 19 Mo 6: Week 19
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
TO-24-AD-LPT-1-01 | AGHADA LONG POINT
TO-24-BAL-DRY-1-05 | BALTRASNA DRYBRIDGE
TO-24-BIN-CF-1-01 | BINBANE CATHALEENS FALL
TO-24-BOL-T141-01 | BOOLTIAGH T141
TO-24-COS-FLA-1-03 | CARRICK ON SHANNON FLAGFORD 1
TO-24-CSH-CAP2-01 | CASHLA CAP2
TO-24-110 kV A2 @ CF-01 | CATHALEENS FALL 110 kV A2
TO-24-CLG-110K1-02 | CLOGHRAN 110K1
TO-24-CLN-T142-01 | CLOON T142
TO-24-220 kV A2 @ CUL-02 | CULLENAGH 220 kV A2
TO-24-220 kV B2 @ CUL-02 | CULLENAGH 220 kV B2
TO-24-CUL-KRA-1-01 | CULLENAGH KNOCKRAHA
Report covers outages commencing/returning/spanning the period: 29/04/2024 - 12/05/2024
Outages spanning Weeks 18-19
OUTAGE ID | PLANT | Week 18 Mo 29: Week 18; Week 19 Mo 6: Week 19
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
TO-24-DND-T121-01 | DARNDALE T121
TO-24-110 kV A1 @ FLA-04 | FLAGFORD 110 kV A1
TO-24-110 kV B1 @ FLA-05 | FLAGFORD 110 kV B1
TO-24-GAL-T102-01 | GALWAY T102
TO-24-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-24-GI-T141-01 | GREAT ISLAND T141
TO-24-INC-220K1-2-02 | INCHICORE 220K1-2
TO-24-KPG-TB-1-02 | KILPADDOGE TARBERT 1
TO-24-220 kV A2 @ KRA-01 | KNOCKRAHA 220 kV A2
TO-24-220 kV B2 @ KRA-01 | KNOCKRAHA 220 kV B2
TO-24-KRA-220K4-02 | KNOCKRAHA 220K4
TO-24-KRA-220SA1-2CB-01 | KNOCKRAHA 220SA1-2CB
TO-24-KRA-220SA2-4CB-02 | KNOCKRAHA 220SA2-4CB
TO-24-KRA-220SB1-2CB-01 | KNOCKRAHA 220SB1-2CB
TO-24-KRA-220SB2-4CB-01 | KNOCKRAHA 220SB2-4CB
TO-24-KRA-RAF-1-01 | KNOCKRAHA RAFFEEN
TO-24-LPT-T2002-02 | LONG POINT T2002
TO-24-110 kV A1 @ LOU-01 | LOUTH 110 kV A1
TO-24-110 kV B1 @ LOU-01 | LOUTH 110 kV B1
TO-24-LOU-RRU-1-01 | LOUTH RATRUSSAN
TO-24-MUL-CAP1-01 | MULLINGAR CAP1
TO-24-NAV-T141-01 | NAVAN T141
TO-24-PB-R2002-02 | POOLBEG R2002
TO-24-PRO-TB-1-01 | PROSPECT TARBERT
TO-24-RRU-110SA1-03 | RATRUSSAN 110SA1
TO-24-RRU-110SA2-03 | RATRUSSAN 110SA2
TO-24-RRU-SKL-1-03 | RATRUSSAN SHANKILL
TO-24-RRU-T121-03 | RATRUSSAN T121
TO-24-RRU-T122-01 | RATRUSSAN T122
TO-24-TB-220K1-2-02 | TARBERT 220K1-2
TO-24-TB-T2003-01 | TARBERT T2003
TO-24-TB-T2004-01 | TARBERT T2004
TO-24-TB-T2004-02
TO-24-TB-T2101-02 | TARBERT T2101
TO-24-TB-T2101-01
TO-24-TRL-CAP2-01 | TRALEE CAP2
TO-24-UGL-T132-01 | UGGOOL T132