## Wks 20 - 21
Report covers outages commencing/returning/spanning the period: 13/05/2024 - 26/05/2024
Outages commencing/returning in Week 20
OUTAGE ID | PLANT |  | Week 20 | [6 empty] | Week 21
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
TO-24-CLH-110SA2-01 | CLAHANE 110SA2 | bar: Week 20 Mo 13 to Week 20 Tu 14
TO-24-CLH-TRI-1-01 | CLAHANE TRIEN | bar: Week 20 Mo 13 to Week 20 Tu 14
TO-24-RAF-110K1-2-01 | RAFFEEN 110K1-2 | bar: Week 20 Mo 13 to Week 20 Tu 14
TO-24-CLH-T122-01 | CLAHANE T122 | bar: Week 20 Mo 13 to Week 20 Tu 14; Week 20 Fr 17
TO-24-GI-WAT-1-04 | GREAT ISLAND WATERFORD 1 | bar: Week 20 Mo 13 to Week 20 Tu 14; Week 20 Fr 17
TO-24-110 kV A2 @ LOU-01 | LOUTH 110 kV A2 | bar: Week 20 Mo 13 to Week 20 Tu 14; Week 20 Fr 17
TO-24-110 kV B2 @ LOU-01 | LOUTH 110 kV B2 | bar: Week 20 Mo 13 to Week 20 Tu 14; Week 20 Fr 17
TO-24-110 kV A1 @ CSH-06 | CASHLA 110 kV A1 | bar: Week 20 Mo 13 to Week 20 Tu 14; Week 20 Fr 17 to Week 20 Sa 18
TO-24-110 kV B1 @ CSH-03 | CASHLA 110 kV B1 | bar: Week 20 Mo 13 to Week 20 Tu 14; Week 20 Fr 17 to Week 20 Sa 18
TO-24-CSH-CLN-1-01 | CASHLA CLOON | bar: Week 20 Mo 13 to Week 20 Tu 14; Week 20 Fr 17 to Week 20 Sa 18
TO-24-LOU-MTH-1-01 | LOUTH MEATH HILL | bar: Week 20 Mo 13 to Week 20 Tu 14; Week 20 Fr 17 to Week 21 Tu 21
TO-24-CL-T102-03 | CLIFF T102 | bar: Week 20 Mo 13 to Week 20 Tu 14; Week 20 Fr 17 to Week 21 Th 23
TO-24-400 kV A1 @ DSN-02 | DUNSTOWN 400 kV A1 | bar: Week 20 Mo 13 to Week 20 Tu 14; Week 20 Fr 17 to Week 21 Fr 24
TO-24-400 kV A2 @ DSN-01 | DUNSTOWN 400 kV A2 | bar: Week 20 Mo 13 to Week 20 Tu 14; Week 20 Fr 17 to Week 21 Fr 24
TO-24-400 kV B1 @ DSN-02 | DUNSTOWN 400 kV B1 | bar: Week 20 Mo 13 to Week 20 Tu 14; Week 20 Fr 17 to Week 21 Fr 24
TO-24-400 kV B2 @ DSN-01 | DUNSTOWN 400 kV B2 | bar: Week 20 Mo 13 to Week 20 Tu 14; Week 20 Fr 17 to Week 21 Fr 24
TO-24-DSN-400K1-2-01 | DUNSTOWN 400K1-2 | bar: Week 20 Mo 13 to Week 20 Tu 14; Week 20 Fr 17 to Week 21 Fr 24
TO-24-KLS-220K1-2-01 | KELLIS 220K1-2 | bar: Week 20 Mo 13 to Week 20 Tu 14; Week 20 Fr 17 to Week 21 Mo 27
TO-24-AD-LPT-1-01 | AGHADA LONG POINT | bar: Su 12 to Week 20 Mo 13
TO-24-LPT-T2002-02 | LONG POINT T2002 | bar: Su 12 to Week 20 Mo 13
TO-24-110 kV B2/B3 @ MAY-01 | MAYNOOTH 110 kV B2/B3 | bar: Su 12 to Week 20 Mo 13
TO-24-MOY-CAP2-01 | MOY CAP2 | bar: Week 20 Tu 14
TO-24-CRA-LWD-1-06 | CRANE LODGEWOOD | bar: Week 20 Tu 14; Week 20 Fr 17
TO-24-CRO-IA-1-02 | COOLROE INNISCARRA | bar: Week 20 Tu 14; Week 20 Fr 17 to Week 21 Mo 20
TO-24-IA-MAC-1-01 | INNISCARRA MACROOM | bar: Week 20 Tu 14; Week 20 Fr 17 to Week 21 Mo 20
TO-24-110 kV A2/A3 @ MAY-01 | MAYNOOTH 110 kV A2/A3 | bar: Week 20 Tu 14; Week 20 Fr 17 to Week 21 Mo 20
TO-24-IA-T101-01 | INNISCARRA T101 | bar: Week 20 Tu 14; Week 20 Fr 17 to Week 21 Th 23
TO-24-400 kV A1 @ MP GIS-02 | MONEYPOINT GIS 400 kV A1 | bar: Week 20 Tu 14; Week 20 Fr 17 to Week 21 Fr 24
TO-24-400 kV B1 @ MP GIS-04 | MONEYPOINT GIS 400 kV B1 | bar: Week 20 Tu 14; Week 20 Fr 17 to Week 21 Fr 24
TO-24-MP GIS-400SA1-2CB-02 | MONEYPOINT GIS 400SA1-2CB | bar: Week 20 Tu 14; Week 20 Fr 17 to Week 21 Fr 24
TO-24-MP GIS-400SA1-2CB-02 | MONEYPOINT GIS 400SA1-3CB | bar: Week 20 Tu 14; Week 20 Fr 17 to Week 21 Fr 24
TO-24-MP GIS-400SB1-2CB-03 | MONEYPOINT GIS 400SB1-2CB | bar: Week 20 Tu 14; Week 20 Fr 17 to Week 21 Fr 24
TO-24-MP GIS-400SB1-3CB-02 | MONEYPOINT GIS 400SB1-3CB | bar: Week 20 Tu 14; Week 20 Fr 17 to Week 21 Fr 24
TO-24-MP GIS-T4001-01 | MONEYPOINT GIS T4001 | bar: Week 20 Tu 14; Week 20 Fr 17 to Week 21 Fr 24
TO-24-110 kV A1 @ GAL GIS-01 | GALWAY GIS 110 kV A1 | bar: Su 12 to Week 20 Tu 14
TO-24-110 kV B1 @ GAL GIS-01 | GALWAY GIS 110 kV B1 | bar: Su 12 to Week 20 Tu 14
TO-24-GAL GIS-110SA1-2CB-01 | GALWAY GIS 110SA1-2CB | bar: Su 12 to Week 20 Tu 14
TO-24-GAL GIS-110SA1-3CB-01 | GALWAY GIS 110SA1-3CB | bar: Su 12 to Week 20 Tu 14
TO-24-GAL GIS-110SB1-2CB-01 | GALWAY GIS 110SB1-2CB | bar: Su 12 to Week 20 Tu 14
TO-24-GAL GIS-110SB1-3CB-01 | GALWAY GIS 110SB1-3CB | bar: Su 12 to Week 20 Tu 14
TO-24-DND-110SB1-2CB-03 | DARNDALE 110SB1-2CB
TO-24-ROP-110SA1-2CB-01 | ROSSPILE 110SA1-2CB
TO-24-110 kV A1 @ GAL GIS-02 | GALWAY GIS 110 kV A1
TO-24-110 kV B1 @ GAL GIS-02 | GALWAY GIS 110 kV B1
TO-24-GAL GIS-110SA1-2CB-02 | GALWAY GIS 110SA1-2CB
TO-24-GAL GIS-110SA1-3CB-02 | GALWAY GIS 110SA1-3CB
TO-24-GAL GIS-110SB1-2CB-02 | GALWAY GIS 110SB1-2CB
TO-24-GAL GIS-110SB1-3CB-02 | GALWAY GIS 110SB1-3CB
TO-24-GAL GIS-SAL-1-01 | GALWAY GIS SALTHILL
TO-24-LOU-MLN-1-01 | LOUTH MULLAGHARLIN | bar: Week 20 Fr 17 to Week 21 Mo 27
TO-24-INC-MAY-2-02 | INCHICORE MAYNOOTH 2 | bar: Su 12 to Week 20 Tu 14
TO-24-ROP-110SB1-2CB-01 | ROSSPILE 110SB1-2CB
TO-24-SLC-T122-03 | SLIEVECALLAN T122
TO-24-220 kV A2 @ CRU-03 | CRUISERATH 220 kV A2 | bar: Week 20 Fr 17
TO-24-220 kV B2 @ CRU-03 | CRUISERATH 220 kV B2 | bar: Week 20 Fr 17
TO-24-CRU-220K2-05 | CRUISERATH 220K2 | bar: Week 20 Fr 17
TO-24-CRU-SA1-2CB-05 | CRUISERATH 220SA1-2CB | bar: Week 20 Fr 17
TO-24-CRU-SB1-2CB-05 | CRUISERATH 220SB1-2CB | bar: Week 20 Fr 17
TO-24-CRU-CDU-2-05 | CRUISERATH CORDUFF 2 | bar: Week 20 Fr 17
TO-24-110 kV A2 @ AA GIS-01 | ARDNACRUSHA GIS 110 kV A2 | bar: Su 12 to Week 20 Tu 14
TO-24-110 kV B2 @ AA GIS-01 | ARDNACRUSHA GIS 110 kV B2 | bar: Su 12 to Week 20 Tu 14
Report covers outages commencing/returning/spanning the period: 13/05/2024 - 26/05/2024
Outages commencing/returning in Week 20
OUTAGE ID | PLANT | Week 20 Mo 13: Week 20; Week 21 Mo 20: Week 21
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
TO-24-AA GIS-110K2-01 | ARDNACRUSHA GIS 110K2 | bar: Su 12 to Week 20 Th 16
TO-24-AA GIS-110SA1-2CB-01 | ARDNACRUSHA GIS 110SA1-2CB | bar: Su 12 to Week 20 Th 16
TO-24-AA GIS-110SB1-2CB-01 | ARDNACRUSHA GIS 110SB1-2CB | bar: Su 12 to Week 20 Th 16
TO-24-AA GIS-ENN-1-04 | ARDNACRUSHA GIS ENNIS | bar: Su 12 to Week 20 Th 16
TO-24-220 kV A2 @ CUL-02 | CULLENAGH 220 kV A2 | bar: Su 12 to Week 20 Th 16
TO-24-220 kV B2 @ CUL-02 | CULLENAGH 220 kV B2 | bar: Su 12 to Week 20 Th 16
TO-24-BVK-T2101-01 | BALLYVOUSKILL T2101 | bar: Week 20 Fr 17 to Week 21 Mo 27
TO-24-CLE-WOO-1-01 | CLONEE WOODLAND | bar: Week 20 Fr 17 to Week 21 Mo 27
TO-24-KYT-WOO-1-01 | KELLYSTOWN WOODLAND | bar: Week 20 Fr 17 to Week 21 Mo 27
TO-24-ATH-LA-1-02 | ATHLONE LANESBORO | bar: Su 12 to Week 20 Fr 17
Outages commencing/returning in Week 21
OUTAGE ID | PLANT | Week 20 Mo 13: Week 20; Week 21 Mo 20: Week 21
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
TO-24-110 kV A1 @ CSH-05 | CASHLA 110 kV A1 | bar: Week 21 Mo 20
TO-24-CSH-GAL GIS-1-01 | CASHLA GALWAY GIS 1 | bar: Week 21 Mo 20
TO-24-220 kV A1/A2 @ FLA-01 | FLAGFORD 220 kV A1/A2 | bar: Week 21 Mo 20; Week 21 Th 23 to Week 21 Fr 24
TO-24-220 kV B1/B2 @ FLA-01 | FLAGFORD 220 kV B1/B2 | bar: Week 21 Mo 20; Week 21 Th 23 to Week 21 Fr 24
TO-24-FLA-220K1-2-01 | FLAGFORD 220K1-2 | bar: Week 21 Mo 20; Week 21 Th 23 to Week 21 Fr 24
TO-24-220 kV A1 @ MP GIS-01 | MONEYPOINT GIS 220 kV A1 | bar: Week 21 Mo 20; Week 21 Th 23 to Week 21 Fr 24
TO-24-220 kV B1 @ MP GIS-01 | MONEYPOINT GIS 220 kV B1 | bar: Week 21 Mo 20; Week 21 Th 23 to Week 21 Fr 24
TO-24-MP GIS-220K1-02 | MONEYPOINT GIS 220K1 | bar: Week 21 Mo 20; Week 21 Th 23 to Week 21 Fr 24
TO-24-MP GIS-220SA1-2CB-02 | MONEYPOINT GIS 220SA1-2CB | bar: Week 21 Mo 20; Week 21 Th 23 to Week 21 Fr 24
TO-24-MP GIS-220SB1-2CB-02 | MONEYPOINT GIS 220SB1-2CB | bar: Week 21 Mo 20; Week 21 Th 23 to Week 21 Fr 24
TO-24-MP GIS-T4201-01 | MONEYPOINT GIS T4201 | bar: Week 21 Mo 20; Week 21 Th 23 to Week 21 Fr 24
TO-24-CBT-T2103-01 | CASTLEBAGOT T2103 | bar: Week 21 Mo 20; Week 21 Th 23 to Week 21 Mo 27
TO-24-CRO-T121-02 | COOLROE T121 | bar: Week 21 Mo 20; Week 21 Th 23 to Week 21 Mo 27
TO-24-FIN-T2104-03 | FINGLAS T2104 | bar: Week 21 Mo 20; Week 21 Th 23 to Week 21 Mo 27
TO-24-KLN-KPG-1-01 | KILLONAN KILPADDOGE | bar: Week 21 Mo 20; Week 21 Th 23 to Week 21 Mo 27
TO-24-220 kV A4 @ KPG-01 | KILPADDOGE 220 kV A4 | bar: Week 21 Mo 20; Week 21 Th 23 to Week 21 Mo 27
TO-24-220 kV B4 @ KPG-01 | KILPADDOGE 220 kV B4 | bar: Week 21 Mo 20; Week 21 Th 23 to Week 21 Mo 27
TO-24-KPG-220K4-02 | KILPADDOGE 220K4 | bar: Week 21 Mo 20; Week 21 Th 23 to Week 21 Mo 27
TO-24-KPG-220SA2-4CB-02 | KILPADDOGE 220SA2-4CB | bar: Week 21 Mo 20; Week 21 Th 23 to Week 21 Mo 27
TO-24-KPG-220SB2-4CB-01 | KILPADDOGE 220SB2-4CB | bar: Week 21 Mo 20; Week 21 Th 23 to Week 21 Mo 27
TO-24-AD-WHI-1-01 | AGHADA WHITEGATE | bar: Week 21 Th 23
TO-24-220 kV A2 @ GI GIS-01 | GREAT ISLAND GIS 220 kV A2 | bar: Week 21 Th 23
TO-24-GI GIS-220K2-01 | GREAT ISLAND GIS 220K2 | bar: Week 21 Th 23
TO-24-GI GIS-220SA1-2CB-04 | GREAT ISLAND GIS 220SA1-2CB | bar: Week 21 Th 23
TO-24-LIS-CAP2-01 | LISDRUM CAP2 | bar: Week 21 Th 23 to Week 21 Fr 24
TO-24-GI GIS-T2004-02 | GREAT ISLAND GIS T2004 | bar: Week 21 Th 23 to Week 21 Mo 27
TO-24-110 kV B2/B3 @ MAY-02 | MAYNOOTH 110 kV B2/B3 | bar: Week 21 Th 23 to Week 21 Mo 27
TO-24-AA GIS-T104-01 | ARDNACRUSHA GIS T104 | bar: Su 12 to Week 21 Mo 20
TO-24-RRU-110SA1-03 | RATRUSSAN 110SA1 | bar: Su 12 to Week 21 Mo 20
TO-24-RRU-110SA2-03 | RATRUSSAN 110SA2 | bar: Su 12 to Week 21 Mo 20
TO-24-RRU-SKL-1-03 | RATRUSSAN SHANKILL | bar: Su 12 to Week 21 Mo 20
TO-24-RRU-T121-03 | RATRUSSAN T121 | bar: Su 12 to Week 21 Mo 20
TO-24-RRU-T122-01 | RATRUSSAN T122 | bar: Su 12 to Week 21 Mo 20
Outages spanning Weeks 20-21
OUTAGE ID | PLANT | Week 20 Mo 13: Week 20; Week 21 Mo 20: Week 21
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
TO-24-AD-T2102-04 | AGHADA T2102
TO-24-AA GIS-T101-01 | ARDNACRUSHA GIS T101
TO-24-BAL-DRY-1-05 | BALTRASNA DRYBRIDGE
TO-24-BAN-CAP1-03 | BANDON CAP1
TO-24-BIN-CF-1-01 | BINBANE CATHALEENS FALL
TO-24-BOL-T141-01 | BOOLTIAGH T141
TO-24-COS-FLA-1-03 | CARRICK ON SHANNON FLAGFORD 1
Report covers outages commencing/returning/spanning the period: 13/05/2024 - 26/05/2024
Outages spanning Weeks 20-21
OUTAGE ID | PLANT | Week 20 Mo 13: Week 20; Week 21 Mo 20: Week 21
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
TO-24-CKM-PB-1-04 | CARRICKMINES POOLBEG
TO-24-110 kV A2 @ CSH-04 | CASHLA 110 kV A2
TO-24-110 kV B2 @ CSH-04 | CASHLA 110 kV B2
TO-24-220 kV B2 @ CSH-01 | CASHLA 220 kV B2
TO-24-CSH-220K2-4-03 | CASHLA 220K2-4
TO-24-CSH-CAP2-01 | CASHLA CAP2
TO-24-CSH-T2102-01 | CASHLA T2102
TO-24-110 kV A2 @ CF-01 | CATHALEENS FALL 110 kV A2
TO-24-CLG-110K1-02 | CLOGHRAN 110K1
TO-24-CLN-T142-01 | CLOON T142
TO-24-CUL-KRA-1-01 | CULLENAGH KNOCKRAHA
TO-24-DND-T121-01 | DARNDALE T121
TO-24-110 kV A1 @ FLA-04 | FLAGFORD 110 kV A1
TO-24-110 kV B1 @ FLA-05 | FLAGFORD 110 kV B1
TO-24-GAL-T102-01 | GALWAY T102
TO-24-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-24-GI-T141-01 | GREAT ISLAND T141
TO-24-INC-220K1-2-02 | INCHICORE 220K1-2
TO-24-KPG-TB-1-02 | KILPADDOGE TARBERT 1
TO-24-220 kV A2 @ KRA-01 | KNOCKRAHA 220 kV A2
TO-24-220 kV B2 @ KRA-01 | KNOCKRAHA 220 kV B2
TO-24-KRA-220K4-02 | KNOCKRAHA 220K4
TO-24-KRA-220SA1-2CB-01 | KNOCKRAHA 220SA1-2CB
TO-24-KRA-220SA2-4CB-02 | KNOCKRAHA 220SA2-4CB
TO-24-KRA-220SB1-2CB-01 | KNOCKRAHA 220SB1-2CB
TO-24-KRA-220SB2-4CB-01 | KNOCKRAHA 220SB2-4CB
TO-24-KRA-RAF-1-01 | KNOCKRAHA RAFFEEN
TO-24-110 kV A1 @ LOU-01 | LOUTH 110 kV A1
TO-24-110 kV B1 @ LOU-01 | LOUTH 110 kV B1
TO-24-LOU-RRU-1-01 | LOUTH RATRUSSAN
TO-24-MAY-TSB-1-02 | MAYNOOTH THORNSBERRY
TO-24-MUL-CAP1-01 | MULLINGAR CAP1
TO-24-NAV-T141-01 | NAVAN T141
TO-24-PB-R2002-02 | POOLBEG R2002
TO-24-PRO-TB-1-01 | PROSPECT TARBERT
TO-24-110 kV A2 @ RAF-02 | RAFFEEN 110 kV A2
TO-24-110 kV B2 @ RAF-02 | RAFFEEN 110 kV B2
TO-24-TB-220K1-2-02 | TARBERT 220K1-2
TO-24-TB-T2003-01 | TARBERT T2003
TO-24-TB-T2004-01 | TARBERT T2004
TO-24-TB-T2004-02
TO-24-TB-T2101-01 | TARBERT T2101
TO-24-TB-T2101-02
TO-24-THU-CAP1-04 | THURLES CAP1
TO-24-TRL-CAP2-01 | TRALEE CAP2