## Wks 22 - 23
Report covers outages commencing/returning/spanning the period: 27/05/2024 - 09/06/2024
Outages commencing/returning in Week 22
OUTAGE ID | PLANT |  | Week 22 | [6 empty] | Week 23
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
TO-24-110 kV A1 @ GAL GIS-02 | GALWAY GIS 110 kV A1
TO-24-110 kV B1 @ GAL GIS-02 | GALWAY GIS 110 kV B1
TO-24-GAL GIS-110SA1-2CB-02 | GALWAY GIS 110SA1-2CB
TO-24-GAL GIS-110SA1-3CB-02 | GALWAY GIS 110SA1-3CB
TO-24-GAL GIS-110SB1-2CB-02 | GALWAY GIS 110SB1-2CB
TO-24-GAL GIS-110SB1-3CB-02 | GALWAY GIS 110SB1-3CB
TO-24-GAL GIS-SAL-1-01 | GALWAY GIS SALTHILL
TO-24-BOG-TTU-1-01 | BANOGE TULLABEG | bar: Week 22 We 29
TO-24-BYH-CDL-1-01 | BALLYNAHULLA CORDAL | bar: Week 22 We 29 to Week 22 Th 30
TO-24-CDL-110SA1-01 | CORDAL 110SA1 | bar: Week 22 We 29 to Week 22 Th 30
TO-24-CDL-110SA2-01 | CORDAL 110SA2 | bar: Week 22 We 29 to Week 22 Th 30
TO-24-CDL-T132-01 | CORDAL T132 | bar: Week 22 We 29 to Week 22 Th 30
TO-24-CDL-T141-01 | CORDAL T141 | bar: Week 22 We 29 to Week 22 Th 30
TO-24-BNK-T122-02 | BARNAKYLE T122 | bar: Week 22 We 29 to Week 22 Fr 31
TO-24-DND-T122-01 | DARNDALE T122 | bar: Week 22 We 29 to Week 22 Fr 31
TO-24-400 kV A2 @ MP GIS-01 | MONEYPOINT GIS 400 kV A2 | bar: Week 22 We 29 to Week 22 Fr 31
TO-24-400 kV B2 @ MP GIS-01 | MONEYPOINT GIS 400 kV B2 | bar: Week 22 We 29 to Week 22 Fr 31
TO-24-MP GIS-400SA1-2CB-03 | MONEYPOINT GIS 400SA1-2CB | bar: Week 22 We 29 to Week 22 Fr 31
TO-24-MP GIS-400SA2-4CB-03 | MONEYPOINT GIS 400SA2-4CB | bar: Week 22 We 29 to Week 22 Fr 31
TO-24-MP GIS-400SB1-2CB-05 | MONEYPOINT GIS 400SB1-2CB | bar: Week 22 We 29 to Week 22 Fr 31
TO-24-MP GIS-400SB2-4CB-01 | MONEYPOINT GIS 400SB2-4CB | bar: Week 22 We 29 to Week 22 Fr 31
TO-24-MP GIS-T4002-02 | MONEYPOINT GIS T4002 | bar: Week 22 We 29 to Week 22 Fr 31
TO-24-110 kV A2 @ CAH-03 | CAHIR 110 kV A2 | bar: Week 22 We 29 to Week 23 Fr 7
TO-24-110 kV B2 @ CAH-03 | CAHIR 110 kV B2 | bar: Week 22 We 29 to Week 23 Fr 7
TO-24-CAH-DOO-1-01 | CAHIR DOON | bar: Week 22 We 29 to Week 23 Fr 7
TO-24-KBY-MR-1-02 | KILBARRY MARINA 1 | bar: Week 22 We 29 to Week 23 Mo 10
TO-24-KBY-MR-2-02 | KILBARRY MARINA 2 | bar: Week 22 We 29 to Week 23 Mo 10
TO-24-110 kV B2/B3 @ MAY-02 | MAYNOOTH 110 kV B2/B3 | bar: Su 26
TO-24-DEY-T134-03 | DERRYCARNEY T134
TO-24-110 kV A2 @ FIN-03 | FINGLAS 110 kV A2 | bar: Week 22 We 29 to Week 22 Th 30
TO-24-110 kV B2 @ FIN-03 | FINGLAS 110 kV B2 | bar: Week 22 We 29 to Week 22 Th 30
TO-24-110 kV A2/A3 @ MAY-02 | MAYNOOTH 110 kV A2/A3 | bar: Week 22 We 29 to Week 23 Mo 3
TO-24-110 kV A1 @ KBY-02 | KILBARRY 110 kV A1 | bar: Week 22 We 29 to Week 23 Mo 10
TO-24-110 kV B1 @ KBY-02 | KILBARRY 110 kV B1 | bar: Week 22 We 29 to Week 23 Mo 10
TO-24-CUL-KRA-1-01 | CULLENAGH KNOCKRAHA | bar: Su 26
TO-24-220 kV A2 @ KRA-01 | KNOCKRAHA 220 kV A2 | bar: Su 26
TO-24-220 kV B2 @ KRA-01 | KNOCKRAHA 220 kV B2 | bar: Su 26
TO-24-KRA-220K4-02 | KNOCKRAHA 220K4 | bar: Su 26
TO-24-KRA-220SA1-2CB-01 | KNOCKRAHA 220SA1-2CB | bar: Su 26
TO-24-KRA-220SA2-4CB-02 | KNOCKRAHA 220SA2-4CB | bar: Su 26
TO-24-KRA-220SB1-2CB-01 | KNOCKRAHA 220SB1-2CB | bar: Su 26
TO-24-KRA-220SB2-4CB-01 | KNOCKRAHA 220SB2-4CB | bar: Su 26
TO-24-KRA-RAF-1-01 | KNOCKRAHA RAFFEEN | bar: Su 26
TO-24-MLC-T121-01 | MOUNTLUCAS T121 | bar: Week 22 We 29
TO-24-DSN-KLS-1-03 | DUNSTOWN KELLIS | bar: Week 22 We 29 to Week 23 Tu 4
TO-24-KLS-T2101-05 | KELLIS T2101 | bar: Week 22 We 29 to Week 23 Tu 4
TO-24-110 kV A2 @ CDU-03 | CORDUFF 110 kV A2 | bar: Week 22 We 29 to Week 23 Mo 10
TO-24-110 kV A4 @ CDU-02 | CORDUFF 110 kV A4 | bar: Week 22 We 29 to Week 23 Mo 10
TO-24-110 kV B2 @ CDU-04 | CORDUFF 110 kV B2 | bar: Week 22 We 29 to Week 23 Mo 10
TO-24-110 kV B4 @ CDU-02 | CORDUFF 110 kV B4 | bar: Week 22 We 29 to Week 23 Mo 10
TO-24-LOU-T2101-04 | LOUTH T2101 | bar: Week 22 Th 30 to Week 23 Mo 10
TO-24-BVK-T2101-01 | BALLYVOUSKILL T2101 | bar: Su 26; Week 22 We 29 to Week 22 Fr 31
TO-24-GI GIS-T2004-02 | GREAT ISLAND GIS T2004 | bar: Su 26; Week 22 We 29 to Week 22 Fr 31
TO-24-KLN-KPG-1-01 | KILLONAN KILPADDOGE | bar: Su 26; Week 22 We 29 to Week 22 Fr 31
TO-24-220 kV A4 @ KPG-01 | KILPADDOGE 220 kV A4 | bar: Su 26; Week 22 We 29 to Week 22 Fr 31
TO-24-220 kV B4 @ KPG-01 | KILPADDOGE 220 kV B4 | bar: Su 26; Week 22 We 29 to Week 22 Fr 31
TO-24-KPG-220K4-02 | KILPADDOGE 220K4 | bar: Su 26; Week 22 We 29 to Week 22 Fr 31
TO-24-KPG-220SA2-4CB-02 | KILPADDOGE 220SA2-4CB | bar: Su 26; Week 22 We 29 to Week 22 Fr 31
TO-24-KPG-220SB2-4CB-01 | KILPADDOGE 220SB2-4CB | bar: Su 26; Week 22 We 29 to Week 22 Fr 31
TO-24-MP GIS-T4001-01 | MONEYPOINT GIS T4001 | bar: Su 26; Week 22 We 29 to Week 22 Fr 31
TO-24-ARV-NAV-1-04 | ARVA NAVAN | bar: Week 22 Sa 1 to Week 22 Su 2
Report covers outages commencing/returning/spanning the period: 27/05/2024 - 09/06/2024
Outages commencing/returning in Week 22
OUTAGE ID | PLANT | Week 22 Mo 27: Week 22; Week 23 Mo 3: Week 23
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
TO-24-GOR-NAV-2-05 | GORMAN NAVAN 2 | bar: Week 22 Sa 1 to Week 22 Su 2
TO-24-NAV-110SA1-2CB-04 | NAVAN 110SA1-2CB | bar: Week 22 Sa 1 to Week 22 Su 2
TO-24-NAV-M/CAP1-03 | NAVAN M/CAP1 | bar: Week 22 Sa 1 to Week 22 Su 2
Outages commencing/returning in Week 23
OUTAGE ID | PLANT | Week 22 Mo 27: Week 22; Week 23 Mo 3: Week 23
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
TO-24-CKM GIS-220SA1-2CB-01 | CARRICKMINES GIS 220SA1-2CB | bar: Week 23 Tu 4 to Week 23 We 5
TO-24-GLE-KCR-1-01 | GLENLARA KNOCKACUMMER | bar: Week 23 Tu 4 to Week 23 Fr 7
TO-24-KCR-T121-01 | KNOCKACUMMER T121 | bar: Week 23 Tu 4 to Week 23 Fr 7
TO-24-CSH-DLT-1-01 | CASHLA DALTON | bar: Week 23 Tu 4 to Week 23 Mo 10
TO-24-GAL GIS-T142-04 | GALWAY GIS T142 | bar: Week 23 Tu 4 to Week 23 Mo 10
TO-24-GOR-NAV-2-02 | GORMAN NAVAN 2 | bar: Week 23 Tu 4 to Week 23 Mo 10
TO-24-110 kV B2/B3 @ MAY-03 | MAYNOOTH 110 kV B2/B3 | bar: Week 23 Tu 4 to Week 23 Mo 10
TO-24-PA-T101-04 | POLLAPHUCA T101 | bar: Week 23 Tu 4 to Week 23 Mo 10
TO-24-LPT-T2002-02 | LONG POINT T2002 | bar: Su 26 to Week 23 Tu 4
TO-24-BYH-110SA1-2CB-01 | BALLYNAHULLA 110SA1-2CB | bar: Week 23 We 5
TO-24-CDU-110K1-3-01 | CORDUFF 110K1-3 | bar: Week 23 We 5
TO-24-CKG-110K2-02 | CORKAGH 110K2 | bar: Week 23 We 5
TO-24-DEY-110K2-01 | DERRYCARNEY 110K2 | bar: Week 23 We 5
TO-24-AA GIS-LIM-1-01 | ARDNACRUSHA GIS LIMERICK | bar: Week 23 We 5 to Week 23 Fr 7
TO-24-BDA-T102-01 | BARODA T102 | bar: Week 23 We 5 to Week 23 Fr 7
TO-24-KLN-T2101-01 | KILLONAN T2101 | bar: Week 23 We 5 to Week 23 Fr 7
TO-24-CF-SRA-1-02 | CATHALEENS FALL SRANANAGH 1 | bar: Week 23 We 5 to Week 23 Mo 10
TO-24-DAL-T141-02 | DALLOW T141 | bar: Week 23 We 5 to Week 23 Mo 10
TO-24-DAL,T-DAL-1-02 | DALLOW tee DALLOW | bar: Week 23 We 5 to Week 23 Mo 10
TO-24-DAL,T-DEY-1-03 | DALLOW tee DERRYCARNEY | bar: Week 23 We 5 to Week 23 Mo 10
TO-24-220 kV A1 @ GI GIS-03 | GREAT ISLAND GIS 220 kV A1 | bar: Week 23 We 5 to Week 23 Mo 10
TO-24-220 kV B1 @ GI GIS-02 | GREAT ISLAND GIS 220 kV B1 | bar: Week 23 We 5 to Week 23 Mo 10
TO-24-GI GIS-KLS-1-01 | GREAT ISLAND GIS KELLIS | bar: Week 23 We 5 to Week 23 Mo 10
TO-24-KLS-T2102-01 | KELLIS T2102 | bar: Week 23 We 5 to Week 23 Mo 10
TO-24-110 kV A1 @ SRA-02 | SRANANAGH 110 kV A1 | bar: Week 23 We 5 to Week 23 Mo 10
TO-24-110 kV B1 @ SRA-01 | SRANANAGH 110 kV B1 | bar: Week 23 We 5 to Week 23 Mo 10
TO-24-MP GIS-400K4-01 | MONEYPOINT GIS 400K4 | bar: Week 23 Th 6
TO-24-BOL-110SA1-3CB-02 | BOOLTIAGH 110SA1-3CB | bar: Week 23 Th 6 to Week 23 Fr 7
TO-24-BOL-ENN-1-02 | BOOLTIAGH ENNIS | bar: Week 23 Th 6 to Week 23 Fr 7
TO-24-BOL-T143-02 | BOOLTIAGH T143 | bar: Week 23 Th 6 to Week 23 Fr 7
TO-24-CKM GIS-220SA1-3CB-01 | CARRICKMINES GIS 220SA1-3CB | bar: Week 23 Th 6 to Week 23 Fr 7
TO-24-CLN-110SA1-02 | CLOON 110SA1 | bar: Week 23 Th 6 to Week 23 Mo 10
TO-24-CLN-110SA2-02 | CLOON 110SA2 | bar: Week 23 Th 6 to Week 23 Mo 10
TO-24-CLN-LA-1-02 | CLOON LANESBORO | bar: Week 23 Th 6 to Week 23 Mo 10
TO-24-BOL-T141-01 | BOOLTIAGH T141 | bar: Su 26 to Week 23 Fr 7
TO-24-NAV-T141-01 | NAVAN T141 | bar: Su 26 to Week 23 Fr 7
Outages spanning Weeks 22-23
OUTAGE ID | PLANT | Week 22 Mo 27: Week 22; Week 23 Mo 3: Week 23
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
TO-24-AA GIS-T101-01 | ARDNACRUSHA GIS T101
TO-24-BAL-DRY-1-05 | BALTRASNA DRYBRIDGE
TO-24-BAN-CAP1-03 | BANDON CAP1
TO-24-BIN-CF-1-01 | BINBANE CATHALEENS FALL
TO-24-BLU-T131-01 | BLUNDELSTOWN T131
TO-24-COS-FLA-1-03 | CARRICK ON SHANNON FLAGFORD 1
TO-24-110 kV A2 @ CSH-04 | CASHLA 110 kV A2
TO-24-110 kV B2 @ CSH-04 | CASHLA 110 kV B2
TO-24-220 kV B2 @ CSH-01 | CASHLA 220 kV B2
TO-24-CSH-220K2-4-03 | CASHLA 220K2-4
TO-24-CSH-CAP2-01 | CASHLA CAP2
Report covers outages commencing/returning/spanning the period: 27/05/2024 - 09/06/2024
Outages spanning Weeks 22-23
OUTAGE ID | PLANT | Week 22 Mo 27: Week 22; Week 23 Mo 3: Week 23
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
TO-24-CSH-T2102-01 | CASHLA T2102
TO-24-110 kV A2 @ CF-01 | CATHALEENS FALL 110 kV A2
TO-24-CLG-110K1-02 | CLOGHRAN 110K1
TO-24-CLE-WOO-1-01 | CLONEE WOODLAND
TO-24-CLN-T142-01 | CLOON T142
TO-24-CRO-T121-02 | COOLROE T121
TO-24-220 kV A2 @ CDU-04 | CORDUFF 220 kV A2
TO-24-220 kV A4 @ CDU-04 | CORDUFF 220 kV A4
TO-24-220 kV B2 @ CDU-04 | CORDUFF 220 kV B2
TO-24-220 kV B4 @ CDU-04 | CORDUFF 220 kV B4
TO-24-DAL,T-SH-1-02 | DALLOW tee SHANNONBRIDGE
TO-24-DND-T121-01 | DARNDALE T121
TO-24-110 kV A1 @ FLA-04 | FLAGFORD 110 kV A1
TO-24-110 kV B1 @ FLA-05 | FLAGFORD 110 kV B1
TO-24-GAL-T102-01 | GALWAY T102
TO-24-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-24-GI-T141-01 | GREAT ISLAND T141
TO-24-INC-220K1-2-02 | INCHICORE 220K1-2
TO-24-KLS-220K1-2-01 | KELLIS 220K1-2
TO-24-KYT-WOO-1-01 | KELLYSTOWN WOODLAND
TO-24-KPG-TB-1-02 | KILPADDOGE TARBERT 1
TO-24-110 kV A1 @ LOU-01 | LOUTH 110 kV A1
TO-24-110 kV B1 @ LOU-01 | LOUTH 110 kV B1
TO-24-LOU-MLN-1-01 | LOUTH MULLAGHARLIN
TO-24-LOU-RRU-1-01 | LOUTH RATRUSSAN
TO-24-MAY-TSB-1-02 | MAYNOOTH THORNSBERRY
TO-24-MUL-CAP1-01 | MULLINGAR CAP1
TO-24-PB-R2002-02 | POOLBEG R2002
TO-24-PRO-TB-1-01 | PROSPECT TARBERT
TO-24-110 kV A2 @ RAF-02 | RAFFEEN 110 kV A2
TO-24-110 kV B2 @ RAF-02 | RAFFEEN 110 kV B2
TO-24-TB-220K1-2-02 | TARBERT 220K1-2
TO-24-TB-T2003-01 | TARBERT T2003
TO-24-TB-T2004-01 | TARBERT T2004
TO-24-TB-T2004-02
TO-24-TB-T2101-02 | TARBERT T2101
TO-24-TB-T2101-01
TO-24-THU-CAP1-04 | THURLES CAP1
TO-24-TRL-CAP2-01 | TRALEE CAP2