## Wks 24 - 25
Report covers outages commencing/returning/spanning the period: 10/06/2024 - 23/06/2024
Outages commencing/returning in Week 24
OUTAGE ID | PLANT |  | Week 24 | [6 empty] | Week 25
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
TO-24-AUG-CFM-2-01 | AUGHINISH CASTLEFARM 2
TO-24-AUG-SK-3-01 | AUGHINISH SEALROCK 3
TO-24-BYH-110K1-01 | BALLYNAHULLA 110K1
TO-24-CFM-T102-01 | CASTLEFARM T102
TO-24-CF-T103-01 | CATHALEENS FALL T103
TO-24-CLA-MAC-1-02 | CLASHAVOON MACROOM 1
TO-24-CRA-LWD-1-01 | CRANE LODGEWOOD
TO-24-CRY-LWD-1-01 | CRORY LODGEWOOD
TO-24-CRY-T121-01 | CRORY T121
TO-24-110 kV A1 @ DND-01 | DARNDALE 110 kV A1
TO-24-110 kV B1 @ DND-01 | DARNDALE 110 kV B1
TO-24-DND-110K1-01 | DARNDALE 110K1
TO-24-DND-110SA1-2CB-01 | DARNDALE 110SA1-2CB
TO-24-DND-110SB1-2CB-01 | DARNDALE 110SB1-2CB
TO-24-110 kV A1 @ KNY-01 | KNOCKRANNY 110 kV A1
TO-24-110 kV B1 @ KNY-01 | KNOCKRANNY 110 kV B1
TO-24-LWD-110SA1-01 | LODGEWOOD 110SA1
TO-24-LWD-110SA2-01 | LODGEWOOD 110SA2
TO-24-SK-T103-01 | SEALROCK T103
TO-24-110 kV A1 @ GAL GIS-01 | GALWAY GIS 110 kV A1 | bar: Week 24 Sa 15 to Week 24 Su 16
TO-24-110 kV B1 @ GAL GIS-01 | GALWAY GIS 110 kV B1 | bar: Week 24 Sa 15 to Week 24 Su 16
TO-24-GAL GIS-110SA1-2CB-01 | GALWAY GIS 110SA1-2CB | bar: Week 24 Sa 15 to Week 24 Su 16
TO-24-GAL GIS-110SA1-3CB-01 | GALWAY GIS 110SA1-3CB | bar: Week 24 Sa 15 to Week 24 Su 16
TO-24-GAL GIS-110SB1-2CB-01 | GALWAY GIS 110SB1-2CB | bar: Week 24 Sa 15 to Week 24 Su 16
TO-24-GAL GIS-110SB1-3CB-01 | GALWAY GIS 110SB1-3CB | bar: Week 24 Sa 15 to Week 24 Su 16
TO-24-KPG-TRL-2-02 | KILPADDOGE TRALEE 2 | bar: Week 24 Sa 15 to Week 25 Mo 17
TO-24-AA GIS-T102-01 | ARDNACRUSHA GIS T102 | bar: Week 24 Sa 15 to Week 25 We 19
TO-24-BRY-RAF-2-01 | BARNAHELY RAFFEEN 2 | bar: Week 24 Sa 15 to Week 25 Mo 24
TO-24-DRU-ENN-1-02 | DRUMLINE ENNIS | bar: Week 24 Sa 15 to Week 25 Mo 24
TO-24-DAL-T141-02 | DALLOW T141 | bar: Su 9
TO-24-DAL,T-DAL-1-02 | DALLOW tee DALLOW | bar: Su 9
TO-24-DAL,T-SH-1-02 | DALLOW tee SHANNONBRIDGE | bar: Su 9
TO-24-110 kV B2/B3 @ MAY-03 | MAYNOOTH 110 kV B2/B3 | bar: Su 9
TO-24-BNK-T121-01 | BARNAKYLE T121
TO-24-110 kV A2/A3 @ MAY-03 | MAYNOOTH 110 kV A2/A3 | bar: Week 24 Sa 15 to Week 25 Mo 17
TO-24-CHA-MAL-1-01 | CHARLEVILLE MALLOW | bar: Week 24 Sa 15 to Week 25 Mo 24
TO-24-KLS-T2102-01 | KELLIS T2102 | bar: Su 9
TO-24-PA-T101-04 | POLLAPHUCA T101 | bar: Su 9
TO-24-110 kV A1 @ CAH-02 | CAHIR 110 kV A1
TO-24-CAH-KHL-1-01 | CAHIR KILL HILL
TO-24-KLN-T2103-01 | KILLONAN T2103
TO-24-SLB-T132-01 | SLIABH BAWN T132
TO-24-AGL-DYN-1-04 | AGANNYGAL DERRYBRIEN
TO-24-DYN-T121-03 | DERRYBRIEN T121
TO-24-LOU-T2101-04 | LOUTH T2101 | bar: Su 9
TO-24-CSH-DLT-1-01 | CASHLA DALTON | bar: Su 9
TO-24-CLN-110SA1-02 | CLOON 110SA1 | bar: Su 9
TO-24-CLN-110SA2-02 | CLOON 110SA2 | bar: Su 9
TO-24-CLN-LA-1-02 | CLOON LANESBORO | bar: Su 9
TO-24-CLN-T142-01 | CLOON T142 | bar: Su 9
TO-24-110 kV A1 @ FLA-04 | FLAGFORD 110 kV A1 | bar: Su 9
TO-24-110 kV B1 @ FLA-05 | FLAGFORD 110 kV B1 | bar: Su 9
TO-24-KPG-TB-1-02 | KILPADDOGE TARBERT 1 | bar: Su 9; Week 24 Sa 15 to Week 24 Su 16
TO-24-TB-220K1-2-02 | TARBERT 220K1-2 | bar: Su 9; Week 24 Sa 15 to Week 24 Su 16
TO-24-TB-T2004-02 | TARBERT T2004 | bar: Su 9; Week 24 Sa 15 to Week 24 Su 16
TO-24-TB-T2101-02 | TARBERT T2101 | bar: Su 9; Week 24 Sa 15 to Week 24 Su 16
Report covers outages commencing/returning/spanning the period: 10/06/2024 - 23/06/2024
Outages commencing/returning in Week 25
OUTAGE ID | PLANT | Week 24 Mo 10: Week 24; Week 25 Mo 17: Week 25
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
TO-24-BLC-DND-1-01 | BELCAMP DARNDALE 1
TO-24-110 kV A1 @ DND-02 | DARNDALE 110 kV A1
TO-24-110 kV B1 @ DND-02 | DARNDALE 110 kV B1
TO-24-DND-110K1-02 | DARNDALE 110K1
TO-24-DND-110SA1-2CB-02 | DARNDALE 110SA1-2CB
TO-24-DND-110SB1-2CB-02 | DARNDALE 110SB1-2CB
TO-24-110 kV A1 @ FLA-05 | FLAGFORD 110 kV A1
TO-24-110 kV B1 @ FLA-06 | FLAGFORD 110 kV B1
TO-24-110 kV A1 @ GAL GIS-02 | GALWAY GIS 110 kV A1
TO-24-110 kV B1 @ GAL GIS-02 | GALWAY GIS 110 kV B1
TO-24-GAL GIS-110SA1-2CB-02 | GALWAY GIS 110SA1-2CB
TO-24-GAL GIS-110SA1-3CB-02 | GALWAY GIS 110SA1-3CB
TO-24-GAL GIS-110SB1-2CB-02 | GALWAY GIS 110SB1-2CB
TO-24-GAL GIS-110SB1-3CB-02 | GALWAY GIS 110SB1-3CB
TO-24-GAL GIS-SAL-1-01 | GALWAY GIS SALTHILL
TO-24-ATH-CAP3-01 | ATHLONE CAP3 | bar: Week 25 We 19 to Week 25 Fr 21
TO-24-BLI-DMY-1-01 | BALLYLICKEY DUNMANWAY | bar: Week 25 We 19 to Week 25 Fr 21
TO-24-BLI-T142-01 | BALLYLICKEY T142 | bar: Week 25 We 19 to Week 25 Fr 21
TO-24-CGG-DMY-1-03 | CARRIGDANGAN DUNMANWAY | bar: Week 25 We 19 to Week 25 Fr 21
TO-24-CGG-T131-02 | CARRIGDANGAN T131 | bar: Week 25 We 19 to Week 25 Fr 21
TO-24-CDK-LWD-1-01 | CASTLEDOCKRELL LODGEWOOD | bar: Week 25 We 19 to Week 25 Fr 21
TO-24-CDK-T121-01 | CASTLEDOCKRELL T121 | bar: Week 25 We 19 to Week 25 Fr 21
TO-24-CUN-T121-01 | CUNGHILL T121 | bar: Week 25 We 19 to Week 25 Fr 21
TO-24-DMY-110SA1-2CB-01 | DUNMANWAY 110SA1-2CB | bar: Week 25 We 19 to Week 25 Fr 21
TO-24-DMY-MAC-1-05 | DUNMANWAY MACROOM | bar: Week 25 We 19 to Week 25 Fr 21
TO-24-DMY-T141-02 | DUNMANWAY T141 | bar: Week 25 We 19 to Week 25 Fr 21
TO-24-KKY-CAP2-01 | KILKENNY CAP2 | bar: Week 25 We 19 to Week 25 Fr 21
TO-24-LWD-110SA1-02 | LODGEWOOD 110SA1 | bar: Week 25 We 19 to Week 25 Fr 21
TO-24-LWD-110SA2-02 | LODGEWOOD 110SA2 | bar: Week 25 We 19 to Week 25 Fr 21
TO-24-LWD-T2102-01 | LODGEWOOD T2102 | bar: Week 25 We 19 to Week 25 Fr 21
TO-24-400 kV A1 @ MP GIS-03 | MONEYPOINT GIS 400 kV A1 | bar: Week 25 We 19 to Week 25 Fr 21
TO-24-400 kV A3 @ MP GIS-01 | MONEYPOINT GIS 400 kV A3 | bar: Week 25 We 19 to Week 25 Fr 21
TO-24-MP GIS-400SA1-3CB-01 | MONEYPOINT GIS 400SA1-3CB | bar: Week 25 We 19 to Week 25 Fr 21
TO-24-ATH-SH-1-02 | ATHLONE SHANNONBRIDGE | bar: Week 25 We 19 to Week 25 Mo 24
TO-24-KPG-TB-2-03 | KILPADDOGE TARBERT 2 | bar: Week 25 We 19 to Week 25 Mo 24
TO-24-110 kV A1 @ SH-05 | SHANNONBRIDGE 110 kV A1 | bar: Week 25 We 19 to Week 25 Mo 24
TO-24-110 kV B1 @ SH-05 | SHANNONBRIDGE 110 kV B1 | bar: Week 25 We 19 to Week 25 Mo 24
TO-24-220 kV A1/A2 @ TB-02 | TARBERT 220 kV A1/A2 | bar: Week 25 We 19 to Week 25 Mo 24
TO-24-220 kV A1 @ GI GIS-03 | GREAT ISLAND GIS 220 kV A1 | bar: Su 9 to Week 24 Su 16
TO-24-220 kV B1 @ GI GIS-02 | GREAT ISLAND GIS 220 kV B1 | bar: Su 9 to Week 24 Su 16
TO-24-GI GIS-KLS-1-01 | GREAT ISLAND GIS KELLIS | bar: Su 9 to Week 24 Su 16
TO-24-FLA-T2101-01 | FLAGFORD T2101
TO-24-CKM GIS-220SA2-4CB-02 | CARRICKMINES GIS 220SA2-4CB | bar: Week 25 We 19
TO-24-CLO-CRD-1-01 | CLOGHER CROAGHONAGH | bar: Week 25 We 19 to Week 25 Fr 21
TO-24-CRD-T131-01 | CROAGHONAGH T131 | bar: Week 25 We 19 to Week 25 Fr 21
TO-24-AUG-MTN-1-01 | AUGHINISH MONETEEN | bar: Week 25 We 19 to Week 25 Mo 24
TO-24-COS-FLA-1-03 | CARRICK ON SHANNON FLAGFORD 1 | bar: Su 9 to Week 24 Su 16
TO-24-DND-T126-01 | DARNDALE T126 | bar: Week 25 We 19
TO-24-GAL GIS-T142-04 | GALWAY GIS T142 | bar: Week 25 We 19 to Week 25 Mo 24
TO-24-220 kV B1 @ AD-03 | AGHADA 220 kV B1 | bar: Week 25 Th 20
TO-24-AD-T2011/12-03 | AGHADA T2011/12 | bar: Week 25 Th 20
TO-24-220 kV B2 @ GOR-01 | GORMAN 220 kV B2 | bar: Week 25 Fr 21 to Week 25 Su 23
TO-24-GOR-LOU-1-04 | GORMAN LOUTH | bar: Week 25 Fr 21 to Week 25 Su 23
TO-24-CSH-TY-1-05 | CASHLA TYNAGH | bar: Week 25 Fr 21 to Week 25 Mo 24
Outages spanning Weeks 24-25
OUTAGE ID | PLANT | Week 24 Mo 10: Week 24; Week 25 Mo 17: Week 25
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
TO-24-AA GIS-T101-01 | ARDNACRUSHA GIS T101
Report covers outages commencing/returning/spanning the period: 10/06/2024 - 23/06/2024
Outages spanning Weeks 24-25
OUTAGE ID | PLANT | Week 24 Mo 10: Week 24; Week 25 Mo 17: Week 25
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
TO-24-BAL-DRY-1-05 | BALTRASNA DRYBRIDGE
TO-24-BAN-CAP1-03 | BANDON CAP1
TO-24-BIN-CF-1-01 | BINBANE CATHALEENS FALL
TO-24-BLU-T131-01 | BLUNDELSTOWN T131
TO-24-BOL-T141-01 | BOOLTIAGH T141
TO-24-110 kV A2 @ CSH-04 | CASHLA 110 kV A2
TO-24-110 kV B2 @ CSH-04 | CASHLA 110 kV B2
TO-24-220 kV B2 @ CSH-01 | CASHLA 220 kV B2
TO-24-CSH-220K2-4-03 | CASHLA 220K2-4
TO-24-CSH-CAP2-01 | CASHLA CAP2
TO-24-CSH-T2102-01 | CASHLA T2102
TO-24-110 kV A2 @ CF-01 | CATHALEENS FALL 110 kV A2
TO-24-CF-SRA-1-02 | CATHALEENS FALL SRANANAGH 1
TO-24-CLG-110K1-02 | CLOGHRAN 110K1
TO-24-CLE-WOO-1-01 | CLONEE WOODLAND
TO-24-CRO-T121-02 | COOLROE T121
TO-24-110 kV A2 @ CDU-03 | CORDUFF 110 kV A2
TO-24-110 kV A4 @ CDU-02 | CORDUFF 110 kV A4
TO-24-110 kV B2 @ CDU-04 | CORDUFF 110 kV B2
TO-24-110 kV B4 @ CDU-02 | CORDUFF 110 kV B4
TO-24-220 kV A2 @ CDU-04 | CORDUFF 220 kV A2
TO-24-220 kV A4 @ CDU-04 | CORDUFF 220 kV A4
TO-24-220 kV B2 @ CDU-04 | CORDUFF 220 kV B2
TO-24-220 kV B4 @ CDU-04 | CORDUFF 220 kV B4
TO-24-DAL,T-DEY-1-03 | DALLOW tee DERRYCARNEY
TO-24-DND-T121-01 | DARNDALE T121
TO-24-GAL-T102-01 | GALWAY T102
TO-24-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-24-GOR-NAV-2-02 | GORMAN NAVAN 2
TO-24-GI-T141-01 | GREAT ISLAND T141
TO-24-INC-220K1-2-02 | INCHICORE 220K1-2
TO-24-KLS-220K1-2-01 | KELLIS 220K1-2
TO-24-KYT-WOO-1-01 | KELLYSTOWN WOODLAND
TO-24-110 kV A1 @ KBY-02 | KILBARRY 110 kV A1
TO-24-110 kV B1 @ KBY-02 | KILBARRY 110 kV B1
TO-24-KBY-MR-1-02 | KILBARRY MARINA 1
TO-24-KBY-MR-2-02 | KILBARRY MARINA 2
TO-24-KTL-CAP1-02 | KILTEEL CAP1
TO-24-110 kV A1 @ LOU-01 | LOUTH 110 kV A1
TO-24-110 kV B1 @ LOU-01 | LOUTH 110 kV B1
TO-24-LOU-MLN-1-01 | LOUTH MULLAGHARLIN
TO-24-LOU-RRU-1-01 | LOUTH RATRUSSAN
TO-24-MAY-TSB-1-02 | MAYNOOTH THORNSBERRY
TO-24-MUL-CAP1-01 | MULLINGAR CAP1
TO-24-PB-R2002-02 | POOLBEG R2002
TO-24-PRO-TB-1-01 | PROSPECT TARBERT
TO-24-110 kV A2 @ RAF-02 | RAFFEEN 110 kV A2
TO-24-110 kV B2 @ RAF-02 | RAFFEEN 110 kV B2
TO-24-110 kV A1 @ SRA-02 | SRANANAGH 110 kV A1
TO-24-110 kV B1 @ SRA-01 | SRANANAGH 110 kV B1
TO-24-TB-T2003-01 | TARBERT T2003
TO-24-TB-T2004-01 | TARBERT T2004
TO-24-TB-T2101-01 | TARBERT T2101
TO-24-THU-CAP1-04 | THURLES CAP1
TO-24-TRL-CAP2-01 | TRALEE CAP2