## Wks 28 - 29
Report covers outages commencing/returning/spanning the period: 08/07/2024 - 21/07/2024
Outages commencing/returning in Week 28
OUTAGE ID | PLANT |  | Week 28 | [6 empty] | Week 29
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
TO-24-CFN-SH-1-01 | CLONIFFEEN SHANNONBRIDGE
TO-24-CFN-T232-01 | CLONIFFEEN T232
TO-24-CRA-LWD-1-02 | CRANE LODGEWOOD
TO-24-CRY-LWD-1-02 | CRORY LODGEWOOD
TO-24-CRY-T121-02 | CRORY T121
TO-24-LWD-110SA1-03 | LODGEWOOD 110SA1
TO-24-LWD-110SA2-03 | LODGEWOOD 110SA2
TO-24-PB-R2001-03 | POOLBEG R2001
TO-24-ARK-LWD-1-02 | ARKLOW LODGEWOOD
TO-24-110 kV A3 @ FIN-02 | FINGLAS 110 kV A3
TO-24-110 kV B3 @ FIN-02 | FINGLAS 110 kV B3
TO-24-220 kV A2 @ FIN-04 | FINGLAS 220 kV A2
TO-24-220 kV B2 @ FIN-02 | FINGLAS 220 kV B2
TO-24-FIN-T2104-03 | FINGLAS T2104
TO-24-TAW-T1/T2-01 | TAWNAGHMORE T1/T2
TO-24-TAW-T3-01 | TAWNAGHMORE T3
TO-24-AUG-SK-4-01 | AUGHINISH SEALROCK 4
TO-24-CLA-CKN-1-01 | CLASHAVOON CLONKEEN
TO-24-CKN-110SA1-2CB-02 | CLONKEEN 110SA1-2CB
TO-24-CKN-CGL-1-02 | CLONKEEN COOMAGEARLAHY
TO-24-CKN-GRO-1-02 | CLONKEEN GARROW
TO-24-CKN-KER-1-02 | CLONKEEN KNOCKEARAGH
TO-24-CGL-110SA1-02 | COOMAGEARLAHY 110SA1
TO-24-CGL-110SA2-02 | COOMAGEARLAHY 110SA2
TO-24-CGL-GAE-1-02 | COOMAGEARLAHY GLANLEE
TO-24-CGL-T121-02 | COOMAGEARLAHY T121
TO-24-CGL-T122-02 | COOMAGEARLAHY T122
TO-24-CUL-DGN-1-01 | CULLENAGH DUNGARVAN
TO-24-GAE-T121-01 | GLANLEE T121
TO-24-SK-T104-01 | SEALROCK T104
TO-24-KLS-220K1-2-01 | KELLIS 220K1-2
TO-24-110 kV A2 @ ARV-02 | ARVA 110 kV A2
TO-24-110 kV B2 @ ARV-02 | ARVA 110 kV B2
TO-24-ARV-SKL-2-02 | ARVA SHANKILL 2
TO-24-BVK-COT-1-01 | BALLYVOUSKILL COOMATAGGART
TO-24-COT-110SA1-01 | COOMATAGGART 110SA1
TO-24-COT-110SA2-01 | COOMATAGGART 110SA2
TO-24-COT-FILTER1-01 | COOMATAGGART FILTER1
TO-24-COT-T132-01 | COOMATAGGART T132
TO-24-COT-T141-01 | COOMATAGGART T141
TO-24-GAL GIS-T142-04 | GALWAY GIS T142
TO-24-DSN-T4202-01 | DUNSTOWN T4202
TO-24-PB-T2007/8-03 | POOLBEG T2007/8
TO-24-TB-220K1-2-08 | TARBERT 220K1-2
TO-24-TB-T2004-05 | TARBERT T2004
TO-24-TB-T2101-06 | TARBERT T2101
TO-24-GAL-GAL GIS-2-02 | GALWAY GALWAY GIS 2
TO-24-GAL-T141-02 | GALWAY T141
TO-24-KLS-KKY-1-03 | KELLIS KILKENNY
TO-24-MAY-RYB GIS-1-05 | MAYNOOTH RYEBROOK GIS
TO-24-GAL-GAL GIS-2-03 | GALWAY GALWAY GIS 2
TO-24-GAL-T141-01 | GALWAY T141
TO-24-CRO-110SA1-03 | COOLROE 110SA1
TO-24-CRO-110SA2-03 | COOLROE 110SA2
TO-24-CRO-KBY-1-04 | COOLROE KILBARRY
TO-24-CRO-T121-04 | COOLROE T121
TO-24-110 kV A2 @ FLA-04 | FLAGFORD 110 kV A2
TO-24-110 kV B2 @ FLA-04 | FLAGFORD 110 kV B2
TO-24-220 kV A2 @ FLA-05 | FLAGFORD 220 kV A2
TO-24-220 kV B2 @ FLA-04 | FLAGFORD 220 kV B2
TO-24-FLA-T2102-01 | FLAGFORD T2102
Report covers outages commencing/returning/spanning the period: 08/07/2024 - 21/07/2024
Outages commencing/returning in Week 28
OUTAGE ID | PLANT | Week 28 Mo 8: Week 28; Week 29 Mo 15: Week 29
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
TO-24-110 kV A2 @ KBY-01 | KILBARRY 110 kV A2 | bar: Su 7 to Week 28 Fr 12
TO-24-110 kV B2 @ KBY-01 | KILBARRY 110 kV B2 | bar: Su 7 to Week 28 Fr 12
TO-24-220 kV A2 @ LOU-01 | LOUTH 220 kV A2 | bar: Su 7 to Week 28 Fr 12
TO-24-220 kV B2 @ LOU-01 | LOUTH 220 kV B2 | bar: Su 7 to Week 28 Fr 12
TO-24-LOU-AT1-01 | LOUTH AT1 | bar: Su 7 to Week 28 Fr 12
TO-24-LOU-AT3-02 | LOUTH AT3 | bar: Su 7 to Week 28 Fr 12
TO-24-LOU-TAN-1-01 | LOUTH TANDRAGEE 1 | bar: Su 7 to Week 28 Fr 12
TO-24-MID-110SA1-03 | MIDLETON 110SA1 | bar: Su 7 to Week 28 Fr 12
TO-24-MID-110SA2-01 | MIDLETON 110SA2 | bar: Su 7 to Week 28 Fr 12
TO-24-MID-T102-01 | MIDLETON T102 | bar: Su 7 to Week 28 Fr 12
TO-24-MID-WHI-1-01 | MIDLETON WHITEGATE | bar: Su 7 to Week 28 Fr 12
Outages commencing/returning in Week 29
OUTAGE ID | PLANT | Week 28 Mo 8: Week 28; Week 29 Mo 15: Week 29
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
TO-24-CDY-GRV-1-01 | CORDERRY GARVAGH | bar: Week 29 Mo 15 to Week 29 Tu 16
TO-24-GRV-110K1-01 | GARVAGH 110K1 | bar: Week 29 Mo 15 to Week 29 Tu 16
TO-24-GRV-T141-02 | GARVAGH T141 | bar: Week 29 Mo 15 to Week 29 Tu 16
TO-24-KIN-T101-02 | KINNEGAD T101 | bar: Week 29 Mo 15 to Week 29 Th 18
TO-24-110 kV A1 @ CAH-03 | CAHIR 110 kV A1 | bar: Week 29 Mo 15 to Week 29 Fr 19
TO-24-110 kV B1 @ CAH-02 | CAHIR 110 kV B1 | bar: Week 29 Mo 15 to Week 29 Fr 19
TO-24-CAH-TIP-1-03 | CAHIR TIPPERARY | bar: Week 29 Mo 15 to Week 29 Fr 19
TO-24-GRO-110SA1-2CB-01 | GARROW 110SA1-2CB | bar: Week 29 Mo 15 to Week 29 Fr 19
TO-24-GRO-T122-01 | GARROW T122 | bar: Week 29 Mo 15 to Week 29 Fr 19
TO-24-220 kV A4 @ KPG-02 | KILPADDOGE 220 kV A4 | bar: Week 29 Mo 15 to Week 29 Fr 19
TO-24-220 kV B4 @ KPG-02 | KILPADDOGE 220 kV B4 | bar: Week 29 Mo 15 to Week 29 Fr 19
TO-24-KPG-MP GIS-2-01 | KILPADDOGE MONEYPOINT GIS 2 | bar: Week 29 Mo 15 to Week 29 Fr 19
TO-24-CDK-LWD-1-02 | CASTLEDOCKRELL LODGEWOOD | bar: Week 29 Mo 15 to Week 29 Mo 22
TO-24-CDK-T121-02 | CASTLEDOCKRELL T121 | bar: Week 29 Mo 15 to Week 29 Mo 22
TO-24-GRV-T121-01 | GARVAGH T121 | bar: Week 29 Mo 15 to Week 29 Mo 22
TO-24-LWD-110SA1-04 | LODGEWOOD 110SA1 | bar: Week 29 Mo 15 to Week 29 Mo 22
TO-24-LWD-110SA2-04 | LODGEWOOD 110SA2 | bar: Week 29 Mo 15 to Week 29 Mo 22
TO-24-LWD-T2102-02 | LODGEWOOD T2102 | bar: Week 29 Mo 15 to Week 29 Mo 22
TO-24-110 kV A2 @ LOU-02 | LOUTH 110 kV A2 | bar: Week 29 Mo 15 to Week 29 Mo 22
TO-24-110 kV B2 @ LOU-02 | LOUTH 110 kV B2 | bar: Week 29 Mo 15 to Week 29 Mo 22
TO-24-220 kV A2 @ LOU-02 | LOUTH 220 kV A2 | bar: Week 29 Mo 15 to Week 29 Mo 22
TO-24-220 kV B2 @ LOU-02 | LOUTH 220 kV B2 | bar: Week 29 Mo 15 to Week 29 Mo 22
TO-24-LOU-T2102-01 | LOUTH T2102 | bar: Week 29 Mo 15 to Week 29 Mo 22
TO-24-FLA-110K1-2-02 | FLAGFORD 110K1-2 | bar: Week 29 Tu 16
TO-24-KHL-T131-01 | KILL HILL T131 | bar: Week 29 Tu 16
TO-24-BLC-DND-1-03 | BELCAMP DARNDALE 1 | bar: Week 29 Tu 16 to Week 29 Fr 19
TO-24-DER-TSB-1-05 | DERRYIRON THORNSBERRY | bar: Week 29 We 17 to Week 29 Fr 19
TO-24-110 kV A2 @ MAY-04 | MAYNOOTH 110 kV A2 | bar: Week 29 We 17 to Week 29 Fr 19
TO-24-110 kV A3 @ MAY-04 | MAYNOOTH 110 kV A3 | bar: Week 29 We 17 to Week 29 Fr 19
TO-24-110 kV B2 @ MAY-04 | MAYNOOTH 110 kV B2 | bar: Week 29 We 17 to Week 29 Fr 19
TO-24-110 kV B3 @ MAY-04 | MAYNOOTH 110 kV B3 | bar: Week 29 We 17 to Week 29 Fr 19
TO-24-TSB-110SA1-02 | THORNSBERRY 110SA1 | bar: Week 29 We 17 to Week 29 Fr 19
TO-24-TSB-110SA2-02 | THORNSBERRY 110SA2 | bar: Week 29 We 17 to Week 29 Fr 19
TO-24-TSB-T142-02 | THORNSBERRY T142 | bar: Week 29 We 17 to Week 29 Fr 19
TO-24-CLA-220K1-2-02 | CLASHAVOON 220K1-2 | bar: Week 29 We 17 to Week 29 Mo 22
TO-24-110 kV A2 @ CSH-04 | CASHLA 110 kV A2 | bar: Su 7 to Week 29 We 17
TO-24-110 kV B2 @ CSH-04 | CASHLA 110 kV B2 | bar: Su 7 to Week 29 We 17
TO-24-220 kV B2 @ CSH-01 | CASHLA 220 kV B2 | bar: Su 7 to Week 29 We 17
TO-24-CUS-KIR-1-02 | CUSHALING KILCUMBER | bar: Su 7 to Week 29 We 17
TO-24-KIR-T131-02 | KILCUMBER T131 | bar: Su 7 to Week 29 We 17
TO-24-110 kV A2 @ CSH-05 | CASHLA 110 kV A2 | bar: Week 29 Th 18 to Week 29 Fr 19
TO-24-110 kV B2 @ CSH-05 | CASHLA 110 kV B2 | bar: Week 29 Th 18 to Week 29 Fr 19
TO-24-220 kV B2 @ CSH-02 | CASHLA 220 kV B2 | bar: Week 29 Th 18 to Week 29 Fr 19
TO-24-OBE-T121-01 | OLDBRIDGE T121 | bar: Week 29 Th 18 to Week 29 Fr 19
TO-24-220 kV B2/B4 @ CSH-01 | CASHLA 220 kV B2/B4 | bar: Week 29 Fr 19
Report covers outages commencing/returning/spanning the period: 08/07/2024 - 21/07/2024
Outages commencing/returning in Week 29
OUTAGE ID | PLANT | Week 28 Mo 8: Week 28; Week 29 Mo 15: Week 29
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
TO-24-CSH-PRO-1-04 | CASHLA PROSPECT
TO-24-BK-CBR-1-03 | BELLACORICK CASTLEBAR
TO-24-CSH-220K2-4-03 | CASHLA 220K2-4
TO-24-CSH-T2102-01 | CASHLA T2102
TO-24-CKM GIS-DSN-1-06 | CARRICKMINES GIS DUNSTOWN
TO-24-KIN-MUL-1-01 | KINNEGAD MULLINGAR
TO-24-LA-MUL-1-02 | LANESBORO MULLINGAR
TO-24-110 kV A1 @ MUL-01 | MULLINGAR 110 kV A1
TO-24-MUL-110SA1-2CB-01 | MULLINGAR 110SA1-2CB
TO-24-MUL-T101-01 | MULLINGAR T101
TO-24-MUL-T141-01 | MULLINGAR T141
Outages spanning Weeks 28-29
OUTAGE ID | PLANT | Week 28 Mo 8: Week 28; Week 29 Mo 15: Week 29
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
TO-24-AA GIS-T101-01 | ARDNACRUSHA GIS T101
TO-24-BAL-DRY-1-05 | BALTRASNA DRYBRIDGE
TO-24-BRY-RAF-2-01 | BARNAHELY RAFFEEN 2
TO-24-BIN-CF-1-01 | BINBANE CATHALEENS FALL
TO-24-CSH-CAP2-01 | CASHLA CAP2
TO-24-CBR-SVC-06 | CASTLEBAR SVC
TO-24-110 kV A2 @ CF-01 | CATHALEENS FALL 110 kV A2
TO-24-CF-SRA-1-02 | CATHALEENS FALL SRANANAGH 1
TO-24-CLG-110K1-02 | CLOGHRAN 110K1
TO-24-CLE-WOO-1-01 | CLONEE WOODLAND
TO-24-CRO-T121-02 | COOLROE T121
TO-24-110 kV A2 @ CDU-03 | CORDUFF 110 kV A2
TO-24-110 kV A4 @ CDU-02 | CORDUFF 110 kV A4
TO-24-110 kV B2 @ CDU-04 | CORDUFF 110 kV B2
TO-24-110 kV B4 @ CDU-02 | CORDUFF 110 kV B4
TO-24-DAL,T-DEY-1-03 | DALLOW tee DERRYCARNEY
TO-24-DND-T121-01 | DARNDALE T121
TO-24-DRU-ENN-1-02 | DRUMLINE ENNIS
TO-24-GAL-T102-01 | GALWAY T102
TO-24-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-24-GOR-NAV-2-02 | GORMAN NAVAN 2
TO-24-GI-T141-01 | GREAT ISLAND T141
TO-24-GRI-T141-02 | GRIFFINRATH T141
TO-24-GRI,T-GCA-1-02 | GRIFFINRATH tee GRANGE CASTLE
TO-24-GRI,T-GRI-1-01 | GRIFFINRATH tee GRIFFINRATH
TO-24-GRI,T-MAY-1-05 | GRIFFINRATH tee MAYNOOTH
TO-24-INC-220K1-2-02 | INCHICORE 220K1-2
TO-24-KYT-WOO-1-01 | KELLYSTOWN WOODLAND
TO-24-KBY-MR-1-02 | KILBARRY MARINA 1
TO-24-KBY-MR-2-02 | KILBARRY MARINA 2
TO-24-KPG-TB-1-07 | KILPADDOGE TARBERT 1
TO-24-LET-PST-02 | LETTERKENNY STRABANE PST
TO-24-110 kV A1 @ LOU-01 | LOUTH 110 kV A1
TO-24-110 kV B1 @ LOU-01 | LOUTH 110 kV B1
TO-24-LOU-MLN-1-01 | LOUTH MULLAGHARLIN
TO-24-LOU-RRU-1-01 | LOUTH RATRUSSAN
TO-24-MAY-TSB-1-02 | MAYNOOTH THORNSBERRY
TO-24-MUL-CAP1-01 | MULLINGAR CAP1
TO-24-PB-R2002-02 | POOLBEG R2002
TO-24-PRO-TB-1-01 | PROSPECT TARBERT
TO-24-110 kV A2 @ RAF-02 | RAFFEEN 110 kV A2
TO-24-110 kV B2 @ RAF-02 | RAFFEEN 110 kV B2
TO-24-110 kV A1 @ SRA-02 | SRANANAGH 110 kV A1
TO-24-110 kV B1 @ SRA-01 | SRANANAGH 110 kV B1
TO-24-TB-T2003-01 | TARBERT T2003
Report covers outages commencing/returning/spanning the period: 08/07/2024 - 21/07/2024
Outages spanning Weeks 28-29
OUTAGE ID | PLANT | Week 28 Mo 8: Week 28; Week 29 Mo 15: Week 29
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
TO-24-TB-T2004-01 | TARBERT T2004
TO-24-TB-T2101-01 | TARBERT T2101
TO-24-THU-CAP1-04 | THURLES CAP1
TO-24-TRL-CAP2-01 | TRALEE CAP2