## Wks 32 - 33
Report covers outages commencing/returning/spanning the period: 05/08/2024 - 18/08/2024
Outages commencing/returning in Week 32
OUTAGE ID | PLANT |  | Week 32 | [6 empty] | Week 33
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
TO-24-KPG-TB-1-04 | KILPADDOGE TARBERT 1 | bar: Week 32 Mo 5 to Week 32 Th 8
TO-24-TB-220K1-2-04 | TARBERT 220K1-2 | bar: Week 32 Mo 5 to Week 32 Th 8
TO-24-TB-T2004-04 | TARBERT T2004 | bar: Week 32 Mo 5 to Week 32 Th 8
TO-24-BVK-T2102-02 | BALLYVOUSKILL T2102 | bar: Week 32 Tu 6 to Week 32 We 7
TO-24-MLN-T124-02 | MULLAGHARLIN T124 | bar: Week 32 Tu 6 to Week 32 We 7
TO-24-CBR-CLN-1-04 | CASTLEBAR CLOON | bar: Week 32 Tu 6 to Week 32 Fr 9
TO-24-110 kV A2 @ CF-06 | CATHALEENS FALL 110 kV A2 | bar: Week 32 Tu 6 to Week 33 Fr 16
TO-24-110 kV B2 @ CF-02 | CATHALEENS FALL 110 kV B2 | bar: Week 32 Tu 6 to Week 33 Fr 16
TO-24-LSN-110SA1-2-03 | LISHEEN 110SA1-2 | bar: Week 32 Tu 6 to Week 33 Fr 16
TO-24-LSN-110SA2-4-03 | LISHEEN 110SA2-4 | bar: Week 32 Tu 6 to Week 33 Fr 16
TO-24-LSN-T122-03 | LISHEEN T122 | bar: Week 32 Tu 6 to Week 33 Fr 16
TO-24-LSN-T131-03 | LISHEEN T131 | bar: Week 32 Tu 6 to Week 33 Fr 16
TO-24-LSN-T142-02 | LISHEEN T142 | bar: Week 32 Tu 6 to Week 33 Fr 16
TO-24-LSN-THU-1-03 | LISHEEN THURLES | bar: Week 32 Tu 6 to Week 33 Fr 16
TO-24-CUS-T101-01 | CUSHALING T101 | bar: Week 32 Tu 6 to Week 33 Mo 19
TO-24-110 kV A2 @ DEY-01 | DERRYCARNEY 110 kV A2 | bar: Week 32 We 7 to Week 33 Mo 19
TO-24-110 kV B2 @ DEY-01 | DERRYCARNEY 110 kV B2 | bar: Week 32 We 7 to Week 33 Mo 19
TO-24-DEY-110K2-03 | DERRYCARNEY 110K2 | bar: Week 32 We 7 to Week 33 Mo 19
TO-24-REM-110SA1-01 | REAMORE 110SA1 | bar: Week 32 We 7 to Week 33 Mo 19
TO-24-REM-110SA2-01 | REAMORE 110SA2 | bar: Week 32 We 7 to Week 33 Mo 19
TO-24-REM-T141-01 | REAMORE T141 | bar: Week 32 We 7 to Week 33 Mo 19
TO-24-REM-T142-01 | REAMORE T142 | bar: Week 32 We 7 to Week 33 Mo 19
TO-24-REM-TRL-1-01 | REAMORE TRALEE | bar: Week 32 We 7 to Week 33 Mo 19
TO-24-CDK-LWD-1-03 | CASTLEDOCKRELL LODGEWOOD | bar: Su 4 to Week 32 We 7
TO-24-CDK-T121-03 | CASTLEDOCKRELL T121 | bar: Su 4 to Week 32 We 7
TO-24-LWD-110SA1-06 | LODGEWOOD 110SA1 | bar: Su 4 to Week 32 We 7
TO-24-LWD-110SA2-06 | LODGEWOOD 110SA2 | bar: Su 4 to Week 32 We 7
TO-24-LWD-T2102-03 | LODGEWOOD T2102 | bar: Su 4 to Week 32 We 7
TO-24-WHI-CKB-T102-01 | WHITEGATE CKB-T102 | bar: Su 4 to Week 32 We 7
TO-24-MLN-T123-03 | MULLAGHARLIN T123 | bar: Week 32 Th 8 to Week 32 Fr 9
TO-24-BLU-CDU-1-01 | BLUNDELSTOWN CORDUFF | bar: Week 32 Th 8 to Week 33 Mo 19
TO-24-PLA-T101/2/3/4-05 | PLATIN T101/2/3/4 | bar: Su 4 to Week 32 Th 8
TO-24-GAR-T131-02 | GARBALLAGH T131 | bar: Week 32 Fr 9
TO-24-KPG-TB-1-08 | KILPADDOGE TARBERT 1 | bar: Week 32 Fr 9 to Week 33 Mo 19
TO-24-TB-220K1-2-09 | TARBERT 220K1-2 | bar: Week 32 Fr 9 to Week 33 Mo 19
TO-24-TB-T2004-06 | TARBERT T2004 | bar: Week 32 Fr 9 to Week 33 Mo 19
TO-24-GRI-T141-02 | GRIFFINRATH T141 | bar: Su 4 to Week 32 Fr 9
TO-24-GRI,T-GCA-1-02 | GRIFFINRATH tee GRANGE CASTLE | bar: Su 4 to Week 32 Fr 9
TO-24-GRI,T-GRI-1-01 | GRIFFINRATH tee GRIFFINRATH | bar: Su 4 to Week 32 Fr 9
TO-24-GRI,T-MAY-1-05 | GRIFFINRATH tee MAYNOOTH | bar: Su 4 to Week 32 Fr 9
TO-24-TSB-TEN-1-03 | THORNSBERRY TIMAHOE | bar: Su 4 to Week 32 Fr 9
TO-24-ISH-T2001-01 | IRISHTOWN T2001 | bar: Week 32 Su 11 to Week 33 Mo 19
Outages commencing/returning in Week 33
OUTAGE ID | PLANT | Week 32 Mo 5: Week 32; Week 33 Mo 12: Week 33
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
TO-24-CRA-LWD-1-04 | CRANE LODGEWOOD | bar: Week 33 Mo 12; Week 33 Fr 16
TO-24-CRY-LWD-1-04 | CRORY LODGEWOOD | bar: Week 33 Mo 12; Week 33 Fr 16
TO-24-CRY-T121-04 | CRORY T121 | bar: Week 33 Mo 12; Week 33 Fr 16
TO-24-DRY-LOU-1-01 | DRYBRIDGE LOUTH | bar: Week 33 Mo 12; Week 33 Fr 16
TO-24-LWD-110SA1-07 | LODGEWOOD 110SA1 | bar: Week 33 Mo 12; Week 33 Fr 16
TO-24-LWD-110SA2-07 | LODGEWOOD 110SA2 | bar: Week 33 Mo 12; Week 33 Fr 16
TO-24-LOU-110K1-2-01 | LOUTH 110K1-2 | bar: Week 33 Mo 12; Week 33 Fr 16
TO-24-LOU-CAP1-03 | LOUTH CAP1 | bar: Week 33 Mo 12; Week 33 Fr 16
TO-24-LOU-T2101-01 | LOUTH T2101 | bar: Week 33 Mo 12; Week 33 Fr 16
TO-24-LOU-T2103-01 | LOUTH T2103 | bar: Week 33 Mo 12; Week 33 Fr 16
TO-24-BYH-BVK-1-02 | BALLYNAHULLA BALLYVOUSKILL | bar: Week 33 Mo 12; Week 33 Fr 16 to Week 33 Mo 19
TO-24-220 kV A2 @ BVK-03 | BALLYVOUSKILL 220 kV A2 | bar: Week 33 Mo 12; Week 33 Fr 16 to Week 33 Mo 19
TO-24-220 kV B2 @ BVK-03 | BALLYVOUSKILL 220 kV B2 | bar: Week 33 Mo 12; Week 33 Fr 16 to Week 33 Mo 19
Report covers outages commencing/returning/spanning the period: 05/08/2024 - 18/08/2024
Outages commencing/returning in Week 33
OUTAGE ID | PLANT | Week 32 Mo 5: Week 32; Week 33 Mo 12: Week 33
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
TO-24-BVK-220K2-06 | BALLYVOUSKILL 220K2
TO-24-BVK-220SA1-2CB-04 | BALLYVOUSKILL 220SA1-2CB
TO-24-BVK-220SB1-2CB-04 | BALLYVOUSKILL 220SB1-2CB
TO-24-110 kV A1 @ CSH-07 | CASHLA 110 kV A1
TO-24-110 kV B1 @ CSH-04 | CASHLA 110 kV B1
TO-24-220 kV A1 @ CSH-01 | CASHLA 220 kV A1
TO-24-220 kV B1 @ CSH-01 | CASHLA 220 kV B1
TO-24-DRU-T141-01 | DRUMLINE T141
TO-24-CUN-110SA1-03 | CUNGHILL 110SA1
TO-24-CUN-110SA2-01 | CUNGHILL 110SA2
TO-24-CUN-SLI-1-03 | CUNGHILL SLIGO
TO-24-CUN-T121-02 | CUNGHILL T121
TO-24-220 kV A2 @ BYH-03 | BALLYNAHULLA 220 kV A2
TO-24-220 kV B2 @ BYH-03 | BALLYNAHULLA 220 kV B2
TO-24-BYH-220K2-04 | BALLYNAHULLA 220K2
TO-24-BYH-220SA1-2CB-05 | BALLYNAHULLA 220SA1-2CB
TO-24-BYH-220SB1-2CB-06 | BALLYNAHULLA 220SB1-2CB
TO-24-CF-SRA-1-02 | CATHALEENS FALL SRANANAGH 1
TO-24-BAN-DMY-1-03 | BANDON DUNMANWAY
TO-24-GAR-T131-03 | GARBALLAGH T131
TO-24-AUN-CBT-3-01 | AUNGIERSTOWN CASTLEBAGOT 3
TO-24-BOL-T141-01 | BOOLTIAGH T141
Outages spanning Weeks 32-33
OUTAGE ID | PLANT | Week 32 Mo 5: Week 32; Week 33 Mo 12: Week 33
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
TO-24-AA GIS-T101-01 | ARDNACRUSHA GIS T101
TO-24-AUG-SK-4-01 | AUGHINISH SEALROCK 4
TO-24-BAL-DRY-1-05 | BALTRASNA DRYBRIDGE
TO-24-BIN-CF-1-01 | BINBANE CATHALEENS FALL
TO-24-CSH-CAP2-01 | CASHLA CAP2
TO-24-CSH-T2101-01 | CASHLA T2101
TO-24-CBR-SVC-06 | CASTLEBAR SVC
TO-24-CLA-220K1-2-02 | CLASHAVOON 220K1-2
TO-24-CLG-110K1-02 | CLOGHRAN 110K1
TO-24-CLE-WOO-1-01 | CLONEE WOODLAND
TO-24-CRO-T121-02 | COOLROE T121
TO-24-CUL-DGN-1-03 | CULLENAGH DUNGARVAN
TO-24-DAL,T-DEY-1-03 | DALLOW tee DERRYCARNEY
TO-24-DND-T121-01 | DARNDALE T121
TO-24-DRU-ENN-1-02 | DRUMLINE ENNIS
TO-24-GAL-GAL GIS-2-02 | GALWAY GALWAY GIS 2
TO-24-GAL-T141-02 | GALWAY T141
TO-24-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-24-GOR-NAV-2-02 | GORMAN NAVAN 2
TO-24-GI-T141-01 | GREAT ISLAND T141
TO-24-INC-220K1-2-02 | INCHICORE 220K1-2
TO-24-KYT-WOO-1-01 | KELLYSTOWN WOODLAND
TO-24-KBY-MR-1-02 | KILBARRY MARINA 1
TO-24-KBY-MR-2-02 | KILBARRY MARINA 2
TO-24-LET-PST-02 | LETTERKENNY STRABANE PST
TO-24-110 kV A1 @ LOU-01 | LOUTH 110 kV A1
TO-24-110 kV B1 @ LOU-01 | LOUTH 110 kV B1
TO-24-LOU-MLN-1-01 | LOUTH MULLAGHARLIN
TO-24-LOU-RRU-1-01 | LOUTH RATRUSSAN
TO-24-110 kV A2 @ MAY-01 | MAYNOOTH 110 kV A2
TO-24-110 kV A3 @ MAY-03 | MAYNOOTH 110 kV A3
TO-24-110 kV B2 @ MAY-01 | MAYNOOTH 110 kV B2
TO-24-110 kV B3 @ MAY-03 | MAYNOOTH 110 kV B3
TO-24-MAY-TSB-1-02 | MAYNOOTH THORNSBERRY
Report covers outages commencing/returning/spanning the period: 05/08/2024 - 18/08/2024
Outages spanning Weeks 32-33
OUTAGE ID | PLANT | Week 32 Mo 5: Week 32; Week 33 Mo 12: Week 33
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
TO-24-PB-R2002-02 | POOLBEG R2002
TO-24-PRO-TB-1-01 | PROSPECT TARBERT
TO-24-110 kV A2 @ RAF-02 | RAFFEEN 110 kV A2
TO-24-110 kV B2 @ RAF-02 | RAFFEEN 110 kV B2
TO-24-SK-T104-01 | SEALROCK T104
TO-24-220 kV A2 @ TB-01 | TARBERT 220 kV A2
TO-24-220 kV B2 @ TB-01 | TARBERT 220 kV B2
TO-24-TB-T2003-01 | TARBERT T2003
TO-24-TB-T2004-01 | TARBERT T2004
TO-24-THU-CAP1-04 | THURLES CAP1
TO-24-TRL-CAP2-01 | TRALEE CAP2