## Wks 34 - 35
Report covers outages commencing/returning/spanning the period: 19/08/2024 - 01/09/2024
Outages commencing/returning in Week 34
OUTAGE ID | PLANT |  | Week 34 | [6 empty] | Week 35
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2
TO-24-110 kV A2 @ GOR-01 | GORMAN 110 kV A2
TO-24-GOR-MTH-1-01 | GORMAN MEATH HILL
TO-24-KNY-UGL-1-01 | KNOCKRANNY UGGOOL
TO-24-UGL-110SA1-2CB-01 | UGGOOL 110SA1-2CB
TO-24-CDU-220SB2-4-02 | CORDUFF 220SB2-4
TO-24-GOL-T101-03 | GOLAGH T101
TO-24-ARK-T2101-01 | ARKLOW T2101
TO-24-110 kV A1 @ ARV-02 | ARVA 110 kV A1
TO-24-110 kV A2 @ ARV-01 | ARVA 110 kV A2
TO-24-110 kV B1 @ ARV-01 | ARVA 110 kV B1
TO-24-110 kV B2 @ ARV-01 | ARVA 110 kV B2
TO-24-ARV-110K1-2-01 | ARVA 110K1-2
TO-24-BAN-RAF-1-02 | BANDON RAFFEEN
TO-24-MLN-T123-01 | MULLAGHARLIN T123
TO-24-SNU-T131-01 | SNUGBOROUGH T131
TO-24-UGL-T131-02 | UGGOOL T131
TO-24-KHL-THU-1-01 | KILL HILL THURLES
TO-24-110 kV A1 @ CUL-01 | CULLENAGH 110 kV A1
TO-24-110 kV B1 @ CUL-02 | CULLENAGH 110 kV B1
TO-24-CUL-WAT-1-03 | CULLENAGH WATERFORD
TO-24-UGL-T132-04 | UGGOOL T132
TO-24-UGL-T134-03 | UGGOOL T134
TO-24-BGH-110SA1-01 | BOGGERAGH 110SA1
TO-24-BGH-110SA2-01 | BOGGERAGH 110SA2
TO-24-BGH-CLA-1-01 | BOGGERAGH CLASHAVOON
TO-24-BGH-T121-01 | BOGGERAGH T121
TO-24-BGH-T132-01 | BOGGERAGH T132
TO-24-BGH-T142-01 | BOGGERAGH T142
TO-24-BOL-110SA1-3CB-03 | BOOLTIAGH 110SA1-3CB
TO-24-BOL-T121-01 | BOOLTIAGH T121
TO-24-220 kV A1 @ CBT-02 | CASTLEBAGOT 220 kV A1
TO-24-220 kV B1 @ CBT-02 | CASTLEBAGOT 220 kV B1
TO-24-CBT-220K1-01 | CASTLEBAGOT 220K1
TO-24-CBT-220SA1-2CB-08 | CASTLEBAGOT 220SA1-2CB
TO-24-CBT-220SB1-2CB-08 | CASTLEBAGOT 220SB1-2CB
TO-24-110 kV A1 @ CLA-01 | CLASHAVOON 110 kV A1
TO-24-110 kV B1 @ CLA-01 | CLASHAVOON 110 kV B1
TO-24-TBK-T141-01 | TULLABRACK T141
TO-24-TBK,T-BOL-1-01 | TULLABRACK tee BOOLTIAGH
TO-24-TBK,T-MP GIS-1-01 | TULLABRACK tee MONEYPOINT GIS
TO-24-TBK,T-TBK-1-01 | TULLABRACK tee TULLABRACK
TO-24-CDK-LWD-1-04 | CASTLEDOCKRELL LODGEWOOD
TO-24-CDK-T121-04 | CASTLEDOCKRELL T121
TO-24-LWD-110SA1-08 | LODGEWOOD 110SA1
TO-24-LWD-110SA2-08 | LODGEWOOD 110SA2
TO-24-LWD-T2102-06 | LODGEWOOD T2102
TO-24-GOR-NAV-2-02 | GORMAN NAVAN 2
TO-24-110 kV A2 @ SH-05 | SHANNONBRIDGE 110 kV A2
TO-24-110 kV B2 @ SH-05 | SHANNONBRIDGE 110 kV B2
TO-24-220 kV A6 @ INC-01 | INCHICORE 220 kV A6
TO-24-220 kV B6 @ INC-01 | INCHICORE 220 kV B6
TO-24-INC-T2106-02 | INCHICORE T2106
TO-24-DAL-T141-06 | DALLOW T141
TO-24-DAL,T-DAL-1-08 | DALLOW tee DALLOW
TO-24-DAL,T-SH-1-10 | DALLOW tee SHANNONBRIDGE
TO-24-GOR-NAV-1-01 | GORMAN NAVAN 1
TO-24-220 kV A1 @ AD-05 | AGHADA 220 kV A1
TO-24-220 kV B1 @ AD-04 | AGHADA 220 kV B1
TO-24-AD-220K1-06 | AGHADA 220K1
TO-24-AD-SA1-2CB-08 | AGHADA 220SA1-2CB
TO-24-AD-SB1-2CB-08 | AGHADA 220SB1-2CB
Report covers outages commencing/returning/spanning the period: 19/08/2024 - 01/09/2024
Outages commencing/returning in Week 34
OUTAGE ID | PLANT | Week 34 Mo 19: Week 34; Week 35 Mo 26: Week 35
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2
TO-24-AD-T2011/12-02 | AGHADA T2011/12 | bar: Week 34 We 21 to Week 35 We 28
TO-24-AD-T2014-02 | AGHADA T2014 | bar: Week 34 We 21 to Week 35 We 28
TO-24-BRY-RAF-2-01 | BARNAHELY RAFFEEN 2 | bar: Week 34 Th 22 to Week 35 Mo 2
TO-24-CUS-T101-01 | CUSHALING T101 | bar: Su 18 to Week 34 Th 22
TO-24-220 kV A2 @ BYH-03 | BALLYNAHULLA 220 kV A2 | bar: Su 18 to Week 34 Fr 23
TO-24-220 kV B2 @ BYH-03 | BALLYNAHULLA 220 kV B2 | bar: Su 18 to Week 34 Fr 23
TO-24-BYH-220K2-04 | BALLYNAHULLA 220K2 | bar: Su 18 to Week 34 Fr 23
TO-24-BYH-220SA1-2CB-05 | BALLYNAHULLA 220SA1-2CB | bar: Su 18 to Week 34 Fr 23
TO-24-BYH-220SB1-2CB-06 | BALLYNAHULLA 220SB1-2CB | bar: Su 18 to Week 34 Fr 23
TO-24-BYH-BVK-1-02 | BALLYNAHULLA BALLYVOUSKILL | bar: Su 18 to Week 34 Fr 23
TO-24-220 kV A2 @ BVK-03 | BALLYVOUSKILL 220 kV A2 | bar: Su 18 to Week 34 Fr 23
TO-24-220 kV B2 @ BVK-03 | BALLYVOUSKILL 220 kV B2 | bar: Su 18 to Week 34 Fr 23
TO-24-BVK-220K2-06 | BALLYVOUSKILL 220K2 | bar: Su 18 to Week 34 Fr 23
TO-24-BVK-220SA1-2CB-04 | BALLYVOUSKILL 220SA1-2CB | bar: Su 18 to Week 34 Fr 23
TO-24-BVK-220SB1-2CB-04 | BALLYVOUSKILL 220SB1-2CB | bar: Su 18 to Week 34 Fr 23
TO-24-110 kV A2 @ DEY-01 | DERRYCARNEY 110 kV A2 | bar: Su 18 to Week 34 Fr 23
TO-24-110 kV B2 @ DEY-01 | DERRYCARNEY 110 kV B2 | bar: Su 18 to Week 34 Fr 23
TO-24-DEY-110K2-03 | DERRYCARNEY 110K2 | bar: Su 18 to Week 34 Fr 23
Outages commencing/returning in Week 35
OUTAGE ID | PLANT | Week 34 Mo 19: Week 34; Week 35 Mo 26: Week 35
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2
TO-24-ROP-T131-02 | ROSSPILE T131
TO-24-110 kV A2 @ CF-02 | CATHALEENS FALL 110 kV A2 | bar: Week 35 Th 29
TO-24-CRO-110SA1-05 | COOLROE 110SA1 | bar: Week 35 Th 29
TO-24-CRO-110SA2-05 | COOLROE 110SA2 | bar: Week 35 Th 29
TO-24-CRO-KBY-1-05 | COOLROE KILBARRY | bar: Week 35 Th 29
TO-24-CDU-MCE-1-04 | CORDUFF MACETOWN | bar: Week 35 Th 29
TO-24-110 kV A2 @ FIN GIS-03 | FINGLAS GIS 110 kV A2 | bar: Week 35 Th 29
TO-24-110 kV B2 @ FIN GIS-03 | FINGLAS GIS 110 kV B2 | bar: Week 35 Th 29
TO-24-FIN GIS-110K2-04 | FINGLAS GIS 110K2 | bar: Week 35 Th 29
TO-24-FIN GIS-110SA1-2CB-04 | FINGLAS GIS 110SA1-2CB | bar: Week 35 Th 29
TO-24-FIN GIS-110SA2-4CB-05 | FINGLAS GIS 110SA2-4CB | bar: Week 35 Th 29
TO-24-FIN GIS-110SB1-2CB-04 | FINGLAS GIS 110SB1-2CB | bar: Week 35 Th 29
TO-24-FIN GIS-110SB2-4CB-06 | FINGLAS GIS 110SB2-4CB | bar: Week 35 Th 29
TO-24-GLR-110SA1-2CB-03 | GLENREE 110SA1-2CB | bar: Week 35 Th 29
TO-24-GLR-T121-01 | GLENREE T121 | bar: Week 35 Th 29
TO-24-MOY-110SA1-2CB-01 | MOY 110SA1-2CB | bar: Week 35 Th 29
TO-24-MOY-T141-01 | MOY T141 | bar: Week 35 Th 29
TO-24-SNU-T133-01 | SNUGBOROUGH T133 | bar: Week 35 Th 29
TO-24-110 kV A1 @ CF-04 | CATHALEENS FALL 110 kV A1 | bar: Week 35 Th 29; Week 35 Sa 31 to Week 35 Mo 2
TO-24-110 kV B1 @ CF-03 | CATHALEENS FALL 110 kV B1 | bar: Week 35 Th 29; Week 35 Sa 31 to Week 35 Mo 2
TO-24-CF-COR-1-01 | CATHALEENS FALL CORRACLASSY | bar: Week 35 Th 29; Week 35 Sa 31 to Week 35 Mo 2
TO-24-COR-PST-02 | CORRACLASSY ENNISKILLEN PST | bar: Week 35 Th 29; Week 35 Sa 31 to Week 35 Mo 2
TO-24-COR-GWE-1-03 | CORRACLASSY GORTAWEE | bar: Week 35 Th 29; Week 35 Sa 31 to Week 35 Mo 2
TO-24-GLR-MOY-1-01 | GLENREE MOY | bar: Week 35 Th 29; Week 35 Sa 31 to Week 35 Mo 2
TO-24-MOY-CAP1-01 | MOY CAP1 | bar: Week 35 Th 29; Week 35 Sa 31 to Week 35 Mo 2
TO-24-MOY-TAW-1-04 | MOY TAWNAGHMORE 1 | bar: Week 35 Th 29; Week 35 Sa 31 to Week 35 Mo 2
TO-24-WOO-T4204-01 | WOODLAND T4204 | bar: Week 35 Th 29; Week 35 Sa 31 to Week 35 Mo 2
TO-24-BAL-110SA1-02 | BALTRASNA 110SA1
TO-24-BAL-110SA2-04 | BALTRASNA 110SA2
TO-24-BAL-T121-03 | BALTRASNA T121
TO-24-CHA-GLE-1-03 | CHARLEVILLE GLENLARA | bar: Week 35 Th 29; Week 35 Sa 31 to Week 35 Mo 2
TO-24-GLE-110SA1-2CB-01 | GLENLARA 110SA1-2CB | bar: Week 35 Th 29; Week 35 Sa 31 to Week 35 Mo 2
TO-24-CLA-220K1-2-02 | CLASHAVOON 220K1-2 | bar: Su 18 to Week 34 Su 25
TO-24-REM-110SA1-01 | REAMORE 110SA1 | bar: Su 18 to Week 34 Su 25
TO-24-REM-110SA2-01 | REAMORE 110SA2 | bar: Su 18 to Week 34 Su 25
TO-24-REM-T141-01 | REAMORE T141 | bar: Su 18 to Week 34 Su 25
TO-24-REM-T142-01 | REAMORE T142 | bar: Su 18 to Week 34 Su 25
TO-24-REM-TRL-1-01 | REAMORE TRALEE | bar: Su 18 to Week 34 Su 25
Report covers outages commencing/returning/spanning the period: 19/08/2024 - 01/09/2024
Outages commencing/returning in Week 35
OUTAGE ID | PLANT | Week 34 Mo 19: Week 34; Week 35 Mo 26: Week 35
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2
TO-24-MAY-TSB-1-02 | MAYNOOTH THORNSBERRY
TO-24-110 kV A1 @ LOU-05 | LOUTH 110 kV A1
TO-24-110 kV A2 @ LOU-03 | LOUTH 110 kV A2
TO-24-110 kV B1 @ LOU-05 | LOUTH 110 kV B1
TO-24-110 kV B2 @ LOU-03 | LOUTH 110 kV B2
TO-24-LOU-T2104-03 | LOUTH T2104
TO-24-110 kV A1 @ CSH-07 | CASHLA 110 kV A1
TO-24-110 kV B1 @ CSH-04 | CASHLA 110 kV B1
TO-24-220 kV A1 @ CSH-01 | CASHLA 220 kV A1
TO-24-220 kV B1 @ CSH-01 | CASHLA 220 kV B1
TO-24-CRO-T121-02 | COOLROE T121
TO-24-ISH-T2001-01 | IRISHTOWN T2001
TO-24-110 kV A2 @ MAY-01 | MAYNOOTH 110 kV A2
TO-24-110 kV A3 @ MAY-03 | MAYNOOTH 110 kV A3
TO-24-110 kV B2 @ MAY-01 | MAYNOOTH 110 kV B2
TO-24-110 kV B3 @ MAY-03 | MAYNOOTH 110 kV B3
TO-24-SHL-T2015-01 | SHELLYBANKS T2015
Outages spanning Weeks 34-35
OUTAGE ID | PLANT | Week 34 Mo 19: Week 34; Week 35 Mo 26: Week 35
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2
TO-24-AA GIS-T101-01 | ARDNACRUSHA GIS T101
TO-24-AUG-SK-4-01 | AUGHINISH SEALROCK 4
TO-24-AUN-CBT-3-01 | AUNGIERSTOWN CASTLEBAGOT 3
TO-24-BAL-DRY-1-05 | BALTRASNA DRYBRIDGE
TO-24-BIN-CF-1-01 | BINBANE CATHALEENS FALL
TO-24-BLU-CDU-1-01 | BLUNDELSTOWN CORDUFF
TO-24-CSH-CAP2-01 | CASHLA CAP2
TO-24-CSH-T2101-01 | CASHLA T2101
TO-24-CBR-SVC-06 | CASTLEBAR SVC
TO-24-CLG-110K1-02 | CLOGHRAN 110K1
TO-24-CLE-WOO-1-01 | CLONEE WOODLAND
TO-24-CUL-DGN-1-03 | CULLENAGH DUNGARVAN
TO-24-DAL,T-DEY-1-03 | DALLOW tee DERRYCARNEY
TO-24-DND-T121-01 | DARNDALE T121
TO-24-DRU-ENN-1-02 | DRUMLINE ENNIS
TO-24-DRU-T141-01 | DRUMLINE T141
TO-24-GAL-GAL GIS-2-02 | GALWAY GALWAY GIS 2
TO-24-GAL-T141-02 | GALWAY T141
TO-24-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-24-GI-T141-01 | GREAT ISLAND T141
TO-24-INC-220K1-2-02 | INCHICORE 220K1-2
TO-24-KYT-WOO-1-01 | KELLYSTOWN WOODLAND
TO-24-KBY-MR-1-02 | KILBARRY MARINA 1
TO-24-KBY-MR-2-02 | KILBARRY MARINA 2
TO-24-KPG-TB-1-08 | KILPADDOGE TARBERT 1
TO-24-LET-PST-02 | LETTERKENNY STRABANE PST
TO-24-110 kV A1 @ LOU-01 | LOUTH 110 kV A1
TO-24-110 kV B1 @ LOU-01 | LOUTH 110 kV B1
TO-24-LOU-MLN-1-01 | LOUTH MULLAGHARLIN
TO-24-LOU-RRU-1-01 | LOUTH RATRUSSAN
TO-24-PB-R2002-02 | POOLBEG R2002
TO-24-PRO-TB-1-01 | PROSPECT TARBERT
TO-24-110 kV A2 @ RAF-02 | RAFFEEN 110 kV A2
TO-24-110 kV B2 @ RAF-02 | RAFFEEN 110 kV B2
TO-24-SK-T104-01 | SEALROCK T104
TO-24-220 kV A2 @ TB-01 | TARBERT 220 kV A2
TO-24-220 kV B2 @ TB-01 | TARBERT 220 kV B2
TO-24-TB-220K1-2-09 | TARBERT 220K1-2
TO-24-TB-T2003-01 | TARBERT T2003
Report covers outages commencing/returning/spanning the period: 19/08/2024 - 01/09/2024
Outages spanning Weeks 34-35
OUTAGE ID | PLANT | Week 34 Mo 19: Week 34; Week 35 Mo 26: Week 35
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2
TO-24-TB-T2004-06 | TARBERT T2004
TO-24-TB-T2004-01
TO-24-THU-CAP1-04 | THURLES CAP1
TO-24-TRL-CAP2-01 | TRALEE CAP2