## Wks 36 - 37
Report covers outages commencing/returning/spanning the period: 02/09/2024 - 15/09/2024
Outages commencing/returning in Week 36
OUTAGE ID | PLANT |  | Week 36 | [6 empty] | Week 37
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
TO-24-ROP-T131-03 | ROSSPILE T131 | bar: Week 36 Mo 2
TO-24-BIN-110SA1-2CB-02 | BINBANE 110SA1-2CB | bar: Week 36 Mo 2 to Week 36 Tu 3
TO-24-BIN-T142-03 | BINBANE T142 | bar: Week 36 Mo 2 to Week 36 Tu 3
TO-24-DRY-LOU-1-02 | DRYBRIDGE LOUTH | bar: Week 36 Mo 2 to Week 36 Tu 3
TO-24-MP GIS-T121-01 | MONEYPOINT GIS T121 | bar: Week 36 Mo 2 to Week 36 Tu 3; Week 36 Th 5
TO-24-MP GIS-T2102-01 | MONEYPOINT GIS T2102 | bar: Week 36 Mo 2 to Week 36 Tu 3; Week 36 Th 5
TO-24-MP GIS-T4202-02 | MONEYPOINT GIS T4202 | bar: Week 36 Mo 2 to Week 36 Tu 3; Week 36 Th 5
TO-24-RNW-T121-01 | RINAWADE T121 | bar: Week 36 Mo 2 to Week 36 Tu 3; Week 36 Th 5
TO-24-110 kV A1 @ SNU-04 | SNUGBOROUGH 110 kV A1 | bar: Week 36 Mo 2 to Week 36 Tu 3; Week 36 Th 5
TO-24-110 kV B1 @ SNU-04 | SNUGBOROUGH 110 kV B1 | bar: Week 36 Mo 2 to Week 36 Tu 3; Week 36 Th 5
TO-24-SNU-110K1-04 | SNUGBOROUGH 110K1 | bar: Week 36 Mo 2 to Week 36 Tu 3; Week 36 Th 5
TO-24-SNU-110SA1-2CB-08 | SNUGBOROUGH 110SA1-2CB | bar: Week 36 Mo 2 to Week 36 Tu 3; Week 36 Th 5
TO-24-SNU-110SB1-2CB-09 | SNUGBOROUGH 110SB1-2CB | bar: Week 36 Mo 2 to Week 36 Tu 3; Week 36 Th 5
TO-24-BDA-T101-01 | BARODA T101 | bar: Week 36 Mo 2 to Week 36 Tu 3; Week 36 Th 5; Week 36 Sa 7 to Week 37 Tu 10
TO-24-CLH-TRL-1-01 | CLAHANE TRALEE | bar: Week 36 Mo 2 to Week 36 Tu 3; Week 36 Th 5; Week 36 Sa 7 to Week 37 Mo 16
TO-24-CRO-T122-02 | COOLROE T122 | bar: Week 36 Mo 2 to Week 36 Tu 3; Week 36 Th 5; Week 36 Sa 7 to Week 37 Mo 16
TO-24-AUG-SK-4-01 | AUGHINISH SEALROCK 4 | bar: Su 1 to Week 36 Mo 2
TO-24-SK-T104-01 | SEALROCK T104 | bar: Su 1 to Week 36 Mo 2
TO-24-BAN-BRI-1-02 | BANDON BRINNY 1 | bar: Week 36 Tu 3
TO-24-BRI-T101-03 | BRINNY T101 | bar: Week 36 Tu 3
TO-24-110 kV A3 @ KPG-01 | KILPADDOGE 110 kV A3 | bar: Week 36 Tu 3; Week 36 Th 5; Week 36 Sa 7 to Week 37 Fr 13
TO-24-110 kV B3 @ KPG-01 | KILPADDOGE 110 kV B3 | bar: Week 36 Tu 3; Week 36 Th 5; Week 36 Sa 7 to Week 37 Fr 13
TO-24-KPG-110K3-01 | KILPADDOGE 110K3 | bar: Week 36 Tu 3; Week 36 Th 5; Week 36 Sa 7 to Week 37 Fr 13
TO-24-KPG-110SA1-3CB-02 | KILPADDOGE 110SA1-3CB | bar: Week 36 Tu 3; Week 36 Th 5; Week 36 Sa 7 to Week 37 Fr 13
TO-24-KPG-110SB1-3CB-02 | KILPADDOGE 110SB1-3CB | bar: Week 36 Tu 3; Week 36 Th 5; Week 36 Sa 7 to Week 37 Fr 13
TO-24-KPG-RAT-1-01 | KILPADDOGE RATHKEALE | bar: Week 36 Tu 3; Week 36 Th 5; Week 36 Sa 7 to Week 37 Fr 13
TO-24-CHA-GLE-1-03 | CHARLEVILLE GLENLARA | bar: Su 1 to Week 36 Tu 3
TO-24-GLE-110SA1-2CB-01 | GLENLARA 110SA1-2CB | bar: Su 1 to Week 36 Tu 3
TO-24-MP GIS-400K4-01 | MONEYPOINT GIS 400K4
TO-24-RRU-110SA1-04 | RATRUSSAN 110SA1 | bar: Week 36 Th 5; Week 36 Sa 7 to Week 37 Tu 10
TO-24-RRU-110SA2-04 | RATRUSSAN 110SA2 | bar: Week 36 Th 5; Week 36 Sa 7 to Week 37 Tu 10
TO-24-RRU-T121-04 | RATRUSSAN T121 | bar: Week 36 Th 5; Week 36 Sa 7 to Week 37 Tu 10
TO-24-110 kV A2 @ CDU-05 | CORDUFF 110 kV A2 | bar: Week 36 Th 5; Week 36 Sa 7 to Week 37 Mo 16
TO-24-110 kV B2 @ CDU-05 | CORDUFF 110 kV B2 | bar: Week 36 Th 5; Week 36 Sa 7 to Week 37 Mo 16
TO-24-220 kV A2 @ CDU-06 | CORDUFF 220 kV A2 | bar: Week 36 Th 5; Week 36 Sa 7 to Week 37 Mo 16
TO-24-220 kV B2 @ CDU-05 | CORDUFF 220 kV B2 | bar: Week 36 Th 5; Week 36 Sa 7 to Week 37 Mo 16
TO-24-CDU-T2102-02 | CORDUFF T2102 | bar: Week 36 Th 5; Week 36 Sa 7 to Week 37 Mo 16
TO-24-DAL-T141-06 | DALLOW T141 | bar: Su 1 to Week 36 Tu 3
TO-24-DAL,T-DAL-1-08 | DALLOW tee DALLOW | bar: Su 1 to Week 36 Tu 3
TO-24-DAL,T-DEY-1-03 | DALLOW tee DERRYCARNEY | bar: Su 1 to Week 36 Tu 3
TO-24-DAL,T-SH-1-10 | DALLOW tee SHANNONBRIDGE | bar: Su 1 to Week 36 Tu 3
TO-24-IKE-T141-03 | IKERRIN T141 | bar: Week 36 Th 5; Week 36 Sa 7 to Week 37 Fr 13
TO-24-IKE,T-IKE-1-03 | IKERRIN tee IKERRIN | bar: Week 36 Th 5; Week 36 Sa 7 to Week 37 Fr 13
TO-24-IKE,T-SH-1-05 | IKERRIN tee SHANNONBRIDGE | bar: Week 36 Th 5; Week 36 Sa 7 to Week 37 Fr 13
TO-24-IKE,T-THU-1-05 | IKERRIN tee THURLES | bar: Week 36 Th 5; Week 36 Sa 7 to Week 37 Fr 13
TO-24-CDU-GLN-1-05 | CORDUFF GALLANSTOWN | bar: Week 36 Sa 7 to Week 36 Su 8
TO-24-CDK-LWD-1-04 | CASTLEDOCKRELL LODGEWOOD | bar: Su 1 to Week 36 Tu 3; Week 36 Th 5
TO-24-CDK-T121-04 | CASTLEDOCKRELL T121 | bar: Su 1 to Week 36 Tu 3; Week 36 Th 5
TO-24-110 kV A1 @ CF-04 | CATHALEENS FALL 110 kV A1 | bar: Su 1 to Week 36 Tu 3; Week 36 Th 5
TO-24-110 kV B1 @ CF-03 | CATHALEENS FALL 110 kV B1 | bar: Su 1 to Week 36 Tu 3; Week 36 Th 5
TO-24-CF-COR-1-01 | CATHALEENS FALL CORRACLASSY | bar: Su 1 to Week 36 Tu 3; Week 36 Th 5
TO-24-COR-PST-02 | CORRACLASSY ENNISKILLEN PST | bar: Su 1 to Week 36 Tu 3; Week 36 Th 5
TO-24-COR-GWE-1-03 | CORRACLASSY GORTAWEE | bar: Su 1 to Week 36 Tu 3; Week 36 Th 5
TO-24-LWD-110SA1-08 | LODGEWOOD 110SA1 | bar: Su 1 to Week 36 Tu 3; Week 36 Th 5
TO-24-LWD-110SA2-08 | LODGEWOOD 110SA2 | bar: Su 1 to Week 36 Tu 3; Week 36 Th 5
TO-24-LWD-T2102-06 | LODGEWOOD T2102 | bar: Su 1 to Week 36 Tu 3; Week 36 Th 5
TO-24-MOY-CAP1-01 | MOY CAP1 | bar: Su 1 to Week 36 Tu 3; Week 36 Th 5
TO-24-MOY-TAW-1-04 | MOY TAWNAGHMORE 1 | bar: Su 1 to Week 36 Tu 3; Week 36 Th 5
Report covers outages commencing/returning/spanning the period: 02/09/2024 - 15/09/2024
Outages commencing/returning in Week 37
OUTAGE ID | PLANT | Week 36 Mo 2: Week 36; Week 37 Mo 9: Week 37
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
TO-24-CDK-LWD-1-05 | CASTLEDOCKRELL LODGEWOOD
TO-24-CDK-T121-05 | CASTLEDOCKRELL T121
TO-24-LWD-110SA1-09 | LODGEWOOD 110SA1
TO-24-LWD-110SA2-09 | LODGEWOOD 110SA2
TO-24-LWD-T2102-05 | LODGEWOOD T2102
TO-24-FIN-FIN GIS-1-01 | FINGLAS FINGLAS GIS 1
TO-24-110 kV A2 @ FIN GIS-05 | FINGLAS GIS 110 kV A2
TO-24-110 kV A4 @ FIN GIS-02 | FINGLAS GIS 110 kV A4
TO-24-110 kV B2 @ FIN GIS-05 | FINGLAS GIS 110 kV B2
TO-24-110 kV B4 @ FIN GIS-03 | FINGLAS GIS 110 kV B4
TO-24-FIN GIS-110K2-05 | FINGLAS GIS 110K2
TO-24-FIN GIS-110SA1-2CB-06 | FINGLAS GIS 110SA1-2CB
TO-24-FIN GIS-110SA2-4CB-07 | FINGLAS GIS 110SA2-4CB
TO-24-FIN GIS-110SA4-6CB-02 | FINGLAS GIS 110SA4-6CB
TO-24-FIN GIS-110SB1-2CB-06 | FINGLAS GIS 110SB1-2CB
TO-24-FIN GIS-110SB2-4CB-08 | FINGLAS GIS 110SB2-4CB
TO-24-FIN GIS-110SB4-6CB-04 | FINGLAS GIS 110SB4-6CB
TO-24-110 kV A1 @ LOU-06 | LOUTH 110 kV A1
TO-24-110 kV A2 @ LOU-04 | LOUTH 110 kV A2
TO-24-110 kV B1 @ LOU-06 | LOUTH 110 kV B1
TO-24-110 kV B2 @ LOU-04 | LOUTH 110 kV B2
TO-24-SOM-T142-01 | SOMERSET T142 | bar: Week 37 We 11
TO-24-SOM,T-CSH-1-05 | SOMERSET tee CASHLA | bar: Week 37 We 11
TO-24-SOM,T-SH-1-02 | SOMERSET tee SHANNONBRIDGE | bar: Week 37 We 11
TO-24-SOM,T-SOM-1-01 | SOMERSET tee SOMERSET | bar: Week 37 We 11
TO-24-ATY-110SA1-01 | ATHY 110SA1 | bar: Week 37 We 11 to Week 37 Fr 13
TO-24-ATY-110SA2-04 | ATHY 110SA2 | bar: Week 37 We 11 to Week 37 Fr 13
TO-24-110 kV A1 @ GI-02 | GREAT ISLAND 110 kV A1 | bar: Week 37 We 11 to Week 37 Fr 13
TO-24-110 kV A2 @ GI-01 | GREAT ISLAND 110 kV A2 | bar: Week 37 We 11 to Week 37 Fr 13
TO-24-110 kV B1 @ GI-02 | GREAT ISLAND 110 kV B1 | bar: Week 37 We 11 to Week 37 Fr 13
TO-24-110 kV B2 @ GI-01 | GREAT ISLAND 110 kV B2 | bar: Week 37 We 11 to Week 37 Fr 13
TO-24-GI-110K1-2-01 | GREAT ISLAND 110K1-2 | bar: Week 37 We 11 to Week 37 Fr 13
TO-24-GGO-T2001-01 | GLANAGOW T2001 | bar: Week 37 We 11 to Week 37 Mo 16
TO-24-220 kV A1 @ KNR-01 | KNOCKANURE 220 kV A1 | bar: Week 37 We 11 to Week 37 Mo 16
TO-24-220 kV B1 @ KNR-01 | KNOCKANURE 220 kV B1 | bar: Week 37 We 11 to Week 37 Mo 16
TO-24-KNR-220K1-01 | KNOCKANURE 220K1 | bar: Week 37 We 11 to Week 37 Mo 16
TO-24-KNR-220SA1-2CB-03 | KNOCKANURE 220SA1-2CB | bar: Week 37 We 11 to Week 37 Mo 16
TO-24-KNR-220SB1-2CB-02 | KNOCKANURE 220SB1-2CB | bar: Week 37 We 11 to Week 37 Mo 16
TO-24-110 kV A2 @ SNU-02 | SNUGBOROUGH 110 kV A2 | bar: Week 37 We 11 to Week 37 Mo 16
TO-24-110 kV B2 @ SNU-02 | SNUGBOROUGH 110 kV B2 | bar: Week 37 We 11 to Week 37 Mo 16
TO-24-SNU-110K2-01 | SNUGBOROUGH 110K2 | bar: Week 37 We 11 to Week 37 Mo 16
TO-24-SNU-110SA1-2CB-06 | SNUGBOROUGH 110SA1-2CB | bar: Week 37 We 11 to Week 37 Mo 16
TO-24-SNU-110SB1-2CB-07 | SNUGBOROUGH 110SB1-2CB | bar: Week 37 We 11 to Week 37 Mo 16
TO-24-BLU-CDU-1-01 | BLUNDELSTOWN CORDUFF | bar: Su 1 to Week 36 Su 8
TO-24-CLE-WOO-1-01 | CLONEE WOODLAND | bar: Su 1 to Week 36 Su 8
TO-24-KYT-WOO-1-01 | KELLYSTOWN WOODLAND | bar: Su 1 to Week 36 Su 8
TO-24-AA GIS-110K2-02 | ARDNACRUSHA GIS 110K2
TO-24-AA GIS-110SA1-2CB-02 | ARDNACRUSHA GIS 110SA1-2CB
TO-24-LOU-AT3-01 | LOUTH AT3 | bar: Week 37 We 11 to Week 37 Th 12
TO-24-SHL-T2016-01 | SHELLYBANKS T2016 | bar: Week 37 We 11 to Week 37 Mo 16
TO-24-KBY-MR-1-02 | KILBARRY MARINA 1 | bar: Su 1 to Week 36 Su 8
TO-24-KBY-MR-2-02 | KILBARRY MARINA 2 | bar: Su 1 to Week 36 Su 8
TO-24-AA GIS-110SA1-3CB-02 | ARDNACRUSHA GIS 110SA1-3CB | bar: Week 37 We 11
TO-24-110 kV A2 @ CF-03 | CATHALEENS FALL 110 kV A2 | bar: Week 37 We 11
TO-24-CF-SRA-2-02 | CATHALEENS FALL SRANANAGH 2 | bar: Week 37 We 11
TO-24-CLA-110K1-2-02 | CLASHAVOON 110K1-2 | bar: Week 37 We 11
TO-24-KYT-220K2-01 | KELLYSTOWN 220K2 | bar: Week 37 We 11
TO-24-220 kV A2 @ AD-02 | AGHADA 220 kV A2 | bar: Week 37 We 11 to Week 37 Mo 16
TO-24-220 kV B2 @ AD-02 | AGHADA 220 kV B2 | bar: Week 37 We 11 to Week 37 Mo 16
TO-24-AD-SA1-2CB-02 | AGHADA 220SA1-2CB | bar: Week 37 We 11 to Week 37 Mo 16
TO-24-AD-SB1-2CB-02 | AGHADA 220SB1-2CB | bar: Week 37 We 11 to Week 37 Mo 16
Report covers outages commencing/returning/spanning the period: 02/09/2024 - 15/09/2024
Outages commencing/returning in Week 37
OUTAGE ID | PLANT | Week 36 Mo 2: Week 36; Week 37 Mo 9: Week 37
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
TO-24-AD-RAF-1-04 | AGHADA RAFFEEN
TO-24-220 kV A4 @ KRA-01 | KNOCKRAHA 220 kV A4
TO-24-220 kV B4 @ KRA-01 | KNOCKRAHA 220 kV B4
TO-24-KRA-220K4-04 | KNOCKRAHA 220K4
TO-24-KRA-220SA2-4CB-04 | KNOCKRAHA 220SA2-4CB
TO-24-KRA-220SB2-4CB-04 | KNOCKRAHA 220SB2-4CB
TO-24-220 kV A2 @ RAF-02 | RAFFEEN 220 kV A2
TO-24-220 kV B2 @ RAF-02 | RAFFEEN 220 kV B2
TO-24-BIN-CF-1-01 | BINBANE CATHALEENS FALL
TO-24-AA GIS-110SB1-2CB-02 | ARDNACRUSHA GIS 110SB1-2CB
TO-24-KYT-220K3-01 | KELLYSTOWN 220K3
TO-24-110 kV A2 @ CSH-01 | CASHLA 110 kV A2
TO-24-110 kV A2 @ CSH-07
TO-24-110 kV B2 @ CSH-01 | CASHLA 110 kV B2
TO-24-110 kV B2 @ CSH-06
TO-24-SOM,T-CSH-1-01 | SOMERSET tee CASHLA
TO-24-AA GIS-110SB1-3CB-02 | ARDNACRUSHA GIS 110SB1-3CB
TO-24-LOU-220K1-2-05 | LOUTH 220K1-2
TO-24-AA GIS-T101-01 | ARDNACRUSHA GIS T101
TO-24-ATH-SH-1-04 | ATHLONE SHANNONBRIDGE
Outages spanning Weeks 36-37
OUTAGE ID | PLANT | Week 36 Mo 2: Week 36; Week 37 Mo 9: Week 37
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
TO-24-AUN-CBT-3-01 | AUNGIERSTOWN CASTLEBAGOT 3
TO-24-BAL-DRY-1-05 | BALTRASNA DRYBRIDGE
TO-24-BRY-RAF-2-01 | BARNAHELY RAFFEEN 2
TO-24-CSH-CAP2-01 | CASHLA CAP2
TO-24-CSH-T2101-01 | CASHLA T2101
TO-24-CBR-SVC-06 | CASTLEBAR SVC
TO-24-CLG-110K1-02 | CLOGHRAN 110K1
TO-24-CUL-DGN-1-03 | CULLENAGH DUNGARVAN
TO-24-DND-T121-01 | DARNDALE T121
TO-24-DRU-ENN-1-02 | DRUMLINE ENNIS
TO-24-DRU-T141-01 | DRUMLINE T141
TO-24-GAL-GAL GIS-2-02 | GALWAY GALWAY GIS 2
TO-24-GAL-T141-02 | GALWAY T141
TO-24-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-24-GLR-MOY-1-01 | GLENREE MOY
TO-24-GOR-NAV-1-01 | GORMAN NAVAN 1
TO-24-GI-T141-01 | GREAT ISLAND T141
TO-24-INC-220K1-2-02 | INCHICORE 220K1-2
TO-24-KPG-TB-1-08 | KILPADDOGE TARBERT 1
TO-24-LET-PST-02 | LETTERKENNY STRABANE PST
TO-24-110 kV A1 @ LOU-01 | LOUTH 110 kV A1
TO-24-110 kV B1 @ LOU-01 | LOUTH 110 kV B1
TO-24-LOU-MLN-1-01 | LOUTH MULLAGHARLIN
TO-24-LOU-RRU-1-01 | LOUTH RATRUSSAN
TO-24-PB-R2002-02 | POOLBEG R2002
TO-24-PRO-TB-1-01 | PROSPECT TARBERT
TO-24-110 kV A2 @ RAF-02 | RAFFEEN 110 kV A2
TO-24-110 kV B2 @ RAF-02 | RAFFEEN 110 kV B2
TO-24-SHL-T2015-01 | SHELLYBANKS T2015
TO-24-220 kV A2 @ TB-01 | TARBERT 220 kV A2
TO-24-220 kV B2 @ TB-01 | TARBERT 220 kV B2
TO-24-TB-220K1-2-09 | TARBERT 220K1-2
TO-24-TB-T2003-01 | TARBERT T2003
TO-24-TB-T2004-06 | TARBERT T2004
TO-24-TB-T2004-01
TO-24-THU-CAP1-04 | THURLES CAP1
Report covers outages commencing/returning/spanning the period: 02/09/2024 - 15/09/2024
Outages spanning Weeks 36-37
OUTAGE ID | PLANT | Week 36 Mo 2: Week 36; Week 37 Mo 9: Week 37
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
TO-24-TRL-CAP2-01 | TRALEE CAP2
TO-24-WOO-T4204-01 | WOODLAND T4204