## Wks 40 - 41
Report covers outages commencing/returning/spanning the period: 30/09/2024 - 13/10/2024
Outages commencing/returning in Week 40
OUTAGE ID | PLANT |  | Week 40 | [6 empty] | Week 41
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
TO-24-110 kV A2 @ LOU-06 | LOUTH 110 kV A2
TO-24-110 kV B2 @ LOU-06 | LOUTH 110 kV B2
TO-24-LOU-T2104-06 | LOUTH T2104
TO-24-ROP-T131-04 | ROSSPILE T131
TO-24-CSH-GAL GIS-1-03 | CASHLA GALWAY GIS 1 | bar: Week 40 Tu 1
TO-24-CHA-KLN-1-01 | CHARLEVILLE KILLONAN | bar: Week 40 Tu 1 to Week 40 Fr 4
TO-24-CDU-SNU-1-02 | CORDUFF SNUGBOROUGH | bar: Week 40 Tu 1 to Week 40 Fr 4
TO-24-110 kV A2 @ SNU-03 | SNUGBOROUGH 110 kV A2 | bar: Week 40 Tu 1 to Week 40 Fr 4
TO-24-110 kV B2 @ SNU-03 | SNUGBOROUGH 110 kV B2 | bar: Week 40 Tu 1 to Week 40 Fr 4
TO-24-SNU-110K2-04 | SNUGBOROUGH 110K2 | bar: Week 40 Tu 1 to Week 40 Fr 4
TO-24-SNU-110SA1-2CB-07 | SNUGBOROUGH 110SA1-2CB | bar: Week 40 Tu 1 to Week 40 Fr 4
TO-24-SNU-110SB1-2CB-08 | SNUGBOROUGH 110SB1-2CB | bar: Week 40 Tu 1 to Week 40 Fr 4
TO-24-110 kV A2 @ FLA-05 | FLAGFORD 110 kV A2 | bar: Week 40 Tu 1 to Week 41 Fr 11
TO-24-110 kV B2 @ FLA-05 | FLAGFORD 110 kV B2 | bar: Week 40 Tu 1 to Week 41 Fr 11
TO-24-COS-FLA-2-01 | CARRICK ON SHANNON FLAGFORD 2 | bar: Week 40 Tu 1 to Week 41 Mo 14
TO-24-COS-FLA-2-03 | bar: Week 40 Tu 1 to Week 41 Mo 14
TO-24-110 kV A2 @ FLA-01 | FLAGFORD 110 kV A2 | bar: Week 40 Tu 1 to Week 41 Mo 14
TO-24-110 kV B2 @ FLA-01 | FLAGFORD 110 kV B2 | bar: Week 40 Tu 1 to Week 41 Mo 14
TO-24-MLC-TSB-1-04 | MOUNTLUCAS THORNSBERRY | bar: Week 40 Tu 1 to Week 41 Mo 14
TO-24-COW-RAF-1-03 | COW CROSS RAFFEEN | bar: Su 29
TO-24-110 kV A1 @ LOU-01 | LOUTH 110 kV A1 | bar: Su 29
TO-24-110 kV B1 @ LOU-01 | LOUTH 110 kV B1 | bar: Su 29
TO-24-LOU-MLN-1-01 | LOUTH MULLAGHARLIN | bar: Su 29
TO-24-LIM-RAT-1-02 | LIMERICK RATHKEALE | bar: Week 40 Tu 1
TO-24-ATH-T142-01 | ATHLONE T142 | bar: Week 40 Tu 1 to Week 40 We 2
TO-24-BOG-T122-01 | BANOGE T122 | bar: Week 40 Tu 1 to Week 40 We 2
TO-24-TB-T101-02 | TARBERT T101 | bar: Week 40 Tu 1 to Week 40 We 2
TO-24-ARV-NAV-1-03 | ARVA NAVAN | bar: Week 40 Tu 1 to Week 40 Fr 4
TO-24-110 kV A3 @ GAL GIS-03 | GALWAY GIS 110 kV A3 | bar: Su 29; Week 40 Tu 1
TO-24-110 kV B3 @ GAL GIS-01 | GALWAY GIS 110 kV B3 | bar: Su 29; Week 40 Tu 1
TO-24-GAL GIS-110K3-01 | GALWAY GIS 110K3 | bar: Su 29; Week 40 Tu 1
TO-24-GAL GIS-110SA1-3CB-03 | GALWAY GIS 110SA1-3CB | bar: Su 29; Week 40 Tu 1
TO-24-GAL GIS-110SB1-3CB-03 | GALWAY GIS 110SB1-3CB | bar: Su 29; Week 40 Tu 1
TO-24-GAL-T141-02 | GALWAY T141 | bar: Su 29; Week 40 Tu 1
TO-24-BLC-110K1-01 | BELCAMP 110K1 | bar: Week 40 We 2
TO-24-CD-MAC-1-02 | CARRIGADROHID MACROOM | bar: Week 40 We 2 to Week 41 Th 10
TO-24-MAC-110SA1-2CB-01 | MACROOM 110SA1-2CB | bar: Week 40 We 2 to Week 41 Th 10
TO-24-GAL-GAL GIS-1-04 | GALWAY GALWAY GIS 1 | bar: Week 40 We 2 to Week 41 Mo 14
TO-24-GAL-T103-01 | GALWAY T103 | bar: Week 40 We 2 to Week 41 Mo 14
TO-24-BDN-MRK1-01 | BALLYDINE MRK1 | bar: Su 29; Week 40 Tu 1 to Week 40 We 2
TO-24-BVK-R2001-01 | BALLYVOUSKILL R2001 | bar: Week 40 Th 3
TO-24-BLC-110K3-01 | BELCAMP 110K3 | bar: Week 40 Th 3
TO-24-110 kV A2 @ KLN-02 | KILLONAN 110 kV A2 | bar: Su 29; Week 40 Tu 1 to Week 40 Th 3
TO-24-110 kV B2 @ KLN-03 | KILLONAN 110 kV B2 | bar: Su 29; Week 40 Tu 1 to Week 40 Th 3
TO-24-220 kV A2 @ KLN-03 | KILLONAN 220 kV A2 | bar: Su 29; Week 40 Tu 1 to Week 40 Th 3
TO-24-220 kV B2 @ KLN-02 | KILLONAN 220 kV B2 | bar: Su 29; Week 40 Tu 1 to Week 40 Th 3
TO-24-KLN-T2104-01 | KILLONAN T2104 | bar: Su 29; Week 40 Tu 1 to Week 40 Th 3
TO-24-BLU-CDU-1-01 | BLUNDELSTOWN CORDUFF | bar: Su 29; Week 40 Tu 1 to Week 40 Fr 4
TO-24-110 kV A1 @ CLG-02 | CLOGHRAN 110 kV A1 | bar: Su 29; Week 40 Tu 1 to Week 40 Fr 4
TO-24-110 kV B1 @ CLG-02 | CLOGHRAN 110 kV B1 | bar: Su 29; Week 40 Tu 1 to Week 40 Fr 4
TO-24-CLG-110K1-05 | CLOGHRAN 110K1 | bar: Su 29; Week 40 Tu 1 to Week 40 Fr 4
TO-24-CLG-110SA1-2CB-03 | CLOGHRAN 110SA1-2CB | bar: Su 29; Week 40 Tu 1 to Week 40 Fr 4
TO-24-CLG-110SB1-2CB-02 | CLOGHRAN 110SB1-2CB | bar: Su 29; Week 40 Tu 1 to Week 40 Fr 4
TO-24-CLG-T121-01 | CLOGHRAN T121 | bar: Su 29; Week 40 Tu 1 to Week 40 Fr 4
TO-24-CLE-WOO-1-01 | CLONEE WOODLAND | bar: Su 29; Week 40 Tu 1 to Week 40 Fr 4
TO-24-KYT-WOO-1-01 | KELLYSTOWN WOODLAND | bar: Su 29; Week 40 Tu 1 to Week 40 Fr 4
TO-24-DSN-MP GIS-1-04 | DUNSTOWN MONEYPOINT GIS | bar: Week 40 Sa 5 to Week 40 Su 6
TO-24-CDU-HN-1-01 | CORDUFF HUNTSTOWN | bar: Week 40 Sa 5 to Week 41 Mo 14
TO-24-HN-T2002-01 | HUNTSTOWN T2002 | bar: Week 40 Sa 5 to Week 41 Mo 14
Report covers outages commencing/returning/spanning the period: 30/09/2024 - 13/10/2024
Outages commencing/returning in Week 41
OUTAGE ID | PLANT | Week 40 Mo 30: Week 40; Week 41 Mo 7: Week 41
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
TO-24-AUG-CFM-1-02 | AUGHINISH CASTLEFARM 1
TO-24-220 kV A1 @ BVK-01 | BALLYVOUSKILL 220 kV A1
TO-24-220 kV B1 @ BVK-01 | BALLYVOUSKILL 220 kV B1
TO-24-BVK-220K1-01 | BALLYVOUSKILL 220K1
TO-24-BVK-220SA1-2CB-05 | BALLYVOUSKILL 220SA1-2CB
TO-24-BVK-220SB1-2CB-05 | BALLYVOUSKILL 220SB1-2CB
TO-24-110 kV A4 @ CBT-01 | CASTLEBAGOT 110 kV A4
TO-24-110 kV B4 @ CBT-01 | CASTLEBAGOT 110 kV B4
TO-24-CBT-110K4-01 | CASTLEBAGOT 110K4
TO-24-CBT-110SA2-4CB-01 | CASTLEBAGOT 110SA2-4CB
TO-24-CBT-110SB2-4CB-01 | CASTLEBAGOT 110SB2-4CB
TO-24-CFM-T101-02 | CASTLEFARM T101
TO-24-CUS-NEW-1-01 | CUSHALING NEWBRIDGE
TO-24-DDK-110SA1-01 | DUNDALK 110SA1
TO-24-DDK-110SA2-03 | DUNDALK 110SA2
TO-24-DDK-MLN-1-03 | DUNDALK MULLAGHARLIN
TO-24-DDK-T141-02 | DUNDALK T141
TO-24-GI-KKY-1-02 | GREAT ISLAND KILKENNY
TO-24-GI-WAT-1-05 | GREAT ISLAND WATERFORD 1
TO-24-MOY-TAW-2-02 | MOY TAWNAGHMORE 2
TO-24-CBT-INC-1-03 | CASTLEBAGOT INCHICORE 1 | bar: Week 41 Sa 12 to Week 41 Mo 14
TO-24-INC-MAY-2-07 | INCHICORE MAYNOOTH 2 | bar: Week 41 Sa 12 to Week 41 Mo 14
TO-24-KBY-KRA-1-01 | KILBARRY KNOCKRAHA 1 | bar: Week 41 Sa 12 to Week 41 Mo 14
TO-24-110 kV A2 @ KLN-03 | KILLONAN 110 kV A2 | bar: Week 41 Sa 12 to Week 41 Mo 14
TO-24-110 kV B2 @ KLN-04 | KILLONAN 110 kV B2 | bar: Week 41 Sa 12 to Week 41 Mo 14
TO-24-220 kV A2 @ KLN-04 | KILLONAN 220 kV A2 | bar: Week 41 Sa 12 to Week 41 Mo 14
TO-24-220 kV B2 @ KLN-03 | KILLONAN 220 kV B2 | bar: Week 41 Sa 12 to Week 41 Mo 14
TO-24-KLN-T2102-02 | KILLONAN T2102 | bar: Week 41 Sa 12 to Week 41 Mo 14
TO-24-110 kV A1 @ KRA-02 | KNOCKRAHA 110 kV A1 | bar: Week 41 Sa 12 to Week 41 Mo 14
TO-24-110 kV B1 @ KRA-02 | KNOCKRAHA 110 kV B1 | bar: Week 41 Sa 12 to Week 41 Mo 14
TO-24-LOU-T2104-01 | LOUTH T2104 | bar: Week 41 Sa 12 to Week 41 Mo 14
TO-24-CSH-T2101-01 | CASHLA T2101 | bar: Su 29 to Week 40 Su 6
TO-24-CLE-T222-02 | CLONEE T222 | bar: Su 29 to Week 40 Su 6
TO-24-LLA-110K1-02 | LENALEA 110K1
TO-24-RYB GIS-110K4-02 | RYEBROOK GIS 110K4
TO-24-KPG-MP GIS-1-01 | KILPADDOGE MONEYPOINT GIS 1 | bar: Week 41 Sa 12 to Week 41 Mo 14
TO-24-DRU-ENN-1-02 | DRUMLINE ENNIS | bar: Su 29 to Week 40 Su 6
TO-24-110 kV A2 @ CF-03 | CATHALEENS FALL 110 kV A2
TO-24-CF-SRA-2-02 | CATHALEENS FALL SRANANAGH 2
TO-24-GAR-GOR-1-02 | GARBALLAGH GORMAN
TO-24-110 kV A1 @ GOR-01 | GORMAN 110 kV A1
TO-24-MAY-RYB GIS-1-02 | MAYNOOTH RYEBROOK GIS
TO-24-BIN-CF-1-01 | BINBANE CATHALEENS FALL | bar: Su 29 to Week 40 Su 6
TO-24-CLH-TRL-1-01 | CLAHANE TRALEE | bar: Su 29 to Week 40 Su 6
TO-24-GOR-NAV-1-01 | GORMAN NAVAN 1 | bar: Su 29 to Week 40 Su 6
TO-24-RYB GIS-T103-01 | RYEBROOK GIS T103 | bar: Su 29 to Week 40 Su 6
Outages spanning Weeks 40-41
OUTAGE ID | PLANT | Week 40 Mo 30: Week 40; Week 41 Mo 7: Week 41
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
TO-24-AA GIS-T101-01 | ARDNACRUSHA GIS T101
TO-24-AUN-CBT-3-01 | AUNGIERSTOWN CASTLEBAGOT 3
TO-24-BAL-DRY-1-05 | BALTRASNA DRYBRIDGE
TO-24-BRY-RAF-2-01 | BARNAHELY RAFFEEN 2
TO-24-CAH-TIP-1-01 | CAHIR TIPPERARY
TO-24-110 kV A2 @ CSH-01 | CASHLA 110 kV A2
TO-24-110 kV B2 @ CSH-01 | CASHLA 110 kV B2
TO-24-CSH-CAP2-01 | CASHLA CAP2
TO-24-CBR-SVC-06 | CASTLEBAR SVC
Report covers outages commencing/returning/spanning the period: 30/09/2024 - 13/10/2024
Outages spanning Weeks 40-41
OUTAGE ID | PLANT | Week 40 Mo 30: Week 40; Week 41 Mo 7: Week 41
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
TO-24-CLA-MAC-2-01 | CLASHAVOON MACROOM 2
TO-24-CLG-110K1-02 | CLOGHRAN 110K1
TO-24-CRO-T122-02 | COOLROE T122
TO-24-CRA-WEX-1-01 | CRANE WEXFORD
TO-24-CUL-110K1-2-01 | CULLENAGH 110K1-2
TO-24-CUL-220K1-2-02 | CULLENAGH 220K1-2
TO-24-CUL-DGN-1-03 | CULLENAGH DUNGARVAN
TO-24-DND-T121-01 | DARNDALE T121
TO-24-DRU-T141-01 | DRUMLINE T141
TO-24-GAL-GAL GIS-2-02 | GALWAY GALWAY GIS 2
TO-24-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-24-GLR-MOY-1-01 | GLENREE MOY
TO-24-GI-T141-01 | GREAT ISLAND T141
TO-24-INC-220K1-2-02 | INCHICORE 220K1-2
TO-24-220 kV A4 @ KRA-01 | KNOCKRAHA 220 kV A4
TO-24-220 kV B4 @ KRA-01 | KNOCKRAHA 220 kV B4
TO-24-KRA-220K4-04 | KNOCKRAHA 220K4
TO-24-KRA-220SA2-4CB-04 | KNOCKRAHA 220SA2-4CB
TO-24-KRA-220SB2-4CB-04 | KNOCKRAHA 220SB2-4CB
TO-24-LET-PST-02 | LETTERKENNY STRABANE PST
TO-24-LIS-LSA-1-01 | LISDRUM LISLEA
TO-24-PB-R2002-02 | POOLBEG R2002
TO-24-PRO-TB-1-01 | PROSPECT TARBERT
TO-24-110 kV A2 @ RAF-02 | RAFFEEN 110 kV A2
TO-24-110 kV B2 @ RAF-02 | RAFFEEN 110 kV B2
TO-24-SHL-T2016-01 | SHELLYBANKS T2016
TO-24-SOM,T-CSH-1-01 | SOMERSET tee CASHLA
TO-24-TB-T2003-01 | TARBERT T2003
TO-24-TB-T2004-01 | TARBERT T2004
TO-24-THU-CAP1-04 | THURLES CAP1
TO-24-TRL-CAP2-01 | TRALEE CAP2