## Wks 44 - 45
Report covers outages commencing/returning/spanning the period: 28/10/2024 - 10/11/2024
Outages commencing/returning in Week 44
OUTAGE ID | PLANT |  | Week 44 | [6 empty] | Week 45
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
TO-24-GAR-GOR-1-02 | GARBALLAGH GORMAN | bar: Week 44 Mo 28
TO-24-110 kV A1 @ GOR-01 | GORMAN 110 kV A1 | bar: Week 44 Mo 28
TO-24-GOR-NAV-1-01 | GORMAN NAVAN 1 | bar: Su 27 to Week 44 Mo 28
TO-24-GAL GIS-110SB1-3CB-04 | GALWAY GIS 110SB1-3CB
TO-24-TRI-110SA1-2CB-02 | TRIEN 110SA1-2CB
TO-24-TRI-T142-03 | TRIEN T142
TO-24-BAL-110SA1-02 | BALTRASNA 110SA1
TO-24-BAL-110SA2-04 | BALTRASNA 110SA2
TO-24-BAL-110SA2-03
TO-24-BAL-T121-03 | BALTRASNA T121
TO-24-CLG-T122-01 | CLOGHRAN T122
TO-24-DRY-110SA1-04 | DRYBRIDGE 110SA1
TO-24-DRY-110SA2-04 | DRYBRIDGE 110SA2
TO-24-DRY-GOR-1-07 | DRYBRIDGE GORMAN
TO-24-DRY-T142-04 | DRYBRIDGE T142
TO-24-KNR-TRI-2-03 | KNOCKANURE TRIEN 2
TO-24-KLN-KRA-1-01 | KILLONAN KNOCKRAHA | bar: Week 44 Th 31 to Week 44 Fr 1
TO-24-BAN-DMY-1-04 | BANDON DUNMANWAY | bar: Week 44 Th 31 to Week 45 Fr 8
TO-24-CLA-DMY-1-01 | CLASHAVOON DUNMANWAY | bar: Week 44 Th 31 to Week 45 Fr 8
TO-24-DMY-110SA1-2CB-01 | DUNMANWAY 110SA1-2CB | bar: Week 44 Th 31 to Week 45 Fr 8
TO-24-DMY-CAP2-02 | DUNMANWAY CAP2 | bar: Week 44 Th 31 to Week 45 Fr 8
TO-24-DMY-T142-02 | DUNMANWAY T142 | bar: Week 44 Th 31 to Week 45 Fr 8
TO-24-110 kV A1 @ GOR-03 | GORMAN 110 kV A1 | bar: Week 44 Th 31 to Week 45 Fr 8
TO-24-110 kV B1 @ GOR-02 | GORMAN 110 kV B1 | bar: Week 44 Th 31 to Week 45 Fr 8
TO-24-GOR-NAV-3-02 | GORMAN NAVAN 3 | bar: Week 44 Th 31 to Week 45 Fr 8
TO-24-110 kV A2 @ SNU-05 | SNUGBOROUGH 110 kV A2 | bar: Week 44 Th 31 to Week 45 Fr 8
TO-24-110 kV B2 @ SNU-06 | SNUGBOROUGH 110 kV B2 | bar: Week 44 Th 31 to Week 45 Fr 8
TO-24-SNU-110K2-07 | SNUGBOROUGH 110K2 | bar: Week 44 Th 31 to Week 45 Fr 8
TO-24-SNU-110SA1-2CB-10 | SNUGBOROUGH 110SA1-2CB | bar: Week 44 Th 31 to Week 45 Fr 8
TO-24-SNU-110SB1-2CB-11 | SNUGBOROUGH 110SB1-2CB | bar: Week 44 Th 31 to Week 45 Fr 8
TO-24-SNU-T104-01 | SNUGBOROUGH T104 | bar: Week 44 Th 31 to Week 45 Fr 8
TO-24-KTL-MAY-1-02 | KILTEEL MAYNOOTH | bar: Week 44 Th 31 to Week 45 Mo 11
TO-24-BAN-BRI-2-01 | BANDON BRINNY 2
TO-24-BRI-T102-01 | BRINNY T102
TO-24-CBT-T2102-01 | CASTLEBAGOT T2102 | bar: Week 44 Th 31
TO-24-CLG-T124-01 | CLOGHRAN T124 | bar: Week 44 Th 31 to Week 44 Fr 1
TO-24-SHL-T2016-01 | SHELLYBANKS T2016 | bar: Su 27 to Week 44 Mo 28; Week 44 Th 31
TO-24-220 kV A1 @ CBT-03 | CASTLEBAGOT 220 kV A1 | bar: Su 27 to Week 44 Mo 28; Week 44 Th 31 to Week 44 Fr 1
TO-24-220 kV B1 @ CBT-01 | CASTLEBAGOT 220 kV B1 | bar: Su 27 to Week 44 Mo 28; Week 44 Th 31 to Week 44 Fr 1
TO-24-CBT-220K1-02 | CASTLEBAGOT 220K1 | bar: Su 27 to Week 44 Mo 28; Week 44 Th 31 to Week 44 Fr 1
TO-24-CBT-220SA1-2CB-05 | CASTLEBAGOT 220SA1-2CB | bar: Su 27 to Week 44 Mo 28; Week 44 Th 31 to Week 44 Fr 1
TO-24-CBT-220SB1-2CB-05 | CASTLEBAGOT 220SB1-2CB | bar: Su 27 to Week 44 Mo 28; Week 44 Th 31 to Week 44 Fr 1
TO-24-CBT-MAY-1-04 | CASTLEBAGOT MAYNOOTH 1 | bar: Su 27 to Week 44 Mo 28; Week 44 Th 31 to Week 44 Fr 1
TO-24-GLR-MOY-1-01 | GLENREE MOY | bar: Su 27 to Week 44 Mo 28; Week 44 Th 31 to Week 44 Fr 1
TO-24-110 kV A2 @ LOU-08 | LOUTH 110 kV A2 | bar: Su 27 to Week 44 Mo 28; Week 44 Th 31 to Week 44 Fr 1
TO-24-110 kV B2 @ LOU-08 | LOUTH 110 kV B2 | bar: Su 27 to Week 44 Mo 28; Week 44 Th 31 to Week 44 Fr 1
TO-24-220 kV A2 @ LOU-03 | LOUTH 220 kV A2 | bar: Su 27 to Week 44 Mo 28; Week 44 Th 31 to Week 44 Fr 1
TO-24-220 kV B2 @ LOU-03 | LOUTH 220 kV B2 | bar: Su 27 to Week 44 Mo 28; Week 44 Th 31 to Week 44 Fr 1
TO-24-LOU-T2104-01 | LOUTH T2104 | bar: Su 27 to Week 44 Mo 28; Week 44 Th 31 to Week 44 Fr 1
TO-24-220 kV A1 @ MAY-05 | MAYNOOTH 220 kV A1 | bar: Su 27 to Week 44 Mo 28; Week 44 Th 31 to Week 44 Fr 1
TO-24-220 kV B1 @ MAY-05 | MAYNOOTH 220 kV B1 | bar: Su 27 to Week 44 Mo 28; Week 44 Th 31 to Week 44 Fr 1
TO-24-MOY-TAW-1-03 | MOY TAWNAGHMORE 1 | bar: Su 27 to Week 44 Mo 28; Week 44 Th 31 to Week 44 Fr 1
Outages commencing/returning in Week 45
OUTAGE ID | PLANT | Week 44 Mo 28: Week 44; Week 45 Mo 4: Week 45
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
TO-24-BK-110SA1-01 | BELLACORICK 110SA1 | bar: Week 45 Mo 4; Week 45 Th 7
TO-24-BK-110SA2-01 | BELLACORICK 110SA2 | bar: Week 45 Mo 4; Week 45 Th 7
TO-24-BK-T141-01 | BELLACORICK T141 | bar: Week 45 Mo 4; Week 45 Th 7
Report covers outages commencing/returning/spanning the period: 28/10/2024 - 10/11/2024
Outages commencing/returning in Week 45
OUTAGE ID | PLANT | Week 44 Mo 28: Week 44; Week 45 Mo 4: Week 45
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
TO-24-ATH-110SA1-2CB-05 | ATHLONE 110SA1-2CB
TO-24-ATH-SH-1-06 | ATHLONE SHANNONBRIDGE
TO-24-ATH-T142-02 | ATHLONE T142
TO-24-220 kV A2 @ BYH-04 | BALLYNAHULLA 220 kV A2
TO-24-220 kV B2 @ BYH-04 | BALLYNAHULLA 220 kV B2
TO-24-BYH-220K2-01 | BALLYNAHULLA 220K2
TO-24-BYH-220SA1-2CB-04 | BALLYNAHULLA 220SA1-2CB
TO-24-BYH-220SB1-2CB-05 | BALLYNAHULLA 220SB1-2CB
TO-24-PLA-T105-02 | PLATIN T105
TO-24-SLI-110SA1-2CB-06 | SLIGO 110SA1-2CB
TO-24-SLI-T142-03 | SLIGO T142
TO-24-BK-MOY-1-04 | BELLACORICK MOY
TO-24-220 kV A1 @ CBT-01 | CASTLEBAGOT 220 kV A1
TO-24-220 kV B1 @ CBT-03 | CASTLEBAGOT 220 kV B1
TO-24-CBT-220K1-03 | CASTLEBAGOT 220K1
TO-24-CBT-220SA1-2CB-06 | CASTLEBAGOT 220SA1-2CB
TO-24-CBT-220SB1-2CB-06 | CASTLEBAGOT 220SB1-2CB
TO-24-CBT-INC-1-05 | CASTLEBAGOT INCHICORE 1
TO-24-INC-MAY-2-07 | INCHICORE MAYNOOTH 2
TO-24-WOO-T4202-03 | WOODLAND T4202
TO-24-MLC-TSB-1-02 | MOUNTLUCAS THORNSBERRY
TO-24-BLU-T131-02 | BLUNDELSTOWN T131
TO-24-CSH-GAL GIS-4-02 | CASHLA GALWAY GIS 4
TO-24-KPG-KNR-2-01 | KILPADDOGE KNOCKANURE 2
TO-24-110 kV A2 @ KBY-02 | KILBARRY 110 kV A2
TO-24-110 kV B2 @ KBY-02 | KILBARRY 110 kV B2
TO-24-KBY-MAL-1-01 | KILBARRY MALLOW
TO-24-220 kV A1 @ KNR-01 | KNOCKANURE 220 kV A1
TO-24-220 kV B1 @ KNR-01 | KNOCKANURE 220 kV B1
TO-24-KNR-220K1-01 | KNOCKANURE 220K1
TO-24-KNR-220SA1-2CB-03 | KNOCKANURE 220SA1-2CB
TO-24-KNR-220SB1-2CB-02 | KNOCKANURE 220SB1-2CB
TO-24-MLN-T123-01 | MULLAGHARLIN T123
TO-24-CUS-T103/5-02 | CUSHALING T103/5
TO-24-220 kV A4 @ KRA-01 | KNOCKRAHA 220 kV A4
TO-24-220 kV B4 @ KRA-01 | KNOCKRAHA 220 kV B4
TO-24-KRA-220K4-04 | KNOCKRAHA 220K4
TO-24-KRA-220SA2-4CB-04 | KNOCKRAHA 220SA2-4CB
TO-24-KRA-220SB2-4CB-04 | KNOCKRAHA 220SB2-4CB
TO-24-110 kV A2 @ CSH-01 | CASHLA 110 kV A2
TO-24-110 kV B2 @ CSH-01 | CASHLA 110 kV B2
TO-24-KYT-T232-02 | KELLYSTOWN T232
Outages spanning Weeks 44-45
OUTAGE ID | PLANT | Week 44 Mo 28: Week 44; Week 45 Mo 4: Week 45
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
TO-24-AUN-CBT-3-01 | AUNGIERSTOWN CASTLEBAGOT 3
TO-24-BAL-DRY-1-05 | BALTRASNA DRYBRIDGE
TO-24-BRY-RAF-2-01 | BARNAHELY RAFFEEN 2
TO-24-CAH-TIP-1-01 | CAHIR TIPPERARY
TO-24-COS-FLA-2-03 | CARRICK ON SHANNON FLAGFORD 2
TO-24-CSH-CAP2-01 | CASHLA CAP2
TO-24-CLA-MAC-2-01 | CLASHAVOON MACROOM 2
TO-24-CRO-T122-02 | COOLROE T122
TO-24-CRA-WEX-1-01 | CRANE WEXFORD
TO-24-CUL-110K1-2-01 | CULLENAGH 110K1-2
TO-24-CUL-220K1-2-02 | CULLENAGH 220K1-2
TO-24-CUL-DGN-1-03 | CULLENAGH DUNGARVAN
TO-24-DND-T121-01 | DARNDALE T121
TO-24-DRU-T141-01 | DRUMLINE T141
Report covers outages commencing/returning/spanning the period: 28/10/2024 - 10/11/2024
Outages spanning Weeks 44-45
OUTAGE ID | PLANT | Week 44 Mo 28: Week 44; Week 45 Mo 4: Week 45
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
TO-24-110 kV A2 @ FLA-01 | FLAGFORD 110 kV A2
TO-24-110 kV B2 @ FLA-01 | FLAGFORD 110 kV B2
TO-24-GAL-GAL GIS-2-02 | GALWAY GALWAY GIS 2
TO-24-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-24-GI-T141-01 | GREAT ISLAND T141
TO-24-INC-220K1-2-02 | INCHICORE 220K1-2
TO-24-INC-MAY-2-03 | INCHICORE MAYNOOTH 2
TO-24-LET-PST-02 | LETTERKENNY STRABANE PST
TO-24-LIS-LSA-1-02 | LISDRUM LISLEA
TO-24-PB-R2002-02 | POOLBEG R2002
TO-24-PRO-TB-1-01 | PROSPECT TARBERT
TO-24-110 kV A2 @ RAF-02 | RAFFEEN 110 kV A2
TO-24-110 kV B2 @ RAF-02 | RAFFEEN 110 kV B2
TO-24-SOM,T-CSH-1-01 | SOMERSET tee CASHLA
TO-24-TB-T2003-01 | TARBERT T2003
TO-24-TB-T2004-01 | TARBERT T2004
TO-24-THU-CAP1-04 | THURLES CAP1
TO-24-TRL-CAP2-01 | TRALEE CAP2