## Wks 46 - 47
Report covers outages commencing/returning/spanning the period: 11/11/2024 - 24/11/2024
Outages commencing/returning in Week 46
OUTAGE ID | PLANT |  | Week 46 | [6 empty] | Week 47
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
TO-24-220 kV B1 @ AD-05 | AGHADA 220 kV B1 | bar: Week 46 Th 14 to Week 46 Fr 15
TO-24-220 kV B2 @ AD-07 | AGHADA 220 kV B2 | bar: Week 46 Th 14 to Week 46 Fr 15
TO-24-AD-220K1-07 | AGHADA 220K1 | bar: Week 46 Th 14 to Week 46 Fr 15
TO-24-AD-SB1-2CB-04 | AGHADA 220SB1-2CB | bar: Week 46 Th 14 to Week 46 Fr 15
TO-24-110 kV A2 @ CF-09 | CATHALEENS FALL 110 kV A2 | bar: Week 46 Th 14 to Week 46 Fr 15
TO-24-110 kV B2 @ CF-05 | CATHALEENS FALL 110 kV B2 | bar: Week 46 Th 14 to Week 46 Fr 15
TO-24-CF-CLO-2-01 | CATHALEENS FALL CLOGHER 2 | bar: Week 46 Th 14 to Week 46 Fr 15
TO-24-110 kV A2 @ CLO-03 | CLOGHER 110 kV A2 | bar: Week 46 Th 14 to Week 46 Fr 15
TO-24-110 kV B2 @ CLO-03 | CLOGHER 110 kV B2 | bar: Week 46 Th 14 to Week 46 Fr 15
TO-24-LOU-T2103-04 | LOUTH T2103 | bar: Week 46 Th 14 to Week 46 Fr 15
TO-24-110 kV A2 @ CSH-02 | CASHLA 110 kV A2 | bar: Week 46 Th 14 to Week 47 Mo 18
TO-24-110 kV B2 @ CSH-05 | CASHLA 110 kV B2 | bar: Week 46 Th 14 to Week 47 Mo 18
TO-24-CSH-ENN-1-01 | CASHLA ENNIS | bar: Week 46 Th 14 to Week 47 Mo 18
TO-24-CRO-110SA1-04 | COOLROE 110SA1 | bar: Week 46 Th 14 to Week 47 Fr 22
TO-24-CRO-110SA2-04 | COOLROE 110SA2 | bar: Week 46 Th 14 to Week 47 Fr 22
TO-24-CRO-IA-1-06 | COOLROE INNISCARRA | bar: Week 46 Th 14 to Week 47 Fr 22
TO-24-110 kV A1 @ FIN-01 | FINGLAS 110 kV A1 | bar: Week 46 Th 14 to Week 47 Fr 22
TO-24-110 kV B1 @ FIN-01 | FINGLAS 110 kV B1 | bar: Week 46 Th 14 to Week 47 Fr 22
TO-24-GRI,T-MAY-1-04 | GRIFFINRATH tee MAYNOOTH | bar: Week 46 Th 14 to Week 47 Mo 25
TO-24-110 kV A1 @ KRA-03 | KNOCKRAHA 110 kV A1 | bar: Week 46 Th 14 to Week 47 Mo 25
TO-24-110 kV B1 @ KRA-03 | KNOCKRAHA 110 kV B1 | bar: Week 46 Th 14 to Week 47 Mo 25
TO-24-220 kV A1 @ KRA-03 | KNOCKRAHA 220 kV A1 | bar: Week 46 Th 14 to Week 47 Mo 25
TO-24-220 kV B1 @ KRA-03 | KNOCKRAHA 220 kV B1 | bar: Week 46 Th 14 to Week 47 Mo 25
TO-24-KRA-220K1-04 | KNOCKRAHA 220K1 | bar: Week 46 Th 14 to Week 47 Mo 25
TO-24-KRA-220SA1-2CB-04 | KNOCKRAHA 220SA1-2CB | bar: Week 46 Th 14 to Week 47 Mo 25
TO-24-KRA-220SB1-2CB-04 | KNOCKRAHA 220SB1-2CB | bar: Week 46 Th 14 to Week 47 Mo 25
TO-24-KRA-T2101-02 | KNOCKRAHA T2101 | bar: Week 46 Th 14 to Week 47 Mo 25
TO-24-110 kV A2 @ MAY-05 | MAYNOOTH 110 kV A2 | bar: Week 46 Th 14 to Week 47 Mo 25
TO-24-110 kV A3 @ MAY-06 | MAYNOOTH 110 kV A3 | bar: Week 46 Th 14 to Week 47 Mo 25
TO-24-110 kV B2 @ MAY-05 | MAYNOOTH 110 kV B2 | bar: Week 46 Th 14 to Week 47 Mo 25
TO-24-110 kV B3 @ MAY-06 | MAYNOOTH 110 kV B3 | bar: Week 46 Th 14 to Week 47 Mo 25
TO-24-RYB GIS-T104-03 | RYEBROOK GIS T104 | bar: Week 46 Th 14 to Week 47 Mo 25
TO-24-220 kV A2 @ TB-02 | TARBERT 220 kV A2 | bar: Week 46 Th 14 to Week 47 Mo 25
TO-24-220 kV B2 @ TB-02 | TARBERT 220 kV B2 | bar: Week 46 Th 14 to Week 47 Mo 25
TO-24-110 kV A2 @ CSH-01 | CASHLA 110 kV A2 | bar: Su 10
TO-24-110 kV B2 @ CSH-01 | CASHLA 110 kV B2 | bar: Su 10
TO-24-SOM-T142-02 | SOMERSET T142 | bar: Su 10
TO-24-SOM,T-CSH-1-01 | SOMERSET tee CASHLA | bar: Su 10
TO-24-SOM,T-SH-1-03 | SOMERSET tee SHANNONBRIDGE | bar: Su 10
TO-24-SOM,T-SOM-1-02 | SOMERSET tee SOMERSET | bar: Su 10
TO-24-GAL GIS-KNY-1-03 | GALWAY GIS KNOCKRANNY
TO-24-FIN-FIN GIS-1-01 | FINGLAS FINGLAS GIS 1
TO-24-110 kV A2 @ FIN GIS-05 | FINGLAS GIS 110 kV A2
TO-24-110 kV A4 @ FIN GIS-02 | FINGLAS GIS 110 kV A4
TO-24-110 kV B2 @ FIN GIS-05 | FINGLAS GIS 110 kV B2
TO-24-FIN GIS-110K2-05 | FINGLAS GIS 110K2
TO-24-FIN GIS-110SA1-2CB-06 | FINGLAS GIS 110SA1-2CB
TO-24-FIN GIS-110SB1-2CB-06 | FINGLAS GIS 110SB1-2CB
TO-24-FIN GIS-110SB2-4CB-08 | FINGLAS GIS 110SB2-4CB
TO-24-FIN GIS-110SB4-6CB-04 | FINGLAS GIS 110SB4-6CB
TO-24-FIN-T2103-03 | FINGLAS T2103
TO-24-110 kV B4 @ FIN GIS-03 | FINGLAS GIS 110 kV B4 | bar: Week 46 Th 14 to Week 47 Mo 25
TO-24-FIN GIS-110SA2-4CB-07 | FINGLAS GIS 110SA2-4CB | bar: Week 46 Th 14 to Week 47 Mo 25
TO-24-FIN GIS-110SA4-6CB-02 | FINGLAS GIS 110SA4-6CB | bar: Week 46 Th 14 to Week 47 Mo 25
TO-24-110 kV A2 @ KBY-02 | KILBARRY 110 kV A2 | bar: Su 10
TO-24-110 kV B2 @ KBY-02 | KILBARRY 110 kV B2 | bar: Su 10
TO-24-KBY-MAL-1-01 | KILBARRY MALLOW | bar: Su 10
TO-24-KPG-KNR-2-01 | KILPADDOGE KNOCKANURE 2 | bar: Su 10
TO-24-KKY-110SA1-2CB-01 | KILKENNY 110SA1-2CB
TO-24-KKY-T141-01 | KILKENNY T141
TO-24-110 kV B1 @ FIN GIS-01 | FINGLAS GIS 110 kV B1 | bar: Week 46 Th 14 to Week 47 Fr 22
TO-24-110 kV B3 @ FIN GIS-01 | FINGLAS GIS 110 kV B3 | bar: Week 46 Th 14 to Week 47 Fr 22
TO-24-FIN GIS-110K1-01 | FINGLAS GIS 110K1 | bar: Week 46 Th 14 to Week 47 Fr 22
TO-24-FIN GIS-110SB1-3CB-01 | FINGLAS GIS 110SB1-3CB | bar: Week 46 Th 14 to Week 47 Fr 22
Report covers outages commencing/returning/spanning the period: 11/11/2024 - 24/11/2024
Outages commencing/returning in Week 46
OUTAGE ID | PLANT | Week 46 Mo 11: Week 46; Week 47 Mo 18: Week 47
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
TO-24-LIS-LSA-1-02 | LISDRUM LISLEA | bar: Su 10 to Week 46 Th 14
TO-24-BK-MOY-1-04 | BELLACORICK MOY | bar: Su 10 to Week 46 Fr 15
TO-24-220 kV A1 @ KNR-01 | KNOCKANURE 220 kV A1 | bar: Su 10 to Week 46 Fr 15
TO-24-220 kV B1 @ KNR-01 | KNOCKANURE 220 kV B1 | bar: Su 10 to Week 46 Fr 15
TO-24-KNR-220K1-01 | KNOCKANURE 220K1 | bar: Su 10 to Week 46 Fr 15
TO-24-KNR-220SA1-2CB-03 | KNOCKANURE 220SA1-2CB | bar: Su 10 to Week 46 Fr 15
TO-24-KNR-220SB1-2CB-02 | KNOCKANURE 220SB1-2CB | bar: Su 10 to Week 46 Fr 15
TO-24-WOO-T4202-03 | WOODLAND T4202 | bar: Su 10 to Week 46 Fr 15
Outages commencing/returning in Week 47
OUTAGE ID | PLANT | Week 46 Mo 11: Week 46; Week 47 Mo 18: Week 47
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
TO-24-110 kV B1 @ CUL-01 | CULLENAGH 110 kV B1 | bar: Week 47 Mo 18 to Week 47 Tu 19
TO-24-CUL-WAT-1-01 | CULLENAGH WATERFORD | bar: Week 47 Mo 18 to Week 47 Tu 19
TO-24-ATY-110SA1-01 | ATHY 110SA1 | bar: Week 47 Mo 18 to Week 47 Fr 22
TO-24-ATY-110SA2-04 | ATHY 110SA2 | bar: Week 47 Mo 18 to Week 47 Fr 22
TO-24-ATY-CLW-1-08 | ATHY CARLOW | bar: Week 47 Mo 18 to Week 47 Fr 22
TO-24-ATY-T101-02 | ATHY T101 | bar: Week 47 Mo 18 to Week 47 Fr 22
TO-24-BYH-110K1-01 | BALLYNAHULLA 110K1 | bar: Week 47 Mo 18 to Week 47 Fr 22
TO-24-CF-T104-05 | CATHALEENS FALL T104 | bar: Week 47 Mo 18 to Week 47 Fr 22
TO-24-110 kV A1/A2/A3/A4 @ CDU-01 | CORDUFF 110 kV A1/A2/A3/A4 | bar: Week 47 Mo 18 to Week 47 Fr 22
TO-24-110 kV B1/B2/B3/B4 @ CDU-01 | CORDUFF 110 kV B1/B2/B3/B4 | bar: Week 47 Mo 18 to Week 47 Fr 22
TO-24-CDU-110SA2-4-04 | CORDUFF 110SA2-4 | bar: Week 47 Mo 18 to Week 47 Fr 22
TO-24-CDU-110SB2-4-03 | CORDUFF 110SB2-4 | bar: Week 47 Mo 18 to Week 47 Fr 22
TO-24-CDU-T121-01 | CORDUFF T121 | bar: Week 47 Mo 18 to Week 47 Fr 22
TO-24-CDU-T2104-03 | CORDUFF T2104 | bar: Week 47 Mo 18 to Week 47 Fr 22
TO-24-GAL GIS-T142-05 | GALWAY GIS T142 | bar: Week 47 Mo 18 to Week 47 Fr 22
TO-24-BLU-MUL-1-02 | BLUNDELSTOWN MULLINGAR | bar: Week 47 Mo 18 to Week 47 Mo 25
TO-24-CSH-DLT-1-01 | CASHLA DALTON | bar: Week 47 Mo 18 to Week 47 Mo 25
TO-24-CKN-GRO-1-04 | CLONKEEN GARROW | bar: Week 47 Mo 18 to Week 47 Mo 25
TO-24-DGN-WOH-1-04 | DUNGARVAN WOODHOUSE | bar: Week 47 Tu 19
TO-24-KRA-WOH-1-04 | KNOCKRAHA WOODHOUSE | bar: Week 47 Tu 19
TO-24-CUL-DGN-1-03 | CULLENAGH DUNGARVAN | bar: Su 10 to Week 47 Tu 19
TO-24-DDK-LOU-1-02 | DUNDALK LOUTH | bar: Week 47 We 20 to Week 47 Fr 22
TO-24-RAF-110K1-2-03 | RAFFEEN 110K1-2 | bar: Week 47 We 20 to Week 47 Fr 22
TO-24-CAH-TIP-1-01 | CAHIR TIPPERARY | bar: Su 10 to Week 47 We 20
TO-24-CUL-110K1-2-01 | CULLENAGH 110K1-2 | bar: Su 10 to Week 47 We 20
TO-24-CUL-220K1-2-02 | CULLENAGH 220K1-2 | bar: Su 10 to Week 47 We 20
TO-24-110 kV A2 @ FLA-01 | FLAGFORD 110 kV A2 | bar: Su 10 to Week 47 We 20
TO-24-110 kV B2 @ FLA-01 | FLAGFORD 110 kV B2 | bar: Su 10 to Week 47 We 20
TO-24-BRT-CLE-2-02 | BRACETOWN CLONEE 2 | bar: Week 47 Th 21
TO-24-110 kV A2 @ FLA-02 | FLAGFORD 110 kV A2 | bar: Week 47 Th 21 to Week 47 Su 24
TO-24-110 kV B2 @ FLA-02 | FLAGFORD 110 kV B2 | bar: Week 47 Th 21 to Week 47 Su 24
TO-24-AUN-CBT-3-01 | AUNGIERSTOWN CASTLEBAGOT 3 | bar: Su 10 to Week 47 Th 21
TO-24-MCE-T124-04 | MACETOWN T124 | bar: Week 47 Fr 22 to Week 47 Mo 25
TO-24-220 kV A1 @ CBT-01 | CASTLEBAGOT 220 kV A1 | bar: Su 10 to Week 47 Fr 22
TO-24-220 kV B1 @ CBT-03 | CASTLEBAGOT 220 kV B1 | bar: Su 10 to Week 47 Fr 22
TO-24-CBT-220K1-03 | CASTLEBAGOT 220K1 | bar: Su 10 to Week 47 Fr 22
TO-24-CBT-220SA1-2CB-06 | CASTLEBAGOT 220SA1-2CB | bar: Su 10 to Week 47 Fr 22
TO-24-CBT-220SB1-2CB-06 | CASTLEBAGOT 220SB1-2CB | bar: Su 10 to Week 47 Fr 22
TO-24-CBT-INC-1-05 | CASTLEBAGOT INCHICORE 1 | bar: Su 10 to Week 47 Fr 22
TO-24-CRO-T122-02 | COOLROE T122 | bar: Su 10 to Week 47 Fr 22
TO-24-KTL-MAY-1-02 | KILTEEL MAYNOOTH | bar: Su 10 to Week 47 Fr 22
TO-24-FLA-T2102-02 | FLAGFORD T2102 | bar: Week 47 Su 24
TO-24-COS-FLA-2-03 | CARRICK ON SHANNON FLAGFORD 2
Outages spanning Weeks 46-47
OUTAGE ID | PLANT | Week 46 Mo 11: Week 46; Week 47 Mo 18: Week 47
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
TO-24-AA GIS-SNG-1-05 | ARDNACRUSHA GIS SINGLAND
TO-24-BAL-DRY-1-05 | BALTRASNA DRYBRIDGE
Report covers outages commencing/returning/spanning the period: 11/11/2024 - 24/11/2024
Outages spanning Weeks 46-47
OUTAGE ID | PLANT | Week 46 Mo 11: Week 46; Week 47 Mo 18: Week 47
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
TO-24-BRY-RAF-2-01 | BARNAHELY RAFFEEN 2
TO-24-CSH-CAP2-01 | CASHLA CAP2
TO-24-CLA-MAC-2-01 | CLASHAVOON MACROOM 2
TO-24-CRA-WEX-1-01 | CRANE WEXFORD
TO-24-DND-T121-01 | DARNDALE T121
TO-24-DRU-T141-01 | DRUMLINE T141
TO-24-FIN-110K1-2-01 | FINGLAS 110K1-2
TO-24-GAL-GAL GIS-2-02 | GALWAY GALWAY GIS 2
TO-24-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-24-GI-T141-01 | GREAT ISLAND T141
TO-24-INC-220K1-2-02 | INCHICORE 220K1-2
TO-24-INC-MAY-2-03 | INCHICORE MAYNOOTH 2
TO-24-220 kV A4 @ KRA-01 | KNOCKRAHA 220 kV A4
TO-24-220 kV B4 @ KRA-01 | KNOCKRAHA 220 kV B4
TO-24-KRA-220K4-04 | KNOCKRAHA 220K4
TO-24-KRA-220SA2-4CB-04 | KNOCKRAHA 220SA2-4CB
TO-24-KRA-220SB2-4CB-04 | KNOCKRAHA 220SB2-4CB
TO-24-LET-PST-02 | LETTERKENNY STRABANE PST
TO-24-220 kV A2 @ MAY-02 | MAYNOOTH 220 kV A2
TO-24-220 kV B2 @ MAY-02 | MAYNOOTH 220 kV B2
TO-24-MAY-T2102-07 | MAYNOOTH T2102
TO-24-PB-R2001-09 | POOLBEG R2001
TO-24-PB-R2002-02 | POOLBEG R2002
TO-24-PRO-TB-1-01 | PROSPECT TARBERT
TO-24-110 kV A2 @ RAF-02 | RAFFEEN 110 kV A2
TO-24-110 kV B2 @ RAF-02 | RAFFEEN 110 kV B2
TO-24-TB-T2003-01 | TARBERT T2003
TO-24-TB-T2004-01 | TARBERT T2004
TO-24-TSB-TEN-1-04 | THORNSBERRY TIMAHOE
TO-24-THU-CAP1-04 | THURLES CAP1
TO-24-TRL-CAP2-01 | TRALEE CAP2