## Wks 48 - 49
Report covers outages commencing/returning/spanning the period: 25/11/2024 - 08/12/2024
Outages commencing/returning in Week 48
OUTAGE ID | PLANT |  | Week 48 | [6 empty] | Week 49
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
TO-24-KPG-110SA1-2CB-02 | KILPADDOGE 110SA1-2CB | bar: Week 48 Mo 25
TO-24-BAL-110SA1-03 | BALTRASNA 110SA1 | bar: Week 48 Mo 25
TO-24-BAL-110SA2-03 | BALTRASNA 110SA2 | bar: Week 48 Mo 25
TO-24-BAL-T121-03 | BALTRASNA T121 | bar: Week 48 Mo 25
TO-24-BAL-T121-04 | bar: Week 48 Mo 25
TO-24-110 kV A1 @ BAG-01 | BARNAGEERAGH 110 kV A1 | bar: Week 48 Mo 25
TO-24-110 kV B1 @ BAG-01 | BARNAGEERAGH 110 kV B1 | bar: Week 48 Mo 25
TO-24-BAG-110K1-01 | BARNAGEERAGH 110K1 | bar: Week 48 Mo 25
TO-24-BAG-110SA1-2CB-01 | BARNAGEERAGH 110SA1-2CB | bar: Week 48 Mo 25
TO-24-BAG-110SB1-2CB-01 | BARNAGEERAGH 110SB1-2CB | bar: Week 48 Mo 25
TO-24-DRY-110SA1-04 | DRYBRIDGE 110SA1 | bar: Week 48 Mo 25
TO-24-DRY-110SA2-04 | DRYBRIDGE 110SA2 | bar: Week 48 Mo 25
TO-24-DRY-GOR-1-07 | DRYBRIDGE GORMAN | bar: Week 48 Mo 25
TO-24-DRY-T142-04 | DRYBRIDGE T142 | bar: Week 48 Mo 25
TO-24-OPR-TB-1-01 | OLDPIER TARBERT | bar: Week 48 Mo 25
TO-24-110 kV A1 @ SNU-03 | SNUGBOROUGH 110 kV A1 | bar: Week 48 Mo 25
TO-24-110 kV B1 @ SNU-03 | SNUGBOROUGH 110 kV B1 | bar: Week 48 Mo 25
TO-24-SNU-110K1-02 | SNUGBOROUGH 110K1 | bar: Week 48 Mo 25
TO-24-SNU-110SA1-2CB-03 | SNUGBOROUGH 110SA1-2CB | bar: Week 48 Mo 25
TO-24-SNU-110SB1-2CB-03 | SNUGBOROUGH 110SB1-2CB | bar: Week 48 Mo 25
TO-24-DLT-110SA1-09 | DALTON 110SA1 | bar: Week 48 Mo 25; Week 48 We 27
TO-24-DLT-110SA2-08 | DALTON 110SA2 | bar: Week 48 Mo 25; Week 48 We 27
TO-24-DLT-T142-07 | DALTON T142 | bar: Week 48 Mo 25; Week 48 We 27
TO-24-220 kV A2 @ MAY-03 | MAYNOOTH 220 kV A2 | bar: Week 48 Mo 25; Week 48 We 27
TO-24-220 kV B2 @ MAY-03 | MAYNOOTH 220 kV B2 | bar: Week 48 Mo 25; Week 48 We 27
TO-24-AGL-ENN-1-05 | AGANNYGAL ENNIS | bar: Week 48 Mo 25; Week 48 We 27 to Week 48 Fr 29
TO-24-CL-T102-04 | CLIFF T102 | bar: Week 48 Mo 25; Week 48 We 27 to Week 48 Fr 29
TO-24-220 kV A1 @ GI GIS-06 | GREAT ISLAND GIS 220 kV A1 | bar: Week 48 Mo 25; Week 48 We 27 to Week 48 Fr 29
TO-24-220 kV B1 @ GI GIS-04 | GREAT ISLAND GIS 220 kV B1 | bar: Week 48 Mo 25; Week 48 We 27 to Week 48 Fr 29
TO-24-GI GIS-220K1-06 | GREAT ISLAND GIS 220K1 | bar: Week 48 Mo 25; Week 48 We 27 to Week 48 Fr 29
TO-24-GI GIS-220SA1-2CB-07 | GREAT ISLAND GIS 220SA1-2CB | bar: Week 48 Mo 25; Week 48 We 27 to Week 48 Fr 29
TO-24-GI GIS-220SB1-2CB-05 | GREAT ISLAND GIS 220SB1-2CB | bar: Week 48 Mo 25; Week 48 We 27 to Week 48 Fr 29
TO-24-LIS-LOU-1-02 | LISDRUM LOUTH | bar: Week 48 Mo 25; Week 48 We 27 to Week 48 Fr 29
TO-24-DEY-PLS-1-04 | DERRYCARNEY PORTLAOISE | bar: Week 48 Mo 25; Week 48 We 27 to Week 49 Tu 3
TO-24-KTL-MON-1-01 | KILTEEL MONREAD | bar: Week 48 Mo 25; Week 48 We 27 to Week 49 Tu 3
TO-24-110 kV A2 @ PLS-01 | PORTLAOISE 110 kV A2 | bar: Week 48 Mo 25; Week 48 We 27 to Week 49 Tu 3
TO-24-110 kV B2 @ PLS-01 | PORTLAOISE 110 kV B2 | bar: Week 48 Mo 25; Week 48 We 27 to Week 49 Tu 3
TO-24-CAH-TIP-1-01 | CAHIR TIPPERARY | bar: Su 24 to Week 48 Mo 25
TO-24-CRA-WEX-1-01 | CRANE WEXFORD | bar: Su 24 to Week 48 Mo 25
TO-24-MLN-T124-01 | MULLAGHARLIN T124
TO-24-FIN-220SB1-2CB-05 | FINGLAS 220SB1-2CB | bar: Week 48 We 27
TO-24-WOO-220K1-2-03 | WOODLAND 220K1-2 | bar: Week 48 We 27
TO-24-DRM-LET-1-04 | DRUMKEEN LETTERKENNY | bar: Week 48 We 27 to Week 48 Th 28
TO-24-BDN-110SA1-02 | BALLYDINE 110SA1 | bar: Week 48 We 27 to Week 48 Fr 29
TO-24-BDN-110SA2-01 | BALLYDINE 110SA2 | bar: Week 48 We 27 to Week 48 Fr 29
TO-24-BDN-DOO-1-02 | BALLYDINE DOON | bar: Week 48 We 27 to Week 48 Fr 29
TO-24-BDN-MRK3-02 | BALLYDINE MRK3 | bar: Week 48 We 27 to Week 48 Fr 29
TO-24-BAN-RAF-1-03 | BANDON RAFFEEN | bar: Week 48 We 27 to Week 48 Fr 29
TO-24-KPG-TB-1-11 | KILPADDOGE TARBERT 1 | bar: Week 48 We 27 to Week 48 Fr 29
TO-24-110 kV A2 @ SNU-05 | SNUGBOROUGH 110 kV A2 | bar: Week 48 We 27 to Week 49 Fr 6
TO-24-110 kV B2 @ SNU-06 | SNUGBOROUGH 110 kV B2 | bar: Week 48 We 27 to Week 49 Fr 6
TO-24-SNU-110K1-06 | SNUGBOROUGH 110K1 | bar: Week 48 We 27 to Week 49 Fr 6
TO-24-SNU-110SA1-2CB-10 | SNUGBOROUGH 110SA1-2CB | bar: Week 48 We 27 to Week 49 Fr 6
TO-24-SNU-110SB1-2CB-11 | SNUGBOROUGH 110SB1-2CB | bar: Week 48 We 27 to Week 49 Fr 6
TO-24-SNU-T104-01 | SNUGBOROUGH T104 | bar: Week 48 We 27 to Week 49 Fr 6
TO-24-LOU-T2101-02 | LOUTH T2101 | bar: Week 48 We 27 to Week 49 Mo 9
TO-24-CSH-DLT-1-01 | CASHLA DALTON | bar: Su 24 to Week 48 Mo 25; Week 48 We 27
TO-24-KPG-110SA2-4CB-02 | KILPADDOGE 110SA2-4CB | bar: Week 48 Th 28
TO-24-WOO-T4202-03 | WOODLAND T4202 | bar: Week 48 Th 28 to Week 49 Mo 9
TO-24-CDU-RYB GIS-1-04 | CORDUFF RYEBROOK GIS | bar: Week 48 Fr 29
TO-24-DRU-110SA1-01 | DRUMLINE 110SA1 | bar: Week 48 Fr 29
Report covers outages commencing/returning/spanning the period: 25/11/2024 - 08/12/2024
Outages commencing/returning in Week 48
OUTAGE ID | PLANT | Week 48 Mo 25: Week 48; Week 49 Mo 2: Week 49
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
TO-24-DRU-110SA2-01 | DRUMLINE 110SA2 | bar: Week 48 Fr 29
TO-24-DRU-ENN-1-03 | DRUMLINE ENNIS | bar: Week 48 Fr 29
TO-24-KPG-110SB2-4CB-01 | KILPADDOGE 110SB2-4CB | bar: Week 48 Fr 29
TO-24-110 kV B1 @ RYB GIS-01 | RYEBROOK GIS 110 kV B1 | bar: Week 48 Fr 29
TO-24-110 kV B2 @ RYB GIS-01 | RYEBROOK GIS 110 kV B2 | bar: Week 48 Fr 29
TO-24-110 kV B3 @ RYB GIS-01 | RYEBROOK GIS 110 kV B3 | bar: Week 48 Fr 29
TO-24-RYB GIS-110K3-03 | RYEBROOK GIS 110K3 | bar: Week 48 Fr 29
TO-24-RYB GIS-110SB1-2CB-01 | RYEBROOK GIS 110SB1-2CB | bar: Week 48 Fr 29
TO-24-RYB GIS-110SB1-3CB-02 | RYEBROOK GIS 110SB1-3CB | bar: Week 48 Fr 29
TO-24-RYB GIS-110SB2-4CB-02 | RYEBROOK GIS 110SB2-4CB | bar: Week 48 Fr 29
TO-24-BLU-MUL-1-02 | BLUNDELSTOWN MULLINGAR | bar: Su 24 to Week 48 Fr 29
TO-24-CKN-GRO-1-04 | CLONKEEN GARROW | bar: Su 24 to Week 48 Fr 29
TO-24-DRU-T141-01 | DRUMLINE T141 | bar: Su 24 to Week 48 Fr 29
TO-24-GRI,T-MAY-1-04 | GRIFFINRATH tee MAYNOOTH | bar: Su 24 to Week 48 Fr 29
TO-24-220 kV A2 @ KLN-05 | KILLONAN 220 kV A2 | bar: Su 24 to Week 48 Fr 29
TO-24-220 kV B2 @ KLN-04 | KILLONAN 220 kV B2 | bar: Su 24 to Week 48 Fr 29
TO-24-KLN-SH-1-03 | KILLONAN SHANNONBRIDGE | bar: Su 24 to Week 48 Fr 29
TO-24-110 kV A1 @ KRA-03 | KNOCKRAHA 110 kV A1 | bar: Su 24 to Week 48 Fr 29
TO-24-110 kV B1 @ KRA-03 | KNOCKRAHA 110 kV B1 | bar: Su 24 to Week 48 Fr 29
TO-24-220 kV A1 @ KRA-03 | KNOCKRAHA 220 kV A1 | bar: Su 24 to Week 48 Fr 29
TO-24-220 kV B1 @ KRA-03 | KNOCKRAHA 220 kV B1 | bar: Su 24 to Week 48 Fr 29
TO-24-KRA-220K1-04 | KNOCKRAHA 220K1 | bar: Su 24 to Week 48 Fr 29
TO-24-KRA-220SA1-2CB-04 | KNOCKRAHA 220SA1-2CB | bar: Su 24 to Week 48 Fr 29
TO-24-KRA-220SB1-2CB-04 | KNOCKRAHA 220SB1-2CB | bar: Su 24 to Week 48 Fr 29
TO-24-KRA-T2101-02 | KNOCKRAHA T2101 | bar: Su 24 to Week 48 Fr 29
TO-24-110 kV A2 @ MAY-05 | MAYNOOTH 110 kV A2 | bar: Su 24 to Week 48 Fr 29
TO-24-110 kV A3 @ MAY-06 | MAYNOOTH 110 kV A3 | bar: Su 24 to Week 48 Fr 29
TO-24-110 kV B2 @ MAY-05 | MAYNOOTH 110 kV B2 | bar: Su 24 to Week 48 Fr 29
TO-24-110 kV B3 @ MAY-06 | MAYNOOTH 110 kV B3 | bar: Su 24 to Week 48 Fr 29
TO-24-MOY-TAW-1-01 | MOY TAWNAGHMORE 1 | bar: Su 24 to Week 48 Fr 29
TO-24-PB-T2007/8-04 | POOLBEG T2007/8 | bar: Su 24 to Week 48 Fr 29
TO-24-110 kV A2 @ RAF-02 | RAFFEEN 110 kV A2 | bar: Su 24 to Week 48 Fr 29
TO-24-110 kV B2 @ RAF-02 | RAFFEEN 110 kV B2 | bar: Su 24 to Week 48 Fr 29
TO-24-RYB GIS-T104-03 | RYEBROOK GIS T104 | bar: Su 24 to Week 48 Fr 29
Outages commencing/returning in Week 49
OUTAGE ID | PLANT | Week 48 Mo 25: Week 48; Week 49 Mo 2: Week 49
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
TO-24-BRT-220K2-01 | BRACETOWN 220K2 | bar: Week 49 Mo 2
TO-24-KPG-110SA1-3CB-01 | KILPADDOGE 110SA1-3CB | bar: Week 49 Mo 2
TO-24-GAR-T131-01 | GARBALLAGH T131 | bar: Week 49 Mo 2 to Week 49 We 4
TO-24-220 kV A1 @ AD-04 | AGHADA 220 kV A1 | bar: Week 49 Mo 2 to Week 49 Fr 6
TO-24-220 kV A2 @ AD-07 | AGHADA 220 kV A2 | bar: Week 49 Mo 2 to Week 49 Fr 6
TO-24-AD-220K1-05 | AGHADA 220K1 | bar: Week 49 Mo 2 to Week 49 Fr 6
TO-24-AD-SA1-2CB-04 | AGHADA 220SA1-2CB | bar: Week 49 Mo 2 to Week 49 Fr 6
TO-24-220 kV A2 @ CSH-02 | CASHLA 220 kV A2 | bar: Week 49 Mo 2 to Week 49 Fr 6
TO-24-220 kV A4 @ CSH-03 | CASHLA 220 kV A4 | bar: Week 49 Mo 2 to Week 49 Fr 6
TO-24-220 kV B2 @ CSH-04 | CASHLA 220 kV B2 | bar: Week 49 Mo 2 to Week 49 Fr 6
TO-24-220 kV B4 @ CSH-02 | CASHLA 220 kV B4 | bar: Week 49 Mo 2 to Week 49 Fr 6
TO-24-CSH-220K2-4-01 | CASHLA 220K2-4 | bar: Week 49 Mo 2 to Week 49 Fr 6
TO-24-LLA-TIV-1-01 | LENALEA TIEVEBRACK | bar: Week 49 Mo 2 to Week 49 Fr 6
TO-24-110 kV A2 @ ARV-02 | ARVA 110 kV A2 | bar: Week 49 Mo 2 to Week 49 Mo 9
TO-24-110 kV B2 @ ARV-02 | ARVA 110 kV B2 | bar: Week 49 Mo 2 to Week 49 Mo 9
TO-24-ARV-SKL-2-02 | ARVA SHANKILL 2 | bar: Week 49 Mo 2 to Week 49 Mo 9
TO-24-CD-KBY-1-03 | CARRIGADROHID KILBARRY | bar: Week 49 Mo 2 to Week 49 Mo 9
TO-24-110 kV A1 @ CLG-05 | CLOGHRAN 110 kV A1 | bar: Week 49 Mo 2 to Week 49 Mo 9
TO-24-110 kV B1 @ CLG-05 | CLOGHRAN 110 kV B1 | bar: Week 49 Mo 2 to Week 49 Mo 9
TO-24-CLG-110K1-03 | CLOGHRAN 110K1 | bar: Week 49 Mo 2 to Week 49 Mo 9
TO-24-CLG-110SA1-2CB-06 | CLOGHRAN 110SA1-2CB | bar: Week 49 Mo 2 to Week 49 Mo 9
TO-24-CLG-110SB1-2CB-06 | CLOGHRAN 110SB1-2CB | bar: Week 49 Mo 2 to Week 49 Mo 9
Report covers outages commencing/returning/spanning the period: 25/11/2024 - 08/12/2024
Outages commencing/returning in Week 49
OUTAGE ID | PLANT | Week 48 Mo 25: Week 48; Week 49 Mo 2: Week 49
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
TO-24-110 kV A1 @ CUL-03 | CULLENAGH 110 kV A1 | bar: Week 49 Mo 2 to Week 49 Mo 9
TO-24-110 kV B1 @ CUL-04 | CULLENAGH 110 kV B1 | bar: Week 49 Mo 2 to Week 49 Mo 9
TO-24-CUL-WAT-1-03 | CULLENAGH WATERFORD | bar: Week 49 Mo 2 to Week 49 Mo 9
TO-24-MOY-TAW-2-04 | MOY TAWNAGHMORE 2 | bar: Week 49 Mo 2 to Week 49 Mo 9
TO-24-AA GIS-110SA1-2CB-02 | ARDNACRUSHA GIS 110SA1-2CB | bar: Week 49 Tu 3
TO-24-110 kV A1 @ CSH-05 | CASHLA 110 kV A1 | bar: Week 49 Tu 3 to Week 49 Th 5
TO-24-CSH-GAL GIS-1-01 | CASHLA GALWAY GIS 1 | bar: Week 49 Tu 3 to Week 49 Th 5
TO-24-MAY-RNW-1-01 | MAYNOOTH RINAWADE | bar: Week 49 Tu 3 to Week 49 Th 5
TO-24-110 kV A2 @ FIN GIS-04 | FINGLAS GIS 110 kV A2 | bar: Week 49 Tu 3 to Week 49 Fr 6
TO-24-110 kV B2 @ FIN GIS-04 | FINGLAS GIS 110 kV B2 | bar: Week 49 Tu 3 to Week 49 Fr 6
TO-24-FIN GIS-110K2-02 | FINGLAS GIS 110K2 | bar: Week 49 Tu 3 to Week 49 Fr 6
TO-24-FIN GIS-110SA1-2CB-05 | FINGLAS GIS 110SA1-2CB | bar: Week 49 Tu 3 to Week 49 Fr 6
TO-24-FIN GIS-110SA2-4CB-06 | FINGLAS GIS 110SA2-4CB | bar: Week 49 Tu 3 to Week 49 Fr 6
TO-24-FIN GIS-110SB1-2CB-05 | FINGLAS GIS 110SB1-2CB | bar: Week 49 Tu 3 to Week 49 Fr 6
TO-24-FIN GIS-110SB2-4CB-07 | FINGLAS GIS 110SB2-4CB | bar: Week 49 Tu 3 to Week 49 Fr 6
TO-24-AUN-CBT-3-01 | AUNGIERSTOWN CASTLEBAGOT 3 | bar: Su 24 to Week 49 Tu 3
TO-24-AA GIS-110SA1-3CB-02 | ARDNACRUSHA GIS 110SA1-3CB | bar: Week 49 We 4
TO-24-AUN-CBT-1-01 | AUNGIERSTOWN CASTLEBAGOT 1 | bar: Week 49 We 4 to Week 49 Su 8
TO-24-AA GIS-110SB1-2CB-02 | ARDNACRUSHA GIS 110SB1-2CB | bar: Week 49 Th 5
TO-24-TSB-TEN-1-04 | THORNSBERRY TIMAHOE | bar: Su 24 to Week 49 Th 5
TO-24-AA GIS-110SB1-3CB-02 | ARDNACRUSHA GIS 110SB1-3CB | bar: Week 49 Fr 6
TO-24-CLA-MAC-2-01 | CLASHAVOON MACROOM 2 | bar: Su 24 to Week 49 Fr 6
Outages spanning Weeks 48-49
OUTAGE ID | PLANT | Week 48 Mo 25: Week 48; Week 49 Mo 2: Week 49
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
TO-24-AA GIS-SNG-1-05 | ARDNACRUSHA GIS SINGLAND
TO-24-BAL-DRY-1-05 | BALTRASNA DRYBRIDGE
TO-24-BRY-RAF-2-01 | BARNAHELY RAFFEEN 2
TO-24-CAH-CAP1/3-01 | CAHIR CAP1/3
TO-24-CSH-CAP2-01 | CASHLA CAP2
TO-24-DND-T121-01 | DARNDALE T121
TO-24-FIN-110K1-2-01 | FINGLAS 110K1-2
TO-24-GAL-GAL GIS-2-02 | GALWAY GALWAY GIS 2
TO-24-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-24-GI-T141-01 | GREAT ISLAND T141
TO-24-INC-220K1-2-02 | INCHICORE 220K1-2
TO-24-INC-MAY-2-03 | INCHICORE MAYNOOTH 2
TO-24-220 kV A4 @ KRA-01 | KNOCKRAHA 220 kV A4
TO-24-220 kV B4 @ KRA-01 | KNOCKRAHA 220 kV B4
TO-24-KRA-220K4-04 | KNOCKRAHA 220K4
TO-24-KRA-220SA2-4CB-04 | KNOCKRAHA 220SA2-4CB
TO-24-KRA-220SB2-4CB-04 | KNOCKRAHA 220SB2-4CB
TO-24-LET-PST-02 | LETTERKENNY STRABANE PST
TO-24-220 kV A2 @ MAY-02 | MAYNOOTH 220 kV A2
TO-24-220 kV B2 @ MAY-02 | MAYNOOTH 220 kV B2
TO-24-MAY-T2102-07 | MAYNOOTH T2102
TO-24-PB-R2001-09 | POOLBEG R2001
TO-24-PRO-TB-1-01 | PROSPECT TARBERT
TO-24-220 kV A2 @ TB-02 | TARBERT 220 kV A2
TO-24-220 kV B2 @ TB-02 | TARBERT 220 kV B2
TO-24-TB-T2003-01 | TARBERT T2003
TO-24-TB-T2004-01 | TARBERT T2004
TO-24-THU-CAP1-04 | THURLES CAP1
TO-24-TRL-CAP2-01 | TRALEE CAP2