## Wks 50 - 51
Report covers outages commencing/returning/spanning the period: 09/12/2024 - 22/12/2024
Outages commencing/returning in Week 50
OUTAGE ID | PLANT |  | Week 50 | [6 empty] | Week 51
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
TO-24-ROP-T131-01 | ROSSPILE T131 | bar: Week 50 Mo 9
TO-24-FIN-FIN GIS-1-01 | FINGLAS FINGLAS GIS 1 | bar: Week 50 Mo 9 to Week 50 Tu 10
TO-24-110 kV A2 @ FIN GIS-05 | FINGLAS GIS 110 kV A2 | bar: Week 50 Mo 9 to Week 50 Tu 10
TO-24-110 kV A4 @ FIN GIS-02 | FINGLAS GIS 110 kV A4 | bar: Week 50 Mo 9 to Week 50 Tu 10
TO-24-110 kV B2 @ FIN GIS-05 | FINGLAS GIS 110 kV B2 | bar: Week 50 Mo 9 to Week 50 Tu 10
TO-24-110 kV B4 @ FIN GIS-03 | FINGLAS GIS 110 kV B4 | bar: Week 50 Mo 9 to Week 50 Tu 10
TO-24-FIN GIS-110K2-05 | FINGLAS GIS 110K2 | bar: Week 50 Mo 9 to Week 50 Tu 10
TO-24-FIN GIS-110SA1-2CB-06 | FINGLAS GIS 110SA1-2CB | bar: Week 50 Mo 9 to Week 50 Tu 10
TO-24-FIN GIS-110SA2-4CB-07 | FINGLAS GIS 110SA2-4CB | bar: Week 50 Mo 9 to Week 50 Tu 10
TO-24-FIN GIS-110SA4-6CB-02 | FINGLAS GIS 110SA4-6CB | bar: Week 50 Mo 9 to Week 50 Tu 10
TO-24-FIN GIS-110SB1-2CB-06 | FINGLAS GIS 110SB1-2CB | bar: Week 50 Mo 9 to Week 50 Tu 10
TO-24-FIN GIS-110SB2-4CB-08 | FINGLAS GIS 110SB2-4CB | bar: Week 50 Mo 9 to Week 50 Tu 10
TO-24-FIN GIS-110SB4-6CB-04 | FINGLAS GIS 110SB4-6CB | bar: Week 50 Mo 9 to Week 50 Tu 10
TO-24-FIN-T2103-03 | FINGLAS T2103 | bar: Week 50 Mo 9 to Week 50 Tu 10
TO-24-CBT-CKG-2-05 | CASTLEBAGOT CORKAGH 2 | bar: Week 50 Mo 9 to Week 50 Fr 13
TO-24-CBR-DLT-1-04 | CASTLEBAR DALTON | bar: Week 50 Mo 9 to Week 50 Fr 13
TO-24-110 kV A1 @ CKG-03 | CORKAGH 110 kV A1 | bar: Week 50 Mo 9 to Week 50 Fr 13
TO-24-110 kV B1 @ CKG-04 | CORKAGH 110 kV B1 | bar: Week 50 Mo 9 to Week 50 Fr 13
TO-24-CKG-110SA1-2CB-06 | CORKAGH 110SA1-2CB | bar: Week 50 Mo 9 to Week 50 Fr 13
TO-24-CKG-110SA1-3CB-06 | CORKAGH 110SA1-3CB | bar: Week 50 Mo 9 to Week 50 Fr 13
TO-24-CKG-110SB1-2CB-06 | CORKAGH 110SB1-2CB | bar: Week 50 Mo 9 to Week 50 Fr 13
TO-24-CKG-110SB1-3CB-06 | CORKAGH 110SB1-3CB | bar: Week 50 Mo 9 to Week 50 Fr 13
TO-24-110 kV A2/A4 @ CDU-01 | CORDUFF 110 kV A2/A4 | bar: Week 50 Mo 9 to Week 51 Mo 16
TO-24-110 kV A1 @ CUL-03 | CULLENAGH 110 kV A1 | bar: Week 50 Mo 9 to Week 51 Fr 20
TO-24-110 kV B1 @ CUL-04 | CULLENAGH 110 kV B1 | bar: Week 50 Mo 9 to Week 51 Fr 20
TO-24-CUL-WAT-1-03 | CULLENAGH WATERFORD | bar: Week 50 Mo 9 to Week 51 Fr 20
TO-24-GOR-LOU-1-05 | GORMAN LOUTH | bar: Week 50 Mo 9 to Week 51 Fr 20
TO-24-220 kV A2 @ CBT-02 | CASTLEBAGOT 220 kV A2 | bar: Week 50 Tu 10 to Week 50 We 11
TO-24-220 kV B2 @ CBT-02 | CASTLEBAGOT 220 kV B2 | bar: Week 50 Tu 10 to Week 50 We 11
TO-24-CBT-220K2-02 | CASTLEBAGOT 220K2 | bar: Week 50 Tu 10 to Week 50 We 11
TO-24-CBT-220SA1-2CB-02 | CASTLEBAGOT 220SA1-2CB | bar: Week 50 Tu 10 to Week 50 We 11
TO-24-CBT-220SB1-2CB-02 | CASTLEBAGOT 220SB1-2CB | bar: Week 50 Tu 10 to Week 50 We 11
TO-24-ATY-CLW-1-09 | ATHY CARLOW | bar: Su 8 to Week 50 Tu 10
TO-24-MCE-SNU-1-04 | MACETOWN SNUGBOROUGH | bar: Week 50 We 11 to Week 51 Tu 17
TO-24-110 kV A2 @ SNU-06 | SNUGBOROUGH 110 kV A2 | bar: Week 50 We 11 to Week 51 Tu 17
TO-24-110 kV B2 @ SNU-07 | SNUGBOROUGH 110 kV B2 | bar: Week 50 We 11 to Week 51 Tu 17
TO-24-SNU-110K2-08 | SNUGBOROUGH 110K2 | bar: Week 50 We 11 to Week 51 Tu 17
TO-24-SNU-110SA1-2CB-11 | SNUGBOROUGH 110SA1-2CB | bar: Week 50 We 11 to Week 51 Tu 17
TO-24-SNU-110SB1-2CB-12 | SNUGBOROUGH 110SB1-2CB | bar: Week 50 We 11 to Week 51 Tu 17
TO-24-110 kV A1 @ FIN GIS-02 | FINGLAS GIS 110 kV A1 | bar: Week 50 We 11 to Week 51 Fr 20
TO-24-110 kV A3 @ FIN GIS-02 | FINGLAS GIS 110 kV A3 | bar: Week 50 We 11 to Week 51 Fr 20
TO-24-FIN GIS-110K1-04 | FINGLAS GIS 110K1 | bar: Week 50 We 11 to Week 51 Fr 20
TO-24-FIN GIS-110SA1-2CB-07 | FINGLAS GIS 110SA1-2CB | bar: Week 50 We 11 to Week 51 Fr 20
TO-24-FIN GIS-110SA1-3CB-01 | FINGLAS GIS 110SA1-3CB | bar: Week 50 We 11 to Week 51 Fr 20
TO-24-FIN GIS-110SA3-5CB-04 | FINGLAS GIS 110SA3-5CB | bar: Week 50 We 11 to Week 51 Fr 20
TO-24-CUS-PLS-1-03 | CUSHALING PORTLAOISE | bar: Week 50 We 11 to Week 51 Mo 23
TO-24-110 kV A2 @ PLS-02 | PORTLAOISE 110 kV A2 | bar: Week 50 We 11 to Week 51 Mo 23
TO-24-110 kV B2 @ PLS-02 | PORTLAOISE 110 kV B2 | bar: Week 50 We 11 to Week 51 Mo 23
TO-24-INC-MAY-2-03 | INCHICORE MAYNOOTH 2 | bar: Su 8 to Week 50 We 11
TO-24-CRU-T221-03 | CRUISERATH T221 | bar: Week 50 Th 12
TO-24-MAY-TH-1-03 | MAYNOOTH TURLOUGH HILL | bar: Week 50 Th 12 to Week 51 Fr 20
TO-24-NW-PB-1-01 | NORTH WALL POOLBEG | bar: Week 50 Th 12 to Week 51 Fr 20
TO-24-110 kV A2 @ ARV-02 | ARVA 110 kV A2 | bar: Su 8 to Week 50 Fr 13
TO-24-110 kV B2 @ ARV-02 | ARVA 110 kV B2 | bar: Su 8 to Week 50 Fr 13
TO-24-ARV-SKL-2-02 | ARVA SHANKILL 2 | bar: Su 8 to Week 50 Fr 13
TO-24-CD-KBY-1-03 | CARRIGADROHID KILBARRY | bar: Su 8 to Week 50 Fr 13
TO-24-110 kV A1 @ CLG-05 | CLOGHRAN 110 kV A1 | bar: Su 8 to Week 50 Fr 13
TO-24-110 kV B1 @ CLG-05 | CLOGHRAN 110 kV B1 | bar: Su 8 to Week 50 Fr 13
TO-24-CLG-110K1-03 | CLOGHRAN 110K1 | bar: Su 8 to Week 50 Fr 13
TO-24-CLG-110SA1-2CB-06 | CLOGHRAN 110SA1-2CB | bar: Su 8 to Week 50 Fr 13
TO-24-CLG-110SB1-2CB-06 | CLOGHRAN 110SB1-2CB | bar: Su 8 to Week 50 Fr 13
Report covers outages commencing/returning/spanning the period: 09/12/2024 - 22/12/2024
Outages commencing/returning in Week 51
OUTAGE ID | PLANT | Week 50 Mo 9: Week 50; Week 51 Mo 16: Week 51
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
TO-24-CDU-T2104-04 | CORDUFF T2104 | bar: Week 51 Mo 16
TO-24-AA GIS-CAP1-04 | ARDNACRUSHA GIS CAP1 | bar: Week 51 Mo 16 to Week 51 Tu 17
TO-24-220 kV A1 @ CSH-02 | CASHLA 220 kV A1 | bar: Week 51 Mo 16 to Week 51 Fr 20
TO-24-220 kV A2 @ CSH-03 | CASHLA 220 kV A2 | bar: Week 51 Mo 16 to Week 51 Fr 20
TO-24-220 kV B1 @ CSH-02 | CASHLA 220 kV B1 | bar: Week 51 Mo 16 to Week 51 Fr 20
TO-24-220 kV B2 @ CSH-05 | CASHLA 220 kV B2 | bar: Week 51 Mo 16 to Week 51 Fr 20
TO-24-CSH-220K1-2-01 | CASHLA 220K1-2 | bar: Week 51 Mo 16 to Week 51 Fr 20
TO-24-CBT-CKG-1-02 | CASTLEBAGOT CORKAGH 1 | bar: Week 51 Mo 16 to Week 51 Fr 20
TO-24-110 kV A3 @ CKG-02 | CORKAGH 110 kV A3 | bar: Week 51 Mo 16 to Week 51 Fr 20
TO-24-110 kV B3 @ CKG-02 | CORKAGH 110 kV B3 | bar: Week 51 Mo 16 to Week 51 Fr 20
TO-24-CKG-110K3-03 | CORKAGH 110K3 | bar: Week 51 Mo 16 to Week 51 Fr 20
TO-24-CKG-110SA1-3CB-05 | CORKAGH 110SA1-3CB | bar: Week 51 Mo 16 to Week 51 Fr 20
TO-24-CKG-110SB1-3CB-05 | CORKAGH 110SB1-3CB | bar: Week 51 Mo 16 to Week 51 Fr 20
TO-24-CRA-LWD-1-10 | CRANE LODGEWOOD | bar: Week 51 Mo 16 to Week 51 Fr 20
TO-24-KPG-T2102-02 | KILPADDOGE T2102 | bar: Week 51 Mo 16 to Week 51 Fr 20
TO-24-DMY-MAC-1-05 | DUNMANWAY MACROOM | bar: Week 51 Tu 17
TO-24-AUN-CBT-1-01 | AUNGIERSTOWN CASTLEBAGOT 1 | bar: Week 51 Tu 17 to Week 51 Th 19
TO-24-DND-110K1-04 | DARNDALE 110K1 | bar: Week 51 Tu 17 to Week 51 Fr 20
TO-24-DND-110K2-01 | DARNDALE 110K2 | bar: Week 51 Tu 17 to Week 51 Fr 20
TO-24-DND-110SA1-2CB-04 | DARNDALE 110SA1-2CB | bar: Week 51 Tu 17 to Week 51 Fr 20
TO-24-FLA-SLI-1-05 | FLAGFORD SLIGO | bar: Week 51 Th 19
TO-24-220 kV A4 @ KRA-01 | KNOCKRAHA 220 kV A4 | bar: Su 8 to Week 51 Fr 20
TO-24-220 kV B4 @ KRA-01 | KNOCKRAHA 220 kV B4 | bar: Su 8 to Week 51 Fr 20
TO-24-KRA-220K4-04 | KNOCKRAHA 220K4 | bar: Su 8 to Week 51 Fr 20
TO-24-KRA-220SA2-4CB-04 | KNOCKRAHA 220SA2-4CB | bar: Su 8 to Week 51 Fr 20
TO-24-KRA-220SB2-4CB-04 | KNOCKRAHA 220SB2-4CB | bar: Su 8 to Week 51 Fr 20
Outages spanning Weeks 50-51
OUTAGE ID | PLANT | Week 50 Mo 9: Week 50; Week 51 Mo 16: Week 51
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
TO-24-AA GIS-SNG-1-05 | ARDNACRUSHA GIS SINGLAND
TO-24-BAL-DRY-1-05 | BALTRASNA DRYBRIDGE
TO-24-BRY-RAF-2-01 | BARNAHELY RAFFEEN 2
TO-24-CAH-CAP1/3-01 | CAHIR CAP1/3
TO-24-CSH-CAP2-01 | CASHLA CAP2
TO-24-CBR-SVC-07 | CASTLEBAR SVC
TO-24-DND-T121-01 | DARNDALE T121
TO-24-FIN-110K1-2-01 | FINGLAS 110K1-2
TO-24-GAL-GAL GIS-2-02 | GALWAY GALWAY GIS 2
TO-24-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-24-GI-T141-01 | GREAT ISLAND T141
TO-24-INC-220K1-2-02 | INCHICORE 220K1-2
TO-24-LET-PST-02 | LETTERKENNY STRABANE PST
TO-24-LOU-CAP1-04 | LOUTH CAP1
TO-24-MAY-T2102-07 | MAYNOOTH T2102
TO-24-PB-R2001-09 | POOLBEG R2001
TO-24-PRO-TB-1-01 | PROSPECT TARBERT
TO-24-TB-T2003-01 | TARBERT T2003
TO-24-TB-T2004-01 | TARBERT T2004
TO-24-THU-CAP1-04 | THURLES CAP1
TO-24-THU-STATCOM-03 | THURLES STATCOM
TO-24-TRL-CAP2-01 | TRALEE CAP2

## Wk 52
Report covers outages commencing/returning/spanning the period: 23/12/2024 - 29/12/2024
Outages spanning Week 52
OUTAGE ID | PLANT |  | Week 52
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 16
TO-24-AA GIS-SNG-1-05 | ARDNACRUSHA GIS SINGLAND
TO-24-BAL-DRY-1-05 | BALTRASNA DRYBRIDGE
TO-24-BRY-RAF-2-01 | BARNAHELY RAFFEEN 2
TO-24-CAH-CAP1/3-01 | CAHIR CAP1/3
TO-24-CSH-CAP2-01 | CASHLA CAP2
TO-24-CBR-SVC-07 | CASTLEBAR SVC
TO-24-CUS-PLS-1-03 | CUSHALING PORTLAOISE
TO-24-DND-T121-01 | DARNDALE T121
TO-24-FIN-110K1-2-01 | FINGLAS 110K1-2
TO-24-GAL-GAL GIS-2-02 | GALWAY GALWAY GIS 2
TO-24-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-24-GI-T141-01 | GREAT ISLAND T141
TO-24-INC-220K1-2-02 | INCHICORE 220K1-2
TO-24-LET-PST-02 | LETTERKENNY STRABANE PST
TO-24-LOU-CAP1-04 | LOUTH CAP1
TO-24-MAY-T2102-07 | MAYNOOTH T2102
TO-24-PB-R2001-09 | POOLBEG R2001
TO-24-110 kV A2 @ PLS-02 | PORTLAOISE 110 kV A2
TO-24-110 kV B2 @ PLS-02 | PORTLAOISE 110 kV B2
TO-24-PRO-TB-1-01 | PROSPECT TARBERT
TO-24-TB-T2003-01 | TARBERT T2003
TO-24-TB-T2004-01 | TARBERT T2004
TO-24-THU-CAP1-04 | THURLES CAP1
TO-24-THU-STATCOM-03 | THURLES STATCOM
TO-24-TRL-CAP2-01 | TRALEE CAP2