## Wks 14 - 15
Report covers outages commencing/returning/spanning the period: 31/03/2025 - 13/04/2025
Outages commencing/returning in Week 14
OUTAGE ID | PLANT |  | Week 14 | [6 empty] | Week 15
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
TO-25-220 kV A1 @ LOU-08 | LOUTH 220 kV A1
TO-25-LOU-AT2-03 | LOUTH AT2
TO-25-LOU-TAN-2-03 | LOUTH TANDRAGEE 2
TO-25-BYH-STATCOM-01 | BALLYNAHULLA STATCOM
TO-25-110 kV A1 @ BLC-01 | BELCAMP 110 kV A1
TO-25-110 kV B1 @ BLC-01 | BELCAMP 110 kV B1
TO-25-BLC-110K1-02 | BELCAMP 110K1
TO-25-BLC-110SA1-3CB-03 | BELCAMP 110SA1-3CB
TO-25-BLC-110SB1-3CB-03 | BELCAMP 110SB1-3CB
TO-25-BLC-DND-1-02 | BELCAMP DARNDALE 1
TO-25-110 kV A1 @ CSH-07 | CASHLA 110 kV A1
TO-25-110 kV B1 @ CSH-01 | CASHLA 110 kV B1
TO-25-CSH-GAL GIS-1-02 | CASHLA GALWAY GIS 1
TO-25-CLO-CRD-1-01 | CLOGHER CROAGHONAGH
TO-25-CRD-T131-01 | CROAGHONAGH T131
TO-25-110 kV A1 @ DND-04 | DARNDALE 110 kV A1
TO-25-110 kV B1 @ DND-02 | DARNDALE 110 kV B1
TO-25-DND-110K1-04 | DARNDALE 110K1
TO-25-DND-110SA1-2CB-06 | DARNDALE 110SA1-2CB
TO-25-DND-110SB1-2CB-05 | DARNDALE 110SB1-2CB
TO-25-WOH-T122-01 | WOODHOUSE T122
TO-25-AD-T2014-01 | AGHADA T2014 | bar: Week 14 Sa 5 to Week 15 Tu 8
TO-25-220 kV A2 @ FIN-07 | FINGLAS 220 kV A2 | bar: Week 14 Sa 5 to Week 15 Fr 11
TO-25-FIN-220K2-09 | FINGLAS 220K2 | bar: Week 14 Sa 5 to Week 15 Fr 11
TO-25-FIN-220SA1-2CB-12 | FINGLAS 220SA1-2CB | bar: Week 14 Sa 5 to Week 15 Fr 11
TO-25-110 kV A3 @ FIN GIS-01 | FINGLAS GIS 110 kV A3 | bar: Week 14 Sa 5 to Week 15 Fr 11
TO-25-110 kV B3 @ FIN GIS-01 | FINGLAS GIS 110 kV B3 | bar: Week 14 Sa 5 to Week 15 Fr 11
TO-25-FIN GIS-110SA1-3CB-02 | FINGLAS GIS 110SA1-3CB | bar: Week 14 Sa 5 to Week 15 Fr 11
TO-25-FIN GIS-110SA3-5CB-04 | FINGLAS GIS 110SA3-5CB | bar: Week 14 Sa 5 to Week 15 Fr 11
TO-25-FIN GIS-110SB1-3CB-02 | FINGLAS GIS 110SB1-3CB | bar: Week 14 Sa 5 to Week 15 Fr 11
TO-25-FIN GIS-110SB3-5CB-03 | FINGLAS GIS 110SB3-5CB | bar: Week 14 Sa 5 to Week 15 Fr 11
TO-25-FIN GIS-T2106-02 | FINGLAS GIS T2106 | bar: Week 14 Sa 5 to Week 15 Fr 11
TO-25-GLE-KCR-1-01 | GLENLARA KNOCKACUMMER | bar: Week 14 Sa 5 to Week 15 Fr 11
TO-25-KCR-T121-01 | KNOCKACUMMER T121 | bar: Week 14 Sa 5 to Week 15 Fr 11
TO-25-MOY-TAW-1-01 | MOY TAWNAGHMORE 1 | bar: Week 14 Sa 5 to Week 15 Fr 11
TO-25-110 kV A2 @ CLU-01 | CLUTTERLAND 110 kV A2 | bar: Week 14 Sa 5 to Week 15 Mo 14
TO-25-110 kV B2 @ CLU-01 | CLUTTERLAND 110 kV B2 | bar: Week 14 Sa 5 to Week 15 Mo 14
TO-25-CLU-110K2-01 | CLUTTERLAND 110K2 | bar: Week 14 Sa 5 to Week 15 Mo 14
TO-25-CLU-110SA1-2CB-01 | CLUTTERLAND 110SA1-2CB | bar: Week 14 Sa 5 to Week 15 Mo 14
TO-25-CLU-110SB1-2CB-01 | CLUTTERLAND 110SB1-2CB | bar: Week 14 Sa 5 to Week 15 Mo 14
TO-25-220 kV A1 @ LOU-01 | LOUTH 220 kV A1 | bar: Week 14 Sa 5 to Week 15 Mo 14
TO-25-220 kV B1 @ LOU-01 | LOUTH 220 kV B1 | bar: Week 14 Sa 5 to Week 15 Mo 14
TO-25-110 kV A2 @ SLB-01 | SLIABH BAWN 110 kV A2 | bar: Su 30
TO-25-110 kV B2 @ SLB-01 | SLIABH BAWN 110 kV B2 | bar: Su 30
TO-25-SLB-110K2-01 | SLIABH BAWN 110K2 | bar: Su 30
TO-25-BYH-110K1-02 | BALLYNAHULLA 110K1
TO-25-BYH-110SB1-2CB-01 | BALLYNAHULLA 110SB1-2CB
TO-25-SLB-110K2-02 | SLIABH BAWN 110K2
TO-25-SNU-T102-01 | SNUGBOROUGH T102
TO-25-AA GIS-LIM-1-01 | ARDNACRUSHA GIS LIMERICK
TO-25-220 kV A3 @ PB-01 | POOLBEG 220 kV A3 | bar: Week 14 Sa 5 to Week 15 Mo 14
TO-25-220 kV B3 @ PB-01 | POOLBEG 220 kV B3 | bar: Week 14 Sa 5 to Week 15 Mo 14
TO-25-AD-T2011/12-02 | AGHADA T2011/12 | bar: Su 30
TO-25-220 kV A1 @ TH-01 | TURLOUGH HILL 220 kV A1 | bar: Su 30
TO-25-220 kV B1 @ TH-01 | TURLOUGH HILL 220 kV B1 | bar: Su 30
TO-25-TH-T2001/2-01 | TURLOUGH HILL T2001/2 | bar: Su 30
TO-25-KTL-T131-01 | KILTEEL T131
TO-25-ROP-110K1-01 | ROSSPILE 110K1
TO-25-220 kV A2 @ TH-01 | TURLOUGH HILL 220 kV A2 | bar: Week 14 Sa 5 to Week 15 Fr 11
TO-25-220 kV B2 @ TH-01 | TURLOUGH HILL 220 kV B2 | bar: Week 14 Sa 5 to Week 15 Fr 11
TO-25-TH-T2003/4-02 | TURLOUGH HILL T2003/4 | bar: Week 14 Sa 5 to Week 15 Fr 11
Report covers outages commencing/returning/spanning the period: 31/03/2025 - 13/04/2025
Outages commencing/returning in Week 14
OUTAGE ID | PLANT | Week 14 Mo 31: Week 14; Week 15 Mo 7: Week 15
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
TO-25-LET-PST-02 | LETTERKENNY STRABANE PST | bar: Week 14 We 2 to Week 15 Mo 7; Week 15 Fr 11 to Week 15 Mo 14
TO-25-NAV-T142-01 | NAVAN T142 | bar: Week 14 We 2 to Week 15 Mo 7; Week 15 Fr 11 to Week 15 Mo 14
TO-25-TEN-T132-02 | TIMAHOE T132 | bar: Week 14 Fr 4
Outages commencing/returning in Week 15
OUTAGE ID | PLANT | Week 14 Mo 31: Week 14; Week 15 Mo 7: Week 15
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
TO-25-CF-CL-1-02 | CATHALEENS FALL CLIFF | bar: Week 15 Mo 7
TO-25-CL-T101-03 | CLIFF T101 | bar: Week 15 Mo 7
TO-25-BVK-STATCOM-01 | BALLYVOUSKILL STATCOM | bar: Week 15 Mo 7; Week 15 Fr 11
TO-25-110 kV A3 @ BLC-01 | BELCAMP 110 kV A3 | bar: Week 15 Mo 7; Week 15 Fr 11
TO-25-110 kV B3 @ BLC-01 | BELCAMP 110 kV B3 | bar: Week 15 Mo 7; Week 15 Fr 11
TO-25-BLC-110K3-02 | BELCAMP 110K3 | bar: Week 15 Mo 7; Week 15 Fr 11
TO-25-BLC-110SA1-3CB-02 | BELCAMP 110SA1-3CB | bar: Week 15 Mo 7; Week 15 Fr 11
TO-25-BLC-110SB1-3CB-02 | BELCAMP 110SB1-3CB | bar: Week 15 Mo 7; Week 15 Fr 11
TO-25-BLC-DND-3-01 | BELCAMP DARNDALE 3 | bar: Week 15 Mo 7; Week 15 Fr 11
TO-25-110 kV A2 @ DND-01 | DARNDALE 110 kV A2 | bar: Week 15 Mo 7; Week 15 Fr 11
TO-25-110 kV B2 @ DND-01 | DARNDALE 110 kV B2 | bar: Week 15 Mo 7; Week 15 Fr 11
TO-25-DND-110K2-02 | DARNDALE 110K2 | bar: Week 15 Mo 7; Week 15 Fr 11
TO-25-DND-110SA1-2CB-03 | DARNDALE 110SA1-2CB | bar: Week 15 Mo 7; Week 15 Fr 11
TO-25-DND-110SB1-2CB-02 | DARNDALE 110SB1-2CB | bar: Week 15 Mo 7; Week 15 Fr 11
TO-25-110 kV A2 @ DEY-01 | DERRYCARNEY 110 kV A2 | bar: Week 15 Mo 7; Week 15 Fr 11
TO-25-110 kV B2 @ DEY-01 | DERRYCARNEY 110 kV B2 | bar: Week 15 Mo 7; Week 15 Fr 11
TO-25-DEY-110K2-02 | DERRYCARNEY 110K2 | bar: Week 15 Mo 7; Week 15 Fr 11
TO-25-DEY-T132-01 | DERRYCARNEY T132 | bar: Week 15 Mo 7; Week 15 Fr 11
TO-25-220 kV A2 @ AD-01 | AGHADA 220 kV A2 | bar: Week 15 Mo 7; Week 15 Fr 11 to Week 15 Mo 14
TO-25-220 kV B2 @ AD-01 | AGHADA 220 kV B2 | bar: Week 15 Mo 7; Week 15 Fr 11 to Week 15 Mo 14
TO-25-AD-SA1-2CB-02 | AGHADA 220SA1-2CB | bar: Week 15 Mo 7; Week 15 Fr 11 to Week 15 Mo 14
TO-25-AD-SB1-2CB-02 | AGHADA 220SB1-2CB | bar: Week 15 Mo 7; Week 15 Fr 11 to Week 15 Mo 14
TO-25-AD-ST101-01 | AGHADA ST101 | bar: Week 15 Mo 7; Week 15 Fr 11 to Week 15 Mo 14
TO-25-AD-T2102-01 | AGHADA T2102 | bar: Week 15 Mo 7; Week 15 Fr 11 to Week 15 Mo 14
TO-25-AD-WHI-1-01 | AGHADA WHITEGATE | bar: Week 15 Mo 7; Week 15 Fr 11 to Week 15 Mo 14
TO-25-CL-T102-01 | CLIFF T102 | bar: Week 15 Mo 7; Week 15 Fr 11 to Week 15 Mo 14
TO-25-220 kV A1 @ MP GIS-01 | MONEYPOINT GIS 220 kV A1 | bar: Week 15 Mo 7; Week 15 Fr 11 to Week 15 Mo 14
TO-25-220 kV B1 @ MP GIS-01 | MONEYPOINT GIS 220 kV B1 | bar: Week 15 Mo 7; Week 15 Fr 11 to Week 15 Mo 14
TO-25-MP GIS-220K1-01 | MONEYPOINT GIS 220K1 | bar: Week 15 Mo 7; Week 15 Fr 11 to Week 15 Mo 14
TO-25-MP GIS-220SA1-2CB-02 | MONEYPOINT GIS 220SA1-2CB | bar: Week 15 Mo 7; Week 15 Fr 11 to Week 15 Mo 14
TO-25-MP GIS-220SB1-2CB-02 | MONEYPOINT GIS 220SB1-2CB | bar: Week 15 Mo 7; Week 15 Fr 11 to Week 15 Mo 14
TO-25-TTU-131-02 | TULLABEG T131
TO-25-BLU-T131-01 | BLUNDELSTOWN T131
TO-25-KHL-THU-1-02 | KILL HILL THURLES
TO-25-AA GIS-SNG-1-01 | ARDNACRUSHA GIS SINGLAND
TO-25-GI GIS-LON-1-01 | GREAT ISLAND GIS LOUGHTOWN
TO-25-LON-T2401-01 | LOUGHTOWN T2401
TO-25-BOG-TTU-1-01 | BANOGE TULLABEG | bar: Week 15 Fr 11
TO-25-BRT-T224-01 | BRACETOWN T224 | bar: Week 15 Fr 11 to Week 15 Mo 14
TO-25-CSH-T2104-01 | CASHLA T2104 | bar: Su 30 to Week 15 Mo 7; Week 15 Fr 11
TO-25-RRU-SKL-1-01 | RATRUSSAN SHANKILL | bar: Su 30 to Week 15 Mo 7; Week 15 Fr 11
Outages spanning Weeks 14-15
OUTAGE ID | PLANT | Week 14 Mo 31: Week 14; Week 15 Mo 7: Week 15
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
TO-25-BNK-110SA1-2CB-01 | BARNAKYLE 110SA1-2CB
TO-25-BNK-CBT-2-01 | BARNAKYLE CASTLEBAGOT 2
TO-25-BNK-T122-01 | BARNAKYLE T122
TO-25-CAH-CAP1/3-02 | CAHIR CAP1/3
TO-25-CSH-CAP2-01 | CASHLA CAP2
TO-25-CSH-ENN-1-02 | CASHLA ENNIS
Report covers outages commencing/returning/spanning the period: 31/03/2025 - 13/04/2025
Outages spanning Weeks 14-15
OUTAGE ID | PLANT | Week 14 Mo 31: Week 14; Week 15 Mo 7: Week 15
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
TO-25-CBR-SVC-01 | CASTLEBAR SVC
TO-25-CLA-110K1-2-01 | CLASHAVOON 110K1-2
TO-25-CUS-PLS-1-01 | CUSHALING PORTLAOISE
TO-25-DND-T121-01 | DARNDALE T121
TO-25-DRY-OBE-1-01 | DRYBRIDGE OLDBRIDGE
TO-25-400 kV A1 @ DSN-01 | DUNSTOWN 400 kV A1
TO-25-400 kV B1 @ DSN-01 | DUNSTOWN 400 kV B1
TO-25-DSN-MP GIS-1-01 | DUNSTOWN MONEYPOINT GIS
TO-25-FIN-110K1-2-02 | FINGLAS 110K1-2
TO-25-FIN-SHL-1-07 | FINGLAS SHELLYBANKS
TO-25-110 kV A1 @ FLA-01 | FLAGFORD 110 kV A1
TO-25-110 kV B1 @ FLA-01 | FLAGFORD 110 kV B1
TO-25-FLA-SLB-1-03 | FLAGFORD SLIABH BAWN
TO-25-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-25-GI-T141-01 | GREAT ISLAND T141
TO-25-INC-220K1-2-01 | INCHICORE 220K1-2
TO-25-INC-PB-2-02 | INCHICORE POOLBEG 2
TO-25-KBY-MR-1-03 | KILBARRY MARINA 1
TO-25-KBY-MR-2-03 | KILBARRY MARINA 2
TO-25-KTN-T102-01 | KILLOTERAN T102
TO-25-KTN-WAT-1-03 | KILLOTERAN WATERFORD
TO-25-220 kV A4 @ KRA-01 | KNOCKRAHA 220 kV A4
TO-25-220 kV B4 @ KRA-01 | KNOCKRAHA 220 kV B4
TO-25-KRA-220K4-01 | KNOCKRAHA 220K4
TO-25-KRA-220SA2-4CB-02 | KNOCKRAHA 220SA2-4CB
TO-25-KRA-220SB2-4CB-02 | KNOCKRAHA 220SB2-4CB
TO-25-LET-PST-01 | LETTERKENNY STRABANE PST
TO-25-LOU-CAP1-02 | LOUTH CAP1
TO-25-400 kV A4 @ MP GIS-01 | MONEYPOINT GIS 400 kV A4
TO-25-400 kV B4 @ MP GIS-01 | MONEYPOINT GIS 400 kV B4
TO-25-MP GIS-400K4-01 | MONEYPOINT GIS 400K4
TO-25-MP GIS-400SA2-4CB-01 | MONEYPOINT GIS 400SA2-4CB
TO-25-MP GIS-400SB2-4CB-01 | MONEYPOINT GIS 400SB2-4CB
TO-25-MUL-CAP2-01 | MULLINGAR CAP2
TO-25-PB-R2001-01 | POOLBEG R2001
TO-25-110 kV A2 @ PLS-01 | PORTLAOISE 110 kV A2
TO-25-110 kV B2 @ PLS-01 | PORTLAOISE 110 kV B2
TO-25-PRO-TB-1-01 | PROSPECT TARBERT
TO-25-220 kV A1 @ SH-03 | SHANNONBRIDGE 220 kV A1
TO-25-220 kV B1 @ SH-03 | SHANNONBRIDGE 220 kV B1
TO-25-SH-T2101-03 | SHANNONBRIDGE T2101
TO-25-TB-T2003-01 | TARBERT T2003
TO-25-TB-T2004-01 | TARBERT T2004