## Wks 16 - 17
Report covers outages commencing/returning/spanning the period: 14/04/2025 - 27/04/2025
Outages commencing/returning in Week 16
OUTAGE ID | PLANT |  | Week 16 | [6 empty] | Week 17
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
TO-25-400 kV A1 @ WOO-02 | WOODLAND 400 kV A1 | bar: Week 16 Mo 14
TO-25-BUF-KNY-1-01 | BUFFY KNOCKRANNY | bar: Week 16 Mo 14
TO-25-BUF-T131-01 | BUFFY T131 | bar: Week 16 Mo 14
TO-25-CHA-MAL-1-06 | CHARLEVILLE MALLOW | bar: Week 16 Mo 14; Week 16 We 16
TO-25-220 kV A1 @ BYH-01 | BALLYNAHULLA 220 kV A1 | bar: Week 16 Mo 14; Week 16 We 16 to Week 16 Th 17
TO-25-220 kV A2 @ BYH-01 | BALLYNAHULLA 220 kV A2 | bar: Week 16 Mo 14; Week 16 We 16 to Week 16 Th 17
TO-25-BYH-220K1-02 | BALLYNAHULLA 220K1 | bar: Week 16 Mo 14; Week 16 We 16 to Week 16 Th 17
TO-25-BYH-220K2-01 | BALLYNAHULLA 220K2 | bar: Week 16 Mo 14; Week 16 We 16 to Week 16 Th 17
TO-25-BYH-220SA1-2CB-01 | BALLYNAHULLA 220SA1-2CB | bar: Week 16 Mo 14; Week 16 We 16 to Week 16 Th 17
TO-25-110 kV A2 @ DEY-02 | DERRYCARNEY 110 kV A2 | bar: Week 16 Mo 14; Week 16 We 16 to Week 16 Th 17
TO-25-110 kV B2 @ DEY-02 | DERRYCARNEY 110 kV B2 | bar: Week 16 Mo 14; Week 16 We 16 to Week 16 Th 17
TO-25-DEY-110K2-01 | DERRYCARNEY 110K2 | bar: Week 16 Mo 14; Week 16 We 16 to Week 16 Th 17
TO-25-PRN-T4301-01 | PORTAN T4301 | bar: Week 16 Mo 14; Week 16 We 16 to Week 16 Fr 18
TO-25-PRN-WOO-1-01 | PORTAN WOODLAND | bar: Week 16 Mo 14; Week 16 We 16 to Week 16 Fr 18
TO-25-KPG-TRL-2-02 | KILPADDOGE TRALEE 2 | bar: Week 16 Mo 14; Week 16 We 16 to Week 17 Mo 28
TO-25-AD-ST101-01 | AGHADA ST101 | bar: Su 13 to Week 16 Mo 14
TO-25-AD-WHI-1-01 | AGHADA WHITEGATE | bar: Su 13 to Week 16 Mo 14
TO-25-110 kV B1 @ LOU-04 | LOUTH 110 kV B1
TO-25-LOU-MLN-1-02 | LOUTH MULLAGHARLIN
TO-25-CDY-GRV-1-02 | CORDERRY GARVAGH | bar: Week 16 We 16 to Week 16 Th 17
TO-25-GRV-110K1-02 | GARVAGH 110K1 | bar: Week 16 We 16 to Week 16 Th 17
TO-25-GRV-T121-03 | GARVAGH T121 | bar: Week 16 We 16 to Week 16 Th 17
TO-25-GRV-T141-02 | GARVAGH T141 | bar: Week 16 We 16 to Week 16 Th 17
TO-25-MOY-TAW-2-01 | MOY TAWNAGHMORE 2 | bar: Week 16 We 16 to Week 16 Th 17
TO-25-400 kV B1 @ WOO-02 | WOODLAND 400 kV B1 | bar: Week 16 We 16 to Week 16 Fr 18
TO-25-WOO-400K1-2-01 | WOODLAND 400K1-2 | bar: Week 16 We 16 to Week 16 Fr 18
TO-25-WOO-T4201-02 | WOODLAND T4201 | bar: Week 16 We 16 to Week 16 Fr 18
TO-25-CL-T102-01 | CLIFF T102 | bar: Su 13 to Week 16 Mo 14
TO-25-INC-PB-2-02 | INCHICORE POOLBEG 2 | bar: Su 13 to Week 16 Mo 14
TO-25-220 kV A1 @ MP GIS-01 | MONEYPOINT GIS 220 kV A1 | bar: Su 13 to Week 16 Mo 14
TO-25-220 kV B1 @ MP GIS-01 | MONEYPOINT GIS 220 kV B1 | bar: Su 13 to Week 16 Mo 14
TO-25-MP GIS-220K1-01 | MONEYPOINT GIS 220K1 | bar: Su 13 to Week 16 Mo 14
TO-25-MP GIS-220SA1-2CB-02 | MONEYPOINT GIS 220SA1-2CB | bar: Su 13 to Week 16 Mo 14
TO-25-MP GIS-220SB1-2CB-02 | MONEYPOINT GIS 220SB1-2CB | bar: Su 13 to Week 16 Mo 14
TO-25-220 kV A3 @ PB-01 | POOLBEG 220 kV A3 | bar: Su 13 to Week 16 Mo 14
TO-25-220 kV B3 @ PB-01 | POOLBEG 220 kV B3 | bar: Su 13 to Week 16 Mo 14
TO-25-LOU-T2101-08 | LOUTH T2101 | bar: Week 16 We 16 to Week 16 Th 17
TO-25-220 kV A2 @ MP GIS-01 | MONEYPOINT GIS 220 kV A2 | bar: Week 16 We 16 to Week 17 Mo 28
TO-25-220 kV B2 @ MP GIS-01 | MONEYPOINT GIS 220 kV B2 | bar: Week 16 We 16 to Week 17 Mo 28
TO-25-MP GIS-220K2-01 | MONEYPOINT GIS 220K2 | bar: Week 16 We 16 to Week 17 Mo 28
TO-25-MP GIS-220SA1-2CB-03 | MONEYPOINT GIS 220SA1-2CB | bar: Week 16 We 16 to Week 17 Mo 28
TO-25-MP GIS-220SB1-2CB-03 | MONEYPOINT GIS 220SB1-2CB | bar: Week 16 We 16 to Week 17 Mo 28
TO-25-CHA-GLE-1-01 | CHARLEVILLE GLENLARA | bar: Week 16 Th 17 to Week 17 Mo 28
TO-25-CUS-PLS-1-01 | CUSHALING PORTLAOISE | bar: Su 13 to Week 16 Mo 14; Week 16 We 16 to Week 16 Th 17
TO-25-400 kV A1 @ DSN-01 | DUNSTOWN 400 kV A1 | bar: Su 13 to Week 16 Mo 14; Week 16 We 16 to Week 16 Th 17
TO-25-400 kV B1 @ DSN-01 | DUNSTOWN 400 kV B1 | bar: Su 13 to Week 16 Mo 14; Week 16 We 16 to Week 16 Th 17
TO-25-DSN-MP GIS-1-01 | DUNSTOWN MONEYPOINT GIS | bar: Su 13 to Week 16 Mo 14; Week 16 We 16 to Week 16 Th 17
TO-25-LET-PST-02 | LETTERKENNY STRABANE PST | bar: Su 13 to Week 16 Mo 14; Week 16 We 16 to Week 16 Th 17
TO-25-400 kV A4 @ MP GIS-01 | MONEYPOINT GIS 400 kV A4 | bar: Su 13 to Week 16 Mo 14; Week 16 We 16 to Week 16 Th 17
TO-25-400 kV B4 @ MP GIS-01 | MONEYPOINT GIS 400 kV B4 | bar: Su 13 to Week 16 Mo 14; Week 16 We 16 to Week 16 Th 17
TO-25-MP GIS-400K4-01 | MONEYPOINT GIS 400K4 | bar: Su 13 to Week 16 Mo 14; Week 16 We 16 to Week 16 Th 17
TO-25-MP GIS-400SA2-4CB-01 | MONEYPOINT GIS 400SA2-4CB | bar: Su 13 to Week 16 Mo 14; Week 16 We 16 to Week 16 Th 17
TO-25-MP GIS-400SB2-4CB-01 | MONEYPOINT GIS 400SB2-4CB | bar: Su 13 to Week 16 Mo 14; Week 16 We 16 to Week 16 Th 17
TO-25-110 kV A2 @ PLS-01 | PORTLAOISE 110 kV A2 | bar: Su 13 to Week 16 Mo 14; Week 16 We 16 to Week 16 Th 17
TO-25-110 kV B2 @ PLS-01 | PORTLAOISE 110 kV B2 | bar: Su 13 to Week 16 Mo 14; Week 16 We 16 to Week 16 Th 17
TO-25-ARV-COS-1-03 | ARVA CARRICK ON SHANNON | bar: Week 16 Fr 18 to Week 17 Mo 21
TO-25-CUS-PLS-1-04 | CUSHALING PORTLAOISE | bar: Week 16 Fr 18 to Week 17 Mo 28
TO-25-110 kV A2 @ CSH-03 | CASHLA 110 kV A2 | bar: Su 13 to Week 16 Mo 14; Week 16 We 16 to Week 16 Fr 18
TO-25-110 kV B2 @ CSH-05 | CASHLA 110 kV B2 | bar: Su 13 to Week 16 Mo 14; Week 16 We 16 to Week 16 Fr 18
TO-25-220 kV A4 @ CSH-02 | CASHLA 220 kV A4 | bar: Su 13 to Week 16 Mo 14; Week 16 We 16 to Week 16 Fr 18
TO-25-220 kV B4 @ CSH-02 | CASHLA 220 kV B4 | bar: Su 13 to Week 16 Mo 14; Week 16 We 16 to Week 16 Fr 18
Report covers outages commencing/returning/spanning the period: 14/04/2025 - 27/04/2025
Outages commencing/returning in Week 16
OUTAGE ID | PLANT | Week 16 Mo 14: Week 16; Week 17 Mo 21: Week 17
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
TO-25-CSH-T2104-01 | CASHLA T2104 | bar: Su 13 to Week 16 Fr 18
Outages commencing/returning in Week 17
OUTAGE ID | PLANT | Week 16 Mo 14: Week 16; Week 17 Mo 21: Week 17
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
TO-25-AUG-MTN-1-01 | AUGHINISH MONETEEN | bar: Week 17 Tu 22 to Week 17 Th 24
TO-25-220 kV A1 @ ARK-01 | ARKLOW 220 kV A1 | bar: Week 17 Tu 22 to Week 17 Fr 25
TO-25-220 kV A2 @ ARK-01 | ARKLOW 220 kV A2 | bar: Week 17 Tu 22 to Week 17 Fr 25
TO-25-220 kV B1 @ ARK-01 | ARKLOW 220 kV B1 | bar: Week 17 Tu 22 to Week 17 Fr 25
TO-25-220 kV B2 @ ARK-01 | ARKLOW 220 kV B2 | bar: Week 17 Tu 22 to Week 17 Fr 25
TO-25-ARK-220K1-2-01 | ARKLOW 220K1-2 | bar: Week 17 Tu 22 to Week 17 Fr 25
TO-25-220 kV A2 @ AD-01 | AGHADA 220 kV A2 | bar: Su 13 to Week 17 Tu 22
TO-25-220 kV B2 @ AD-01 | AGHADA 220 kV B2 | bar: Su 13 to Week 17 Tu 22
TO-25-AD-SA1-2CB-02 | AGHADA 220SA1-2CB | bar: Su 13 to Week 17 Tu 22
TO-25-AD-SB1-2CB-02 | AGHADA 220SB1-2CB | bar: Su 13 to Week 17 Tu 22
TO-25-AD-T2102-01 | AGHADA T2102 | bar: Su 13 to Week 17 Tu 22
TO-25-FLA-220K1-2-01 | FLAGFORD 220K1-2 | bar: Week 17 We 23
TO-25-ROP-T131-01 | ROSSPILE T131 | bar: Week 17 We 23
TO-25-CBT-CLU-1-01 | CASTLEBAGOT CLUTTERLAND | bar: Week 17 We 23 to Week 17 Th 24
TO-25-MR-T106-01 | MARINA T106 | bar: Week 17 We 23 to Week 17 Th 24
TO-25-CD-T103-02 | CARRIGADROHID T103 | bar: Week 17 We 23 to Week 17 Mo 28
TO-25-110 kV A2 @ DND-02 | DARNDALE 110 kV A2 | bar: Week 17 We 23 to Week 17 Mo 28
TO-25-110 kV B2 @ DND-02 | DARNDALE 110 kV B2 | bar: Week 17 We 23 to Week 17 Mo 28
TO-25-DND-110K2-01 | DARNDALE 110K2 | bar: Week 17 We 23 to Week 17 Mo 28
TO-25-DND-110SA1-2CB-05 | DARNDALE 110SA1-2CB | bar: Week 17 We 23 to Week 17 Mo 28
TO-25-DND-110SB1-2CB-04 | DARNDALE 110SB1-2CB | bar: Week 17 We 23 to Week 17 Mo 28
TO-25-KLS-220K1-2-01 | KELLIS 220K1-2 | bar: Week 17 Th 24
TO-25-STN-T131-02 | STONESTOWN T131 | bar: Week 17 Th 24
TO-25-IKE-T141-01 | IKERRIN T141 | bar: Week 17 Th 24 to Week 17 Fr 25
TO-25-IKE,T-IKE-1-01 | IKERRIN tee IKERRIN | bar: Week 17 Th 24 to Week 17 Fr 25
TO-25-IKE,T-SH-1-01 | IKERRIN tee SHANNONBRIDGE | bar: Week 17 Th 24 to Week 17 Fr 25
TO-25-110 kV A2 @ CF-03 | CATHALEENS FALL 110 kV A2 | bar: Week 17 Th 24 to Week 17 Mo 28
TO-25-110 kV B2 @ CF-02 | CATHALEENS FALL 110 kV B2 | bar: Week 17 Th 24 to Week 17 Mo 28
TO-25-CF-T104-01 | CATHALEENS FALL T104 | bar: Week 17 Th 24 to Week 17 Mo 28
TO-25-IKE,T-THU-1-05 | IKERRIN tee THURLES | bar: Week 17 Th 24 to Week 17 Mo 28
TO-25-IKE,T-THU-1-01 | bar: Week 17 Th 24 to Week 17 Mo 28
TO-25-110 kV A2 @ CLU-01 | CLUTTERLAND 110 kV A2 | bar: Su 13 to Week 17 Th 24
TO-25-110 kV B2 @ CLU-01 | CLUTTERLAND 110 kV B2 | bar: Su 13 to Week 17 Th 24
TO-25-CLU-110K2-01 | CLUTTERLAND 110K2 | bar: Su 13 to Week 17 Th 24
TO-25-CLU-110SA1-2CB-01 | CLUTTERLAND 110SA1-2CB | bar: Su 13 to Week 17 Th 24
TO-25-CLU-110SB1-2CB-01 | CLUTTERLAND 110SB1-2CB | bar: Su 13 to Week 17 Th 24
TO-25-RRU-SKL-1-01 | RATRUSSAN SHANKILL | bar: Su 13 to Week 17 Fr 25
TO-25-CKM-PB-1-03 | CARRICKMINES POOLBEG | bar: Week 17 Sa 26 to Week 17 Su 27
TO-25-FIN-HN-1-01 | FINGLAS HUNTSTOWN | bar: Week 17 Sa 26 to Week 17 Mo 28
TO-25-HN-T2010/11-01 | HUNTSTOWN T2010/11 | bar: Week 17 Sa 26 to Week 17 Mo 28
Outages spanning Weeks 16-17
OUTAGE ID | PLANT | Week 16 Mo 14: Week 16; Week 17 Mo 21: Week 17
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
TO-25-BNK-110SA1-2CB-01 | BARNAKYLE 110SA1-2CB
TO-25-BNK-CBT-2-01 | BARNAKYLE CASTLEBAGOT 2
TO-25-BNK-T122-01 | BARNAKYLE T122
TO-25-BRT-T224-01 | BRACETOWN T224
TO-25-CSH-CAP2-01 | CASHLA CAP2
TO-25-CSH-ENN-1-02 | CASHLA ENNIS
TO-25-CBR-SVC-01 | CASTLEBAR SVC
TO-25-CVW-COW-1-05 | CASTLEVIEW COW CROSS
TO-25-CLA-110K1-2-01 | CLASHAVOON 110K1-2
Report covers outages commencing/returning/spanning the period: 14/04/2025 - 27/04/2025
Outages spanning Weeks 16-17
OUTAGE ID | PLANT | Week 16 Mo 14: Week 16; Week 17 Mo 21: Week 17
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
TO-25-DLT-CAP1-02 | DALTON CAP1
TO-25-DND-T121-01 | DARNDALE T121
TO-25-DRY-OBE-1-01 | DRYBRIDGE OLDBRIDGE
TO-25-FIN-110K1-2-02 | FINGLAS 110K1-2
TO-25-FIN-SHL-1-07 | FINGLAS SHELLYBANKS
TO-25-110 kV A1 @ FLA-01 | FLAGFORD 110 kV A1
TO-25-110 kV B1 @ FLA-01 | FLAGFORD 110 kV B1
TO-25-FLA-SLB-1-03 | FLAGFORD SLIABH BAWN
TO-25-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-25-GI-T141-01 | GREAT ISLAND T141
TO-25-INC-220K1-2-01 | INCHICORE 220K1-2
TO-25-KYT-T232-02 | KELLYSTOWN T232
TO-25-KBY-MR-1-03 | KILBARRY MARINA 1
TO-25-KBY-MR-2-03 | KILBARRY MARINA 2
TO-25-KTN-110SA1-01 | KILLOTERAN 110SA1
TO-25-KTN-110SA2-01 | KILLOTERAN 110SA2
TO-25-KTN-T102-01 | KILLOTERAN T102
TO-25-KTN-WAT-1-03 | KILLOTERAN WATERFORD
TO-25-220 kV A4 @ KRA-01 | KNOCKRAHA 220 kV A4
TO-25-220 kV B4 @ KRA-01 | KNOCKRAHA 220 kV B4
TO-25-KRA-220K4-01 | KNOCKRAHA 220K4
TO-25-KRA-220SA2-4CB-02 | KNOCKRAHA 220SA2-4CB
TO-25-KRA-220SB2-4CB-02 | KNOCKRAHA 220SB2-4CB
TO-25-LET-PST-01 | LETTERKENNY STRABANE PST
TO-25-220 kV A1 @ LOU-01 | LOUTH 220 kV A1
TO-25-220 kV B1 @ LOU-01 | LOUTH 220 kV B1
TO-25-LOU-CAP1-02 | LOUTH CAP1
TO-25-MUL-CAP2-01 | MULLINGAR CAP2
TO-25-NAV-T142-01 | NAVAN T142
TO-25-PB-R2001-01 | POOLBEG R2001
TO-25-RTH-T133-01 | RATHNASKILLOGE T133
TO-25-220 kV A1 @ SH-03 | SHANNONBRIDGE 220 kV A1
TO-25-220 kV B1 @ SH-03 | SHANNONBRIDGE 220 kV B1
TO-25-SH-T2101-03 | SHANNONBRIDGE T2101
TO-25-TB-T2003-01 | TARBERT T2003
TO-25-TB-T2004-01 | TARBERT T2004