## Wks 18 - 19
Report covers outages commencing/returning/spanning the period: 28/04/2025 - 11/05/2025
Outages commencing/returning in Week 18
OUTAGE ID | PLANT |  | Week 18 | [6 empty] | Week 19
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
TO-25-BVK-110K2-01 | BALLYVOUSKILL 110K2 | bar: Week 18 Mo 28 to Week 18 Tu 29
TO-25-LLA-110K1-01 | LENALEA 110K1 | bar: Week 18 Mo 28 to Week 18 Tu 29
TO-25-LLA-T133-02 | LENALEA T133 | bar: Week 18 Mo 28 to Week 18 We 30
TO-25-110 kV A2 @ AA GIS-01 | ARDNACRUSHA GIS 110 kV A2 | bar: Week 18 Mo 28 to Week 18 Fr 2
TO-25-110 kV B2 @ AA GIS-01 | ARDNACRUSHA GIS 110 kV B2 | bar: Week 18 Mo 28 to Week 18 Fr 2
TO-25-AA GIS-110K2-02 | ARDNACRUSHA GIS 110K2 | bar: Week 18 Mo 28 to Week 18 Fr 2
TO-25-AA GIS-110SA1-2CB-01 | ARDNACRUSHA GIS 110SA1-2CB | bar: Week 18 Mo 28 to Week 18 Fr 2
TO-25-AA GIS-110SB1-2CB-01 | ARDNACRUSHA GIS 110SB1-2CB | bar: Week 18 Mo 28 to Week 18 Fr 2
TO-25-220 kV A1 @ BVK-01 | BALLYVOUSKILL 220 kV A1 | bar: Week 18 Mo 28 to Week 18 Fr 2
TO-25-220 kV B1 @ BVK-01 | BALLYVOUSKILL 220 kV B1 | bar: Week 18 Mo 28 to Week 18 Fr 2
TO-25-BVK-220K1-02 | BALLYVOUSKILL 220K1 | bar: Week 18 Mo 28 to Week 18 Fr 2
TO-25-BVK-220SA1-2CB-03 | BALLYVOUSKILL 220SA1-2CB | bar: Week 18 Mo 28 to Week 18 Fr 2
TO-25-BVK-220SB1-2CB-04 | BALLYVOUSKILL 220SB1-2CB | bar: Week 18 Mo 28 to Week 18 Fr 2
TO-25-BVK-R2001-01 | BALLYVOUSKILL R2001 | bar: Week 18 Mo 28 to Week 18 Fr 2
TO-25-GAR-110K1-01 | GARBALLAGH 110K1 | bar: Week 18 Mo 28 to Week 18 Fr 2
TO-25-GAR-110SA1-2CB-01 | GARBALLAGH 110SA1-2CB | bar: Week 18 Mo 28 to Week 18 Fr 2
TO-25-GAR-110SB1-2CB-01 | GARBALLAGH 110SB1-2CB | bar: Week 18 Mo 28 to Week 18 Fr 2
TO-25-220 kV A1 @ FIN-06 | FINGLAS 220 kV A1 | bar: Week 18 Mo 28 to Week 19 Fr 9
TO-25-220 kV B1 @ FIN-05 | FINGLAS 220 kV B1 | bar: Week 18 Mo 28 to Week 19 Fr 9
TO-25-FIN-220K1-09 | FINGLAS 220K1 | bar: Week 18 Mo 28 to Week 19 Fr 9
TO-25-FIN-220SA1-2CB-13 | FINGLAS 220SA1-2CB | bar: Week 18 Mo 28 to Week 19 Fr 9
TO-25-FIN-220SB1-2CB-10 | FINGLAS 220SB1-2CB | bar: Week 18 Mo 28 to Week 19 Fr 9
TO-25-LSA-SKL-1-02 | LISLEA SHANKILL | bar: Week 18 Mo 28 to Week 19 Fr 9
TO-25-AA GIS-T102-02 | ARDNACRUSHA GIS T102
TO-25-CAH-110K1-2-01 | CAHIR 110K1-2
TO-25-CBT-T2103-01 | CASTLEBAGOT T2103
TO-25-220 kV A2 @ MP GIS-01 | MONEYPOINT GIS 220 kV A2 | bar: Su 27 to Week 18 Mo 28
TO-25-220 kV B2 @ MP GIS-01 | MONEYPOINT GIS 220 kV B2 | bar: Su 27 to Week 18 Mo 28
TO-25-MP GIS-220K2-01 | MONEYPOINT GIS 220K2 | bar: Su 27 to Week 18 Mo 28
TO-25-MP GIS-220SA1-2CB-03 | MONEYPOINT GIS 220SA1-2CB | bar: Su 27 to Week 18 Mo 28
TO-25-MP GIS-220SB1-2CB-03 | MONEYPOINT GIS 220SB1-2CB | bar: Su 27 to Week 18 Mo 28
TO-25-PLA-T101/2/3/4-02 | PLATIN T101/2/3/4 | bar: Week 18 Tu 29 to Week 19 Mo 12
TO-25-110 kV A2 @ DND-02 | DARNDALE 110 kV A2 | bar: Su 27 to Week 18 Tu 29
TO-25-110 kV B2 @ DND-02 | DARNDALE 110 kV B2 | bar: Su 27 to Week 18 Tu 29
TO-25-DND-110K2-01 | DARNDALE 110K2 | bar: Su 27 to Week 18 Tu 29
TO-25-DND-110SA1-2CB-05 | DARNDALE 110SA1-2CB | bar: Su 27 to Week 18 Tu 29
TO-25-DND-110SB1-2CB-04 | DARNDALE 110SB1-2CB | bar: Su 27 to Week 18 Tu 29
TO-25-COW-OLD-2-02 | COW CROSS OLDCOURT 2 | bar: Week 18 We 30 to Week 18 Th 1
TO-25-OLD-T102-02 | OLDCOURT T102 | bar: Week 18 We 30 to Week 18 Th 1
TO-25-110 kV A1 @ DND-03 | DARNDALE 110 kV A1 | bar: Week 18 We 30 to Week 19 We 7
TO-25-110 kV A2 @ DND-03 | DARNDALE 110 kV A2 | bar: Week 18 We 30 to Week 19 We 7
TO-25-DND-110K1-03 | DARNDALE 110K1 | bar: Week 18 We 30 to Week 19 We 7
TO-25-DND-110K2-03 | DARNDALE 110K2 | bar: Week 18 We 30 to Week 19 We 7
TO-25-DND-110SA1-2CB-02 | DARNDALE 110SA1-2CB | bar: Week 18 We 30 to Week 19 We 7
TO-25-CRA-WEX-1-02 | CRANE WEXFORD | bar: Week 18 We 30 to Week 19 Mo 12
TO-25-CD-T103-02 | CARRIGADROHID T103 | bar: Su 27 to Week 18 We 30
TO-25-CLA-110K1-2-01 | CLASHAVOON 110K1-2 | bar: Su 27 to Week 18 We 30
TO-25-SH-T2101-03 | SHANNONBRIDGE T2101 | bar: Su 27 to Week 18 We 30
TO-25-CDU-CRU-2-04 | CORDUFF CRUISERATH 2 | bar: Week 18 Th 1
TO-25-CD-MAC-1-01 | CARRIGADROHID MACROOM | bar: Week 18 Th 1 to Week 19 Mo 12
TO-25-220 kV A2/A4 @ CDU-01 | CORDUFF 220 kV A2/A4 | bar: Su 27 to Week 18 Th 1
TO-25-220 kV B2/B4 @ CDU-02 | CORDUFF 220 kV B2/B4 | bar: Week 18 Fr 2 to Week 19 Fr 9
TO-25-CKM-PB-1-04 | CARRICKMINES POOLBEG | bar: Week 18 Sa 3 to Week 18 Su 4
Outages commencing/returning in Week 19
OUTAGE ID | PLANT | Week 18 Mo 28: Week 18; Week 19 Mo 5: Week 19
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
TO-25-BLU-MUL-1-01 | BLUNDELSTOWN MULLINGAR | bar: Week 19 Tu 6 to Week 19 We 7
TO-25-MUL-110SA1-2CB-02 | MULLINGAR 110SA1-2CB | bar: Week 19 Tu 6 to Week 19 We 7
Report covers outages commencing/returning/spanning the period: 28/04/2025 - 11/05/2025
Outages commencing/returning in Week 19
OUTAGE ID | PLANT | Week 18 Mo 28: Week 18; Week 19 Mo 5: Week 19
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
TO-25-MUL-CAP2-02 | MULLINGAR CAP2 | bar: Week 19 Tu 6
TO-25-MUL-T102-01 | MULLINGAR T102 | bar: Week 19 Tu 6
TO-25-MUL-T142-01 | MULLINGAR T142 | bar: Week 19 Tu 6
TO-25-BDA-MON-1-01 | BARODA MONREAD | bar: Week 19 Tu 6
TO-25-BLU-MUL-1-02 | BLUNDELSTOWN MULLINGAR | bar: Week 19 Tu 6; Week 19 Sa 10 to Week 19 Mo 12
TO-25-CF-SRA-2-01 | CATHALEENS FALL SRANANAGH 2 | bar: Week 19 Tu 6; Week 19 Sa 10 to Week 19 Mo 12
TO-25-CHA-GLE-1-02 | CHARLEVILLE GLENLARA | bar: Week 19 Tu 6; Week 19 Sa 10 to Week 19 Mo 12
TO-25-220 kV A3 @ KPG-01 | KILPADDOGE 220 kV A3 | bar: Week 19 Tu 6; Week 19 Sa 10 to Week 19 Mo 12
TO-25-220 kV B3 @ KPG-01 | KILPADDOGE 220 kV B3 | bar: Week 19 Tu 6; Week 19 Sa 10 to Week 19 Mo 12
TO-25-KPG-220K3-02 | KILPADDOGE 220K3 | bar: Week 19 Tu 6; Week 19 Sa 10 to Week 19 Mo 12
TO-25-KPG-220SA1-3CB-02 | KILPADDOGE 220SA1-3CB | bar: Week 19 Tu 6; Week 19 Sa 10 to Week 19 Mo 12
TO-25-KPG-220SB1-3CB-02 | KILPADDOGE 220SB1-3CB | bar: Week 19 Tu 6; Week 19 Sa 10 to Week 19 Mo 12
TO-25-KPG-TB-1-01 | KILPADDOGE TARBERT 1 | bar: Week 19 Tu 6; Week 19 Sa 10 to Week 19 Mo 12
TO-25-MP GIS-T4001-03 | MONEYPOINT GIS T4001 | bar: Week 19 Tu 6; Week 19 Sa 10 to Week 19 Mo 12
TO-25-220 kV A1 @ TB-01 | TARBERT 220 kV A1 | bar: Week 19 Tu 6; Week 19 Sa 10 to Week 19 Mo 12
TO-25-220 kV B1 @ TB-01 | TARBERT 220 kV B1 | bar: Week 19 Tu 6; Week 19 Sa 10 to Week 19 Mo 12
TO-25-GI GIS-220K2-02 | GREAT ISLAND GIS 220K2
TO-25-GI GIS-220SA1-2CB-01 | GREAT ISLAND GIS 220SA1-2CB
TO-25-CGG-DMY-1-01 | CARRIGDANGAN DUNMANWAY | bar: Week 19 Sa 10 to Week 19 Mo 12
TO-25-CGG-T131-01 | CARRIGDANGAN T131 | bar: Week 19 Sa 10 to Week 19 Mo 12
TO-25-220 kV A1 @ CSH-01 | CASHLA 220 kV A1 | bar: Week 19 Sa 10 to Week 19 Mo 12
TO-25-220 kV A2 @ CSH-01 | CASHLA 220 kV A2 | bar: Week 19 Sa 10 to Week 19 Mo 12
TO-25-220 kV B1 @ CSH-01 | CASHLA 220 kV B1 | bar: Week 19 Sa 10 to Week 19 Mo 12
TO-25-220 kV B2 @ CSH-01 | CASHLA 220 kV B2 | bar: Week 19 Sa 10 to Week 19 Mo 12
TO-25-CSH-220K1-2-01 | CASHLA 220K1-2 | bar: Week 19 Sa 10 to Week 19 Mo 12
TO-25-CUN-SLI-1-05 | CUNGHILL SLIGO | bar: Week 19 Sa 10 to Week 19 Mo 12
TO-25-220 kV A2 @ KNR-01 | KNOCKANURE 220 kV A2 | bar: Week 19 Sa 10 to Week 19 Mo 12
TO-25-220 kV B2 @ KNR-01 | KNOCKANURE 220 kV B2 | bar: Week 19 Sa 10 to Week 19 Mo 12
TO-25-KNR-220K2-02 | KNOCKANURE 220K2 | bar: Week 19 Sa 10 to Week 19 Mo 12
TO-25-KNR-220SA1-2CB-02 | KNOCKANURE 220SA1-2CB | bar: Week 19 Sa 10 to Week 19 Mo 12
TO-25-KNR-220SB1-2CB-02 | KNOCKANURE 220SB1-2CB | bar: Week 19 Sa 10 to Week 19 Mo 12
TO-25-KNR-R2002-01 | KNOCKANURE R2002 | bar: Week 19 Sa 10 to Week 19 Mo 12
TO-25-LOU-MLN-1-01 | LOUTH MULLAGHARLIN | bar: Week 19 Sa 10 to Week 19 Mo 12
TO-25-110 kV A2 @ CF-03 | CATHALEENS FALL 110 kV A2 | bar: Su 27 to Week 19 Tu 6
TO-25-110 kV B2 @ CF-02 | CATHALEENS FALL 110 kV B2 | bar: Su 27 to Week 19 Tu 6
TO-25-CF-T104-01 | CATHALEENS FALL T104 | bar: Su 27 to Week 19 Tu 6
TO-25-220 kV A1 @ LOU-01 | LOUTH 220 kV A1 | bar: Su 27 to Week 19 Tu 6
TO-25-220 kV B1 @ LOU-01 | LOUTH 220 kV B1 | bar: Su 27 to Week 19 Tu 6
TO-25-CBT-CLU-1-01 | CASTLEBAGOT CLUTTERLAND
TO-25-110 kV A2 @ CF-04 | CATHALEENS FALL 110 kV A2 | bar: Week 19 Sa 10 to Week 19 Mo 12
TO-25-110 kV B2 @ CF-03 | CATHALEENS FALL 110 kV B2 | bar: Week 19 Sa 10 to Week 19 Mo 12
TO-25-CF-SRA-2-02 | CATHALEENS FALL SRANANAGH 2 | bar: Week 19 Sa 10 to Week 19 Mo 12
TO-25-110 kV B1 @ DND-03 | DARNDALE 110 kV B1 | bar: Week 19 Sa 10 to Week 19 Mo 12
TO-25-110 kV B2 @ DND-03 | DARNDALE 110 kV B2 | bar: Week 19 Sa 10 to Week 19 Mo 12
TO-25-DND-110K1-05 | DARNDALE 110K1 | bar: Week 19 Sa 10 to Week 19 Mo 12
TO-25-DND-110K2-04 | DARNDALE 110K2 | bar: Week 19 Sa 10 to Week 19 Mo 12
TO-25-DND-110SB1-2CB-01 | DARNDALE 110SB1-2CB | bar: Week 19 Sa 10 to Week 19 Mo 12
TO-25-CDU-CRU-2-05 | CORDUFF CRUISERATH 2
TO-25-GI-WAT-2-04 | GREAT ISLAND WATERFORD 2 | bar: Week 19 Sa 10 to Week 19 Mo 12
TO-25-WAT-110SA1-02 | WATERFORD 110SA1 | bar: Week 19 Sa 10 to Week 19 Mo 12
TO-25-WAT-110SA2-02 | WATERFORD 110SA2 | bar: Week 19 Sa 10 to Week 19 Mo 12
TO-25-WAT-T141-01 | WATERFORD T141 | bar: Week 19 Sa 10 to Week 19 Mo 12
TO-25-110 kV A2 @ CLU-01 | CLUTTERLAND 110 kV A2 | bar: Su 27 to Week 19 Tu 6
TO-25-110 kV B2 @ CLU-01 | CLUTTERLAND 110 kV B2 | bar: Su 27 to Week 19 Tu 6
TO-25-CLU-110K2-01 | CLUTTERLAND 110K2 | bar: Su 27 to Week 19 Tu 6
TO-25-CLU-110SA1-2CB-01 | CLUTTERLAND 110SA1-2CB | bar: Su 27 to Week 19 Tu 6
TO-25-CLU-110SB1-2CB-01 | CLUTTERLAND 110SB1-2CB | bar: Su 27 to Week 19 Tu 6
TO-25-FIN-HN-1-01 | FINGLAS HUNTSTOWN | bar: Su 27 to Week 19 Tu 6
TO-25-HN-T2010/11-01 | HUNTSTOWN T2010/11 | bar: Su 27 to Week 19 Tu 6
Report covers outages commencing/returning/spanning the period: 28/04/2025 - 11/05/2025
Outages spanning Weeks 18-19
OUTAGE ID | PLANT | Week 18 Mo 28: Week 18; Week 19 Mo 5: Week 19
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
TO-25-BNK-110SA1-2CB-01 | BARNAKYLE 110SA1-2CB
TO-25-BNK-CBT-2-01 | BARNAKYLE CASTLEBAGOT 2
TO-25-BNK-T122-01 | BARNAKYLE T122
TO-25-BRT-T224-01 | BRACETOWN T224
TO-25-CSH-CAP2-01 | CASHLA CAP2
TO-25-CSH-ENN-1-02 | CASHLA ENNIS
TO-25-CBR-SVC-01 | CASTLEBAR SVC
TO-25-CVW-COW-1-05 | CASTLEVIEW COW CROSS
TO-25-CHA-GLE-1-01 | CHARLEVILLE GLENLARA
TO-25-CUS-PLS-1-04 | CUSHALING PORTLAOISE
TO-25-DLT-CAP1-02 | DALTON CAP1
TO-25-DND-T121-01 | DARNDALE T121
TO-25-DRY-OBE-1-01 | DRYBRIDGE OLDBRIDGE
TO-25-FIN-110K1-2-02 | FINGLAS 110K1-2
TO-25-FIN GIS-T2101-03 | FINGLAS GIS T2101
TO-25-FIN-SHL-1-07 | FINGLAS SHELLYBANKS
TO-25-110 kV A1 @ FLA-01 | FLAGFORD 110 kV A1
TO-25-110 kV B1 @ FLA-01 | FLAGFORD 110 kV B1
TO-25-FLA-SLB-1-03 | FLAGFORD SLIABH BAWN
TO-25-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-25-GI-T141-01 | GREAT ISLAND T141
TO-25-IKE,T-THU-1-05 | IKERRIN tee THURLES
TO-25-INC-220K1-2-01 | INCHICORE 220K1-2
TO-25-KYT-T232-02 | KELLYSTOWN T232
TO-25-KBY-MR-1-03 | KILBARRY MARINA 1
TO-25-KBY-MR-2-03 | KILBARRY MARINA 2
TO-25-KTN-110SA1-01 | KILLOTERAN 110SA1
TO-25-KTN-110SA2-01 | KILLOTERAN 110SA2
TO-25-KTN-T102-01 | KILLOTERAN T102
TO-25-KTN-WAT-1-03 | KILLOTERAN WATERFORD
TO-25-KPG-TRL-2-02 | KILPADDOGE TRALEE 2
TO-25-220 kV A4 @ KRA-01 | KNOCKRAHA 220 kV A4
TO-25-220 kV B4 @ KRA-01 | KNOCKRAHA 220 kV B4
TO-25-KRA-220K4-01 | KNOCKRAHA 220K4
TO-25-KRA-220SA2-4CB-02 | KNOCKRAHA 220SA2-4CB
TO-25-KRA-220SB2-4CB-02 | KNOCKRAHA 220SB2-4CB
TO-25-LET-PST-01 | LETTERKENNY STRABANE PST
TO-25-LOU-CAP1-02 | LOUTH CAP1
TO-25-MUL-CAP2-01 | MULLINGAR CAP2
TO-25-NAV-T142-01 | NAVAN T142
TO-25-PB-R2001-01 | POOLBEG R2001
TO-25-RTH-T133-01 | RATHNASKILLOGE T133
TO-25-220 kV A2 @ SH-02 | SHANNONBRIDGE 220 kV A2
TO-25-220 kV B2 @ SH-02 | SHANNONBRIDGE 220 kV B2
TO-25-TB-T2003-01 | TARBERT T2003
TO-25-TB-T2004-01 | TARBERT T2004