## Wks 22 - 23
Report covers outages commencing/returning/spanning the period: 26/05/2025 - 08/06/2025
Outages commencing/returning in Week 22
OUTAGE ID | PLANT |  | Week 22 | [6 empty] | Week 23
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
TO-25-DEY-T134-02 | DERRYCARNEY T134
TO-25-220 kV A2 @ CDU-02 | CORDUFF 220 kV A2
TO-25-220 kV A4 @ CDU-02 | CORDUFF 220 kV A4
TO-25-220 kV B2 @ CDU-02 | CORDUFF 220 kV B2
TO-25-220 kV B4 @ CDU-02 | CORDUFF 220 kV B4
TO-25-KPG-T2102-02 | KILPADDOGE T2102
TO-25-KTL-CAP1-01 | KILTEEL CAP1
TO-25-LIM-MTN-1-03 | LIMERICK MONETEEN
TO-25-CSH-CLN-1-03 | CASHLA CLOON | bar: Week 22 Sa 31 to Week 23 Fr 6
TO-25-BGH-110SA1-01 | BOGGERAGH 110SA1 | bar: Week 22 Sa 31 to Week 23 Mo 9
TO-25-BGH-110SA2-01 | BOGGERAGH 110SA2 | bar: Week 22 Sa 31 to Week 23 Mo 9
TO-25-BGH-CLA-1-01 | BOGGERAGH CLASHAVOON | bar: Week 22 Sa 31 to Week 23 Mo 9
TO-25-BGH-T121-02 | BOGGERAGH T121 | bar: Week 22 Sa 31 to Week 23 Mo 9
TO-25-BGH-T132-01 | BOGGERAGH T132 | bar: Week 22 Sa 31 to Week 23 Mo 9
TO-25-BGH-T142-01 | BOGGERAGH T142 | bar: Week 22 Sa 31 to Week 23 Mo 9
TO-25-BUT-KTN-1-04 | BUTLERSTOWN KILLOTERAN | bar: Week 22 Sa 31 to Week 23 Mo 9
TO-25-110 kV A1 @ CLA-02 | CLASHAVOON 110 kV A1 | bar: Week 22 Sa 31 to Week 23 Mo 9
TO-25-110 kV B1 @ CLA-02 | CLASHAVOON 110 kV B1 | bar: Week 22 Sa 31 to Week 23 Mo 9
TO-25-KTN-110SA1-02 | KILLOTERAN 110SA1 | bar: Week 22 Sa 31 to Week 23 Mo 9
TO-25-KTN-110SA2-02 | KILLOTERAN 110SA2 | bar: Week 22 Sa 31 to Week 23 Mo 9
TO-25-KTN-T101-01 | KILLOTERAN T101 | bar: Week 22 Sa 31 to Week 23 Mo 9
TO-25-SH-220K1-2-01 | SHANNONBRIDGE 220K1-2
TO-25-220 kV A1 @ WOO-04 | WOODLAND 220 kV A1
TO-25-WOO-T4201-05 | WOODLAND T4201
TO-25-110 kV A1 @ CSH-08 | CASHLA 110 kV A1 | bar: Week 22 Sa 31 to Week 23 Sa 7
TO-25-110 kV B1 @ CSH-06 | CASHLA 110 kV B1 | bar: Week 22 Sa 31 to Week 23 Sa 7
TO-25-DDK-110SA1-01 | DUNDALK 110SA1 | bar: Su 25
TO-25-DDK-110SA2-02 | DUNDALK 110SA2 | bar: Su 25
TO-25-DDK-MLN-1-01 | DUNDALK MULLAGHARLIN | bar: Su 25
TO-25-DDK-T141-01 | DUNDALK T141 | bar: Su 25
TO-25-SH-T2101-03 | SHANNONBRIDGE T2101 | bar: Su 25
TO-25-TTU-131-03 | TULLABEG T131
TO-25-DDK-110SA1-02 | DUNDALK 110SA1 | bar: Week 22 Sa 31 to Week 23 Fr 6
TO-25-DDK-110SA2-01 | DUNDALK 110SA2 | bar: Week 22 Sa 31 to Week 23 Fr 6
TO-25-DDK-LOU-1-03 | DUNDALK LOUTH | bar: Week 22 Sa 31 to Week 23 Fr 6
TO-25-DDK-T142-01 | DUNDALK T142 | bar: Week 22 Sa 31 to Week 23 Fr 6
TO-25-220 kV A2 @ SH-02 | SHANNONBRIDGE 220 kV A2 | bar: Su 25
TO-25-220 kV B2 @ SH-02 | SHANNONBRIDGE 220 kV B2 | bar: Su 25
TO-25-AUG-CFM-2-01 | AUGHINISH CASTLEFARM 2 | bar: Su 25
TO-25-BRT-T224-01 | BRACETOWN T224 | bar: Su 25
TO-25-CFM-T102-01 | CASTLEFARM T102 | bar: Su 25
TO-25-110 kV A2 @ CLO-01 | CLOGHER 110 kV A2 | bar: Su 25
TO-25-110 kV B2 @ CLO-01 | CLOGHER 110 kV B2 | bar: Su 25
TO-25-CRA-LWD-1-05 | CRANE LODGEWOOD | bar: Su 25
TO-25-GOL-T101-01 | GOLAGH T101 | bar: Su 25
TO-25-GOL,T-CLO-1-01 | GOLAGH tee CLOGHER | bar: Su 25
TO-25-GOL,T-GOL-1-01 | GOLAGH tee GOLAGH | bar: Su 25
TO-25-GOL,T-LET-1-01 | GOLAGH tee LETTERKENNY | bar: Su 25
TO-25-GOR-MTH-1-01 | GORMAN MEATH HILL | bar: Su 25
TO-25-NAV-T142-01 | NAVAN T142 | bar: Su 25
TO-25-RYB GIS-T105-01 | RYEBROOK GIS T105 | bar: Su 25
TO-25-WEX-110SA1-2CB-01 | WEXFORD 110SA1-2CB | bar: Su 25
TO-25-WEX-CAP2-01 | WEXFORD CAP2 | bar: Su 25
TO-25-WEX-CAP4-01 | WEXFORD CAP4 | bar: Su 25
TO-25-WEX-T122-01 | WEXFORD T122 | bar: Su 25
TO-25-WEX-T142-01 | WEXFORD T142 | bar: Su 25
Report covers outages commencing/returning/spanning the period: 26/05/2025 - 08/06/2025
Outages commencing/returning in Week 23
OUTAGE ID | PLANT | Week 22 Mo 26: Week 22; Week 23 Mo 2: Week 23
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
TO-25-WOO-T4202-02 | WOODLAND T4202 | bar: Week 23 Tu 3
TO-25-BLU-MUL-1-01 | BLUNDELSTOWN MULLINGAR | bar: Week 23 Tu 3
TO-25-MUL-110SA1-2CB-02 | MULLINGAR 110SA1-2CB | bar: Week 23 Tu 3
TO-25-MUL-CAP2-02 | MULLINGAR CAP2 | bar: Week 23 Tu 3
TO-25-MUL-T102-01 | MULLINGAR T102 | bar: Week 23 Tu 3
TO-25-MUL-T142-01 | MULLINGAR T142 | bar: Week 23 Tu 3
TO-25-CDK-LWD-1-02 | CASTLEDOCKRELL LODGEWOOD | bar: Week 23 Tu 3
TO-25-CDK-T121-02 | CASTLEDOCKRELL T121 | bar: Week 23 Tu 3
TO-25-GOR-NAV-3-01 | GORMAN NAVAN 3 | bar: Week 23 Tu 3
TO-25-CSH-GAL GIS-2-01 | CASHLA GALWAY GIS 2 | bar: Week 23 Tu 3; Week 23 Sa 7 to Week 23 Mo 9
TO-25-110 kV A1 @ CLO-02 | CLOGHER 110 kV A1 | bar: Week 23 Tu 3; Week 23 Sa 7 to Week 23 Mo 9
TO-25-110 kV B1 @ CLO-02 | CLOGHER 110 kV B1 | bar: Week 23 Tu 3; Week 23 Sa 7 to Week 23 Mo 9
TO-25-CLO-DRM-1-01 | CLOGHER DRUMKEEN | bar: Week 23 Tu 3; Week 23 Sa 7 to Week 23 Mo 9
TO-25-DRM-110SA1-01 | DRUMKEEN 110SA1 | bar: Week 23 Tu 3; Week 23 Sa 7 to Week 23 Mo 9
TO-25-DRM-110SA2-01 | DRUMKEEN 110SA2 | bar: Week 23 Tu 3; Week 23 Sa 7 to Week 23 Mo 9
TO-25-DRM-LET-1-01 | DRUMKEEN LETTERKENNY | bar: Week 23 Tu 3; Week 23 Sa 7 to Week 23 Mo 9
TO-25-220 kV A2 @ GOR-01 | GORMAN 220 kV A2 | bar: Week 23 Tu 3; Week 23 Sa 7 to Week 23 Mo 9
TO-25-220 kV B2 @ GOR-01 | GORMAN 220 kV B2 | bar: Week 23 Tu 3; Week 23 Sa 7 to Week 23 Mo 9
TO-25-GOR-LOU-1-02 | GORMAN LOUTH | bar: Week 23 Tu 3; Week 23 Sa 7 to Week 23 Mo 9
TO-25-220 kV A2 @ LOU-09 | LOUTH 220 kV A2 | bar: Week 23 Tu 3; Week 23 Sa 7 to Week 23 Mo 9
TO-25-220 kV B2 @ LOU-09 | LOUTH 220 kV B2 | bar: Week 23 Tu 3; Week 23 Sa 7 to Week 23 Mo 9
TO-25-OUG-T141-01 | OUGHTRAGH T141 | bar: Week 23 Tu 3; Week 23 Sa 7 to Week 23 Mo 9
TO-25-OUG,T-OUG-1-01 | OUGHTRAGH tee OUGHTRAGH | bar: Week 23 Tu 3; Week 23 Sa 7 to Week 23 Mo 9
TO-25-OUG,T-TRL-1-04 | OUGHTRAGH tee TRALEE | bar: Week 23 Tu 3; Week 23 Sa 7 to Week 23 Mo 9
TO-25-110 kV A3 @ RYB GIS-01 | RYEBROOK GIS 110 kV A3 | bar: Week 23 Tu 3; Week 23 Sa 7 to Week 23 Mo 9
TO-25-110 kV B3 @ RYB GIS-01 | RYEBROOK GIS 110 kV B3 | bar: Week 23 Tu 3; Week 23 Sa 7 to Week 23 Mo 9
TO-25-RYB GIS-110K3-02 | RYEBROOK GIS 110K3 | bar: Week 23 Tu 3; Week 23 Sa 7 to Week 23 Mo 9
TO-25-RYB GIS-110SA1-3CB-02 | RYEBROOK GIS 110SA1-3CB | bar: Week 23 Tu 3; Week 23 Sa 7 to Week 23 Mo 9
TO-25-RYB GIS-110SB1-3CB-03 | RYEBROOK GIS 110SB1-3CB | bar: Week 23 Tu 3; Week 23 Sa 7 to Week 23 Mo 9
TO-25-RYB GIS-T106-01 | RYEBROOK GIS T106 | bar: Week 23 Tu 3; Week 23 Sa 7 to Week 23 Mo 9
TO-25-220 kV A2 @ WOO-05 | WOODLAND 220 kV A2 | bar: Week 23 Tu 3; Week 23 Sa 7 to Week 23 Mo 9
TO-25-WOO-220K1-2-02 | WOODLAND 220K1-2 | bar: Week 23 Tu 3; Week 23 Sa 7 to Week 23 Mo 9
TO-25-CHA-GLE-1-01 | CHARLEVILLE GLENLARA | bar: Su 25 to Week 23 Tu 3
TO-25-KIN-T1/T2-02 | KINNEGAD RHODE T1/T2 | bar: Su 25 to Week 23 Tu 3
TO-25-110 kV A1 @ ARK-01 | ARKLOW 110 kV A1 | bar: Week 23 Sa 7 to Week 23 Mo 9
TO-25-110 kV B1 @ ARK-01 | ARKLOW 110 kV B1 | bar: Week 23 Sa 7 to Week 23 Mo 9
TO-25-220 kV A1 @ ARK-02 | ARKLOW 220 kV A1 | bar: Week 23 Sa 7 to Week 23 Mo 9
TO-25-220 kV B1 @ ARK-02 | ARKLOW 220 kV B1 | bar: Week 23 Sa 7 to Week 23 Mo 9
TO-25-ARK-T2101-01 | ARKLOW T2101 | bar: Week 23 Sa 7 to Week 23 Mo 9
TO-25-BRT-CLE-2-01 | BRACETOWN CLONEE 2 | bar: Week 23 Sa 7 to Week 23 Mo 9
TO-25-220 kV A1 @ CLE-02 | CLONEE 220 kV A1 | bar: Week 23 Sa 7 to Week 23 Mo 9
TO-25-220 kV B1 @ CLE-02 | CLONEE 220 kV B1 | bar: Week 23 Sa 7 to Week 23 Mo 9
TO-25-CLE-220K1-02 | CLONEE 220K1 | bar: Week 23 Sa 7 to Week 23 Mo 9
TO-25-CLE-220SA1-2CB-03 | CLONEE 220SA1-2CB | bar: Week 23 Sa 7 to Week 23 Mo 9
TO-25-CLE-220SB1-2CB-03 | CLONEE 220SB1-2CB | bar: Week 23 Sa 7 to Week 23 Mo 9
TO-25-IA-T101-02 | INNISCARRA T101 | bar: Week 23 Sa 7 to Week 23 Mo 9
TO-25-MOY-CAP1-01 | MOY CAP1 | bar: Week 23 Sa 7 to Week 23 Mo 9
TO-25-DRY-OBE-1-01 | DRYBRIDGE OLDBRIDGE | bar: Su 25 to Week 23 Tu 3
TO-25-KLN-LIM-1-03 | KILLONAN LIMERICK 1 | bar: Su 25 to Week 23 Tu 3
TO-25-220 kV A4 @ KRA-01 | KNOCKRAHA 220 kV A4 | bar: Su 25 to Week 23 Tu 3
TO-25-220 kV B4 @ KRA-01 | KNOCKRAHA 220 kV B4 | bar: Su 25 to Week 23 Tu 3
TO-25-KRA-220K4-01 | KNOCKRAHA 220K4 | bar: Su 25 to Week 23 Tu 3
TO-25-KRA-220SA2-4CB-02 | KNOCKRAHA 220SA2-4CB | bar: Su 25 to Week 23 Tu 3
TO-25-KRA-220SB2-4CB-02 | KNOCKRAHA 220SB2-4CB | bar: Su 25 to Week 23 Tu 3
Outages spanning Weeks 22-23
OUTAGE ID | PLANT | Week 22 Mo 26: Week 22; Week 23 Mo 2: Week 23
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
TO-25-AA GIS-T102-02 | ARDNACRUSHA GIS T102
Report covers outages commencing/returning/spanning the period: 26/05/2025 - 08/06/2025
Outages spanning Weeks 22-23
OUTAGE ID | PLANT | Week 22 Mo 26: Week 22; Week 23 Mo 2: Week 23
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
TO-25-ATH-M/CAP1-06 | ATHLONE M/CAP1
TO-25-BNK-110SA1-2CB-01 | BARNAKYLE 110SA1-2CB
TO-25-BNK-CBT-2-01 | BARNAKYLE CASTLEBAGOT 2
TO-25-BNK-T122-01 | BARNAKYLE T122
TO-25-BIN-T141-01 | BINBANE T141
TO-25-BOT-MLC-1-01 | BOGTOWN MOUNTLUCAS
TO-25-BOT-T132-01 | BOGTOWN T132
TO-25-CAH-110K1-2-01 | CAHIR 110K1-2
TO-25-CD-MAC-1-01 | CARRIGADROHID MACROOM
TO-25-CSH-CAP2-01 | CASHLA CAP2
TO-25-CBR-SVC-01 | CASTLEBAR SVC
TO-25-CVW-COW-1-05 | CASTLEVIEW COW CROSS
TO-25-CF-SRA-2-01 | CATHALEENS FALL SRANANAGH 2
TO-25-CRA-WEX-1-02 | CRANE WEXFORD
TO-25-CUS-PLS-1-04 | CUSHALING PORTLAOISE
TO-25-CUS-PLS-1-01
TO-25-DND-T121-01 | DARNDALE T121
TO-25-110 kV A1/A2/A3 @ FIN-01 | FINGLAS 110 kV A1/A2/A3
TO-25-FIN-110K1-2-02 | FINGLAS 110K1-2
TO-25-FIN-110K2-3-04 | FINGLAS 110K2-3
TO-25-220 kV A2 @ FIN-08 | FINGLAS 220 kV A2
TO-25-220 kV B2 @ FIN-05 | FINGLAS 220 kV B2
TO-25-FIN-220K2-10 | FINGLAS 220K2
TO-25-FIN-220SA1-2CB-14 | FINGLAS 220SA1-2CB
TO-25-FIN-220SB1-2CB-11 | FINGLAS 220SB1-2CB
TO-25-FIN-FIN GIS-1-02 | FINGLAS FINGLAS GIS 1
TO-25-FIN-T2104-03 | FINGLAS T2104
TO-25-110 kV A1 @ FLA-01 | FLAGFORD 110 kV A1
TO-25-110 kV B1 @ FLA-01 | FLAGFORD 110 kV B1
TO-25-FLA-SLB-1-03 | FLAGFORD SLIABH BAWN
TO-25-GAL-GAL GIS-1-01 | GALWAY GALWAY GIS 1
TO-25-GAL-T103-01 | GALWAY T103
TO-25-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-25-GI GIS-220SA1-2CB-02 | GREAT ISLAND GIS 220SA1-2CB
TO-25-GI-T141-01 | GREAT ISLAND T141
TO-25-IKE,T-THU-1-05 | IKERRIN tee THURLES
TO-25-INC-220K1-2-01 | INCHICORE 220K1-2
TO-25-KYT-T232-02 | KELLYSTOWN T232
TO-25-KBY-MR-1-03 | KILBARRY MARINA 1
TO-25-KBY-MR-2-03 | KILBARRY MARINA 2
TO-25-KPG-TRL-2-02 | KILPADDOGE TRALEE 2
TO-25-LET-PST-01 | LETTERKENNY STRABANE PST
TO-25-LOU-CAP1-02 | LOUTH CAP1
TO-25-MP GIS-T4001-03 | MONEYPOINT GIS T4001
TO-25-MUL-CAP2-01 | MULLINGAR CAP2
TO-25-NW-PB-1-03 | NORTH WALL POOLBEG
TO-25-PB-R2001-01 | POOLBEG R2001
TO-25-PLS-T141-01 | PORTLAOISE T141
TO-25-TB-T2003-01 | TARBERT T2003
TO-25-TB-T2004-01 | TARBERT T2004