## Wks 28 - 29
Report covers outages commencing/returning/spanning the period: 07/07/2025 - 20/07/2025
Outages commencing/returning in Week 28
OUTAGE ID | PLANT |  | Week 28 | [6 empty] | Week 29
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
TO-25-NW-T2004/5-02 | NORTH WALL T2004/5
TO-25-ENN-SLC-1-01 | ENNIS SLIEVECALLAN
TO-25-SLC-110SA1-01 | SLIEVECALLAN 110SA1
TO-25-SLC-110SA2-01 | SLIEVECALLAN 110SA2
TO-25-SLC-T121-01 | SLIEVECALLAN T121
TO-25-SLC-T122-01 | SLIEVECALLAN T122
TO-25-FLA-T2101-01 | FLAGFORD T2101
TO-25-SLI-SRA-2-05 | SLIGO SRANANAGH 2
TO-25-ARK-110K1-2-01 | ARKLOW 110K1-2
TO-25-ARK-T101-01 | ARKLOW T101
TO-25-ARK-T141-02 | ARKLOW T141
TO-25-CLU-T122-01 | CLUTTERLAND T122
TO-25-KPG-220K3-01 | KILPADDOGE 220K3
TO-25-KPG-220SA1-2CB-01 | KILPADDOGE 220SA1-2CB
TO-25-KPG-220SA1-3CB-01 | KILPADDOGE 220SA1-3CB
TO-25-KPG-220SB1-2CB-01 | KILPADDOGE 220SB1-2CB
TO-25-KPG-220SB1-3CB-01 | KILPADDOGE 220SB1-3CB
TO-25-110 kV A1 @ CSH-07 | CASHLA 110 kV A1
TO-25-110 kV B1 @ CSH-01 | CASHLA 110 kV B1
TO-25-CSH-GAL GIS-1-02 | CASHLA GALWAY GIS 1
TO-25-BIN-TIV-1-01 | BINBANE TIEVEBRACK
TO-25-CD-KBY-1-02 | CARRIGADROHID KILBARRY
TO-25-CD-T103-04 | CARRIGADROHID T103
TO-25-110 kV A1 @ KBY-01 | KILBARRY 110 kV A1
TO-25-110 kV B1 @ KBY-01 | KILBARRY 110 kV B1
TO-25-110 kV A2 @ SH-01 | SHANNONBRIDGE 110 kV A2
TO-25-110 kV B2 @ SH-01 | SHANNONBRIDGE 110 kV B2
TO-25-220 kV A2 @ SH-06 | SHANNONBRIDGE 220 kV A2
TO-25-220 kV B2 @ SH-06 | SHANNONBRIDGE 220 kV B2
TO-25-WEX-110SA1-2CB-02 | WEXFORD 110SA1-2CB
TO-25-WEX-CAP2-02 | WEXFORD CAP2
TO-25-WEX-CAP4-02 | WEXFORD CAP4
TO-25-WEX-T122-02 | WEXFORD T122
TO-25-WEX-T142-02 | WEXFORD T142
TO-25-220 kV A2 @ FIN-09 | FINGLAS 220 kV A2
TO-25-220 kV B2 @ FIN-04 | FINGLAS 220 kV B2
TO-25-FIN-220K2-11 | FINGLAS 220K2
TO-25-FIN-220SA1-2CB-15 | FINGLAS 220SA1-2CB
TO-25-FIN-220SB1-2CB-12 | FINGLAS 220SB1-2CB
TO-25-110 kV A3 @ FIN GIS-02 | FINGLAS GIS 110 kV A3
TO-25-110 kV B3 @ FIN GIS-01 | FINGLAS GIS 110 kV B3
TO-25-FIN GIS-110SA1-3CB-02 | FINGLAS GIS 110SA1-3CB
TO-25-FIN GIS-110SA3-5CB-04 | FINGLAS GIS 110SA3-5CB
TO-25-FIN GIS-110SB1-3CB-02 | FINGLAS GIS 110SB1-3CB
TO-25-FIN GIS-110SB3-5CB-03 | FINGLAS GIS 110SB3-5CB
TO-25-FIN GIS-T2106-02 | FINGLAS GIS T2106
TO-25-LOU-AT3-05 | LOUTH AT3
TO-25-SH-T2102-01 | SHANNONBRIDGE T2102
TO-25-220 kV A1 @ AD-04 | AGHADA 220 kV A1
TO-25-220 kV A2 @ AD-04 | AGHADA 220 kV A2
TO-25-AD-220K1-03 | AGHADA 220K1
TO-25-AD-SA1-2CB-05 | AGHADA 220SA1-2CB
TO-25-KNY-UGL-1-01 | KNOCKRANNY UGGOOL
TO-25-UGL-110SA1-2CB-01 | UGGOOL 110SA1-2CB
TO-25-UGL-T132-01 | UGGOOL T132
TO-25-UGL-T134-01 | UGGOOL T134
TO-25-110 kV A1/A2 @ CLO-01 | CLOGHER 110 kV A1/A2
TO-25-110 kV B1/B2 @ CLO-01 | CLOGHER 110 kV B1/B2
TO-25-CLO-110K1-2-02 | CLOGHER 110K1-2
TO-25-UGL-T131-01 | UGGOOL T131
TO-25-GLR-MOY-1-02 | GLENREE MOY
Report covers outages commencing/returning/spanning the period: 07/07/2025 - 20/07/2025
Outages commencing/returning in Week 28
OUTAGE ID | PLANT | Week 28 Mo 7: Week 28; Week 29 Mo 14: Week 29
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
TO-25-IKE,T-SH-1-05 | IKERRIN tee SHANNONBRIDGE | bar: Week 28 Tu 8 to Week 29 Mo 21
TO-25-IKE-T141-02 | IKERRIN T141 | bar: Su 6 to Week 28 Tu 8
TO-25-IKE,T-IKE-1-02 | IKERRIN tee IKERRIN | bar: Su 6 to Week 28 Tu 8
TO-25-IKE,T-SH-1-02 | IKERRIN tee SHANNONBRIDGE | bar: Su 6 to Week 28 Tu 8
TO-25-IKE,T-THU-1-02 | IKERRIN tee THURLES | bar: Su 6 to Week 28 Tu 8
TO-25-KLS-110K1-2-05 | KELLIS 110K1-2 | bar: Su 6 to Week 28 Tu 8
TO-25-BDN-MRK1-02 | BALLYDINE MRK1 | bar: Week 28 We 9 to Week 29 Mo 21
TO-25-110 kV A1 @ PLS-01 | PORTLAOISE 110 kV A1 | bar: Week 28 We 9 to Week 29 Mo 21
TO-25-PLS-110K1-2-03 | PORTLAOISE 110K1-2 | bar: Week 28 We 9 to Week 29 Mo 21
TO-25-PLS-T141-02 | PORTLAOISE T141 | bar: Week 28 We 9 to Week 29 Mo 21
TO-25-220 kV A1 @ CBT-02 | CASTLEBAGOT 220 kV A1 | bar: Su 6 to Week 28 We 9
TO-25-220 kV B1 @ CBT-03 | CASTLEBAGOT 220 kV B1 | bar: Su 6 to Week 28 We 9
TO-25-CBT-220K1-05 | CASTLEBAGOT 220K1 | bar: Su 6 to Week 28 We 9
TO-25-CBT-220SA1-2CB-03 | CASTLEBAGOT 220SA1-2CB | bar: Su 6 to Week 28 We 9
TO-25-CBT-220SB1-2CB-03 | CASTLEBAGOT 220SB1-2CB | bar: Su 6 to Week 28 We 9
TO-25-110 kV B1 @ AA GIS-01 | ARDNACRUSHA GIS 110 kV B1 | bar: Week 28 Th 10
TO-25-110 kV B3 @ AA GIS-02 | ARDNACRUSHA GIS 110 kV B3 | bar: Week 28 Th 10
TO-25-AA GIS-110K3-02 | ARDNACRUSHA GIS 110K3 | bar: Week 28 Th 10
TO-25-AA GIS-110SB1-2CB-04 | ARDNACRUSHA GIS 110SB1-2CB | bar: Week 28 Th 10
TO-25-AA GIS-110SB1-3CB-02 | ARDNACRUSHA GIS 110SB1-3CB | bar: Week 28 Th 10
TO-25-AA GIS-T103-02 | ARDNACRUSHA GIS T103 | bar: Week 28 Th 10
TO-25-CUS-T101-04 | CUSHALING T101 | bar: Week 28 Th 10 to Week 28 Fr 11
TO-25-220 kV A2 @ CBT-03 | CASTLEBAGOT 220 kV A2 | bar: Week 28 Th 10 to Week 29 Fr 18
TO-25-220 kV B2 @ CBT-03 | CASTLEBAGOT 220 kV B2 | bar: Week 28 Th 10 to Week 29 Fr 18
TO-25-CBT-220K2-03 | CASTLEBAGOT 220K2 | bar: Week 28 Th 10 to Week 29 Fr 18
TO-25-CBT-220SA1-2CB-05 | CASTLEBAGOT 220SA1-2CB | bar: Week 28 Th 10 to Week 29 Fr 18
TO-25-CBT-220SB1-2CB-05 | CASTLEBAGOT 220SB1-2CB | bar: Week 28 Th 10 to Week 29 Fr 18
TO-25-110 kV A3 @ GAL GIS-01 | GALWAY GIS 110 kV A3 | bar: Week 28 Th 10 to Week 29 Fr 18
TO-25-110 kV B3 @ GAL GIS-01 | GALWAY GIS 110 kV B3 | bar: Week 28 Th 10 to Week 29 Fr 18
TO-25-GAL GIS-110K3-01 | GALWAY GIS 110K3 | bar: Week 28 Th 10 to Week 29 Fr 18
TO-25-GAL GIS-110SA1-3CB-01 | GALWAY GIS 110SA1-3CB | bar: Week 28 Th 10 to Week 29 Fr 18
TO-25-GAL GIS-110SB1-3CB-01 | GALWAY GIS 110SB1-3CB | bar: Week 28 Th 10 to Week 29 Fr 18
TO-25-CF-SRA-2-01 | CATHALEENS FALL SRANANAGH 2 | bar: Su 6 to Week 28 Th 10
TO-25-ATH-SH-1-08 | ATHLONE SHANNONBRIDGE | bar: Week 28 Fr 11 to Week 28 Su 13
TO-25-CDY-GRV-1-01 | CORDERRY GARVAGH | bar: Week 28 Fr 11 to Week 29 Fr 18
TO-25-110 kV A1 @ GRV-01 | GARVAGH 110 kV A1 | bar: Week 28 Fr 11 to Week 29 Fr 18
TO-25-110 kV B1 @ GRV-01 | GARVAGH 110 kV B1 | bar: Week 28 Fr 11 to Week 29 Fr 18
TO-25-GRV-110K1-03 | GARVAGH 110K1 | bar: Week 28 Fr 11 to Week 29 Fr 18
TO-25-GRV-T121-02 | GARVAGH T121 | bar: Week 28 Fr 11 to Week 29 Fr 18
TO-25-GRV-T141-01 | GARVAGH T141 | bar: Week 28 Fr 11 to Week 29 Fr 18
TO-25-110 kV A2 @ BVK-01 | BALLYVOUSKILL 110 kV A2 | bar: Su 6 to Week 28 Fr 11
TO-25-110 kV B2 @ BVK-01 | BALLYVOUSKILL 110 kV B2 | bar: Su 6 to Week 28 Fr 11
TO-25-BVK-110K2-02 | BALLYVOUSKILL 110K2 | bar: Su 6 to Week 28 Fr 11
TO-25-BVK-110SA1-2CB-01 | BALLYVOUSKILL 110SA1-2CB | bar: Su 6 to Week 28 Fr 11
TO-25-BVK-110SB1-2CB-01 | BALLYVOUSKILL 110SB1-2CB | bar: Su 6 to Week 28 Fr 11
TO-25-BVK-COT-1-01 | BALLYVOUSKILL COOMATAGGART | bar: Su 6 to Week 28 Fr 11
TO-25-COT-110SA1-01 | COOMATAGGART 110SA1 | bar: Su 6 to Week 28 Fr 11
TO-25-COT-110SA2-01 | COOMATAGGART 110SA2 | bar: Su 6 to Week 28 Fr 11
TO-25-COT-FILTER1-01 | COOMATAGGART FILTER1 | bar: Su 6 to Week 28 Fr 11
TO-25-COT-T132-01 | COOMATAGGART T132 | bar: Su 6 to Week 28 Fr 11
TO-25-COT-T141-01 | COOMATAGGART T141 | bar: Su 6 to Week 28 Fr 11
Outages commencing/returning in Week 29
OUTAGE ID | PLANT | Week 28 Mo 7: Week 28; Week 29 Mo 14: Week 29
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
TO-25-LOU-MTH-1-02 | LOUTH MEATH HILL | bar: Week 29 Mo 14 to Week 29 We 16
TO-25-AUG-SK-3-01 | AUGHINISH SEALROCK 3 | bar: Week 29 Mo 14 to Week 29 Mo 21
TO-25-SK-T103-01 | SEALROCK T103 | bar: Week 29 Mo 14 to Week 29 Mo 21
TO-25-KBY-KRA-2-01 | KILBARRY KNOCKRAHA 2 | bar: Week 29 Tu 15
TO-25-CAH-110K1-2-01 | CAHIR 110K1-2 | bar: Su 6 to Week 29 Tu 15
Report covers outages commencing/returning/spanning the period: 07/07/2025 - 20/07/2025
Outages commencing/returning in Week 29
OUTAGE ID | PLANT | Week 28 Mo 7: Week 28; Week 29 Mo 14: Week 29
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
TO-25-CBA-110SA1-01 | CLOGHBOOLA 110SA1 | bar: Week 29 We 16 to Week 29 Th 17; Week 29 Sa 19 to Week 29 Mo 21
TO-25-CBA-110SA2-01 | CLOGHBOOLA 110SA2 | bar: Week 29 We 16 to Week 29 Th 17; Week 29 Sa 19 to Week 29 Mo 21
TO-25-CBA-T122-01 | CLOGHBOOLA T122 | bar: Week 29 We 16 to Week 29 Th 17; Week 29 Sa 19 to Week 29 Mo 21
TO-25-CBA-T131-01 | CLOGHBOOLA T131 | bar: Week 29 We 16 to Week 29 Th 17; Week 29 Sa 19 to Week 29 Mo 21
TO-25-CBA-TRI-1-01 | CLOGHBOOLA TRIEN | bar: Week 29 We 16 to Week 29 Th 17; Week 29 Sa 19 to Week 29 Mo 21
TO-25-220 kV A1 @ SH-05 | SHANNONBRIDGE 220 kV A1 | bar: Su 6 to Week 29 We 16
TO-25-220 kV B1 @ SH-05 | SHANNONBRIDGE 220 kV B1 | bar: Su 6 to Week 29 We 16
TO-25-CSH-GAL GIS-1-01 | CASHLA GALWAY GIS 1 | bar: Week 29 Th 17
TO-25-220 kV A2 @ KNR-03 | KNOCKANURE 220 kV A2 | bar: Week 29 Th 17; Week 29 Sa 19 to Week 29 Mo 21
TO-25-220 kV B2 @ KNR-03 | KNOCKANURE 220 kV B2 | bar: Week 29 Th 17; Week 29 Sa 19 to Week 29 Mo 21
TO-25-KNR-220K2-01 | KNOCKANURE 220K2 | bar: Week 29 Th 17; Week 29 Sa 19 to Week 29 Mo 21
TO-25-KNR-220SA1-2CB-04 | KNOCKANURE 220SA1-2CB | bar: Week 29 Th 17; Week 29 Sa 19 to Week 29 Mo 21
TO-25-KNR-220SB1-2CB-04 | KNOCKANURE 220SB1-2CB | bar: Week 29 Th 17; Week 29 Sa 19 to Week 29 Mo 21
TO-25-PA-110SA1-02 | POLLAPHUCA 110SA1 | bar: Week 29 Th 17; Week 29 Sa 19 to Week 29 Mo 21
TO-25-PA-110SA2-02 | POLLAPHUCA 110SA2 | bar: Week 29 Th 17; Week 29 Sa 19 to Week 29 Mo 21
TO-25-PA-T101-02 | POLLAPHUCA T101 | bar: Week 29 Th 17; Week 29 Sa 19 to Week 29 Mo 21
TO-25-STR-T141-02 | STRATFORD T141 | bar: Week 29 Th 17; Week 29 Sa 19 to Week 29 Mo 21
TO-25-STR,T-CLW-1-02 | STRATFORD tee CARLOW | bar: Week 29 Th 17; Week 29 Sa 19 to Week 29 Mo 21
TO-25-STR,T-PA-1-02 | STRATFORD tee POLLAPHUCA | bar: Week 29 Th 17; Week 29 Sa 19 to Week 29 Mo 21
TO-25-STR,T-STR-1-02 | STRATFORD tee STRATFORD | bar: Week 29 Th 17; Week 29 Sa 19 to Week 29 Mo 21
TO-25-BWR-CRA-1-01 | BALLYWATER CRANE | bar: Week 29 Sa 19 to Week 29 Mo 21
TO-25-BWR-T124-01 | BALLYWATER T124 | bar: Week 29 Sa 19 to Week 29 Mo 21
TO-25-CRA-110SA1-01 | CRANE 110SA1 | bar: Week 29 Sa 19 to Week 29 Mo 21
TO-25-CRA-110SA2-01 | CRANE 110SA2 | bar: Week 29 Sa 19 to Week 29 Mo 21
TO-25-CRA-LWD-1-01 | CRANE LODGEWOOD | bar: Week 29 Sa 19 to Week 29 Mo 21
TO-25-CRA-T122-01 | CRANE T122 | bar: Week 29 Sa 19 to Week 29 Mo 21
TO-25-CD-MAC-1-01 | CARRIGADROHID MACROOM | bar: Su 6 to Week 29 Th 17
TO-25-GAL-T103-01 | GALWAY T103 | bar: Su 6 to Week 29 Th 17
TO-25-220 kV A1 @ LOU-02 | LOUTH 220 kV A1 | bar: Su 6 to Week 29 Th 17
TO-25-220 kV A2 @ LOU-03 | LOUTH 220 kV A2 | bar: Su 6 to Week 29 Th 17
TO-25-220 kV B1 @ LOU-02 | LOUTH 220 kV B1 | bar: Su 6 to Week 29 Th 17
TO-25-220 kV B2 @ LOU-02 | LOUTH 220 kV B2 | bar: Su 6 to Week 29 Th 17
TO-25-CUS-PLS-1-01 | CUSHALING PORTLAOISE | bar: Su 6 to Week 29 Th 17; Week 29 Sa 19 to Week 29 Su 20
Outages spanning Weeks 28-29
OUTAGE ID | PLANT | Week 28 Mo 7: Week 28; Week 29 Mo 14: Week 29
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
TO-25-AA GIS-T102-02 | ARDNACRUSHA GIS T102
TO-25-ATH-M/CAP1-06 | ATHLONE M/CAP1
TO-25-BIN-T141-01 | BINBANE T141
TO-25-BUT-KTN-1-04 | BUTLERSTOWN KILLOTERAN
TO-25-CSH-CAP2-01 | CASHLA CAP2
TO-25-CBR-SVC-01 | CASTLEBAR SVC
TO-25-CRA-WEX-1-02 | CRANE WEXFORD
TO-25-DND-T121-01 | DARNDALE T121
TO-25-FIN-110K1-2-02 | FINGLAS 110K1-2
TO-25-FIN-110K2-3-04 | FINGLAS 110K2-3
TO-25-GAL-GAL GIS-1-01 | GALWAY GALWAY GIS 1
TO-25-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-25-GI GIS-220SA1-2CB-02 | GREAT ISLAND GIS 220SA1-2CB
TO-25-GI-T141-01 | GREAT ISLAND T141
TO-25-INC-220K1-2-01 | INCHICORE 220K1-2
TO-25-KYT-T232-02 | KELLYSTOWN T232
TO-25-KBY-MR-1-03 | KILBARRY MARINA 1
TO-25-KBY-MR-2-03 | KILBARRY MARINA 2
TO-25-KTN-110SA1-02 | KILLOTERAN 110SA1
TO-25-KTN-110SA2-02 | KILLOTERAN 110SA2
TO-25-KTN-T101-01 | KILLOTERAN T101
TO-25-KPG-TRL-2-02 | KILPADDOGE TRALEE 2
TO-25-LET-PST-01 | LETTERKENNY STRABANE PST
Report covers outages commencing/returning/spanning the period: 07/07/2025 - 20/07/2025
Outages spanning Weeks 28-29
OUTAGE ID | PLANT | Week 28 Mo 7: Week 28; Week 29 Mo 14: Week 29
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
TO-25-LOU-AT3-02 | LOUTH AT3
TO-25-LOU-CAP1-02 | LOUTH CAP1
TO-25-220 kV B2 @ MAY-01 | MAYNOOTH 220 kV B2
TO-25-MAY-SH-1-03 | MAYNOOTH SHANNONBRIDGE
TO-25-MTN-MUN-1-02 | MONETEEN MUNGRET 1
TO-25-MP GIS-T4001-03 | MONEYPOINT GIS T4001
TO-25-MUL-CAP2-01 | MULLINGAR CAP2
TO-25-NW-PB-1-03 | NORTH WALL POOLBEG
TO-25-OBE-PLA-1-02 | OLDBRIDGE PLATIN
TO-25-PB-R2001-01 | POOLBEG R2001
TO-25-SH-T102/4-01 | SHANNONBRIDGE T102/4
TO-25-TB-T2003-01 | TARBERT T2003
TO-25-TB-T2004-01 | TARBERT T2004
TO-25-WEX-CAP4-04 | WEXFORD CAP4