## Wks 30 - 31
Report covers outages commencing/returning/spanning the period: 21/07/2025 - 03/08/2025
Outages commencing/returning in Week 30
OUTAGE ID | PLANT |  | Week 30 | [6 empty] | Week 31
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4
TO-25-ATY-T102-03 | ATHY T102
TO-25-DEY-T132-02 | DERRYCARNEY T132
TO-25-CRU-T221-01 | CRUISERATH T221
TO-25-KLH-KNY-1-01 | KNOCKALOUGH KNOCKRANNY
TO-25-KLH-T121-01 | KNOCKALOUGH T121
TO-25-ATY-T102-02 | ATHY T102
TO-25-110 kV A2 @ RAF-02 | RAFFEEN 110 kV A2
TO-25-110 kV B2 @ RAF-02 | RAFFEEN 110 kV B2
TO-25-BAN-110SA1-03 | BANDON 110SA1
TO-25-BAN-110SA2-04 | BANDON 110SA2
TO-25-BAN-BRI-2-02 | BANDON BRINNY 2
TO-25-BAN-RAF-1-04 | BANDON RAFFEEN
TO-25-BAN-T142-01 | BANDON T142
TO-25-BOL-ENN-1-01 | BOOLTIAGH ENNIS
TO-25-BRI-T102-01 | BRINNY T102
TO-25-KDN-T131-01 | KNOCKDRIN T131
TO-25-KDN,T-KDN-1-01 | KNOCKDRIN tee KNOCKDRIN
TO-25-KDN,T-TSB-1-01 | KNOCKDRIN tee THORNSBERRY
TO-25-KDN,T-TEN-1-02 | KNOCKDRIN tee TIMAHOE
TO-25-SH-T101/3-01 | SHANNONBRIDGE T101/3
TO-25-CBT-220K1-03 | CASTLEBAGOT 220K1
TO-25-KPG-T2101-01 | KILPADDOGE T2101
TO-25-ROP-T131-02 | ROSSPILE T131
TO-25-220 kV A1 @ CBT-01 | CASTLEBAGOT 220 kV A1
TO-25-220 kV A2 @ CBT-01 | CASTLEBAGOT 220 kV A2
TO-25-CBT-220K2-01 | CASTLEBAGOT 220K2
TO-25-CBT-220SA1-2CB-02 | CASTLEBAGOT 220SA1-2CB
TO-25-CSH-PRO-1-05 | CASHLA PROSPECT
TO-25-220 kV A1 @ MP GIS-02 | MONEYPOINT GIS 220 kV A1
TO-25-220 kV B1 @ MP GIS-02 | MONEYPOINT GIS 220 kV B1
TO-25-MP GIS-220K1-02 | MONEYPOINT GIS 220K1
TO-25-MP GIS-220SA1-2CB-04 | MONEYPOINT GIS 220SA1-2CB
TO-25-MP GIS-220SB1-2CB-04 | MONEYPOINT GIS 220SB1-2CB
TO-25-MP GIS-PRO-1-01 | MONEYPOINT GIS PROSPECT
TO-25-PRO-TB-1-02 | PROSPECT TARBERT
TO-25-220 kV A2 @ TB-04 | TARBERT 220 kV A2
TO-25-220 kV B2 @ TB-04 | TARBERT 220 kV B2
TO-25-CKN-110SA1-2CB-01 | CLONKEEN 110SA1-2CB
TO-25-CKN-CGL-1-01 | CLONKEEN COOMAGEARLAHY
TO-25-CGL-110SA1-01 | COOMAGEARLAHY 110SA1
TO-25-CGL-110SA2-01 | COOMAGEARLAHY 110SA2
TO-25-CGL-GAE-1-01 | COOMAGEARLAHY GLANLEE
TO-25-CGL-T121-01 | COOMAGEARLAHY T121
TO-25-CGL-T122-01 | COOMAGEARLAHY T122
TO-25-GAE-T121-01 | GLANLEE T121
TO-25-220 kV A1 @ RAF-02 | RAFFEEN 220 kV A1
TO-25-220 kV A2 @ RAF-01 | RAFFEEN 220 kV A2
TO-25-220 kV B1 @ RAF-02 | RAFFEEN 220 kV B1
TO-25-220 kV B2 @ RAF-01 | RAFFEEN 220 kV B2
TO-25-RAF-220K1-2-01 | RAFFEEN 220K1-2
TO-25-ATY-PLS-1-02 | ATHY PORTLAOISE
TO-25-110 kV B1 @ LOU-06 | LOUTH 110 kV B1
TO-25-LOU-110K1-2-04 | LOUTH 110K1-2
TO-25-110 kV A1 @ SRA-02 | SRANANAGH 110 kV A1
TO-25-110 kV B1 @ SRA-01 | SRANANAGH 110 kV B1
TO-25-110 kV B1 @ SNU-01 | SNUGBOROUGH 110 kV B1
TO-25-110 kV B2 @ SNU-01 | SNUGBOROUGH 110 kV B2
TO-25-SNU-110K1-01 | SNUGBOROUGH 110K1
TO-25-SNU-110K2-01 | SNUGBOROUGH 110K2
TO-25-SNU-110SB1-2CB-01 | SNUGBOROUGH 110SB1-2CB
TO-25-SLI-110SA1-2CB-02 | SLIGO 110SA1-2CB
Report covers outages commencing/returning/spanning the period: 21/07/2025 - 03/08/2025
Outages commencing/returning in Week 30
OUTAGE ID | PLANT | Week 30 Mo 21: Week 30; Week 31 Mo 28: Week 31
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4
TO-25-SLI-CAP1-01 | SLIGO CAP1 | bar: Week 30 We 23 to Week 31 Mo 4
TO-25-SLI-SRA-1-02 | SLIGO SRANANAGH 1 | bar: Week 30 We 23 to Week 31 Mo 4
TO-25-SLI-T141-02 | SLIGO T141 | bar: Week 30 We 23 to Week 31 Mo 4
TO-25-220 kV A2 @ KNR-03 | KNOCKANURE 220 kV A2 | bar: Su 20 to Week 30 We 23
TO-25-220 kV B2 @ KNR-03 | KNOCKANURE 220 kV B2 | bar: Su 20 to Week 30 We 23
TO-25-KNR-220K2-01 | KNOCKANURE 220K2 | bar: Su 20 to Week 30 We 23
TO-25-KNR-220SA1-2CB-04 | KNOCKANURE 220SA1-2CB | bar: Su 20 to Week 30 We 23
TO-25-KNR-220SB1-2CB-04 | KNOCKANURE 220SB1-2CB | bar: Su 20 to Week 30 We 23
TO-25-220 kV B1 @ TH-02 | TURLOUGH HILL 220 kV B1 | bar: Week 30 Th 24
TO-25-TH-T2001/2-03 | TURLOUGH HILL T2001/2 | bar: Week 30 Th 24
TO-25-TH-T2003/4-03 | TURLOUGH HILL T2003/4 | bar: Week 30 Th 24
TO-25-CSH-GAL GIS-1-01 | CASHLA GALWAY GIS 1 | bar: Week 30 Th 24 to Week 30 Fr 25
TO-25-CF-CLO-2-06 | CATHALEENS FALL CLOGHER 2 | bar: Week 30 Th 24 to Week 30 Fr 25
TO-25-110 kV A3 @ GAL GIS-02 | GALWAY GIS 110 kV A3 | bar: Week 30 Th 24 to Week 30 Fr 25
TO-25-110 kV B3 @ GAL GIS-02 | GALWAY GIS 110 kV B3 | bar: Week 30 Th 24 to Week 30 Fr 25
TO-25-GAL GIS-110K3-03 | GALWAY GIS 110K3 | bar: Week 30 Th 24 to Week 30 Fr 25
TO-25-GAL GIS-110SA1-3CB-03 | GALWAY GIS 110SA1-3CB | bar: Week 30 Th 24 to Week 30 Fr 25
TO-25-GAL GIS-110SB1-3CB-03 | GALWAY GIS 110SB1-3CB | bar: Week 30 Th 24 to Week 30 Fr 25
TO-25-GAL-T103-01 | GALWAY T103 | bar: Su 20 to Week 30 Fr 25
Outages commencing/returning in Week 31
OUTAGE ID | PLANT | Week 30 Mo 21: Week 30; Week 31 Mo 28: Week 31
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4
TO-25-CRU-T223-01 | CRUISERATH T223 | bar: Week 31 Mo 28 to Week 31 We 30
TO-25-MTN-MUN-1-01 | MONETEEN MUNGRET 1 | bar: Week 31 Mo 28 to Week 31 We 30
TO-25-MUN-T101-01 | MUNGRET T101 | bar: Week 31 Mo 28 to Week 31 We 30
TO-25-LIS-T142-01 | LISDRUM T142 | bar: Week 31 Mo 28 to Week 31 We 30; Week 31 Sa 2 to Week 31 Mo 4
TO-25-CUS-T103/5-01 | CUSHALING T103/5 | bar: Week 31 Tu 29 to Week 31 We 30; Week 31 Sa 2 to Week 31 Mo 4
TO-25-400 kV A1 @ WOO-03 | WOODLAND 400 kV A1 | bar: Week 31 Tu 29 to Week 31 We 30; Week 31 Sa 2 to Week 31 Mo 4
TO-25-400 kV A2 @ WOO-01 | WOODLAND 400 kV A2 | bar: Week 31 Tu 29 to Week 31 We 30; Week 31 Sa 2 to Week 31 Mo 4
TO-25-400 kV B1 @ WOO-03 | WOODLAND 400 kV B1 | bar: Week 31 Tu 29 to Week 31 We 30; Week 31 Sa 2 to Week 31 Mo 4
TO-25-400 kV B2 @ WOO-02 | WOODLAND 400 kV B2 | bar: Week 31 Tu 29 to Week 31 We 30; Week 31 Sa 2 to Week 31 Mo 4
TO-25-WOO-400K1-2-03 | WOODLAND 400K1-2 | bar: Week 31 Tu 29 to Week 31 We 30; Week 31 Sa 2 to Week 31 Mo 4
TO-25-AUG-SK-3-01 | AUGHINISH SEALROCK 3 | bar: Su 20 to Week 31 Tu 29
TO-25-BDN-MRK1-02 | BALLYDINE MRK1 | bar: Su 20 to Week 31 Tu 29
TO-25-110 kV A1 @ PLS-01 | PORTLAOISE 110 kV A1 | bar: Su 20 to Week 31 Tu 29
TO-25-PLS-110K1-2-03 | PORTLAOISE 110K1-2 | bar: Su 20 to Week 31 Tu 29
TO-25-SK-T103-01 | SEALROCK T103 | bar: Su 20 to Week 31 Tu 29
TO-25-DFR-T122-01 | DUNFIRTH T122 | bar: Week 31 We 30; Week 31 Sa 2 to Week 31 Mo 4
TO-25-DFR,T-DFR-1-03 | DUNFIRTH tee DUNFIRTH | bar: Week 31 We 30; Week 31 Sa 2 to Week 31 Mo 4
TO-25-DFR,T-KIN-1-03 | DUNFIRTH tee KINNEGAD | bar: Week 31 We 30; Week 31 Sa 2 to Week 31 Mo 4
TO-25-DFR,T-RNW-1-02 | DUNFIRTH tee RINAWADE | bar: Week 31 We 30; Week 31 Sa 2 to Week 31 Mo 4
TO-25-110 kV A2 @ MAY-01 | MAYNOOTH 110 kV A2 | bar: Week 31 We 30; Week 31 Sa 2 to Week 31 Mo 4
TO-25-110 kV A3 @ MAY-01 | MAYNOOTH 110 kV A3 | bar: Week 31 We 30; Week 31 Sa 2 to Week 31 Mo 4
TO-25-110 kV B2 @ MAY-01 | MAYNOOTH 110 kV B2 | bar: Week 31 We 30; Week 31 Sa 2 to Week 31 Mo 4
TO-25-110 kV B3 @ MAY-01 | MAYNOOTH 110 kV B3 | bar: Week 31 We 30; Week 31 Sa 2 to Week 31 Mo 4
TO-25-MAY-RYB GIS-1-01 | MAYNOOTH RYEBROOK GIS | bar: Week 31 We 30; Week 31 Sa 2 to Week 31 Mo 4
TO-25-110 kV A1 @ RYB GIS-01 | RYEBROOK GIS 110 kV A1 | bar: Week 31 We 30; Week 31 Sa 2 to Week 31 Mo 4
TO-25-110 kV B1 @ RYB GIS-01 | RYEBROOK GIS 110 kV B1 | bar: Week 31 We 30; Week 31 Sa 2 to Week 31 Mo 4
TO-25-RYB GIS-110SA1-2CB-02 | RYEBROOK GIS 110SA1-2CB | bar: Week 31 We 30; Week 31 Sa 2 to Week 31 Mo 4
TO-25-RYB GIS-110SA1-3CB-03 | RYEBROOK GIS 110SA1-3CB | bar: Week 31 We 30; Week 31 Sa 2 to Week 31 Mo 4
TO-25-RYB GIS-110SB1-2CB-02 | RYEBROOK GIS 110SB1-2CB | bar: Week 31 We 30; Week 31 Sa 2 to Week 31 Mo 4
TO-25-RYB GIS-110SB1-3CB-02 | RYEBROOK GIS 110SB1-3CB | bar: Week 31 We 30; Week 31 Sa 2 to Week 31 Mo 4
TO-25-MP GIS-T4001-03 | MONEYPOINT GIS T4001 | bar: Su 20 to Week 31 We 30
TO-25-DSN-400K1-2-01 | DUNSTOWN 400K1-2
TO-25-220 kV B1 @ KNR-01 | KNOCKANURE 220 kV B1 | bar: Week 31 Sa 2 to Week 31 Mo 4
TO-25-220 kV B2 @ KNR-04 | KNOCKANURE 220 kV B2 | bar: Week 31 Sa 2 to Week 31 Mo 4
TO-25-KNR-220K1-02 | KNOCKANURE 220K1 | bar: Week 31 Sa 2 to Week 31 Mo 4
TO-25-KNR-220K2-05 | KNOCKANURE 220K2 | bar: Week 31 Sa 2 to Week 31 Mo 4
TO-25-KNR-220SB1-2CB-01 | KNOCKANURE 220SB1-2CB | bar: Week 31 Sa 2 to Week 31 Mo 4
Report covers outages commencing/returning/spanning the period: 21/07/2025 - 03/08/2025
Outages commencing/returning in Week 31
OUTAGE ID | PLANT | Week 30 Mo 21: Week 30; Week 31 Mo 28: Week 31
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4
TO-25-CKN-GRO-1-01 | CLONKEEN GARROW
TO-25-PA-110SA1-02 | POLLAPHUCA 110SA1
TO-25-PA-110SA2-02 | POLLAPHUCA 110SA2
TO-25-PA-T101-02 | POLLAPHUCA T101
TO-25-STR-T141-02 | STRATFORD T141
TO-25-STR,T-CLW-1-02 | STRATFORD tee CARLOW
TO-25-STR,T-PA-1-02 | STRATFORD tee POLLAPHUCA
TO-25-STR,T-STR-1-02 | STRATFORD tee STRATFORD
Outages spanning Weeks 30-31
OUTAGE ID | PLANT | Week 30 Mo 21: Week 30; Week 31 Mo 28: Week 31
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4
TO-25-AA GIS-T102-02 | ARDNACRUSHA GIS T102
TO-25-ATH-M/CAP1-06 | ATHLONE M/CAP1
TO-25-BWR-CRA-1-01 | BALLYWATER CRANE
TO-25-BWR-T124-01 | BALLYWATER T124
TO-25-BIN-T141-01 | BINBANE T141
TO-25-BUT-KTN-1-04 | BUTLERSTOWN KILLOTERAN
TO-25-CSH-CAP2-01 | CASHLA CAP2
TO-25-CBR-SVC-01 | CASTLEBAR SVC
TO-25-CF-T104-02 | CATHALEENS FALL T104
TO-25-CRA-110SA1-01 | CRANE 110SA1
TO-25-CRA-110SA2-01 | CRANE 110SA2
TO-25-CRA-LWD-1-01 | CRANE LODGEWOOD
TO-25-CRA-T122-01 | CRANE T122
TO-25-CRA-WEX-1-02 | CRANE WEXFORD
TO-25-DND-T121-01 | DARNDALE T121
TO-25-110 kV B1/B2/B3 @ FIN-01 | FINGLAS 110 kV B1/B2/B3
TO-25-FIN-110K1-2-02 | FINGLAS 110K1-2
TO-25-FIN-110K2-3-04 | FINGLAS 110K2-3
TO-25-FIN-FIN GIS-1-02 | FINGLAS FINGLAS GIS 1
TO-25-FIN-T2103-01 | FINGLAS T2103
TO-25-GAL-GAL GIS-1-01 | GALWAY GALWAY GIS 1
TO-25-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-25-GLR-MOY-1-02 | GLENREE MOY
TO-25-GI GIS-220SA1-2CB-02 | GREAT ISLAND GIS 220SA1-2CB
TO-25-GI-T141-01 | GREAT ISLAND T141
TO-25-IKE,T-SH-1-05 | IKERRIN tee SHANNONBRIDGE
TO-25-INC-220K1-2-01 | INCHICORE 220K1-2
TO-25-KYT-T232-02 | KELLYSTOWN T232
TO-25-KBY-MR-1-03 | KILBARRY MARINA 1
TO-25-KBY-MR-2-03 | KILBARRY MARINA 2
TO-25-KTN-110SA1-02 | KILLOTERAN 110SA1
TO-25-KTN-110SA2-02 | KILLOTERAN 110SA2
TO-25-KTN-T101-01 | KILLOTERAN T101
TO-25-KPG-TRL-2-02 | KILPADDOGE TRALEE 2
TO-25-LET-PST-01 | LETTERKENNY STRABANE PST
TO-25-110 kV A2 @ LOU-01 | LOUTH 110 kV A2
TO-25-110 kV B2 @ LOU-01 | LOUTH 110 kV B2
TO-25-220 kV A1 @ LOU-02 | LOUTH 220 kV A1
TO-25-220 kV A2 @ LOU-03 | LOUTH 220 kV A2
TO-25-220 kV B1 @ LOU-02 | LOUTH 220 kV B1
TO-25-220 kV B2 @ LOU-02 | LOUTH 220 kV B2
TO-25-LOU-AT3-02 | LOUTH AT3
TO-25-LOU-CAP1-02 | LOUTH CAP1
TO-25-220 kV B2 @ MAY-01 | MAYNOOTH 220 kV B2
TO-25-MAY-SH-1-03 | MAYNOOTH SHANNONBRIDGE
TO-25-MTN-MUN-1-02 | MONETEEN MUNGRET 1
TO-25-MUL-CAP2-01 | MULLINGAR CAP2
TO-25-NW-PB-1-03 | NORTH WALL POOLBEG
Report covers outages commencing/returning/spanning the period: 21/07/2025 - 03/08/2025
Outages spanning Weeks 30-31
OUTAGE ID | PLANT | Week 30 Mo 21: Week 30; Week 31 Mo 28: Week 31
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4
TO-25-OBE-PLA-1-02 | OLDBRIDGE PLATIN
TO-25-PB-R2001-01 | POOLBEG R2001
TO-25-PLS-T141-02 | PORTLAOISE T141
TO-25-SH-T102/4-01 | SHANNONBRIDGE T102/4
TO-25-SH-T2102-01 | SHANNONBRIDGE T2102
TO-25-TB-T2003-01 | TARBERT T2003
TO-25-TB-T2004-01 | TARBERT T2004