## Wks 32 - 33
Report covers outages commencing/returning/spanning the period: 04/08/2025 - 17/08/2025
Outages commencing/returning in Week 32
OUTAGE ID | PLANT |  | Week 32 | [6 empty] | Week 33
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
TO-25-DMY-T141-01 | DUNMANWAY T141
TO-25-MLN-T124-01 | MULLAGHARLIN T124
TO-25-CLW-KLS-1-08 | CARLOW KELLIS 1
TO-25-110 kV A1 @ KLS-01 | KELLIS 110 kV A1
TO-25-110 kV A2 @ TEN-01 | TIMAHOE 110 kV A2
TO-25-110 kV B2 @ TEN-01 | TIMAHOE 110 kV B2
TO-25-TEN-110K2-01 | TIMAHOE 110K2
TO-25-220 kV A2 @ AD-01 | AGHADA 220 kV A2
TO-25-220 kV B2 @ AD-01 | AGHADA 220 kV B2
TO-25-AD-GGO-1-01 | AGHADA GLANAGOW
TO-25-CAH-CAP2/4-01 | CAHIR CAP2/4
TO-25-110 kV A1 @ PLS-02 | PORTLAOISE 110 kV A1
TO-25-110 kV B1 @ PLS-01 | PORTLAOISE 110 kV B1
TO-25-CKM-PB-1-07 | CARRICKMINES POOLBEG | bar: Week 32 Sa 9 to Week 33 Mo 11
TO-25-220 kV A1 @ PB-01 | POOLBEG 220 kV A1 | bar: Week 32 Sa 9 to Week 33 Mo 11
TO-25-220 kV A2 @ PB-01 | POOLBEG 220 kV A2 | bar: Week 32 Sa 9 to Week 33 Mo 11
TO-25-BVK-CLA-1-01 | BALLYVOUSKILL CLASHAVOON | bar: Week 32 Sa 9 to Week 33 Fr 15
TO-25-110 kV A1 @ CLO-02 | CLOGHER 110 kV A1 | bar: Week 32 Sa 9 to Week 33 Fr 15
TO-25-110 kV B1 @ CLO-02 | CLOGHER 110 kV B1 | bar: Week 32 Sa 9 to Week 33 Fr 15
TO-25-CLO-DRM-1-01 | CLOGHER DRUMKEEN | bar: Week 32 Sa 9 to Week 33 Fr 15
TO-25-DRM-110SA1-01 | DRUMKEEN 110SA1 | bar: Week 32 Sa 9 to Week 33 Fr 15
TO-25-DRM-110SA2-01 | DRUMKEEN 110SA2 | bar: Week 32 Sa 9 to Week 33 Fr 15
TO-25-DRM-LET-1-01 | DRUMKEEN LETTERKENNY | bar: Week 32 Sa 9 to Week 33 Fr 15
TO-25-DRM-MEE-1-01 | DRUMKEEN MEENTYCAT | bar: Week 32 Sa 9 to Week 33 Fr 15
TO-25-MEE-T121-01 | MEENTYCAT T121 | bar: Week 32 Sa 9 to Week 33 Fr 15
TO-25-CLG-FIN GIS-1-01 | CLOGHRAN FINGLAS GIS | bar: Week 32 Sa 9 to Week 33 Mo 18
TO-25-110 kV A5 @ FIN GIS-02 | FINGLAS GIS 110 kV A5 | bar: Week 32 Sa 9 to Week 33 Mo 18
TO-25-110 kV B5 @ FIN GIS-02 | FINGLAS GIS 110 kV B5 | bar: Week 32 Sa 9 to Week 33 Mo 18
TO-25-FIN GIS-110K5-03 | FINGLAS GIS 110K5 | bar: Week 32 Sa 9 to Week 33 Mo 18
TO-25-FIN GIS-110SA3-5CB-05 | FINGLAS GIS 110SA3-5CB | bar: Week 32 Sa 9 to Week 33 Mo 18
TO-25-FIN GIS-110SB3-5CB-04 | FINGLAS GIS 110SB3-5CB | bar: Week 32 Sa 9 to Week 33 Mo 18
TO-25-MCE-SNU-1-02 | MACETOWN SNUGBOROUGH | bar: Week 32 Sa 9 to Week 33 Mo 18
TO-25-MCE-SNU-1-01 | bar: Week 32 Sa 9 to Week 33 Mo 18
TO-25-110 kV A2 @ SNU-01 | SNUGBOROUGH 110 kV A2 | bar: Week 32 Sa 9 to Week 33 Mo 18
TO-25-110 kV B2 @ SNU-02 | SNUGBOROUGH 110 kV B2 | bar: Week 32 Sa 9 to Week 33 Mo 18
TO-25-SNU-110SA1-2CB-01 | SNUGBOROUGH 110SA1-2CB | bar: Week 32 Sa 9 to Week 33 Mo 18
TO-25-SNU-110SB1-2CB-02 | SNUGBOROUGH 110SB1-2CB | bar: Week 32 Sa 9 to Week 33 Mo 18
TO-25-CBA-110SA1-01 | CLOGHBOOLA 110SA1 | bar: Week 32 Sa 9 to Week 33 Mo 18
TO-25-CBA-110SA2-01 | CLOGHBOOLA 110SA2 | bar: Week 32 Sa 9 to Week 33 Mo 18
TO-25-CBA-T122-01 | CLOGHBOOLA T122 | bar: Week 32 Sa 9 to Week 33 Mo 18
TO-25-CBA-T131-01 | CLOGHBOOLA T131 | bar: Week 32 Sa 9 to Week 33 Mo 18
TO-25-CBA-TRI-1-01 | CLOGHBOOLA TRIEN | bar: Week 32 Sa 9 to Week 33 Mo 18
TO-25-220 kV B1 @ KNR-01 | KNOCKANURE 220 kV B1 | bar: Su 3 to Week 32 Mo 4
TO-25-220 kV B2 @ KNR-04 | KNOCKANURE 220 kV B2 | bar: Su 3 to Week 32 Mo 4
TO-25-KNR-220K1-02 | KNOCKANURE 220K1 | bar: Su 3 to Week 32 Mo 4
TO-25-KNR-220K2-05 | KNOCKANURE 220K2 | bar: Su 3 to Week 32 Mo 4
TO-25-KNR-220SB1-2CB-01 | KNOCKANURE 220SB1-2CB | bar: Su 3 to Week 32 Mo 4
TO-25-SH-T102/4-01 | SHANNONBRIDGE T102/4 | bar: Su 3 to Week 32 Mo 4
TO-25-BOG-T122-01 | BANOGE T122
TO-25-DMY-T142-01 | DUNMANWAY T142
TO-25-MLN-T123-02 | MULLAGHARLIN T123
TO-25-CD-MAC-1-01 | CARRIGADROHID MACROOM | bar: Su 3 to Week 32 Mo 4
TO-25-220 kV A1 @ LOU-02 | LOUTH 220 kV A1 | bar: Su 3 to Week 32 Mo 4
TO-25-220 kV A2 @ LOU-03 | LOUTH 220 kV A2 | bar: Su 3 to Week 32 Mo 4
TO-25-220 kV B1 @ LOU-02 | LOUTH 220 kV B1 | bar: Su 3 to Week 32 Mo 4
TO-25-220 kV B2 @ LOU-02 | LOUTH 220 kV B2 | bar: Su 3 to Week 32 Mo 4
TO-25-MP GIS-T4201-03 | MONEYPOINT GIS T4201 | bar: Su 3 to Week 32 Mo 4
Report covers outages commencing/returning/spanning the period: 04/08/2025 - 17/08/2025
Outages commencing/returning in Week 33
OUTAGE ID | PLANT | Week 32 Mo 4: Week 32; Week 33 Mo 11: Week 33
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
TO-25-FLA-GIL-1-01 | FLAGFORD GILRA
TO-25-GIL-T121-01 | GILRA T121
TO-25-SLC-T122-03 | SLIEVECALLAN T122
TO-25-220 kV B1 @ BYH-01 | BALLYNAHULLA 220 kV B1 | bar: Week 33 Fr 15
TO-25-220 kV B2 @ BYH-01 | BALLYNAHULLA 220 kV B2 | bar: Week 33 Fr 15
TO-25-BYH-220K1-03 | BALLYNAHULLA 220K1 | bar: Week 33 Fr 15
TO-25-BYH-220K2-02 | BALLYNAHULLA 220K2 | bar: Week 33 Fr 15
TO-25-BYH-220SB1-2CB-01 | BALLYNAHULLA 220SB1-2CB | bar: Week 33 Fr 15
TO-25-400 kV A3 @ MP GIS-01 | MONEYPOINT GIS 400 kV A3 | bar: Week 33 Fr 15
TO-25-400 kV B3 @ MP GIS-01 | MONEYPOINT GIS 400 kV B3 | bar: Week 33 Fr 15
TO-25-MP GIS-400K3-01 | MONEYPOINT GIS 400K3 | bar: Week 33 Fr 15
TO-25-MP GIS-400SA1-3CB-02 | MONEYPOINT GIS 400SA1-3CB | bar: Week 33 Fr 15
TO-25-MP GIS-400SB1-3CB-02 | MONEYPOINT GIS 400SB1-3CB | bar: Week 33 Fr 15
TO-25-PB-T2007/8-01 | POOLBEG T2007/8 | bar: Week 33 Fr 15 to Week 33 Su 17
TO-25-ATY-110SA1-01 | ATHY 110SA1 | bar: Week 33 Fr 15 to Week 33 Mo 18
TO-25-ATY-110SA2-02 | ATHY 110SA2 | bar: Week 33 Fr 15 to Week 33 Mo 18
TO-25-ATY-PLS-1-06 | ATHY PORTLAOISE | bar: Week 33 Fr 15 to Week 33 Mo 18
TO-25-ATY-T102-01 | ATHY T102 | bar: Week 33 Fr 15 to Week 33 Mo 18
TO-25-110 kV A2 @ BYH-01 | BALLYNAHULLA 110 kV A2 | bar: Week 33 Fr 15 to Week 33 Mo 18
TO-25-110 kV B2 @ BYH-01 | BALLYNAHULLA 110 kV B2 | bar: Week 33 Fr 15 to Week 33 Mo 18
TO-25-BYH-110K2-01 | BALLYNAHULLA 110K2 | bar: Week 33 Fr 15 to Week 33 Mo 18
TO-25-BYH-110SA1-2CB-03 | BALLYNAHULLA 110SA1-2CB | bar: Week 33 Fr 15 to Week 33 Mo 18
TO-25-BYH-110SB1-2CB-03 | BALLYNAHULLA 110SB1-2CB | bar: Week 33 Fr 15 to Week 33 Mo 18
TO-25-BYH-CDL-1-01 | BALLYNAHULLA CORDAL | bar: Week 33 Fr 15 to Week 33 Mo 18
TO-25-CRO-IA-1-01 | COOLROE INNISCARRA | bar: Week 33 Fr 15 to Week 33 Mo 18
TO-25-CDL-110SA1-01 | CORDAL 110SA1 | bar: Week 33 Fr 15 to Week 33 Mo 18
TO-25-CDL-110SA2-01 | CORDAL 110SA2 | bar: Week 33 Fr 15 to Week 33 Mo 18
TO-25-CDL-T132-01 | CORDAL T132 | bar: Week 33 Fr 15 to Week 33 Mo 18
TO-25-CDL-T141-01 | CORDAL T141 | bar: Week 33 Fr 15 to Week 33 Mo 18
TO-25-220 kV A2 @ GOR-01 | GORMAN 220 kV A2 | bar: Week 33 Fr 15 to Week 33 Mo 18
TO-25-220 kV B2 @ GOR-02 | GORMAN 220 kV B2 | bar: Week 33 Fr 15 to Week 33 Mo 18
TO-25-GOR-LOU-1-02 | GORMAN LOUTH | bar: Week 33 Fr 15 to Week 33 Mo 18
TO-25-IA-MAC-1-04 | INNISCARRA MACROOM | bar: Week 33 Fr 15 to Week 33 Mo 18
TO-25-IA-MAC-1-03 | bar: Week 33 Mo 11 to Week 33 Mo 18
TO-25-IA-T101-02 | INNISCARRA T101 | bar: Week 33 Fr 15 to Week 33 Mo 18
TO-25-IA-T101-01 | bar: Week 33 Fr 15 to Week 33 Mo 18
TO-25-KHL-T131-01 | KILL HILL T131 | bar: Week 33 Fr 15 to Week 33 Mo 18
TO-25-220 kV A2 @ LOU-09 | LOUTH 220 kV A2 | bar: Week 33 Fr 15 to Week 33 Mo 18
TO-25-220 kV B2 @ LOU-09 | LOUTH 220 kV B2 | bar: Week 33 Fr 15 to Week 33 Mo 18
TO-25-CAH-CAP1/3-04 | CAHIR CAP1/3
TO-25-KLS-T2101-05 | KELLIS T2101
TO-25-DER-KIN-1-03 | DERRYIRON KINNEGAD | bar: Week 33 Fr 15 to Week 33 Mo 18
TO-25-DER-T1/T2-02 | DERRYIRON RHODE T1/T2 | bar: Week 33 Fr 15 to Week 33 Mo 18
TO-25-BUT-KTN-1-04 | BUTLERSTOWN KILLOTERAN | bar: Su 3 to Week 32 Su 10
TO-25-CUS-T103/5-01 | CUSHALING T103/5 | bar: Su 3 to Week 32 Su 10
TO-25-KTN-110SA1-02 | KILLOTERAN 110SA1 | bar: Su 3 to Week 32 Su 10
TO-25-KTN-110SA2-02 | KILLOTERAN 110SA2 | bar: Su 3 to Week 32 Su 10
TO-25-KTN-T101-01 | KILLOTERAN T101 | bar: Su 3 to Week 32 Su 10
TO-25-400 kV A1 @ WOO-03 | WOODLAND 400 kV A1 | bar: Su 3 to Week 32 Su 10
TO-25-400 kV A2 @ WOO-01 | WOODLAND 400 kV A2 | bar: Su 3 to Week 32 Su 10
TO-25-400 kV B1 @ WOO-03 | WOODLAND 400 kV B1 | bar: Su 3 to Week 32 Su 10
TO-25-400 kV B2 @ WOO-02 | WOODLAND 400 kV B2 | bar: Su 3 to Week 32 Su 10
TO-25-WOO-400K1-2-03 | WOODLAND 400K1-2 | bar: Su 3 to Week 32 Su 10
TO-25-BYH-T2102-01 | BALLYNAHULLA T2102
TO-25-CSH-SAL-1-03 | CASHLA SALTHILL | bar: Week 33 Fr 15 to Week 33 Mo 18
TO-25-KNY-SAL-1-02 | KNOCKRANNY SALTHILL | bar: Week 33 Fr 15 to Week 33 Mo 18
TO-25-SAL-110SA1-2CB-01 | SALTHILL 110SA1-2CB | bar: Week 33 Fr 15 to Week 33 Mo 18
TO-25-SAL-T102-01 | SALTHILL T102 | bar: Week 33 Fr 15 to Week 33 Mo 18
TO-25-110 kV A2 @ MAY-01 | MAYNOOTH 110 kV A2 | bar: Su 3 to Week 32 Su 10
TO-25-110 kV A3 @ MAY-01 | MAYNOOTH 110 kV A3 | bar: Su 3 to Week 32 Su 10
TO-25-110 kV B2 @ MAY-01 | MAYNOOTH 110 kV B2 | bar: Su 3 to Week 32 Su 10
Report covers outages commencing/returning/spanning the period: 04/08/2025 - 17/08/2025
Outages commencing/returning in Week 33
OUTAGE ID | PLANT | Week 32 Mo 4: Week 32; Week 33 Mo 11: Week 33
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
TO-25-110 kV B3 @ MAY-01 | MAYNOOTH 110 kV B3
TO-25-110 kV A1 @ RYB GIS-01 | RYEBROOK GIS 110 kV A1
TO-25-110 kV B1 @ RYB GIS-01 | RYEBROOK GIS 110 kV B1
TO-25-RYB GIS-110SA1-2CB-02 | RYEBROOK GIS 110SA1-2CB
TO-25-RYB GIS-110SA1-3CB-03 | RYEBROOK GIS 110SA1-3CB
TO-25-RYB GIS-110SB1-2CB-02 | RYEBROOK GIS 110SB1-2CB
TO-25-RYB GIS-110SB1-3CB-02 | RYEBROOK GIS 110SB1-3CB
TO-25-KTN-WAT-1-04 | KILLOTERAN WATERFORD
Outages spanning Weeks 32-33
OUTAGE ID | PLANT | Week 32 Mo 4: Week 32; Week 33 Mo 11: Week 33
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
TO-25-AA GIS-T102-02 | ARDNACRUSHA GIS T102
TO-25-ATH-M/CAP1-06 | ATHLONE M/CAP1
TO-25-ATY-PLS-1-02 | ATHY PORTLAOISE
TO-25-BIN-T141-01 | BINBANE T141
TO-25-CSH-CAP2-01 | CASHLA CAP2
TO-25-CBR-SVC-01 | CASTLEBAR SVC
TO-25-CF-CLO-1-03 | CATHALEENS FALL CLOGHER 1
TO-25-CF-T104-02 | CATHALEENS FALL T104
TO-25-CDU-T2102-01 | CORDUFF T2102
TO-25-CRA-WEX-1-02 | CRANE WEXFORD
TO-25-DND-T121-01 | DARNDALE T121
TO-25-DFR-T122-01 | DUNFIRTH T122
TO-25-DFR,T-DFR-1-03 | DUNFIRTH tee DUNFIRTH
TO-25-DFR,T-KIN-1-03 | DUNFIRTH tee KINNEGAD
TO-25-DFR,T-RNW-1-02 | DUNFIRTH tee RINAWADE
TO-25-110 kV B1/B2/B3 @ FIN-01 | FINGLAS 110 kV B1/B2/B3
TO-25-FIN-110K1-2-02 | FINGLAS 110K1-2
TO-25-FIN-110K2-3-04 | FINGLAS 110K2-3
TO-25-FIN-FIN GIS-1-02 | FINGLAS FINGLAS GIS 1
TO-25-FIN-T2103-01 | FINGLAS T2103
TO-25-GAL-GAL GIS-1-01 | GALWAY GALWAY GIS 1
TO-25-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-25-GLR-MOY-1-02 | GLENREE MOY
TO-25-GI GIS-220SA1-2CB-02 | GREAT ISLAND GIS 220SA1-2CB
TO-25-GI-T141-01 | GREAT ISLAND T141
TO-25-IKE,T-SH-1-05 | IKERRIN tee SHANNONBRIDGE
TO-25-INC-220K1-2-01 | INCHICORE 220K1-2
TO-25-INC-PB-1-03 | INCHICORE POOLBEG 1
TO-25-KYT-T232-02 | KELLYSTOWN T232
TO-25-KBY-MR-1-03 | KILBARRY MARINA 1
TO-25-KBY-MR-2-03 | KILBARRY MARINA 2
TO-25-KPG-TRL-2-02 | KILPADDOGE TRALEE 2
TO-25-KDN-T131-01 | KNOCKDRIN T131
TO-25-KDN,T-KDN-1-01 | KNOCKDRIN tee KNOCKDRIN
TO-25-KDN,T-TSB-1-01 | KNOCKDRIN tee THORNSBERRY
TO-25-KDN,T-TEN-1-02 | KNOCKDRIN tee TIMAHOE
TO-25-LET-PST-01 | LETTERKENNY STRABANE PST
TO-25-LIS-LOU-1-02 | LISDRUM LOUTH
TO-25-LIS-T142-01 | LISDRUM T142
TO-25-110 kV A2 @ LOU-01 | LOUTH 110 kV A2
TO-25-110 kV B2 @ LOU-01 | LOUTH 110 kV B2
TO-25-LOU-AT3-02 | LOUTH AT3
TO-25-LOU-CAP1-02 | LOUTH CAP1
TO-25-220 kV B2 @ MAY-01 | MAYNOOTH 220 kV B2
TO-25-MAY-RYB GIS-1-01 | MAYNOOTH RYEBROOK GIS
TO-25-MAY-SH-1-03 | MAYNOOTH SHANNONBRIDGE
TO-25-MTN-MUN-1-02 | MONETEEN MUNGRET 1
TO-25-MP GIS-T4001-01 | MONEYPOINT GIS T4001
Report covers outages commencing/returning/spanning the period: 04/08/2025 - 17/08/2025
Outages spanning Weeks 32-33
OUTAGE ID | PLANT | Week 32 Mo 4: Week 32; Week 33 Mo 11: Week 33
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
TO-25-MP GIS-T4002-02 | MONEYPOINT GIS T4002
TO-25-MP GIS-T4003-01 | MONEYPOINT GIS T4003
TO-25-MUL-CAP2-01 | MULLINGAR CAP2
TO-25-NW-PB-1-03 | NORTH WALL POOLBEG
TO-25-OBE-PLA-1-02 | OLDBRIDGE PLATIN
TO-25-PB-R2001-01 | POOLBEG R2001
TO-25-PLS-T141-02 | PORTLAOISE T141
TO-25-SH-T101/3-01 | SHANNONBRIDGE T101/3
TO-25-SH-T2102-01 | SHANNONBRIDGE T2102
TO-25-SLI-110SA1-2CB-02 | SLIGO 110SA1-2CB
TO-25-SLI-CAP1-01 | SLIGO CAP1
TO-25-SLI-SRA-1-02 | SLIGO SRANANAGH 1
TO-25-SLI-T141-02 | SLIGO T141
TO-25-TB-T2003-01 | TARBERT T2003
TO-25-TB-T2004-01 | TARBERT T2004