## Wks 4 - 5
Report covers outages commencing/returning/spanning the period: 20/01/2025 - 02/02/2025
Outages commencing/returning in Week 4
OUTAGE ID | PLANT |  | Week 4 | [6 empty] | Week 5
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3
TO-25-SLI-SRA-2-03 | SLIGO SRANANAGH 2 | bar: Week 4 Mo 20
TO-25-110 kV A4 @ FIN GIS-02 | FINGLAS GIS 110 kV A4 | bar: Week 4 Mo 20 to Week 5 Tu 28
TO-25-110 kV A6 @ FIN GIS-01 | FINGLAS GIS 110 kV A6 | bar: Week 4 Mo 20 to Week 5 Tu 28
TO-25-FIN GIS-110K6-01 | FINGLAS GIS 110K6 | bar: Week 4 Mo 20 to Week 5 Tu 28
TO-25-FIN GIS-110SA2-4CB-03 | FINGLAS GIS 110SA2-4CB | bar: Week 4 Mo 20 to Week 5 Tu 28
TO-25-FIN GIS-110SA4-6CB-02 | FINGLAS GIS 110SA4-6CB | bar: Week 4 Mo 20 to Week 5 Tu 28
TO-25-DSN-MAY-2-03 | DUNSTOWN MAYNOOTH 2 | bar: Week 4 Mo 20 to Week 5 Th 30
TO-25-LA-MUL-1-01 | LANESBORO MULLINGAR | bar: Week 4 Mo 20 to Week 5 Th 30
TO-25-PLA-T105-01 | PLATIN T105
TO-25-KPG-110K4-01 | KILPADDOGE 110K4 | bar: Week 4 Tu 21
TO-25-CUN-SLI-1-02 | CUNGHILL SLIGO | bar: Week 4 Tu 21 to Week 5 Th 30
TO-25-220 kV B1 @ CBT-02 | CASTLEBAGOT 220 kV B1 | bar: Su 19 to Week 4 We 22
TO-25-220 kV B2 @ CBT-01 | CASTLEBAGOT 220 kV B2 | bar: Su 19 to Week 4 We 22
TO-25-CBT-220K1-04 | CASTLEBAGOT 220K1 | bar: Su 19 to Week 4 We 22
TO-25-CBT-220K2-02 | CASTLEBAGOT 220K2 | bar: Su 19 to Week 4 We 22
TO-25-CBT-220SB1-2CB-01 | CASTLEBAGOT 220SB1-2CB | bar: Su 19 to Week 4 We 22
TO-25-IA-MAC-1-02 | INNISCARRA MACROOM | bar: Week 4 Th 23 to Week 5 We 29
TO-25-COW-110SA1-01 | COW CROSS 110SA1 | bar: Su 19 to Week 4 Th 23
TO-25-COW-110SA2-01 | COW CROSS 110SA2 | bar: Su 19 to Week 4 Th 23
TO-25-COW-OLD-2-01 | COW CROSS OLDCOURT 2 | bar: Su 19 to Week 4 Th 23
TO-25-COW-RAF-1-01 | COW CROSS RAFFEEN | bar: Su 19 to Week 4 Th 23
TO-25-COW-T141-01 | COW CROSS T141 | bar: Su 19 to Week 4 Th 23
TO-25-OLD-T102-01 | OLDCOURT T102 | bar: Su 19 to Week 4 Th 23
TO-25-DRY-110SA1-02 | DRYBRIDGE 110SA1 | bar: Week 4 Fr 24 to Week 4 Su 26
TO-25-DRY-110SA2-02 | DRYBRIDGE 110SA2 | bar: Week 4 Fr 24 to Week 4 Su 26
TO-25-DRY-GOR-1-03 | DRYBRIDGE GORMAN | bar: Week 4 Fr 24 to Week 4 Su 26
TO-25-DRY-T142-02 | DRYBRIDGE T142 | bar: Week 4 Fr 24 to Week 4 Su 26
TO-25-110 kV A2 @ LOU-05 | LOUTH 110 kV A2 | bar: Su 19 to Week 4 Fr 24
TO-25-110 kV B2 @ LOU-05 | LOUTH 110 kV B2 | bar: Su 19 to Week 4 Fr 24
TO-25-220 kV A2 @ LOU-07 | LOUTH 220 kV A2 | bar: Su 19 to Week 4 Fr 24
TO-25-220 kV B2 @ LOU-06 | LOUTH 220 kV B2 | bar: Su 19 to Week 4 Fr 24
TO-25-LOU-T2102-01 | LOUTH T2102 | bar: Su 19 to Week 4 Fr 24
TO-25-BAL-DRY-1-03 | BALTRASNA DRYBRIDGE | bar: Su 19 to Week 4 Su 26
Outages commencing/returning in Week 5
OUTAGE ID | PLANT | Week 4 Mo 20: Week 4; Week 5 Mo 27: Week 5
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3
TO-25-BAR-T141-01 | BARRYMORE T141 | bar: Week 5 Mo 27 to Week 5 We 29
TO-25-BAR,T-BAR-1-01 | BARRYMORE tee BARRYMORE | bar: Week 5 Mo 27 to Week 5 We 29
TO-25-BAR,T-KRA-1-02 | BARRYMORE tee KNOCKRAHA | bar: Week 5 Mo 27 to Week 5 We 29
TO-25-CBT-CKG-2-02 | CASTLEBAGOT CORKAGH 2 | bar: Week 5 Mo 27 to Week 5 Fr 31
TO-25-110 kV A4 @ CDU-02 | CORDUFF 110 kV A4 | bar: Week 5 Mo 27 to Week 5 Fr 31
TO-25-110 kV B4 @ CDU-02 | CORDUFF 110 kV B4 | bar: Week 5 Mo 27 to Week 5 Fr 31
TO-25-110 kV A1 @ CKG-02 | CORKAGH 110 kV A1 | bar: Week 5 Mo 27 to Week 5 Fr 31
TO-25-110 kV B1 @ CKG-02 | CORKAGH 110 kV B1 | bar: Week 5 Mo 27 to Week 5 Fr 31
TO-25-CKG-110SA1-2CB-02 | CORKAGH 110SA1-2CB | bar: Week 5 Mo 27 to Week 5 Fr 31
TO-25-CKG-110SA1-3CB-04 | CORKAGH 110SA1-3CB | bar: Week 5 Mo 27 to Week 5 Fr 31
TO-25-CKG-110SB1-2CB-02 | CORKAGH 110SB1-2CB | bar: Week 5 Mo 27 to Week 5 Fr 31
TO-25-CKG-110SB1-3CB-04 | CORKAGH 110SB1-3CB | bar: Week 5 Mo 27 to Week 5 Fr 31
TO-25-220 kV A2 @ BVK-01 | BALLYVOUSKILL 220 kV A2 | bar: Week 5 Mo 27 to Week 5 Mo 3
TO-25-220 kV B2 @ BVK-01 | BALLYVOUSKILL 220 kV B2 | bar: Week 5 Mo 27 to Week 5 Mo 3
TO-25-BVK-220K2-01 | BALLYVOUSKILL 220K2 | bar: Week 5 Mo 27 to Week 5 Mo 3
TO-25-BVK-220SA1-2CB-01 | BALLYVOUSKILL 220SA1-2CB | bar: Week 5 Mo 27 to Week 5 Mo 3
TO-25-BVK-220SB1-2CB-01 | BALLYVOUSKILL 220SB1-2CB | bar: Week 5 Mo 27 to Week 5 Mo 3
TO-25-BAR,T-CAH-1-01 | BARRYMORE tee CAHIR | bar: Week 5 Mo 27 to Week 5 Mo 3
TO-25-110 kV A1 @ CDU-01 | CORDUFF 110 kV A1 | bar: Week 5 Mo 27 to Week 5 Mo 3
TO-25-110 kV A2 @ CDU-01 | CORDUFF 110 kV A2 | bar: Week 5 Mo 27 to Week 5 Mo 3
TO-25-110 kV B1 @ CDU-01 | CORDUFF 110 kV B1 | bar: Week 5 Mo 27 to Week 5 Mo 3
TO-25-110 kV B2 @ CDU-01 | CORDUFF 110 kV B2 | bar: Week 5 Mo 27 to Week 5 Mo 3
Report covers outages commencing/returning/spanning the period: 20/01/2025 - 02/02/2025
Outages commencing/returning in Week 5
OUTAGE ID | PLANT | Week 4 Mo 20: Week 4; Week 5 Mo 27: Week 5
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3
TO-25-CDU-110K1-2-01 | CORDUFF 110K1-2 | bar: Week 5 Mo 27 to Week 5 Mo 3
TO-25-220 kV A2 @ TB-01 | TARBERT 220 kV A2 | bar: Week 5 Mo 27 to Week 5 Mo 3
TO-25-220 kV B2 @ TB-01 | TARBERT 220 kV B2 | bar: Week 5 Mo 27 to Week 5 Mo 3
TO-25-GAR-GOR-1-01 | GARBALLAGH GORMAN | bar: Week 5 Tu 28 to Week 5 Th 30
TO-25-CVW-COW-1-01 | CASTLEVIEW COW CROSS | bar: Week 5 Tu 28 to Week 5 Mo 3
TO-25-COW-110SA1-02 | COW CROSS 110SA1 | bar: Week 5 Tu 28 to Week 5 Mo 3
TO-25-COW-110SA2-02 | COW CROSS 110SA2 | bar: Week 5 Tu 28 to Week 5 Mo 3
TO-25-COW-OLD-1-01 | COW CROSS OLDCOURT 1 | bar: Week 5 Tu 28 to Week 5 Mo 3
TO-25-COW-WHI-1-01 | COW CROSS WHITEGATE | bar: Week 5 Tu 28 to Week 5 Mo 3
TO-25-OLD-T101-01 | OLDCOURT T101 | bar: Week 5 Tu 28 to Week 5 Mo 3
TO-25-KIN-T101-02 | KINNEGAD T101 | bar: Su 19 to Week 5 Tu 28
TO-25-LOU-T2101-03 | LOUTH T2101 | bar: Week 5 We 29 to Week 5 Mo 3
TO-25-110 kV A2 @ CAH-01 | CAHIR 110 kV A2 | bar: Week 5 Th 30 to Week 5 Mo 3
TO-25-110 kV B2 @ CAH-01 | CAHIR 110 kV B2 | bar: Week 5 Th 30 to Week 5 Mo 3
TO-25-GWE-T101-03 | GORTAWEE T101 | bar: Su 19 to Week 5 Th 30
TO-25-FLA-SLB-1-01 | FLAGFORD SLIABH BAWN | bar: Week 5 Fr 31 to Week 5 Mo 3
Outages spanning Weeks 4-5
OUTAGE ID | PLANT | Week 4 Mo 20: Week 4; Week 5 Mo 27: Week 5
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3
TO-25-BNK-110SA1-2CB-01 | BARNAKYLE 110SA1-2CB
TO-25-BNK-CBT-2-01 | BARNAKYLE CASTLEBAGOT 2
TO-25-BNK-T122-01 | BARNAKYLE T122
TO-25-CAH-CAP1/3-01 | CAHIR CAP1/3
TO-25-CSH-CAP2-01 | CASHLA CAP2
TO-25-CBR-SVC-01 | CASTLEBAR SVC
TO-25-CUS-PLS-1-01 | CUSHALING PORTLAOISE
TO-25-FIN-110K1-2-02 | FINGLAS 110K1-2
TO-25-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-25-GI-T141-01 | GREAT ISLAND T141
TO-25-INC-220K1-2-01 | INCHICORE 220K1-2
TO-25-LET-PST-01 | LETTERKENNY STRABANE PST
TO-25-MUL-CAP2-01 | MULLINGAR CAP2
TO-25-PB-R2001-01 | POOLBEG R2001
TO-25-110 kV A2 @ PLS-01 | PORTLAOISE 110 kV A2
TO-25-110 kV B2 @ PLS-01 | PORTLAOISE 110 kV B2
TO-25-PRO-TB-1-01 | PROSPECT TARBERT
TO-25-220 kV A2 @ SH-01 | SHANNONBRIDGE 220 kV A2
TO-25-220 kV B2 @ SH-01 | SHANNONBRIDGE 220 kV B2
TO-25-TB-T2003-01 | TARBERT T2003
TO-25-TB-T2004-01 | TARBERT T2004
TO-25-THU-CAP1-02 | THURLES CAP1