## Wks 40 - 41
Report covers outages commencing/returning/spanning the period: 29/09/2025 - 12/10/2025
Outages commencing/returning in Week 40
OUTAGE ID | PLANT |  | Week 40 | [6 empty] | Week 41
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
TO-25-BOL-T121-02 | BOOLTIAGH T121 | bar: Week 40 Mo 29; Week 40 Fr 3
TO-25-110 kV B2 @ CSH-06 | CASHLA 110 kV B2 | bar: Week 40 Mo 29; Week 40 Fr 3
TO-25-CSH-CAP1-01 | CASHLA CAP1 | bar: Week 40 Mo 29; Week 40 Fr 3
TO-25-CLG-T121-01 | CLOGHRAN T121 | bar: Week 40 Mo 29; Week 40 Fr 3
TO-25-SOM-T142-01 | SOMERSET T142 | bar: Week 40 Mo 29; Week 40 Fr 3
TO-25-SOM,T-CSH-1-01 | SOMERSET tee CASHLA | bar: Week 40 Mo 29; Week 40 Fr 3
TO-25-SOM,T-SH-1-02 | SOMERSET tee SHANNONBRIDGE | bar: Week 40 Mo 29; Week 40 Fr 3
TO-25-SOM,T-SOM-1-01 | SOMERSET tee SOMERSET | bar: Week 40 Mo 29; Week 40 Fr 3
TO-25-110 kV A2 @ CLG-01 | CLOGHRAN 110 kV A2 | bar: Week 40 Mo 29; Week 40 Fr 3 to Week 41 Fr 10
TO-25-110 kV B2 @ CLG-01 | CLOGHRAN 110 kV B2 | bar: Week 40 Mo 29; Week 40 Fr 3 to Week 41 Fr 10
TO-25-CLG-110K2-02 | CLOGHRAN 110K2 | bar: Week 40 Mo 29; Week 40 Fr 3 to Week 41 Fr 10
TO-25-CLG-110SA1-2CB-02 | CLOGHRAN 110SA1-2CB | bar: Week 40 Mo 29; Week 40 Fr 3 to Week 41 Fr 10
TO-25-CLG-110SB1-2CB-02 | CLOGHRAN 110SB1-2CB | bar: Week 40 Mo 29; Week 40 Fr 3 to Week 41 Fr 10
TO-25-CLG-T126-01 | CLOGHRAN T126 | bar: Week 40 Mo 29; Week 40 Fr 3 to Week 41 Fr 10
TO-25-110 kV A1 @ LOU-03 | LOUTH 110 kV A1 | bar: Week 40 Mo 29; Week 40 Fr 3 to Week 41 Fr 10
TO-25-110 kV B1 @ LOU-07 | LOUTH 110 kV B1 | bar: Week 40 Mo 29; Week 40 Fr 3 to Week 41 Fr 10
TO-25-LOU-T2101-05 | LOUTH T2101 | bar: Week 40 Mo 29; Week 40 Fr 3 to Week 41 Fr 10
TO-25-220 kV A1 @ TH-03 | TURLOUGH HILL 220 kV A1 | bar: Week 40 Mo 29; Week 40 Fr 3 to Week 41 Fr 10
TO-25-220 kV A2 @ TH-02 | TURLOUGH HILL 220 kV A2 | bar: Week 40 Mo 29; Week 40 Fr 3 to Week 41 Fr 10
TO-25-220 kV B1 @ TH-03 | TURLOUGH HILL 220 kV B1 | bar: Week 40 Mo 29; Week 40 Fr 3 to Week 41 Fr 10
TO-25-220 kV B2 @ TH-02 | TURLOUGH HILL 220 kV B2 | bar: Week 40 Mo 29; Week 40 Fr 3 to Week 41 Fr 10
TO-25-TH-220K1-2-02 | TURLOUGH HILL 220K1-2 | bar: Week 40 Mo 29; Week 40 Fr 3 to Week 41 Fr 10
TO-25-LOU-WOO-1-01 | LOUTH WOODLAND | bar: Week 40 Mo 29; Week 40 Fr 3 to Week 41 Mo 13
TO-25-110 kV A2 @ PLS-03 | PORTLAOISE 110 kV A2 | bar: Week 40 Mo 29; Week 40 Fr 3 to Week 41 Mo 13
TO-25-PLS-110K1-2-04 | PORTLAOISE 110K1-2 | bar: Week 40 Mo 29; Week 40 Fr 3 to Week 41 Mo 13
TO-25-CBT-CLU-1-02 | CASTLEBAGOT CLUTTERLAND
TO-25-CDU-T102-01 | CORDUFF T102
TO-25-220 kV A1 @ LOU-03 | LOUTH 220 kV A1 | bar: Week 40 Fr 3
TO-25-220 kV B1 @ LOU-03 | LOUTH 220 kV B1 | bar: Week 40 Fr 3
TO-25-220 kV A6 @ INC-01 | INCHICORE 220 kV A6 | bar: Week 40 Fr 3 to Week 41 Fr 10
TO-25-220 kV B6 @ INC-01 | INCHICORE 220 kV B6 | bar: Week 40 Fr 3 to Week 41 Fr 10
TO-25-CBT-INC-2-03 | CASTLEBAGOT INCHICORE 2 | bar: Week 40 Fr 3 to Week 41 Mo 13
TO-25-AA GIS-T104-01 | ARDNACRUSHA GIS T104 | bar: Su 28 to Week 40 Mo 29
TO-25-ATY-PLS-1-02 | ATHY PORTLAOISE | bar: Su 28 to Week 40 Mo 29
TO-25-GLR-MOY-1-02 | GLENREE MOY | bar: Su 28 to Week 40 Mo 29
TO-25-110 kV A2 @ KLN-02 | KILLONAN 110 kV A2 | bar: Su 28 to Week 40 Mo 29
TO-25-110 kV B2 @ KLN-02 | KILLONAN 110 kV B2 | bar: Su 28 to Week 40 Mo 29
TO-25-KLN-LIM-2-03 | KILLONAN LIMERICK 2 | bar: Su 28 to Week 40 Mo 29
TO-25-KNR-TRI-2-02 | KNOCKANURE TRIEN 2
TO-25-BAN-110SA1-06 | BANDON 110SA1 | bar: Week 40 Fr 3 to Week 41 Th 9
TO-25-BAN-110SA2-06 | BANDON 110SA2 | bar: Week 40 Fr 3 to Week 41 Th 9
TO-25-BAN-BRI-2-03 | BANDON BRINNY 2 | bar: Week 40 Fr 3 to Week 41 Th 9
TO-25-BAN-T142-04 | BANDON T142 | bar: Week 40 Fr 3 to Week 41 Th 9
TO-25-BRI-T102-05 | BRINNY T102 | bar: Week 40 Fr 3 to Week 41 Th 9
TO-25-110 kV A2 @ ARV-01 | ARVA 110 kV A2 | bar: Week 40 Fr 3 to Week 41 Fr 10
TO-25-110 kV B2 @ ARV-01 | ARVA 110 kV B2 | bar: Week 40 Fr 3 to Week 41 Fr 10
TO-25-ARV-GWE-1-02 | ARVA GORTAWEE | bar: Week 40 Fr 3 to Week 41 Fr 10
TO-25-NEW-PLS-1-03 | NEWBRIDGE PORTLAOISE | bar: Week 40 Fr 3 to Week 41 Mo 13
TO-25-DER-KDN-1-01 | DERRYIRON KNOCKDRIN | bar: Su 28 to Week 40 Mo 29
TO-25-400 kV A2 @ DSN-01 | DUNSTOWN 400 kV A2 | bar: Su 28 to Week 40 Mo 29
TO-25-DSN-T4202-02 | DUNSTOWN T4202 | bar: Su 28 to Week 40 Mo 29
TO-25-IKE-T141-03 | IKERRIN T141 | bar: Su 28 to Week 40 Mo 29
TO-25-IKE,T-IKE-1-03 | IKERRIN tee IKERRIN | bar: Su 28 to Week 40 Mo 29
TO-25-IKE,T-SH-1-04 | IKERRIN tee SHANNONBRIDGE | bar: Su 28 to Week 40 Mo 29
TO-25-IKE,T-THU-1-03 | IKERRIN tee THURLES | bar: Su 28 to Week 40 Mo 29
TO-25-KDN-T131-03 | KNOCKDRIN T131 | bar: Su 28 to Week 40 Mo 29
TO-25-AUG-110SA1-2CB-01 | AUGHINISH 110SA1-2CB
TO-25-KNR-TRI-1-01 | KNOCKANURE TRIEN 1
TO-25-CDU-CRU-2-03 | CORDUFF CRUISERATH 2 | bar: Week 40 Fr 3 to Week 41 We 8
TO-25-400 kV B2 @ DSN-01 | DUNSTOWN 400 kV B2 | bar: Week 40 Fr 3 to Week 41 Mo 13
TO-25-LIS-T131-01 | LISDRUM T131 | bar: Su 28 to Week 40 Mo 29
Report covers outages commencing/returning/spanning the period: 29/09/2025 - 12/10/2025
Outages commencing/returning in Week 40
OUTAGE ID | PLANT | Week 40 Mo 29: Week 40; Week 41 Mo 6: Week 41
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
TO-25-TY-T2001/2-04 | TYNAGH T2001/2 | bar: Su 28 to Week 40 Th 2
TO-25-400 kV A1/A2 @ MP GIS-01 | MONEYPOINT GIS 400 kV A1/A2 | bar: Week 40 Fr 3 to Week 40 Su 5; Week 41 Th 9
TO-25-MP GIS-400SA1-2CB-01 | MONEYPOINT GIS 400SA1-2CB | bar: Week 40 Fr 3 to Week 40 Su 5; Week 41 Th 9
TO-25-BNK-T121-02 | BARNAKYLE T121 | bar: Su 28 to Week 40 Fr 3
TO-25-CRA-WEX-1-02 | CRANE WEXFORD | bar: Su 28 to Week 40 Fr 3
TO-25-110 kV A2 @ MAY-02 | MAYNOOTH 110 kV A2 | bar: Su 28 to Week 40 Fr 3
TO-25-110 kV A3 @ MAY-03 | MAYNOOTH 110 kV A3 | bar: Su 28 to Week 40 Fr 3
TO-25-110 kV B2 @ MAY-02 | MAYNOOTH 110 kV B2 | bar: Su 28 to Week 40 Fr 3
TO-25-110 kV B3 @ MAY-03 | MAYNOOTH 110 kV B3 | bar: Su 28 to Week 40 Fr 3
TO-25-MAY-T2103-01 | MAYNOOTH T2103 | bar: Su 28 to Week 40 Fr 3
Outages commencing/returning in Week 41
OUTAGE ID | PLANT | Week 40 Mo 29: Week 40; Week 41 Mo 6: Week 41
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
TO-25-KPG-MP GIS-1-01 | KILPADDOGE MONEYPOINT GIS 1 | bar: Week 41 Th 9 to Week 41 Fr 10
TO-25-220 kV A2 @ WOO-02 | WOODLAND 220 kV A2 | bar: Week 41 Th 9 to Week 41 Fr 10
TO-25-220 kV B2 @ WOO-02 | WOODLAND 220 kV B2 | bar: Week 41 Th 9 to Week 41 Fr 10
TO-25-WOO-220K1-2-01 | WOODLAND 220K1-2 | bar: Week 41 Th 9 to Week 41 Fr 10
TO-25-BK-MOY-1-03 | BELLACORICK MOY | bar: Week 41 Th 9 to Week 41 Mo 13
TO-25-CLG-CDU-1-01 | CLOGHRAN CORDUFF | bar: Week 41 Th 9 to Week 41 Mo 13
TO-25-110 kV A2 @ CDU-02 | CORDUFF 110 kV A2 | bar: Week 41 Th 9 to Week 41 Mo 13
TO-25-110 kV A4 @ CDU-06 | CORDUFF 110 kV A4 | bar: Week 41 Th 9 to Week 41 Mo 13
TO-25-110 kV B2 @ CDU-04 | CORDUFF 110 kV B2 | bar: Week 41 Th 9 to Week 41 Mo 13
TO-25-110 kV B4 @ CDU-07 | CORDUFF 110 kV B4 | bar: Week 41 Th 9 to Week 41 Mo 13
TO-25-CDU-110SA2-4CB-04 | CORDUFF 110SA2-4CB | bar: Week 41 Th 9 to Week 41 Mo 13
TO-25-CDU-110SB2-4CB-07 | CORDUFF 110SB2-4CB | bar: Week 41 Th 9 to Week 41 Mo 13
TO-25-110 kV A2 @ KLN-01 | KILLONAN 110 kV A2 | bar: Week 41 Th 9 to Week 41 Mo 13
TO-25-110 kV B2 @ KLN-01 | KILLONAN 110 kV B2 | bar: Week 41 Th 9 to Week 41 Mo 13
TO-25-220 kV A2 @ KLN-05 | KILLONAN 220 kV A2 | bar: Week 41 Th 9 to Week 41 Mo 13
TO-25-220 kV B2 @ KLN-05 | KILLONAN 220 kV B2 | bar: Week 41 Th 9 to Week 41 Mo 13
TO-25-KLN-T2102-01 | KILLONAN T2102 | bar: Week 41 Th 9 to Week 41 Mo 13
TO-25-REM-110SA1-01 | REAMORE 110SA1 | bar: Week 41 Th 9 to Week 41 Mo 13
TO-25-REM-110SA2-01 | REAMORE 110SA2 | bar: Week 41 Th 9 to Week 41 Mo 13
TO-25-REM-T141-01 | REAMORE T141 | bar: Week 41 Th 9 to Week 41 Mo 13
TO-25-REM-T142-01 | REAMORE T142 | bar: Week 41 Th 9 to Week 41 Mo 13
TO-25-REM-TRL-1-01 | REAMORE TRALEE | bar: Week 41 Th 9 to Week 41 Mo 13
TO-25-110 kV A2 @ TB-01 | TARBERT 110 kV A2 | bar: Week 41 Th 9 to Week 41 Mo 13
TO-25-110 kV B2 @ TB-01 | TARBERT 110 kV B2 | bar: Week 41 Th 9 to Week 41 Mo 13
TO-25-220 kV A2 @ TB-03 | TARBERT 220 kV A2 | bar: Week 41 Th 9 to Week 41 Mo 13
TO-25-220 kV B2 @ TB-03 | TARBERT 220 kV B2 | bar: Week 41 Th 9 to Week 41 Mo 13
TO-25-TB-T102-01 | TARBERT T102 | bar: Week 41 Th 9 to Week 41 Mo 13
TO-25-TB-T2102-01 | TARBERT T2102 | bar: Week 41 Th 9 to Week 41 Mo 13
TO-25-KDN-T131-02 | KNOCKDRIN T131 | bar: Su 28 to Week 40 Su 5
TO-25-KDN,T-KDN-1-01 | KNOCKDRIN tee KNOCKDRIN | bar: Su 28 to Week 40 Su 5
TO-25-KDN,T-TSB-1-01 | KNOCKDRIN tee THORNSBERRY | bar: Su 28 to Week 40 Su 5
TO-25-KDN,T-TEN-1-02 | KNOCKDRIN tee TIMAHOE | bar: Su 28 to Week 40 Su 5
TO-25-TB-T101-01 | TARBERT T101
TO-25-110 kV A1 @ CSH-01 | CASHLA 110 kV A1 | bar: Su 28 to Week 40 Su 5
TO-25-110 kV B1 @ CSH-02 | CASHLA 110 kV B1 | bar: Su 28 to Week 40 Su 5
TO-25-110 kV A2 @ CDU-01 | CORDUFF 110 kV A2 | bar: Su 28 to Week 40 Su 5
TO-25-110 kV A4 @ CDU-05 | CORDUFF 110 kV A4 | bar: Su 28 to Week 40 Su 5
TO-25-110 kV B2 @ CDU-03 | CORDUFF 110 kV B2 | bar: Su 28 to Week 40 Su 5
TO-25-110 kV B4 @ CDU-06 | CORDUFF 110 kV B4 | bar: Su 28 to Week 40 Su 5
TO-25-CDU-110SA2-4CB-03 | CORDUFF 110SA2-4CB | bar: Su 28 to Week 40 Su 5
TO-25-CDU-110SB2-4CB-06 | CORDUFF 110SB2-4CB | bar: Su 28 to Week 40 Su 5
TO-25-220 kV A2 @ CDU-04 | CORDUFF 220 kV A2 | bar: Su 28 to Week 40 Su 5
TO-25-220 kV A4 @ CDU-04 | CORDUFF 220 kV A4 | bar: Su 28 to Week 40 Su 5
TO-25-220 kV B2 @ CDU-04 | CORDUFF 220 kV B2 | bar: Su 28 to Week 40 Su 5
TO-25-220 kV B4 @ CDU-03 | CORDUFF 220 kV B4 | bar: Su 28 to Week 40 Su 5
TO-25-CDU-220SA2-4CB-04 | CORDUFF 220SA2-4CB | bar: Su 28 to Week 40 Su 5
Report covers outages commencing/returning/spanning the period: 29/09/2025 - 12/10/2025
Outages commencing/returning in Week 41
OUTAGE ID | PLANT | Week 40 Mo 29: Week 40; Week 41 Mo 6: Week 41
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
TO-25-CDU-220SB2-4CB-04 | CORDUFF 220SB2-4CB
TO-25-CDU-T2102-03 | CORDUFF T2102
TO-25-220 kV A1 @ AD-05 | AGHADA 220 kV A1
TO-25-220 kV A2 @ AD-06 | AGHADA 220 kV A2
TO-25-AD-220K1-05 | AGHADA 220K1
TO-25-AD-SA1-2CB-06 | AGHADA 220SA1-2CB
TO-25-AD-T2011/12-03 | AGHADA T2011/12
TO-25-CSH-T2101-03 | CASHLA T2101
TO-25-AD-KRA-1-04 | AGHADA KNOCKRAHA 1
TO-25-AD-KRA-2-04 | AGHADA KNOCKRAHA 2
TO-25-BAN-RAF-1-06 | BANDON RAFFEEN | bar: Su 28 to Week 41 Fr 10
TO-25-110 kV A2 @ KRA-06 | KNOCKRAHA 110 kV A2
TO-25-110 kV B2 @ KRA-05 | KNOCKRAHA 110 kV B2
TO-25-220 kV A1 @ KRA-02 | KNOCKRAHA 220 kV A1
TO-25-220 kV A2 @ KRA-01 | KNOCKRAHA 220 kV A2
TO-25-220 kV B1 @ KRA-02 | KNOCKRAHA 220 kV B1
TO-25-220 kV B2 @ KRA-01 | KNOCKRAHA 220 kV B2
TO-25-KRA-220K1-02 | KNOCKRAHA 220K1
TO-25-KRA-220SA1-2CB-03 | KNOCKRAHA 220SA1-2CB
TO-25-KRA-220SA2-4CB-01 | KNOCKRAHA 220SA2-4CB
TO-25-KRA-220SB1-2CB-03 | KNOCKRAHA 220SB1-2CB
TO-25-KRA-220SB2-4CB-01 | KNOCKRAHA 220SB2-4CB
TO-25-KRA-T2102-02 | KNOCKRAHA T2102
TO-25-SRA-T2102-03 | SRANANAGH T2102
Outages spanning Weeks 40-41
OUTAGE ID | PLANT | Week 40 Mo 29: Week 40; Week 41 Mo 6: Week 41
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
TO-25-ATH-M/CAP1-06 | ATHLONE M/CAP1
TO-25-220 kV A4 @ CSH-04 | CASHLA 220 kV A4
TO-25-220 kV B4 @ CSH-03 | CASHLA 220 kV B4
TO-25-CSH-CAP2-01 | CASHLA CAP2
TO-25-CSH-PRO-1-02 | CASHLA PROSPECT
TO-25-CBR-CAP2-03 | CASTLEBAR CAP2
TO-25-CBR-SVC-01 | CASTLEBAR SVC
TO-25-CF-CLO-1-03 | CATHALEENS FALL CLOGHER 1
TO-25-220 kV A1 @ CLE-04 | CLONEE 220 kV A1
TO-25-220 kV B1 @ CLE-04 | CLONEE 220 kV B1
TO-25-CLE-T221-01 | CLONEE T221
TO-25-CRU-T224-01 | CRUISERATH T224
TO-25-DND-T121-01 | DARNDALE T121
TO-25-110 kV B1/B2/B3 @ FIN-01 | FINGLAS 110 kV B1/B2/B3
TO-25-FIN-110K1-2-02 | FINGLAS 110K1-2
TO-25-FIN-110K2-3-04 | FINGLAS 110K2-3
TO-25-FIN-FIN GIS-1-02 | FINGLAS FINGLAS GIS 1
TO-25-FIN-T2103-01 | FINGLAS T2103
TO-25-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-25-GI GIS-220SA1-2CB-02 | GREAT ISLAND GIS 220SA1-2CB
TO-25-GI-T141-01 | GREAT ISLAND T141
TO-25-INC-220K1-2-01 | INCHICORE 220K1-2
TO-25-KYT-T232-02 | KELLYSTOWN T232
TO-25-KIN-MUL-1-01 | KINNEGAD MULLINGAR
TO-25-LET-PST-01 | LETTERKENNY STRABANE PST
TO-25-LIS-T142-01 | LISDRUM T142
TO-25-LOU-RRU-1-03 | LOUTH RATRUSSAN
TO-25-220 kV B2 @ MAY-01 | MAYNOOTH 220 kV B2
TO-25-MAY-SH-1-03 | MAYNOOTH SHANNONBRIDGE
TO-25-MAY-TEN-1-01 | MAYNOOTH TIMAHOE
TO-25-MUL-CAP2-01 | MULLINGAR CAP2
TO-25-PB-R2001-01 | POOLBEG R2001
Report covers outages commencing/returning/spanning the period: 29/09/2025 - 12/10/2025
Outages spanning Weeks 40-41
OUTAGE ID | PLANT | Week 40 Mo 29: Week 40; Week 41 Mo 6: Week 41
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
TO-25-PLS-T142-01 | PORTLAOISE T142
TO-25-SKL-M/CAP2-03 | SHANKILL M/CAP2
TO-25-SLI-SRA-1-02 | SLIGO SRANANAGH 1
TO-25-TB-T2003-01 | TARBERT T2003
TO-25-TB-T2004-01 | TARBERT T2004