## Wks 42 - 43
Report covers outages commencing/returning/spanning the period: 13/10/2025 - 26/10/2025
Outages commencing/returning in Week 42
OUTAGE ID | PLANT |  | Week 42 | [6 empty] | Week 43
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
TO-25-IKE,T-SH-1-07 | IKERRIN tee SHANNONBRIDGE | bar: Week 42 Mo 13
TO-25-110 kV A1 @ SH-01 | SHANNONBRIDGE 110 kV A1 | bar: Week 42 Mo 13
TO-25-SH-T2101-04 | SHANNONBRIDGE T2101 | bar: Week 42 Mo 13
TO-25-110 kV A2 @ CLA-01 | CLASHAVOON 110 kV A2 | bar: Week 42 Mo 13
TO-25-110 kV B2 @ CLA-01 | CLASHAVOON 110 kV B2 | bar: Week 42 Mo 13
TO-25-CLA-T2102-02 | CLASHAVOON T2102 | bar: Week 42 Mo 13
TO-25-110 kV A1 @ DND-01 | DARNDALE 110 kV A1 | bar: Week 42 Mo 13
TO-25-110 kV B1 @ DND-01 | DARNDALE 110 kV B1 | bar: Week 42 Mo 13
TO-25-DND-110K1-02 | DARNDALE 110K1 | bar: Week 42 Mo 13
TO-25-DND-110SA1-2CB-04 | DARNDALE 110SA1-2CB | bar: Week 42 Mo 13
TO-25-DND-110SB1-2CB-03 | DARNDALE 110SB1-2CB | bar: Week 42 Mo 13
TO-25-220 kV A2 @ WOO-03 | WOODLAND 220 kV A2 | bar: Week 42 Mo 13
TO-25-220 kV A1/A2 @ MP GIS-01 | MONEYPOINT GIS 220 kV A1/A2 | bar: Week 42 Mo 13; Week 42 Sa 18 to Week 43 Tu 21
TO-25-MP GIS-220K1-03 | MONEYPOINT GIS 220K1 | bar: Week 42 Mo 13; Week 42 Sa 18 to Week 43 Tu 21
TO-25-MP GIS-220K2-02 | MONEYPOINT GIS 220K2 | bar: Week 42 Mo 13; Week 42 Sa 18 to Week 43 Tu 21
TO-25-MP GIS-220SA1-2CB-01 | MONEYPOINT GIS 220SA1-2CB | bar: Week 42 Mo 13; Week 42 Sa 18 to Week 43 Tu 21
TO-25-BAN-110SA1-04 | BANDON 110SA1 | bar: Week 42 Mo 13; Week 42 Sa 18 to Week 43 Fr 24
TO-25-BAN-110SA2-05 | BANDON 110SA2 | bar: Week 42 Mo 13; Week 42 Sa 18 to Week 43 Fr 24
TO-25-BAN-BRI-1-03 | BANDON BRINNY 1 | bar: Week 42 Mo 13; Week 42 Sa 18 to Week 43 Fr 24
TO-25-BAN-CAP1-03 | BANDON CAP1 | bar: Week 42 Mo 13; Week 42 Sa 18 to Week 43 Fr 24
TO-25-BAN-DMY-1-04 | BANDON DUNMANWAY | bar: Week 42 Mo 13; Week 42 Sa 18 to Week 43 Fr 24
TO-25-BAN-T101-03 | BANDON T101 | bar: Week 42 Mo 13; Week 42 Sa 18 to Week 43 Fr 24
TO-25-BAN-T141-03 | BANDON T141 | bar: Week 42 Mo 13; Week 42 Sa 18 to Week 43 Fr 24
TO-25-BRI-T101-07 | BRINNY T101 | bar: Week 42 Mo 13; Week 42 Sa 18 to Week 43 Fr 24
TO-25-CDU-WOO-1-02 | CORDUFF WOODLAND | bar: Week 42 Mo 13; Week 42 Sa 18 to Week 43 Fr 24
TO-25-220 kV A2 @ KPG-01 | KILPADDOGE 220 kV A2 | bar: Week 42 Mo 13; Week 42 Sa 18 to Week 43 Fr 24
TO-25-220 kV B2 @ KPG-01 | KILPADDOGE 220 kV B2 | bar: Week 42 Mo 13; Week 42 Sa 18 to Week 43 Fr 24
TO-25-KPG-220SA1-2CB-02 | KILPADDOGE 220SA1-2CB | bar: Week 42 Mo 13; Week 42 Sa 18 to Week 43 Fr 24
TO-25-KPG-220SA2-4CB-01 | KILPADDOGE 220SA2-4CB | bar: Week 42 Mo 13; Week 42 Sa 18 to Week 43 Fr 24
TO-25-KPG-220SB1-2CB-02 | KILPADDOGE 220SB1-2CB | bar: Week 42 Mo 13; Week 42 Sa 18 to Week 43 Fr 24
TO-25-KPG-220SB2-4CB-01 | KILPADDOGE 220SB2-4CB | bar: Week 42 Mo 13; Week 42 Sa 18 to Week 43 Fr 24
TO-25-KPG-TB-2-01 | KILPADDOGE TARBERT 2 | bar: Week 42 Mo 13; Week 42 Sa 18 to Week 43 Fr 24
TO-25-110 kV A1 @ RAF-02 | RAFFEEN 110 kV A1 | bar: Week 42 Mo 13; Week 42 Sa 18 to Week 43 Fr 24
TO-25-110 kV B1 @ RAF-03 | RAFFEEN 110 kV B1 | bar: Week 42 Mo 13; Week 42 Sa 18 to Week 43 Fr 24
TO-25-RAF-TBG-1-01 | RAFFEEN TRABEG 1 | bar: Week 42 Mo 13; Week 42 Sa 18 to Week 43 Fr 24
TO-25-220 kV A2 @ TB-06 | TARBERT 220 kV A2 | bar: Week 42 Mo 13; Week 42 Sa 18 to Week 43 Fr 24
TO-25-220 kV B2 @ TB-06 | TARBERT 220 kV B2 | bar: Week 42 Mo 13; Week 42 Sa 18 to Week 43 Fr 24
TO-25-110 kV A2 @ TBG-01 | TRABEG 110 kV A2 | bar: Week 42 Mo 13; Week 42 Sa 18 to Week 43 Fr 24
TO-25-110 kV B2 @ TBG-01 | TRABEG 110 kV B2 | bar: Week 42 Mo 13; Week 42 Sa 18 to Week 43 Fr 24
TO-25-CBT-KUD-1-01 | CASTLEBAGOT KILMAHUD
TO-25-AUG-110SA1-2CB-01 | AUGHINISH 110SA1-2CB
TO-25-BVK-T2102-01 | BALLYVOUSKILL T2102
TO-25-CFM-T101-02 | CASTLEFARM T101
TO-25-CLG-110K1-01 | CLOGHRAN 110K1
TO-25-KBY-KRA-1-05 | KILBARRY KNOCKRAHA 1
TO-25-KPG-KNR-1-110-01 | KILPADDOGE KNOCKANURE 110
TO-25-IKE,T-SH-1-05 | IKERRIN tee SHANNONBRIDGE | bar: Su 12 to Week 42 Mo 13
TO-25-IKE-T141-03 | IKERRIN T141
TO-25-IKE,T-IKE-1-03 | IKERRIN tee IKERRIN
TO-25-IKE,T-THU-1-08 | IKERRIN tee THURLES
TO-25-IKE,T-TMY-1-01 | IKERRIN tee TIMONEY
TO-25-400 kV B2 @ DSN-01 | DUNSTOWN 400 kV B2 | bar: Su 12 to Week 42 Mo 13
TO-25-KPG-TRL-2-02 | KILPADDOGE TRALEE 2 | bar: Su 12 to Week 42 Mo 13
TO-25-AD-HWL-1-01 | AGHADA HADWELL
TO-25-BYH-BVK-1-01 | BALLYNAHULLA BALLYVOUSKILL
TO-25-HWL-ATA10-01 | HADWELL ATA10
TO-25-HWL-ATA20-01 | HADWELL ATA20
TO-25-DER-110SA1-2CB-03 | DERRYIRON 110SA1-2CB | bar: Week 42 Sa 18 to Week 43 Fr 24
TO-25-DER-T1/T2-01 | DERRYIRON RHODE T1/T2 | bar: Week 42 Sa 18 to Week 43 Fr 24
TO-25-DER-TSB-1-02 | DERRYIRON THORNSBERRY | bar: Week 42 Sa 18 to Week 43 Fr 24
TO-25-DER-TEN-1-01 | DERRYIRON TIMAHOE | bar: Week 42 Sa 18 to Week 43 Fr 24
Report covers outages commencing/returning/spanning the period: 13/10/2025 - 26/10/2025
Outages commencing/returning in Week 42
OUTAGE ID | PLANT | Week 42 Mo 13: Week 42; Week 43 Mo 20: Week 43
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
TO-25-TEN-110K2-03 | TIMAHOE 110K2 | bar: Week 42 Th 16 to Week 43 Fr 24
TO-25-TEN-T132-01 | TIMAHOE T132 | bar: Week 42 Th 16 to Week 43 Fr 24
TO-25-BK-MOY-1-03 | BELLACORICK MOY | bar: Su 12 to Week 42 Fr 17
TO-25-CLG-CDU-1-01 | CLOGHRAN CORDUFF | bar: Su 12 to Week 42 Fr 17
TO-25-110 kV A2 @ CDU-02 | CORDUFF 110 kV A2 | bar: Su 12 to Week 42 Fr 17
TO-25-110 kV A4 @ CDU-06 | CORDUFF 110 kV A4 | bar: Su 12 to Week 42 Fr 17
TO-25-110 kV B2 @ CDU-04 | CORDUFF 110 kV B2 | bar: Su 12 to Week 42 Fr 17
TO-25-110 kV B4 @ CDU-07 | CORDUFF 110 kV B4 | bar: Su 12 to Week 42 Fr 17
TO-25-CDU-110SA2-4CB-04 | CORDUFF 110SA2-4CB | bar: Su 12 to Week 42 Fr 17
TO-25-CDU-110SB2-4CB-07 | CORDUFF 110SB2-4CB | bar: Su 12 to Week 42 Fr 17
TO-25-110 kV A2 @ KLN-01 | KILLONAN 110 kV A2 | bar: Su 12 to Week 42 Fr 17
TO-25-110 kV B2 @ KLN-01 | KILLONAN 110 kV B2 | bar: Su 12 to Week 42 Fr 17
TO-25-220 kV A2 @ KLN-05 | KILLONAN 220 kV A2 | bar: Su 12 to Week 42 Fr 17
TO-25-220 kV B2 @ KLN-05 | KILLONAN 220 kV B2 | bar: Su 12 to Week 42 Fr 17
TO-25-KLN-T2102-01 | KILLONAN T2102 | bar: Su 12 to Week 42 Fr 17
TO-25-110 kV A2 @ PLS-03 | PORTLAOISE 110 kV A2 | bar: Su 12 to Week 42 Fr 17
TO-25-PLS-110K1-2-04 | PORTLAOISE 110K1-2 | bar: Su 12 to Week 42 Fr 17
TO-25-110 kV A2 @ TB-01 | TARBERT 110 kV A2 | bar: Su 12 to Week 42 Fr 17
TO-25-110 kV B2 @ TB-01 | TARBERT 110 kV B2 | bar: Su 12 to Week 42 Fr 17
TO-25-220 kV A2 @ TB-03 | TARBERT 220 kV A2 | bar: Su 12 to Week 42 Fr 17
TO-25-220 kV B2 @ TB-03 | TARBERT 220 kV B2 | bar: Su 12 to Week 42 Fr 17
TO-25-TB-T101-01 | TARBERT T101 | bar: Su 12 to Week 42 Fr 17
TO-25-TB-T102-01 | TARBERT T102 | bar: Su 12 to Week 42 Fr 17
TO-25-TB-T2102-01 | TARBERT T2102 | bar: Su 12 to Week 42 Fr 17
TO-25-IKE,T-THU-1-07 | IKERRIN tee THURLES | bar: Week 42 Sa 18 to Week 43 Tu 21
TO-25-ARK-CKM GIS-1-03 | ARKLOW CARRICKMINES GIS | bar: Week 42 Sa 18 to Week 43 Mo 27
TO-25-BEG-CKM GIS-1-02 | BALLYBEG CARRICKMINES GIS | bar: Week 42 Sa 18 to Week 43 Mo 27
TO-25-WOO-220K1-2-04 | WOODLAND 220K1-2 | bar: Week 42 Su 19 to Week 43 Fr 24
TO-25-WOO-T4202-01 | WOODLAND T4202 | bar: Week 42 Su 19 to Week 43 Fr 24
TO-25-WOO-T4204-01 | WOODLAND T4204 | bar: Week 42 Su 19 to Week 43 Fr 24
Outages commencing/returning in Week 43
OUTAGE ID | PLANT | Week 42 Mo 13: Week 42; Week 43 Mo 20: Week 43
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
TO-25-LSN-110SA1-2-01 | LISHEEN 110SA1-2 | bar: Week 43 Mo 20
TO-25-LSN-110SA2-4-01 | LISHEEN 110SA2-4 | bar: Week 43 Mo 20
TO-25-LSN-T122-01 | LISHEEN T122 | bar: Week 43 Mo 20
TO-25-LSN-T131-02 | LISHEEN T131 | bar: Week 43 Mo 20
TO-25-LSN-T142-01 | LISHEEN T142 | bar: Week 43 Mo 20
TO-25-LSN-THU-1-01 | LISHEEN THURLES | bar: Week 43 Mo 20
TO-25-THU-110SA1-2CB-01 | THURLES 110SA1-2CB | bar: Week 43 Mo 20
TO-25-THU-STATCOM-01 | THURLES STATCOM | bar: Week 43 Mo 20
TO-25-THU-T142-01 | THURLES T142 | bar: Week 43 Mo 20
TO-25-KIN-T102-04 | KINNEGAD T102 | bar: Week 43 Mo 20; Week 43 We 22
TO-25-220 kV A1 @ LOU-04 | LOUTH 220 kV A1 | bar: Week 43 Mo 20; Week 43 We 22 to Week 43 Fr 24
TO-25-220 kV B1 @ LOU-04 | LOUTH 220 kV B1 | bar: Week 43 Mo 20; Week 43 We 22 to Week 43 Fr 24
TO-25-LOU-220K1-2-02 | LOUTH 220K1-2 | bar: Week 43 Mo 20; Week 43 We 22 to Week 43 Fr 24
TO-25-LOU-T2104-08 | LOUTH T2104 | bar: Week 43 Mo 20; Week 43 We 22 to Week 43 Fr 24
TO-25-220 kV A2 @ MAY-01 | MAYNOOTH 220 kV A2 | bar: Week 43 Mo 20; Week 43 We 22 to Week 43 Fr 24
TO-25-220 kV B2 @ MAY-02 | MAYNOOTH 220 kV B2 | bar: Week 43 Mo 20; Week 43 We 22 to Week 43 Fr 24
TO-25-MAY-220K1-2-02 | MAYNOOTH 220K1-2 | bar: Week 43 Mo 20; Week 43 We 22 to Week 43 Fr 24
TO-25-CBR-DLT-1-04 | CASTLEBAR DALTON | bar: Week 43 Mo 20; Week 43 We 22 to Week 43 Sa 25
TO-25-DLT-110SA1-01 | DALTON 110SA1 | bar: Week 43 Mo 20; Week 43 We 22 to Week 43 Sa 25
TO-25-DLT-110SA2-02 | DALTON 110SA2 | bar: Week 43 Mo 20; Week 43 We 22 to Week 43 Sa 25
TO-25-DLT-CAP1-03 | DALTON CAP1 | bar: Week 43 Mo 20; Week 43 We 22 to Week 43 Sa 25
TO-25-DLT-T141-01 | DALTON T141 | bar: Week 43 Mo 20; Week 43 We 22 to Week 43 Sa 25
TO-25-CLA-KRA-1-01 | CLASHAVOON KNOCKRAHA | bar: Week 43 Mo 20; Week 43 We 22 to Week 43 Su 26
TO-25-220 kV A1 @ KRA-04 | KNOCKRAHA 220 kV A1 | bar: Week 43 Mo 20; Week 43 We 22 to Week 43 Su 26
TO-25-220 kV B1 @ KRA-04 | KNOCKRAHA 220 kV B1 | bar: Week 43 Mo 20; Week 43 We 22 to Week 43 Su 26
TO-25-KRA-220K1-04 | KNOCKRAHA 220K1 | bar: Week 43 Mo 20; Week 43 We 22 to Week 43 Su 26
Report covers outages commencing/returning/spanning the period: 13/10/2025 - 26/10/2025
Outages commencing/returning in Week 43
OUTAGE ID | PLANT | Week 42 Mo 13: Week 42; Week 43 Mo 20: Week 43
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
TO-25-KRA-220SA1-2CB-05 | KNOCKRAHA 220SA1-2CB | bar: Week 43 Mo 20 to Week 43 Tu 21; Week 43 Fr 24 to Week 43 Su 26
TO-25-KRA-220SB1-2CB-05 | KNOCKRAHA 220SB1-2CB | bar: Week 43 Mo 20 to Week 43 Tu 21; Week 43 Fr 24 to Week 43 Su 26
TO-25-KRA-T2101-01 | KNOCKRAHA T2101 | bar: Week 43 Mo 20 to Week 43 Tu 21; Week 43 Fr 24 to Week 43 Su 26
TO-25-220 kV A1 @ MAY-03 | MAYNOOTH 220 kV A1 | bar: Week 43 Mo 20 to Week 43 Tu 21; Week 43 Fr 24 to Week 43 Mo 27
TO-25-MAY-TH-1-05 | MAYNOOTH TURLOUGH HILL | bar: Week 43 Mo 20 to Week 43 Tu 21; Week 43 Fr 24 to Week 43 Mo 27
TO-25-MAY-TH-1-01 | bar: Week 43 Mo 20 to Week 43 Tu 21; Week 43 Fr 24 to Week 43 Mo 27
TO-25-110 kV A2 @ RYB GIS-01 | RYEBROOK GIS 110 kV A2 | bar: Week 43 Mo 20 to Week 43 Tu 21; Week 43 Fr 24 to Week 43 Mo 27
TO-25-110 kV B2 @ RYB GIS-01 | RYEBROOK GIS 110 kV B2 | bar: Week 43 Mo 20 to Week 43 Tu 21; Week 43 Fr 24 to Week 43 Mo 27
TO-25-RYB GIS-110SA1-2CB-03 | RYEBROOK GIS 110SA1-2CB | bar: Week 43 Mo 20 to Week 43 Tu 21; Week 43 Fr 24 to Week 43 Mo 27
TO-25-RYB GIS-110SA2-4CB-02 | RYEBROOK GIS 110SA2-4CB | bar: Week 43 Mo 20 to Week 43 Tu 21; Week 43 Fr 24 to Week 43 Mo 27
TO-25-RYB GIS-110SB1-2CB-03 | RYEBROOK GIS 110SB1-2CB | bar: Week 43 Mo 20 to Week 43 Tu 21; Week 43 Fr 24 to Week 43 Mo 27
TO-25-RYB GIS-110SB2-4CB-02 | RYEBROOK GIS 110SB2-4CB | bar: Week 43 Mo 20 to Week 43 Tu 21; Week 43 Fr 24 to Week 43 Mo 27
TO-25-220 kV B2 @ MAY-01 | MAYNOOTH 220 kV B2 | bar: Su 12 to Week 43 Mo 20
TO-25-TH-T2001/2-02 | TURLOUGH HILL T2001/2 | bar: Week 43 Tu 21
TO-25-TH-T2003/4-01 | TURLOUGH HILL T2003/4 | bar: Week 43 Tu 21
TO-25-KLN-LIM-1-04 | KILLONAN LIMERICK 1 | bar: Week 43 Tu 21
TO-25-400 kV B1/B2 @ MP GIS-01 | MONEYPOINT GIS 400 kV B1/B2 | bar: Week 43 Tu 21; Week 43 Fr 24 to Week 43 Mo 27
TO-25-MP GIS-400SB1-2CB-01 | MONEYPOINT GIS 400SB1-2CB | bar: Week 43 Tu 21; Week 43 Fr 24 to Week 43 Mo 27
TO-25-MP GIS-400SB1-3CB-05 | MONEYPOINT GIS 400SB1-3CB | bar: Week 43 Tu 21; Week 43 Fr 24 to Week 43 Mo 27
TO-25-MP GIS-400SB2-4CB-04 | MONEYPOINT GIS 400SB2-4CB | bar: Week 43 Tu 21; Week 43 Fr 24 to Week 43 Mo 27
TO-25-IKE-T141-04 | IKERRIN T141 | bar: Week 43 Fr 24
TO-25-IKE,T-IKE-1-04 | IKERRIN tee IKERRIN | bar: Week 43 Fr 24
TO-25-IKE,T-THU-1-09 | IKERRIN tee THURLES | bar: Week 43 Fr 24
TO-25-IKE,T-TMY-1-02 | IKERRIN tee TIMONEY | bar: Week 43 Fr 24
TO-25-KIN-T101-06 | KINNEGAD T101 | bar: Week 43 Fr 24
TO-25-CSH-T2101-03 | CASHLA T2101 | bar: Su 12 to Week 43 Tu 21; Week 43 Fr 24
TO-25-CBT-INC-2-03 | CASTLEBAGOT INCHICORE 2 | bar: Su 12 to Week 43 Tu 21; Week 43 Fr 24
Outages spanning Weeks 42-43
OUTAGE ID | PLANT | Week 42 Mo 13: Week 42; Week 43 Mo 20: Week 43
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
TO-25-ATH-M/CAP1-06 | ATHLONE M/CAP1
TO-25-BNK-T121-02 | BARNAKYLE T121
TO-25-220 kV A4 @ CSH-04 | CASHLA 220 kV A4
TO-25-220 kV B4 @ CSH-03 | CASHLA 220 kV B4
TO-25-CSH-CAP2-01 | CASHLA CAP2
TO-25-CSH-PRO-1-02 | CASHLA PROSPECT
TO-25-CBR-CAP2-03 | CASTLEBAR CAP2
TO-25-CBR-SVC-01 | CASTLEBAR SVC
TO-25-CF-CLO-1-03 | CATHALEENS FALL CLOGHER 1
TO-25-220 kV A1 @ CLE-04 | CLONEE 220 kV A1
TO-25-220 kV B1 @ CLE-04 | CLONEE 220 kV B1
TO-25-CLE-T221-01 | CLONEE T221
TO-25-CRU-T224-01 | CRUISERATH T224
TO-25-DND-T121-01 | DARNDALE T121
TO-25-110 kV B1/B2/B3 @ FIN-01 | FINGLAS 110 kV B1/B2/B3
TO-25-FIN-110K1-2-02 | FINGLAS 110K1-2
TO-25-FIN-110K2-3-04 | FINGLAS 110K2-3
TO-25-FIN-FIN GIS-1-02 | FINGLAS FINGLAS GIS 1
TO-25-FIN-T2103-01 | FINGLAS T2103
TO-25-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-25-GI GIS-220SA1-2CB-02 | GREAT ISLAND GIS 220SA1-2CB
TO-25-GI-T141-01 | GREAT ISLAND T141
TO-25-INC-220K1-2-01 | INCHICORE 220K1-2
TO-25-KIN-MUL-1-01 | KINNEGAD MULLINGAR
TO-25-LET-PST-01 | LETTERKENNY STRABANE PST
TO-25-LIS-T142-01 | LISDRUM T142
TO-25-LOU-RRU-1-03 | LOUTH RATRUSSAN
TO-25-LOU-WOO-1-01 | LOUTH WOODLAND
TO-25-MAY-SH-1-03 | MAYNOOTH SHANNONBRIDGE
Report covers outages commencing/returning/spanning the period: 13/10/2025 - 26/10/2025
Outages spanning Weeks 42-43
OUTAGE ID | PLANT | Week 42 Mo 13: Week 42; Week 43 Mo 20: Week 43
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
TO-25-MAY-TEN-1-01 | MAYNOOTH TIMAHOE
TO-25-MUL-CAP2-01 | MULLINGAR CAP2
TO-25-NEW-PLS-1-03 | NEWBRIDGE PORTLAOISE
TO-25-PB-R2001-01 | POOLBEG R2001
TO-25-PLS-T142-01 | PORTLAOISE T142
TO-25-REM-110SA1-01 | REAMORE 110SA1
TO-25-REM-110SA2-01 | REAMORE 110SA2
TO-25-REM-T141-01 | REAMORE T141
TO-25-REM-T142-01 | REAMORE T142
TO-25-REM-TRL-1-01 | REAMORE TRALEE
TO-25-SKL-M/CAP2-03 | SHANKILL M/CAP2
TO-25-SLI-SRA-1-02 | SLIGO SRANANAGH 1
TO-25-TB-T101-03 | TARBERT T101
TO-25-TB-T2003-01 | TARBERT T2003
TO-25-TB-T2004-01 | TARBERT T2004