## Wks 44 - 45
Report covers outages commencing/returning/spanning the period: 27/10/2025 - 09/11/2025
Outages commencing/returning in Week 44
OUTAGE ID | PLANT |  | Week 44 | [6 empty] | Week 45
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
TO-25-LOU-220K1-2-01 | LOUTH 220K1-2 | bar: Week 44 Mo 27; Week 44 Th 30 to Week 44 Fr 31
TO-25-LOU-AT2-01 | LOUTH AT2 | bar: Week 44 Mo 27; Week 44 Th 30 to Week 44 Fr 31
TO-25-LOU-T2101-01 | LOUTH T2101 | bar: Week 44 Mo 27; Week 44 Th 30 to Week 44 Fr 31
TO-25-LOU-T2103-01 | LOUTH T2103 | bar: Week 44 Mo 27; Week 44 Th 30 to Week 44 Fr 31
TO-25-LOU-TAN-2-01 | LOUTH TANDRAGEE 2 | bar: Week 44 Mo 27; Week 44 Th 30 to Week 44 Fr 31
TO-25-110 kV A1 @ CSH-07 | CASHLA 110 kV A1 | bar: Week 44 Mo 27; Week 44 Th 30 to Week 45 Fr 7
TO-25-110 kV B1 @ CSH-08 | CASHLA 110 kV B1 | bar: Week 44 Mo 27; Week 44 Th 30 to Week 45 Fr 7
TO-25-BNK-T121-02 | BARNAKYLE T121 | bar: Su 26 to Week 44 Mo 27
TO-25-BAG-110K1-01 | BARNAGEERAGH 110K1
TO-25-GGO-RAF-1-03 | GLANAGOW RAFFEEN
TO-25-LSN-110SA1-2-01 | LISHEEN 110SA1-2
TO-25-LSN-110SA2-4-01 | LISHEEN 110SA2-4
TO-25-LSN-T122-01 | LISHEEN T122
TO-25-LSN-T131-02 | LISHEEN T131
TO-25-LSN-T142-01 | LISHEEN T142
TO-25-LSN-THU-1-01 | LISHEEN THURLES
TO-25-THU-110SA1-2CB-01 | THURLES 110SA1-2CB
TO-25-THU-STATCOM-01 | THURLES STATCOM
TO-25-THU-T142-01 | THURLES T142
TO-25-TRI-110SA1-2CB-02 | TRIEN 110SA1-2CB | bar: Week 44 Th 30
TO-25-MP GIS-T121-02 | MONEYPOINT GIS T121 | bar: Week 44 Th 30 to Week 44 Fr 31
TO-25-CRO-KBY-1-01 | COOLROE KILBARRY | bar: Week 44 Th 30 to Week 45 Tu 4
TO-25-110 kV A2 @ MR-01 | MARINA 110 kV A2 | bar: Week 44 Th 30 to Week 45 Fr 7
TO-25-110 kV B2 @ MR-01 | MARINA 110 kV B2 | bar: Week 44 Th 30 to Week 45 Fr 7
TO-25-MR-TBG-2-01 | MARINA TRABEG 2 | bar: Week 44 Th 30 to Week 45 Fr 7
TO-25-110 kV A2 @ TBG-02 | TRABEG 110 kV A2 | bar: Week 44 Th 30 to Week 45 Fr 7
TO-25-110 kV B2 @ TBG-02 | TRABEG 110 kV B2 | bar: Week 44 Th 30 to Week 45 Fr 7
TO-25-AGL-SH-1-02 | AGANNYGAL SHANNONBRIDGE | bar: Week 44 Th 30 to Week 45 Mo 10
TO-25-110 kV A2 @ CDU-03 | CORDUFF 110 kV A2 | bar: Week 44 Th 30 to Week 45 Mo 10
TO-25-110 kV A4 @ CDU-04 | CORDUFF 110 kV A4 | bar: Week 44 Th 30 to Week 45 Mo 10
TO-25-110 kV B2 @ CDU-05 | CORDUFF 110 kV B2 | bar: Week 44 Th 30 to Week 45 Mo 10
TO-25-110 kV B4 @ CDU-04 | CORDUFF 110 kV B4 | bar: Week 44 Th 30 to Week 45 Mo 10
TO-25-CDU-110SA2-4CB-02 | CORDUFF 110SA2-4CB | bar: Week 44 Th 30 to Week 45 Mo 10
TO-25-CDU-110SB2-4CB-03 | CORDUFF 110SB2-4CB | bar: Week 44 Th 30 to Week 45 Mo 10
TO-25-CDU-MCE-1-01 | CORDUFF MACETOWN | bar: Week 44 Th 30 to Week 45 Mo 10
TO-25-110 kV A2 @ SH-03 | SHANNONBRIDGE 110 kV A2 | bar: Week 44 Th 30 to Week 45 Mo 10
TO-25-110 kV B2 @ SH-03 | SHANNONBRIDGE 110 kV B2 | bar: Week 44 Th 30 to Week 45 Mo 10
TO-25-400 kV B1/B2 @ MP GIS-01 | MONEYPOINT GIS 400 kV B1/B2 | bar: Su 26 to Week 44 Mo 27
TO-25-MP GIS-400SB1-2CB-01 | MONEYPOINT GIS 400SB1-2CB | bar: Su 26 to Week 44 Mo 27
TO-25-MP GIS-400SB1-3CB-05 | MONEYPOINT GIS 400SB1-3CB | bar: Su 26 to Week 44 Mo 27
TO-25-MP GIS-400SB2-4CB-04 | MONEYPOINT GIS 400SB2-4CB | bar: Su 26 to Week 44 Mo 27
TO-25-220 kV A1 @ SH-04 | SHANNONBRIDGE 220 kV A1 | bar: Week 44 Th 30
TO-25-220 kV B1 @ SH-02 | SHANNONBRIDGE 220 kV B1 | bar: Week 44 Th 30
TO-25-IKE,T-THU-1-07 | IKERRIN tee THURLES | bar: Su 26 to Week 44 Mo 27
TO-25-IKE-T141-04 | IKERRIN T141 | bar: Week 44 Th 30 to Week 44 Sa 1
TO-25-IKE,T-IKE-1-04 | IKERRIN tee IKERRIN | bar: Week 44 Th 30 to Week 44 Sa 1
TO-25-IKE,T-THU-1-09 | IKERRIN tee THURLES | bar: Week 44 Th 30 to Week 44 Sa 1
TO-25-IKE,T-TMY-1-02 | IKERRIN tee TIMONEY | bar: Week 44 Th 30 to Week 44 Sa 1
TO-25-REM-110SA1-01 | REAMORE 110SA1 | bar: Su 26 to Week 44 Mo 27; Week 44 Th 30 to Week 44 Fr 31
TO-25-REM-110SA2-01 | REAMORE 110SA2 | bar: Su 26 to Week 44 Mo 27; Week 44 Th 30 to Week 44 Fr 31
TO-25-REM-T141-01 | REAMORE T141 | bar: Su 26 to Week 44 Mo 27; Week 44 Th 30 to Week 44 Fr 31
TO-25-REM-T142-01 | REAMORE T142 | bar: Su 26 to Week 44 Mo 27; Week 44 Th 30 to Week 44 Fr 31
TO-25-REM-TRL-1-01 | REAMORE TRALEE | bar: Su 26 to Week 44 Mo 27; Week 44 Th 30 to Week 44 Fr 31
TO-25-ARK-CKM GIS-1-03 | ARKLOW CARRICKMINES GIS | bar: Su 26 to Week 44 Mo 27; Week 44 Th 30 to Week 44 Sa 1
TO-25-BEG-CKM GIS-1-02 | BALLYBEG CARRICKMINES GIS | bar: Su 26 to Week 44 Mo 27; Week 44 Th 30 to Week 44 Sa 1
Outages commencing/returning in Week 45
OUTAGE ID | PLANT | Week 44 Mo 27: Week 44; Week 45 Mo 3: Week 45
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
TO-25-CUL-RTH-1-01 | CULLENAGH RATHNASKILLOGE | bar: Week 45 Mo 3 to Week 45 Tu 4
TO-25-CLW-T141-03 | CARLOW T141 | bar: Week 45 Mo 3 to Week 45 We 5
TO-25-ATE-110SA1-2CB-02 | ATHEA 110SA1-2CB | bar: Week 45 Mo 3 to Week 45 Th 6
Report covers outages commencing/returning/spanning the period: 27/10/2025 - 09/11/2025
Outages commencing/returning in Week 45
OUTAGE ID | PLANT | Week 44 Mo 27: Week 44; Week 45 Mo 3: Week 45
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
TO-25-ATE-DRO-1-02 | ATHEA DROMADA | bar: Week 45 Mo 3 to Week 45 We 5
TO-25-ATE-KNR-1-02 | ATHEA KNOCKANURE | bar: Week 45 Mo 3 to Week 45 We 5
TO-25-ATE-T121-03 | ATHEA T121 | bar: Week 45 Mo 3 to Week 45 We 5
TO-25-ATE-TOB-1-02 | ATHEA TOBERTOREEN | bar: Week 45 Mo 3 to Week 45 We 5
TO-25-DRO-T121-03 | DROMADA T121 | bar: Week 45 Mo 3 to Week 45 We 5
TO-25-TOB-T132-02 | TOBERTOREEN T132 | bar: Week 45 Mo 3 to Week 45 We 5
TO-25-ARK-110K1-2-01 | ARKLOW 110K1-2 | bar: Week 45 Mo 3 to Week 45 We 5; Week 45 Fr 7
TO-25-BOL-110SA1-03 | BOOLTIAGH 110SA1 | bar: Week 45 Mo 3 to Week 45 We 5; Week 45 Fr 7
TO-25-BOL-110SA2-01 | BOOLTIAGH 110SA2 | bar: Week 45 Mo 3 to Week 45 We 5; Week 45 Fr 7
TO-25-110 kV A4 @ CBT-03 | CASTLEBAGOT 110 kV A4 | bar: Week 45 Mo 3 to Week 45 We 5; Week 45 Fr 7
TO-25-110 kV B4 @ CBT-04 | CASTLEBAGOT 110 kV B4 | bar: Week 45 Mo 3 to Week 45 We 5; Week 45 Fr 7
TO-25-CBT-110K4-04 | CASTLEBAGOT 110K4 | bar: Week 45 Mo 3 to Week 45 We 5; Week 45 Fr 7
TO-25-CBT-110SA2-4CB-04 | CASTLEBAGOT 110SA2-4CB | bar: Week 45 Mo 3 to Week 45 We 5; Week 45 Fr 7
TO-25-CBT-110SB2-4CB-04 | CASTLEBAGOT 110SB2-4CB | bar: Week 45 Mo 3 to Week 45 We 5; Week 45 Fr 7
TO-25-CBT-CKG-2-02 | CASTLEBAGOT CORKAGH 2 | bar: Week 45 Mo 3 to Week 45 We 5; Week 45 Fr 7
TO-25-220 kV A1 @ MAY-01 | MAYNOOTH 220 kV A1 | bar: Week 45 Mo 3 to Week 45 We 5; Week 45 Fr 7
TO-25-220 kV B1 @ MAY-01 | MAYNOOTH 220 kV B1 | bar: Week 45 Mo 3 to Week 45 We 5; Week 45 Fr 7
TO-25-PHT-PLS-1-01 | PHILIPSTOWN PORTLAOISE | bar: Week 45 Mo 3 to Week 45 We 5; Week 45 Fr 7
TO-25-TBK,T-BOL-1-02 | TULLABRACK tee BOOLTIAGH | bar: Week 45 Mo 3 to Week 45 We 5; Week 45 Fr 7
TO-25-220 kV A2 @ KNR-02 | KNOCKANURE 220 kV A2 | bar: Week 45 Mo 3 to Week 45 We 5; Week 45 Fr 7 to Week 45 Mo 10
TO-25-220 kV B2 @ KNR-02 | KNOCKANURE 220 kV B2 | bar: Week 45 Mo 3 to Week 45 We 5; Week 45 Fr 7 to Week 45 Mo 10
TO-25-KNR-220K2-03 | KNOCKANURE 220K2 | bar: Week 45 Mo 3 to Week 45 We 5; Week 45 Fr 7 to Week 45 Mo 10
TO-25-KNR-220SA1-2CB-03 | KNOCKANURE 220SA1-2CB | bar: Week 45 Mo 3 to Week 45 We 5; Week 45 Fr 7 to Week 45 Mo 10
TO-25-KNR-220SB1-2CB-03 | KNOCKANURE 220SB1-2CB | bar: Week 45 Mo 3 to Week 45 We 5; Week 45 Fr 7 to Week 45 Mo 10
TO-25-220 kV A1 @ CLE-04 | CLONEE 220 kV A1 | bar: Su 26 to Week 45 Mo 3
TO-25-220 kV B1 @ CLE-04 | CLONEE 220 kV B1 | bar: Su 26 to Week 45 Mo 3
TO-25-CLE-T221-01 | CLONEE T221 | bar: Su 26 to Week 45 Mo 3
TO-25-LIS-T142-01 | LISDRUM T142 | bar: Su 26 to Week 45 Mo 3
TO-25-220 kV A1 @ BYH-02 | BALLYNAHULLA 220 kV A1 | bar: Week 45 Tu 4 to Week 45 We 5; Week 45 Fr 7 to Week 45 Mo 10
TO-25-220 kV B1 @ BYH-02 | BALLYNAHULLA 220 kV B1 | bar: Week 45 Tu 4 to Week 45 We 5; Week 45 Fr 7 to Week 45 Mo 10
TO-25-FIN-T2103-01 | FINGLAS T2103 | bar: Su 26 to Week 45 Tu 4
TO-25-RAF-T2102-03 | RAFFEEN T2102 | bar: Week 45 We 5
TO-25-CSH-GAL GIS-1-03 | CASHLA GALWAY GIS 1 | bar: Week 45 Fr 7
TO-25-CSH-SAL-1-04 | CASHLA SALTHILL | bar: Week 45 Fr 7
TO-25-SLI-110SA1-2CB-03 | SLIGO 110SA1-2CB | bar: Week 45 Fr 7 to Week 45 Mo 10
TO-25-SLI-CAP1-02 | SLIGO CAP1 | bar: Week 45 Fr 7 to Week 45 Mo 10
TO-25-SLI-T141-01 | SLIGO T141 | bar: Week 45 Fr 7 to Week 45 Mo 10
Outages spanning Weeks 44-45
OUTAGE ID | PLANT | Week 44 Mo 27: Week 44; Week 45 Mo 3: Week 45
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
TO-25-ATH-M/CAP1-06 | ATHLONE M/CAP1
TO-25-220 kV A4 @ CSH-04 | CASHLA 220 kV A4
TO-25-220 kV B4 @ CSH-03 | CASHLA 220 kV B4
TO-25-CSH-CAP2-01 | CASHLA CAP2
TO-25-CSH-PRO-1-02 | CASHLA PROSPECT
TO-25-CSH-T2102-04 | CASHLA T2102
TO-25-CBR-CAP2-03 | CASTLEBAR CAP2
TO-25-CBR-SVC-01 | CASTLEBAR SVC
TO-25-CF-CLO-1-03 | CATHALEENS FALL CLOGHER 1
TO-25-CDU-T2102-05 | CORDUFF T2102
TO-25-220 kV A2 @ CRU-01 | CRUISERATH 220 kV A2
TO-25-220 kV B2 @ CRU-01 | CRUISERATH 220 kV B2
TO-25-CRU-220K2-02 | CRUISERATH 220K2
TO-25-CRU-SA1-2CB-02 | CRUISERATH 220SA1-2CB
TO-25-CRU-SB1-2CB-02 | CRUISERATH 220SB1-2CB
TO-25-CRU-T224-01 | CRUISERATH T224
TO-25-DND-T121-01 | DARNDALE T121
TO-25-110 kV B1/B2/B3 @ FIN-01 | FINGLAS 110 kV B1/B2/B3
TO-25-FIN-110K1-2-02 | FINGLAS 110K1-2
TO-25-FIN-110K2-3-04 | FINGLAS 110K2-3
TO-25-FIN-FIN GIS-1-02 | FINGLAS FINGLAS GIS 1
TO-25-GGO-220K1-2-01 | GLANAGOW 220K1-2
Report covers outages commencing/returning/spanning the period: 27/10/2025 - 09/11/2025
Outages spanning Weeks 44-45
OUTAGE ID | PLANT | Week 44 Mo 27: Week 44; Week 45 Mo 3: Week 45
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
TO-25-GI GIS-220SA1-2CB-02 | GREAT ISLAND GIS 220SA1-2CB
TO-25-GI-T141-01 | GREAT ISLAND T141
TO-25-INC-220K1-2-01 | INCHICORE 220K1-2
TO-25-KPG-TRL-2-02 | KILPADDOGE TRALEE 2
TO-25-KIN-MUL-1-01 | KINNEGAD MULLINGAR
TO-25-LET-PST-01 | LETTERKENNY STRABANE PST
TO-25-LOU-RRU-1-03 | LOUTH RATRUSSAN
TO-25-LOU-WOO-1-01 | LOUTH WOODLAND
TO-25-220 kV A1 @ MAY-03 | MAYNOOTH 220 kV A1
TO-25-220 kV B1 @ MAY-03 | MAYNOOTH 220 kV B1
TO-25-MAY-SH-1-03 | MAYNOOTH SHANNONBRIDGE
TO-25-MAY-TEN-1-01 | MAYNOOTH TIMAHOE
TO-25-MAY-TH-1-05 | MAYNOOTH TURLOUGH HILL
TO-25-MUL-CAP2-01 | MULLINGAR CAP2
TO-25-NEW-PLS-1-03 | NEWBRIDGE PORTLAOISE
TO-25-PB-R2001-01 | POOLBEG R2001
TO-25-PLS-T142-01 | PORTLAOISE T142
TO-25-SKL-M/CAP2-03 | SHANKILL M/CAP2
TO-25-SLI-SRA-1-02 | SLIGO SRANANAGH 1
TO-25-TB-T101-03 | TARBERT T101
TO-25-TB-T2003-01 | TARBERT T2003
TO-25-TB-T2004-01 | TARBERT T2004