## Wks 48 - 49
Report covers outages commencing/returning/spanning the period: 24/11/2025 - 07/12/2025
Outages commencing/returning in Week 48
OUTAGE ID | PLANT |  | Week 48 | [6 empty] | Week 49
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
TO-25-DEN-T132-02 | DEENES T132 | bar: Week 48 Mo 24
TO-25-220 kV A1 @ LOU-05 | LOUTH 220 kV A1 | bar: Week 48 Mo 24
TO-25-220 kV B1 @ LOU-05 | LOUTH 220 kV B1 | bar: Week 48 Mo 24
TO-25-AD-RAF-1-01 | AGHADA RAFFEEN | bar: Week 48 Mo 24 to Week 48 Tu 25; Week 48 Th 27 to Week 48 Fr 28
TO-25-ARK-BOG-1-01 | ARKLOW BANOGE | bar: Week 48 Mo 24 to Week 48 Tu 25; Week 48 Th 27 to Week 48 Fr 28
TO-25-110 kV A2 @ BOG-01 | BANOGE 110 kV A2 | bar: Week 48 Mo 24 to Week 48 Tu 25; Week 48 Th 27 to Week 48 Fr 28
TO-25-BOG-110SA1-02 | BANOGE 110SA1 | bar: Week 48 Mo 24 to Week 48 Tu 25; Week 48 Th 27 to Week 48 Fr 28
TO-25-BOG-110SA2-01 | BANOGE 110SA2 | bar: Week 48 Mo 24 to Week 48 Tu 25; Week 48 Th 27 to Week 48 Fr 28
TO-25-BOG-T122-02 | BANOGE T122 | bar: Week 48 Mo 24 to Week 48 Tu 25; Week 48 Th 27 to Week 48 Fr 28
TO-25-GAL GIS-110SA1-2CB-01 | GALWAY GIS 110SA1-2CB | bar: Week 48 Mo 24 to Week 48 Tu 25; Week 48 Th 27 to Week 48 Fr 28
TO-25-GAL GIS-110SB1-2CB-01 | GALWAY GIS 110SB1-2CB | bar: Week 48 Mo 24 to Week 48 Tu 25; Week 48 Th 27 to Week 48 Fr 28
TO-25-GAL GIS-110SB1-3CB-02 | GALWAY GIS 110SB1-3CB | bar: Week 48 Mo 24 to Week 48 Tu 25; Week 48 Th 27 to Week 48 Fr 28
TO-25-110 kV B1/B2/B3/B4 @ KPG-01 | KILPADDOGE 110 kV B1/B2/B3/B4 | bar: Week 48 Mo 24 to Week 48 Tu 25; Week 48 Th 27 to Week 48 Fr 28
TO-25-KPG-110K3-03 | KILPADDOGE 110K3 | bar: Week 48 Mo 24 to Week 48 Tu 25; Week 48 Th 27 to Week 48 Fr 28
TO-25-KPG-110K4-03 | KILPADDOGE 110K4 | bar: Week 48 Mo 24 to Week 48 Tu 25; Week 48 Th 27 to Week 48 Fr 28
TO-25-KPG-110SB1-2CB-01 | KILPADDOGE 110SB1-2CB | bar: Week 48 Mo 24 to Week 48 Tu 25; Week 48 Th 27 to Week 48 Fr 28
TO-25-KPG-110SB1-3CB-01 | KILPADDOGE 110SB1-3CB | bar: Week 48 Mo 24 to Week 48 Tu 25; Week 48 Th 27 to Week 48 Fr 28
TO-25-KPG-110SB2-4CB-01 | KILPADDOGE 110SB2-4CB | bar: Week 48 Mo 24 to Week 48 Tu 25; Week 48 Th 27 to Week 48 Fr 28
TO-25-PB-T2007/8-01 | POOLBEG T2007/8 | bar: Week 48 Mo 24 to Week 48 Tu 25; Week 48 Th 27 to Week 48 Fr 28
TO-25-110 kV A2 @ CLA-02 | CLASHAVOON 110 kV A2 | bar: Week 48 Mo 24 to Week 48 Tu 25; Week 48 Th 27 to Week 49 Tu 2
TO-25-110 kV B2 @ CLA-02 | CLASHAVOON 110 kV B2 | bar: Week 48 Mo 24 to Week 48 Tu 25; Week 48 Th 27 to Week 49 Tu 2
TO-25-CLA-DMY-1-03 | CLASHAVOON DUNMANWAY | bar: Week 48 Mo 24 to Week 48 Tu 25; Week 48 Th 27 to Week 49 Tu 2
TO-25-CUN-110SA1-03 | CUNGHILL 110SA1 | bar: Week 48 Mo 24 to Week 48 Tu 25; Week 48 Th 27 to Week 49 Tu 2
TO-25-CUN-110SA2-02 | CUNGHILL 110SA2 | bar: Week 48 Mo 24 to Week 48 Tu 25; Week 48 Th 27 to Week 49 Tu 2
TO-25-CUN-SLI-1-07 | CUNGHILL SLIGO | bar: Week 48 Mo 24 to Week 48 Tu 25; Week 48 Th 27 to Week 49 Tu 2
TO-25-CUN-T121-04 | CUNGHILL T121 | bar: Week 48 Mo 24 to Week 48 Tu 25; Week 48 Th 27 to Week 49 Tu 2
TO-25-BOL-ENN-1-01 | BOOLTIAGH ENNIS | bar: Week 48 Mo 24 to Week 48 Tu 25; Week 48 Th 27 to Week 49 Sa 6
TO-25-LOU-WOO-1-01 | LOUTH WOODLAND | bar: Su 23 to Week 48 Mo 24
TO-25-220 kV A1 @ MAY-03 | MAYNOOTH 220 kV A1 | bar: Su 23 to Week 48 Mo 24
TO-25-220 kV B1 @ MAY-03 | MAYNOOTH 220 kV B1 | bar: Su 23 to Week 48 Mo 24
TO-25-MAY-TH-1-05 | MAYNOOTH TURLOUGH HILL | bar: Su 23 to Week 48 Mo 24
TO-25-220 kV A2 @ WOO-04 | WOODLAND 220 kV A2 | bar: Su 23 to Week 48 Mo 24
TO-25-220 kV B2 @ WOO-03 | WOODLAND 220 kV B2 | bar: Su 23 to Week 48 Mo 24
TO-25-WOO-T4204-02 | WOODLAND T4204 | bar: Su 23 to Week 48 Mo 24
TO-25-DER-KIN-1-07 | DERRYIRON KINNEGAD | bar: Week 48 Tu 25
TO-25-KIN-110SA1-2CB-03 | KINNEGAD 110SA1-2CB | bar: Week 48 Tu 25
TO-25-KIN-T101-04 | KINNEGAD T101 | bar: Week 48 Tu 25
TO-25-LA-MUL-1-02 | LANESBORO MULLINGAR | bar: Week 48 Tu 25
TO-25-MUL-110SA1-2CB-01 | MULLINGAR 110SA1-2CB | bar: Week 48 Tu 25
TO-25-MUL-CAP1-01 | MULLINGAR CAP1 | bar: Week 48 Tu 25
TO-25-MUL-T101-01 | MULLINGAR T101 | bar: Week 48 Tu 25
TO-25-MUL-T141-01 | MULLINGAR T141 | bar: Week 48 Tu 25
TO-25-SHL-D1/CB1-02 | SHELLYBANKS D1/CB1 | bar: Week 48 Tu 25
TO-25-SHL-D1/CB2-04 | SHELLYBANKS D1/CB2 | bar: Week 48 Tu 25
TO-25-220 kV A1 @ LOU-10 | LOUTH 220 kV A1 | bar: Week 48 Tu 25; Week 48 Th 27 to Week 48 Fr 28
TO-25-220 kV B1 @ LOU-09 | LOUTH 220 kV B1 | bar: Week 48 Tu 25; Week 48 Th 27 to Week 48 Fr 28
TO-25-220 kV A2 @ WOO-10 | WOODLAND 220 kV A2 | bar: Week 48 Tu 25; Week 48 Th 27 to Week 49 Mo 8
TO-25-220 kV B2 @ WOO-08 | WOODLAND 220 kV B2 | bar: Week 48 Tu 25; Week 48 Th 27 to Week 49 Mo 8
TO-25-WOO-T4202-05 | WOODLAND T4202 | bar: Week 48 Tu 25; Week 48 Th 27 to Week 49 Mo 8
TO-25-DJG-T134-01 | DROMBEG T134
TO-25-DJG-T142-01 | DROMBEG T142
TO-25-110 kV A2 @ DJG-01 | DROMBEG 110 kV A2 | bar: Week 48 Th 27
TO-25-110 kV B2 @ DJG-01 | DROMBEG 110 kV B2 | bar: Week 48 Th 27
TO-25-DJG-110K2-01 | DROMBEG 110K2 | bar: Week 48 Th 27
TO-25-DJG-KPG-1-02 | DROMBEG KILPADDOGE | bar: Week 48 Th 27
TO-25-DJG-TRL-1-02 | DROMBEG TRALEE | bar: Week 48 Th 27
TO-25-220 kV A1 @ SH-04 | SHANNONBRIDGE 220 kV A1 | bar: Week 48 Th 27 to Week 49 Tu 2
TO-25-220 kV B1 @ SH-02 | SHANNONBRIDGE 220 kV B1 | bar: Week 48 Th 27 to Week 49 Tu 2
TO-25-SH-220K1-2-05 | SHANNONBRIDGE 220K1-2 | bar: Week 48 Th 27 to Week 49 Tu 2
TO-25-220 kV A4 @ CKM GIS-01 | CARRICKMINES GIS 220 kV A4 | bar: Su 23 to Week 48 Tu 25; Week 48 Th 27 to Week 48 Fr 28
TO-25-220 kV B4 @ CKM GIS-01 | CARRICKMINES GIS 220 kV B4 | bar: Su 23 to Week 48 Tu 25; Week 48 Th 27 to Week 48 Fr 28
TO-25-CKM GIS-220K4-02 | CARRICKMINES GIS 220K4 | bar: Su 23 to Week 48 Tu 25; Week 48 Th 27 to Week 48 Fr 28
TO-25-CKM GIS-220SA2-4CB-03 | CARRICKMINES GIS 220SA2-4CB | bar: Su 23 to Week 48 Tu 25; Week 48 Th 27 to Week 48 Fr 28
TO-25-CKM GIS-220SB2-4CB-01 | CARRICKMINES GIS 220SB2-4CB | bar: Su 23 to Week 48 Tu 25; Week 48 Th 27 to Week 48 Fr 28
Report covers outages commencing/returning/spanning the period: 24/11/2025 - 07/12/2025
Outages commencing/returning in Week 48
OUTAGE ID | PLANT | Week 48 Mo 24: Week 48; Week 49 Mo 1: Week 49
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
TO-25-CKM GIS-T2104-01 | CARRICKMINES GIS T2104 | bar: Su 23 to Week 48 Fr 28
TO-25-CSH-PRO-1-02 | CASHLA PROSPECT | bar: Su 23 to Week 48 Fr 28
TO-25-DRY-LOU-1-02 | DRYBRIDGE LOUTH | bar: Su 23 to Week 48 Fr 28
Outages commencing/returning in Week 49
OUTAGE ID | PLANT | Week 48 Mo 24: Week 48; Week 49 Mo 1: Week 49
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
TO-25-GAR-T131-01 | GARBALLAGH T131
TO-25-220 kV A1/A2 @ BVK-02 | BALLYVOUSKILL 220 kV A1/A2
TO-25-BVK-220K1-04 | BALLYVOUSKILL 220K1
TO-25-BVK-220K2-03 | BALLYVOUSKILL 220K2
TO-25-BVK-220SA1-2CB-02 | BALLYVOUSKILL 220SA1-2CB
TO-25-110 kV B2 @ CSH-06 | CASHLA 110 kV B2
TO-25-DER-110SA1-2CB-03 | DERRYIRON 110SA1-2CB
TO-25-DER-T1/T2-01 | DERRYIRON RHODE T1/T2
TO-25-DER-TSB-1-01 | DERRYIRON THORNSBERRY
TO-25-DER-TEN-1-01 | DERRYIRON TIMAHOE
TO-25-DSN-MAY-2-02 | DUNSTOWN MAYNOOTH 2
TO-25-KPG-TRL-1-01 | KILPADDOGE TRALEE 1
TO-25-220 kV A2 @ LOU-12 | LOUTH 220 kV A2
TO-25-LOU-T2102-05 | LOUTH T2102
TO-25-400 kV B1/B3 @ MP GIS-01 | MONEYPOINT GIS 400 kV B1/B3
TO-25-MP GIS-400K3-04 | MONEYPOINT GIS 400K3
TO-25-MP GIS-400SB1-2CB-03 | MONEYPOINT GIS 400SB1-2CB
TO-25-MP GIS-400SB1-3CB-01 | MONEYPOINT GIS 400SB1-3CB
TO-25-SOM-T142-01 | SOMERSET T142
TO-25-SOM,T-CSH-1-01 | SOMERSET tee CASHLA
TO-25-SOM,T-SH-1-02 | SOMERSET tee SHANNONBRIDGE
TO-25-SOM,T-SOM-1-01 | SOMERSET tee SOMERSET
TO-25-220 kV A3 @ CKM GIS-03 | CARRICKMINES GIS 220 kV A3 | bar: Week 49 Sa 6 to Week 49 Mo 8
TO-25-220 kV B3 @ CKM GIS-03 | CARRICKMINES GIS 220 kV B3 | bar: Week 49 Sa 6 to Week 49 Mo 8
TO-25-CKM GIS-220K3-04 | CARRICKMINES GIS 220K3 | bar: Week 49 Sa 6 to Week 49 Mo 8
TO-25-CKM GIS-220SA1-3CB-05 | CARRICKMINES GIS 220SA1-3CB | bar: Week 49 Sa 6 to Week 49 Mo 8
TO-25-CKM GIS-220SB1-3CB-03 | CARRICKMINES GIS 220SB1-3CB | bar: Week 49 Sa 6 to Week 49 Mo 8
TO-25-CKM GIS-R2001-01 | CARRICKMINES GIS R2001 | bar: Week 49 Sa 6 to Week 49 Mo 8
TO-25-110 kV A3 @ CDU-01 | CORDUFF 110 kV A3 | bar: Week 49 Sa 6 to Week 49 Mo 8
TO-25-110 kV B3 @ CDU-01 | CORDUFF 110 kV B3 | bar: Week 49 Sa 6 to Week 49 Mo 8
TO-25-CDU-SNU-1-01 | CORDUFF SNUGBOROUGH | bar: Week 49 Sa 6 to Week 49 Mo 8
TO-25-DRY-GOR-1-05 | DRYBRIDGE GORMAN | bar: Week 49 Sa 6 to Week 49 Mo 8
TO-25-110 kV A1 @ GLN-01 | GALLANSTOWN 110 kV A1 | bar: Week 49 Sa 6 to Week 49 Mo 8
TO-25-110 kV B1 @ GLN-01 | GALLANSTOWN 110 kV B1 | bar: Week 49 Sa 6 to Week 49 Mo 8
TO-25-GLN-110K1-03 | GALLANSTOWN 110K1 | bar: Week 49 Sa 6 to Week 49 Mo 8
TO-25-GLN-PLA-1-03 | GALLANSTOWN PLATIN | bar: Week 49 Sa 6 to Week 49 Mo 8
TO-25-110 kV A2 @ GOR-01 | GORMAN 110 kV A2 | bar: Week 49 Sa 6 to Week 49 Mo 8
TO-25-110 kV B2 @ GOR-01 | GORMAN 110 kV B2 | bar: Week 49 Sa 6 to Week 49 Mo 8
TO-25-220 kV A2 @ LOU-11 | LOUTH 220 kV A2 | bar: Week 49 Sa 6 to Week 49 Mo 8
TO-25-110 kV A2 @ SNU-02 | SNUGBOROUGH 110 kV A2 | bar: Week 49 Sa 6 to Week 49 Mo 8
TO-25-110 kV B2 @ SNU-03 | SNUGBOROUGH 110 kV B2 | bar: Week 49 Sa 6 to Week 49 Mo 8
TO-25-SNU-110K2-04 | SNUGBOROUGH 110K2 | bar: Week 49 Sa 6 to Week 49 Mo 8
TO-25-SNU-110SA1-2CB-05 | SNUGBOROUGH 110SA1-2CB | bar: Week 49 Sa 6 to Week 49 Mo 8
TO-25-SNU-110SB1-2CB-05 | SNUGBOROUGH 110SB1-2CB | bar: Week 49 Sa 6 to Week 49 Mo 8
TO-25-CAH-TIP-1-01 | CAHIR TIPPERARY
TO-25-ISH-220K1-2-01 | IRISHTOWN 220K1-2
Outages spanning Weeks 48-49
OUTAGE ID | PLANT | Week 48 Mo 24: Week 48; Week 49 Mo 1: Week 49
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
TO-25-ATH-M/CAP1-06 | ATHLONE M/CAP1
TO-25-CSH-T2102-04 | CASHLA T2102
TO-25-CBR-CAP2-03 | CASTLEBAR CAP2
TO-25-CBR-SVC-01 | CASTLEBAR SVC
Report covers outages commencing/returning/spanning the period: 24/11/2025 - 07/12/2025
Outages spanning Weeks 48-49
OUTAGE ID | PLANT | Week 48 Mo 24: Week 48; Week 49 Mo 1: Week 49
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
TO-25-CRU-T224-01 | CRUISERATH T224
TO-25-DND-T121-01 | DARNDALE T121
TO-25-110 kV B1/B2/B3 @ FIN-01 | FINGLAS 110 kV B1/B2/B3
TO-25-FIN-110K1-2-02 | FINGLAS 110K1-2
TO-25-FIN-110K2-3-04 | FINGLAS 110K2-3
TO-25-FIN-FIN GIS-1-02 | FINGLAS FINGLAS GIS 1
TO-25-FIN-SHL-1-03 | FINGLAS SHELLYBANKS
TO-25-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-25-GI GIS-220SA1-2CB-02 | GREAT ISLAND GIS 220SA1-2CB
TO-25-GI-T141-01 | GREAT ISLAND T141
TO-25-KIN-MUL-1-01 | KINNEGAD MULLINGAR
TO-25-110 kV A2 @ LOU-01 | LOUTH 110 kV A2
TO-25-110 kV B2 @ LOU-01 | LOUTH 110 kV B2
TO-25-MAY-SH-1-03 | MAYNOOTH SHANNONBRIDGE
TO-25-MAY-TEN-1-01 | MAYNOOTH TIMAHOE
TO-25-MUL-CAP2-01 | MULLINGAR CAP2
TO-25-NEW-PLS-1-03 | NEWBRIDGE PORTLAOISE
TO-25-PB-R2001-01 | POOLBEG R2001
TO-25-SKL-M/CAP2-03 | SHANKILL M/CAP2
TO-25-TB-T101-03 | TARBERT T101
TO-25-TB-T2003-01 | TARBERT T2003
TO-25-TB-T2004-01 | TARBERT T2004