## Wks 6 - 7
Report covers outages commencing/returning/spanning the period: 03/02/2025 - 16/02/2025
Outages commencing/returning in Week 6
OUTAGE ID | PLANT |  | Week 6 | [6 empty] | Week 7
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
TO-25-SHL-T2016-01 | SHELLYBANKS T2016 | bar: Week 6 Tu 4
TO-25-AUN-T123-01 | AUNGIERSTOWN T123 | bar: Week 6 Tu 4 to Week 6 Th 6
TO-25-CBR-DLT-1-01 | CASTLEBAR DALTON | bar: Week 6 Tu 4 to Week 6 Fr 7
TO-25-110 kV A2 @ CDU-02 | CORDUFF 110 kV A2 | bar: Week 6 Tu 4 to Week 7 Mo 10
TO-25-110 kV A4 @ CDU-02 | CORDUFF 110 kV A4 | bar: Week 6 Tu 4 to Week 7 Mo 10
TO-25-110 kV B2 @ CDU-02 | CORDUFF 110 kV B2 | bar: Week 6 Tu 4 to Week 7 Mo 10
TO-25-110 kV B4 @ CDU-02 | CORDUFF 110 kV B4 | bar: Week 6 Tu 4 to Week 7 Mo 10
TO-25-CRA-110SA1-06 | CRANE 110SA1 | bar: Week 6 Tu 4 to Week 7 Tu 11
TO-25-CRA-110SA2-06 | CRANE 110SA2 | bar: Week 6 Tu 4 to Week 7 Tu 11
TO-25-CRA-T141-04 | CRANE T141 | bar: Week 6 Tu 4 to Week 7 Tu 11
TO-25-CRA-TTU-1-03 | CRANE TULLABEG | bar: Week 6 Tu 4 to Week 7 Tu 11
TO-25-220 kV A2 @ FIN-05 | FINGLAS 220 kV A2 | bar: Week 6 Tu 4 to Week 7 Fr 14
TO-25-FIN-220K2-08 | FINGLAS 220K2 | bar: Week 6 Tu 4 to Week 7 Fr 14
TO-25-FIN-220SA1-2CB-09 | FINGLAS 220SA1-2CB | bar: Week 6 Tu 4 to Week 7 Fr 14
TO-25-CHA-KLN-1-01 | CHARLEVILLE KILLONAN | bar: Week 6 Tu 4 to Week 7 Mo 17
TO-25-FIN-SHL-1-01 | FINGLAS SHELLYBANKS | bar: Week 6 Tu 4 to Week 7 Mo 17
TO-25-CVW-110SA1-01 | CASTLEVIEW 110SA1 | bar: Week 6 We 5 to Week 6 Th 6
TO-25-CVW-110SA2-01 | CASTLEVIEW 110SA2 | bar: Week 6 We 5 to Week 6 Th 6
TO-25-CVW-T101-01 | CASTLEVIEW T101 | bar: Week 6 We 5 to Week 6 Th 6
TO-25-RRU-SKL-1-01 | RATRUSSAN SHANKILL | bar: Week 6 We 5 to Week 7 Mo 17
TO-25-GLN-PLA-1-01 | GALLANSTOWN PLATIN | bar: Su 2 to Week 6 We 5
TO-25-GAR-PLA-1-01 | GARBALLAGH PLATIN | bar: Su 2 to Week 6 We 5
TO-25-PLA-110SA1-01 | PLATIN 110SA1 | bar: Su 2 to Week 6 We 5
TO-25-PLA-110SA2-01 | PLATIN 110SA2 | bar: Su 2 to Week 6 We 5
TO-25-AUN-KSG-1-01 | AUNGIERSTOWN KISHOGE | bar: Week 6 Fr 7 to Week 7 Mo 10
TO-25-220 kV A2 @ BVK-01 | BALLYVOUSKILL 220 kV A2 | bar: Su 2 to Week 6 Fr 7
TO-25-220 kV B2 @ BVK-01 | BALLYVOUSKILL 220 kV B2 | bar: Su 2 to Week 6 Fr 7
TO-25-BVK-220K2-01 | BALLYVOUSKILL 220K2 | bar: Su 2 to Week 6 Fr 7
TO-25-BVK-220SA1-2CB-01 | BALLYVOUSKILL 220SA1-2CB | bar: Su 2 to Week 6 Fr 7
TO-25-BVK-220SB1-2CB-01 | BALLYVOUSKILL 220SB1-2CB | bar: Su 2 to Week 6 Fr 7
Outages commencing/returning in Week 7
OUTAGE ID | PLANT | Week 6 Mo 3: Week 6; Week 7 Mo 10: Week 7
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
TO-25-220 kV A1 @ CLE-01 | CLONEE 220 kV A1 | bar: Week 7 Mo 10 to Week 7 Fr 14
TO-25-220 kV B1 @ CLE-01 | CLONEE 220 kV B1 | bar: Week 7 Mo 10 to Week 7 Fr 14
TO-25-CLE-220K1-01 | CLONEE 220K1 | bar: Week 7 Mo 10 to Week 7 Fr 14
TO-25-CLE-220SA1-2CB-01 | CLONEE 220SA1-2CB | bar: Week 7 Mo 10 to Week 7 Fr 14
TO-25-CLE-220SB1-2CB-01 | CLONEE 220SB1-2CB | bar: Week 7 Mo 10 to Week 7 Fr 14
TO-25-KPG-TRL-2-01 | KILPADDOGE TRALEE 2 | bar: Week 7 Mo 10 to Week 7 Mo 17
TO-25-220 kV A2 @ TB-01 | TARBERT 220 kV A2 | bar: Su 2 to Week 7 Mo 10
TO-25-220 kV B2 @ TB-01 | TARBERT 220 kV B2 | bar: Su 2 to Week 7 Mo 10
TO-25-AUN-CBT-1-01 | AUNGIERSTOWN CASTLEBAGOT | bar: Week 7 Tu 11 to Week 7 We 12
TO-25-BAR,T-CAH-1-01 | BARRYMORE tee CAHIR | bar: Su 2 to Week 7 Tu 11
TO-25-110 kV A2 @ CAH-01 | CAHIR 110 kV A2 | bar: Su 2 to Week 7 Tu 11
TO-25-110 kV B2 @ CAH-01 | CAHIR 110 kV B2 | bar: Su 2 to Week 7 Tu 11
TO-25-BAR-T141-02 | BARRYMORE T141 | bar: Week 7 We 12 to Week 7 Fr 14
TO-25-BAR,T-BAR-1-02 | BARRYMORE tee BARRYMORE | bar: Week 7 We 12 to Week 7 Fr 14
TO-25-BAR,T-CAH-1-03 | BARRYMORE tee CAHIR | bar: Week 7 We 12 to Week 7 Fr 14
TO-25-BAR,T-KRA-1-01 | BARRYMORE tee KNOCKRAHA | bar: Week 7 We 12 to Week 7 Mo 17
TO-25-110 kV A1 @ KRA-01 | KNOCKRAHA 110 kV A1 | bar: Week 7 We 12 to Week 7 Mo 17
TO-25-110 kV B1 @ KRA-01 | KNOCKRAHA 110 kV B1 | bar: Week 7 We 12 to Week 7 Mo 17
TO-25-ROP-WEX-1-01 | ROSSPILE WEXFORD | bar: Week 7 We 12 to Week 7 Mo 17
TO-25-WEX-110SA1-2CB-03 | WEXFORD 110SA1-2CB | bar: Week 7 We 12 to Week 7 Mo 17
TO-25-WEX-T121-01 | WEXFORD T121 | bar: Week 7 We 12 to Week 7 Mo 17
TO-25-WEX-T141-01 | WEXFORD T141 | bar: Week 7 We 12 to Week 7 Mo 17
TO-25-AUN-T121-01 | AUNGIERSTOWN T121 | bar: Week 7 Th 13 to Week 7 Fr 14
TO-25-LOU-T2101-03 | LOUTH T2101 | bar: Su 2 to Week 7 Th 13
TO-25-CVW-COW-1-01 | CASTLEVIEW COW CROSS | bar: Su 2 to Week 7 Fr 14
Report covers outages commencing/returning/spanning the period: 03/02/2025 - 16/02/2025
Outages commencing/returning in Week 7
OUTAGE ID | PLANT | Week 6 Mo 3: Week 6; Week 7 Mo 10: Week 7
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
TO-25-COW-110SA1-02 | COW CROSS 110SA1 | bar: Su 2 to Week 7 Fr 14
TO-25-COW-110SA2-02 | COW CROSS 110SA2 | bar: Su 2 to Week 7 Fr 14
TO-25-COW-OLD-1-01 | COW CROSS OLDCOURT 1 | bar: Su 2 to Week 7 Fr 14
TO-25-COW-WHI-1-01 | COW CROSS WHITEGATE | bar: Su 2 to Week 7 Fr 14
TO-25-OLD-T101-01 | OLDCOURT T101 | bar: Su 2 to Week 7 Fr 14
Outages spanning Weeks 6-7
OUTAGE ID | PLANT | Week 6 Mo 3: Week 6; Week 7 Mo 10: Week 7
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
TO-25-BNK-110SA1-2CB-01 | BARNAKYLE 110SA1-2CB
TO-25-BNK-CBT-2-01 | BARNAKYLE CASTLEBAGOT 2
TO-25-BNK-T122-01 | BARNAKYLE T122
TO-25-CAH-CAP1/3-02 | CAHIR CAP1/3
TO-25-CSH-CAP2-01 | CASHLA CAP2
TO-25-CBR-SVC-01 | CASTLEBAR SVC
TO-25-CUS-PLS-1-01 | CUSHALING PORTLAOISE
TO-25-DND-T121-01 | DARNDALE T121
TO-25-FIN-110K1-2-02 | FINGLAS 110K1-2
TO-25-FLA-SLB-1-01 | FLAGFORD SLIABH BAWN
TO-25-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-25-GI-T141-01 | GREAT ISLAND T141
TO-25-INC-220K1-2-01 | INCHICORE 220K1-2
TO-25-INC-PB-1-01 | INCHICORE POOLBEG 1
TO-25-KLN-KPG-1-01 | KILLONAN KILPADDOGE
TO-25-LET-PST-01 | LETTERKENNY STRABANE PST
TO-25-LOU-CAP1-02 | LOUTH CAP1
TO-25-MUL-CAP2-01 | MULLINGAR CAP2
TO-25-PLA-T105-01 | PLATIN T105
TO-25-PB-R2001-01 | POOLBEG R2001
TO-25-110 kV A2 @ PLS-01 | PORTLAOISE 110 kV A2
TO-25-110 kV B2 @ PLS-01 | PORTLAOISE 110 kV B2
TO-25-PRO-TB-1-01 | PROSPECT TARBERT
TO-25-220 kV A2 @ SH-01 | SHANNONBRIDGE 220 kV A2
TO-25-220 kV B2 @ SH-01 | SHANNONBRIDGE 220 kV B2
TO-25-TB-T2003-01 | TARBERT T2003
TO-25-TB-T2004-01 | TARBERT T2004
TO-25-THU-CAP1-02 | THURLES CAP1