## Wks 8 - 9
Report covers outages commencing/returning/spanning the period: 17/02/2025 - 02/03/2025
Outages commencing/returning in Week 8
OUTAGE ID | PLANT |  | Week 8 | [6 empty] | Week 9
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3
TO-25-DRY-110SA1-02 | DRYBRIDGE 110SA1
TO-25-DRY-110SA2-02 | DRYBRIDGE 110SA2
TO-25-DRY-GOR-1-03 | DRYBRIDGE GORMAN
TO-25-DRY-T142-02 | DRYBRIDGE T142
TO-25-110 kV A2 @ CAH-01 | CAHIR 110 kV A2
TO-25-110 kV B2 @ CAH-01 | CAHIR 110 kV B2
TO-25-110 kV A2 @ CSH-03 | CASHLA 110 kV A2
TO-25-110 kV B2 @ CSH-05 | CASHLA 110 kV B2
TO-25-220 kV A4 @ CSH-02 | CASHLA 220 kV A4
TO-25-220 kV B4 @ CSH-02 | CASHLA 220 kV B4
TO-25-CUN-GLR-1-01 | CUNGHILL GLENREE
TO-25-CSH-T2104-01 | CASHLA T2104
TO-25-220 kV A4 @ KRA-01 | KNOCKRAHA 220 kV A4
TO-25-220 kV B4 @ KRA-01 | KNOCKRAHA 220 kV B4
TO-25-KRA-220K4-01 | KNOCKRAHA 220K4
TO-25-KRA-220SA2-4CB-02 | KNOCKRAHA 220SA2-4CB
TO-25-KRA-220SB2-4CB-02 | KNOCKRAHA 220SB2-4CB
TO-25-CVW-COW-1-01 | CASTLEVIEW COW CROSS
TO-25-COW-110SA1-02 | COW CROSS 110SA1
TO-25-COW-110SA2-02 | COW CROSS 110SA2
TO-25-COW-OLD-1-01 | COW CROSS OLDCOURT 1
TO-25-COW-WHI-1-01 | COW CROSS WHITEGATE
TO-25-OLD-T101-01 | OLDCOURT T101
TO-25-ROP-WEX-1-01 | ROSSPILE WEXFORD
TO-25-WEX-110SA1-2CB-03 | WEXFORD 110SA1-2CB
TO-25-WEX-T121-01 | WEXFORD T121
TO-25-WEX-T141-01 | WEXFORD T141
TO-25-AUN-T123-01 | AUNGIERSTOWN T123
TO-25-110 kV A2 @ GI-03 | GREAT ISLAND 110 kV A2
TO-25-110 kV B2 @ GI-02 | GREAT ISLAND 110 kV B2
TO-25-GI-ROP-1-01 | GREAT ISLAND ROSSPILE
TO-25-BAL-DRY-1-03 | BALTRASNA DRYBRIDGE
TO-25-AUN-KSG-1-01 | AUNGIERSTOWN KISHOGE
Outages commencing/returning in Week 9
OUTAGE ID | PLANT | Week 8 Mo 17: Week 8; Week 9 Mo 24: Week 9
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3
TO-25-BAR-T141-03 | BARRYMORE T141 | bar: Week 9 Mo 24 to Week 9 Fr 28
TO-25-BAR,T-BAR-1-03 | BARRYMORE tee BARRYMORE | bar: Week 9 Mo 24 to Week 9 Fr 28
TO-25-BAR,T-KRA-1-04 | BARRYMORE tee KNOCKRAHA | bar: Week 9 Mo 24 to Week 9 Fr 28
TO-25-CLA-DMY-1-01 | CLASHAVOON DUNMANWAY | bar: Week 9 Mo 24 to Week 9 Fr 28
TO-25-FIN-SHL-1-01 | FINGLAS SHELLYBANKS | bar: Su 16 to Week 9 Mo 24
TO-25-220 kV A2 @ SH-01 | SHANNONBRIDGE 220 kV A2 | bar: Su 16 to Week 9 Mo 24
TO-25-220 kV B2 @ SH-01 | SHANNONBRIDGE 220 kV B2 | bar: Su 16 to Week 9 Mo 24
TO-25-FIN GIS-T2101-01 | FINGLAS GIS T2101 | bar: Week 9 Tu 25 to Week 9 Th 27
TO-25-110 kV A1 @ CF-04 | CATHALEENS FALL 110 kV A1 | bar: Week 9 We 26 to Week 9 Mo 3
TO-25-110 kV A2 @ CF-02 | CATHALEENS FALL 110 kV A2 | bar: Week 9 We 26 to Week 9 Mo 3
TO-25-110 kV B1 @ CF-03 | CATHALEENS FALL 110 kV B1 | bar: Week 9 We 26 to Week 9 Mo 3
TO-25-110 kV B2 @ CF-01 | CATHALEENS FALL 110 kV B2 | bar: Week 9 We 26 to Week 9 Mo 3
TO-25-CF-110K1-2-01 | CATHALEENS FALL 110K1-2 | bar: Week 9 We 26 to Week 9 Mo 3
TO-25-DEY-T134-01 | DERRYCARNEY T134 | bar: Week 9 Th 27
TO-25-BAR,T-CAH-1-01 | BARRYMORE tee CAHIR | bar: Su 16 to Week 9 Fr 28
TO-25-FLA-SLB-1-01 | FLAGFORD SLIABH BAWN | bar: Su 16 to Week 9 Fr 28
TO-25-GI-T141-01 | GREAT ISLAND T141 | bar: Su 16 to Week 9 Fr 28
TO-25-110 kV A2 @ SLB-01 | SLIABH BAWN 110 kV A2 | bar: Su 16 to Week 9 Fr 28
TO-25-110 kV B2 @ SLB-01 | SLIABH BAWN 110 kV B2 | bar: Su 16 to Week 9 Fr 28
TO-25-SLB-110K2-01 | SLIABH BAWN 110K2 | bar: Su 16 to Week 9 Fr 28
Report covers outages commencing/returning/spanning the period: 17/02/2025 - 02/03/2025
Outages spanning Weeks 8-9
OUTAGE ID | PLANT | Week 8 Mo 17: Week 8; Week 9 Mo 24: Week 9
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3
TO-25-BNK-110SA1-2CB-01 | BARNAKYLE 110SA1-2CB
TO-25-BNK-CBT-2-01 | BARNAKYLE CASTLEBAGOT 2
TO-25-BNK-T122-01 | BARNAKYLE T122
TO-25-CAH-CAP1/3-02 | CAHIR CAP1/3
TO-25-CSH-CAP2-01 | CASHLA CAP2
TO-25-CBR-SVC-01 | CASTLEBAR SVC
TO-25-CHA-KLN-1-01 | CHARLEVILLE KILLONAN
TO-25-CUS-PLS-1-01 | CUSHALING PORTLAOISE
TO-25-DND-T121-01 | DARNDALE T121
TO-25-FIN-110K1-2-02 | FINGLAS 110K1-2
TO-25-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-25-INC-220K1-2-01 | INCHICORE 220K1-2
TO-25-INC-PB-1-01 | INCHICORE POOLBEG 1
TO-25-KLN-KPG-1-01 | KILLONAN KILPADDOGE
TO-25-KPG-TRL-2-01 | KILPADDOGE TRALEE 2
TO-25-LET-PST-01 | LETTERKENNY STRABANE PST
TO-25-LOU-CAP1-02 | LOUTH CAP1
TO-25-MUL-CAP2-01 | MULLINGAR CAP2
TO-25-PB-R2001-01 | POOLBEG R2001
TO-25-PB-R2002-01 | POOLBEG R2002
TO-25-110 kV A2 @ PLS-01 | PORTLAOISE 110 kV A2
TO-25-110 kV B2 @ PLS-01 | PORTLAOISE 110 kV B2
TO-25-PRO-TB-1-01 | PROSPECT TARBERT
TO-25-RRU-SKL-1-01 | RATRUSSAN SHANKILL
TO-25-SH-T2101-03 | SHANNONBRIDGE T2101
TO-25-TB-T2003-01 | TARBERT T2003
TO-25-TB-T2004-01 | TARBERT T2004
TO-25-THU-CAP1-02 | THURLES CAP1