## Wk 1
Report covers outages commencing/returning/spanning the period: 29/12/2025 - 04/01/2026
Outages commencing/returning in Week 1
OUTAGE ID | PLANT |  | Week 1
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5
TO-26-ATH-M/CAP1-03 | ATHLONE M/CAP1
TO-26-CBR-SVC-01 | CASTLEBAR SVC
TO-26-DEN-T132-01 | DEENES T132
TO-26-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-26-GI GIS-220SA1-2CB-02 | GREAT ISLAND GIS 220SA1-2CB
TO-26-KLN-T2102-01 | KILLONAN T2102
TO-26-MUL-CAP2-01 | MULLINGAR CAP2
TO-26-PB-R2001-03 | POOLBEG R2001
TO-26-SKL-M/CAP2-01 | SHANKILL M/CAP2
TO-26-TB-T2003-01 | TARBERT T2003
TO-26-THU-STATCOM-05 | THURLES STATCOM
TO-26-TRL-CAP2-01 | TRALEE CAP2
TO-26-MR-T107-01 | MARINA T107 | bar: Week 1 Th 1 to Week 1 Mo 5
Outages spanning Week 1
OUTAGE ID | PLANT | Week 1 Mo 29: Week 1
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5
TO-26-DND-T121-01 | DARNDALE T121
TO-26-GI-T141-01 | GREAT ISLAND T141

## Wks 2 - 3
Report covers outages commencing/returning/spanning the period: 05/01/2026 - 18/01/2026
Outages commencing/returning in Week 2
OUTAGE ID | PLANT |  | Week 2 | [6 empty] | Week 3
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
TO-26-110 kV A4 @ CBT-01 | CASTLEBAGOT 110 kV A4 | bar: Week 2 Mo 5 to Week 2 Fr 9
TO-26-110 kV B4 @ CBT-01 | CASTLEBAGOT 110 kV B4 | bar: Week 2 Mo 5 to Week 2 Fr 9
TO-26-CBT-110K4-01 | CASTLEBAGOT 110K4 | bar: Week 2 Mo 5 to Week 2 Fr 9
TO-26-CBT-110SA2-4CB-01 | CASTLEBAGOT 110SA2-4CB | bar: Week 2 Mo 5 to Week 2 Fr 9
TO-26-CBT-110SB2-4CB-01 | CASTLEBAGOT 110SB2-4CB | bar: Week 2 Mo 5 to Week 2 Fr 9
TO-26-CHA-MAL-1-02 | CHARLEVILLE MALLOW | bar: Week 2 Mo 5 to Week 2 Fr 9
TO-26-220 kV A2 @ FIN-05 | FINGLAS 220 kV A2 | bar: Week 2 Mo 5 to Week 2 Fr 9
TO-26-220 kV B2 @ FIN-03 | FINGLAS 220 kV B2 | bar: Week 2 Mo 5 to Week 2 Fr 9
TO-26-FIN-220K2-05 | FINGLAS 220K2 | bar: Week 2 Mo 5 to Week 2 Fr 9
TO-26-FIN-220SA1-2CB-06 | FINGLAS 220SA1-2CB | bar: Week 2 Mo 5 to Week 2 Fr 9
TO-26-FIN-220SB1-2CB-04 | FINGLAS 220SB1-2CB | bar: Week 2 Mo 5 to Week 2 Fr 9
TO-26-GWE-T102-01 | GORTAWEE T102 | bar: Week 2 Mo 5 to Week 2 Fr 9
TO-26-KPG-TRL-1-01 | KILPADDOGE TRALEE 1 | bar: Week 2 Mo 5 to Week 2 Fr 9
TO-26-220 kV A2 @ FLA-01 | FLAGFORD 220 kV A2
TO-26-220 kV B2 @ FLA-01 | FLAGFORD 220 kV B2
TO-26-220 kV A2 @ LOU-01 | LOUTH 220 kV A2
TO-26-220 kV B2 @ LOU-01 | LOUTH 220 kV B2
TO-26-GLN-110K1-01 | GALLANSTOWN 110K1 | bar: Week 2 Tu 6
TO-26-BUT-CUL-1-01 | BUTLERSTOWN CULLENAGH | bar: Week 2 Tu 6 to Week 2 We 7
TO-26-BNK-110SA1-2CB-01 | BARNAKYLE 110SA1-2CB | bar: Week 2 Tu 6 to Week 3 Mo 19
TO-26-BNK-CBT-2-02 | BARNAKYLE CASTLEBAGOT 2 | bar: Week 2 Tu 6 to Week 3 Mo 19
TO-26-BNK-T122-01 | BARNAKYLE T122 | bar: Week 2 Tu 6 to Week 3 Mo 19
TO-26-MID-110SA1-02 | MIDLETON 110SA1 | bar: Week 2 Tu 6 to Week 3 Mo 19
TO-26-MID-110SA2-01 | MIDLETON 110SA2 | bar: Week 2 Tu 6 to Week 3 Mo 19
TO-26-MID-T102-01 | MIDLETON T102 | bar: Week 2 Tu 6 to Week 3 Mo 19
TO-26-MID-WHI-1-01 | MIDLETON WHITEGATE | bar: Week 2 Tu 6 to Week 3 Mo 19
TO-26-CLG-110K2-01 | CLOGHRAN 110K2 | bar: Week 2 We 7 to Week 2 Th 8
TO-26-AUN-110K1-01 | AUNGIERSTOWN 110K1 | bar: Week 2 We 7 to Week 2 Fr 9
TO-26-AUN-110SA1-2CB-01 | AUNGIERSTOWN 110SA1-2CB | bar: Week 2 We 7 to Week 2 Fr 9
TO-26-AUN-110SB1-2CB-01 | AUNGIERSTOWN 110SB1-2CB | bar: Week 2 We 7 to Week 2 Fr 9
Outages commencing/returning in Week 3
OUTAGE ID | PLANT | Week 2 Mo 5: Week 2; Week 3 Mo 12: Week 3
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
TO-26-110 kV B2 @ CBT-01 | CASTLEBAGOT 110 kV B2 | bar: Week 3 Mo 12 to Week 3 Fr 16
TO-26-110 kV B4 @ CBT-02 | CASTLEBAGOT 110 kV B4 | bar: Week 3 Mo 12 to Week 3 Fr 16
TO-26-CBT-110K4-02 | CASTLEBAGOT 110K4 | bar: Week 3 Mo 12 to Week 3 Fr 16
TO-26-CBT-110SB2-4CB-02 | CASTLEBAGOT 110SB2-4CB | bar: Week 3 Mo 12 to Week 3 Fr 16
TO-26-LIS-LSA-1-04 | LISDRUM LISLEA | bar: Week 3 Mo 12 to Week 3 Mo 19
TO-26-PRO-TB-1-02 | PROSPECT TARBERT | bar: Week 3 Mo 12 to Week 3 Mo 19
TO-26-110 kV A2 @ SNU-01 | SNUGBOROUGH 110 kV A2 | bar: Week 3 Mo 12 to Week 3 Mo 19
TO-26-110 kV B2 @ SNU-01 | SNUGBOROUGH 110 kV B2 | bar: Week 3 Mo 12 to Week 3 Mo 19
TO-26-SNU-110K2-01 | SNUGBOROUGH 110K2 | bar: Week 3 Mo 12 to Week 3 Mo 19
TO-26-SNU-110SA1-2CB-01 | SNUGBOROUGH 110SA1-2CB | bar: Week 3 Mo 12 to Week 3 Mo 19
TO-26-SNU-110SB1-2CB-01 | SNUGBOROUGH 110SB1-2CB | bar: Week 3 Mo 12 to Week 3 Mo 19
TO-26-TTU-131-01 | TULLABEG T131 | bar: Week 3 Mo 12 to Week 3 Mo 19
TO-26-CRU-220K1-01 | CRUISERATH 220K1 | bar: Week 3 Tu 13
TO-26-DRY-OBE-1-02 | DRYBRIDGE OLDBRIDGE | bar: Week 3 Tu 13 to Week 3 Fr 16
TO-26-CAH-TIP-1-01 | CAHIR TIPPERARY | bar: Week 3 We 14
TO-26-CRU-220K2-01 | CRUISERATH 220K2 | bar: Week 3 We 14
TO-26-DGN-RTH-1-01 | DUNGARVAN RATHNASKILLOGE | bar: Week 3 We 14
TO-26-TIP-110SA1-01 | TIPPERARY 110SA1 | bar: Week 3 We 14
TO-26-TIP-110SA2-01 | TIPPERARY 110SA2 | bar: Week 3 We 14
TO-26-CRU-SA1-2CB-01 | CRUISERATH 220SA1-2CB | bar: Week 3 Th 15
TO-26-CRU-SB1-2CB-01 | CRUISERATH 220SB1-2CB | bar: Week 3 Fr 16
TO-26-110 kV A4 @ CDU-01 | CORDUFF 110 kV A4 | bar: Week 3 Su 18
TO-26-220 kV B4 @ CDU-01 | CORDUFF 220 kV B4 | bar: Week 3 Su 18
TO-26-CDU-T102-01 | CORDUFF T102 | bar: Week 3 Su 18
TO-26-CDU-T2104-01 | CORDUFF T2104 | bar: Week 3 Su 18
Report covers outages commencing/returning/spanning the period: 05/01/2026 - 18/01/2026
Outages commencing/returning in Week 3
OUTAGE ID | PLANT | Week 2 Mo 5: Week 2; Week 3 Mo 12: Week 3
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
TO-26-CDU-WOO-1-02 | CORDUFF WOODLAND | bar: Week 3 Su 18
TO-26-PRN-T4301-01 | PORTAN T4301 | bar: Week 3 Su 18
TO-26-PRN-WOO-1-01 | PORTAN WOODLAND | bar: Week 3 Su 18
TO-26-220 kV B2 @ WOO-02 | WOODLAND 220 kV B2 | bar: Week 3 Su 18
TO-26-400 kV B1/B2 @ WOO-01 | WOODLAND 400 kV B1/B2 | bar: Week 3 Su 18
TO-26-WOO-T4204-04 | WOODLAND T4204 | bar: Week 3 Su 18
Outages spanning Weeks 2-3
OUTAGE ID | PLANT | Week 2 Mo 5: Week 2; Week 3 Mo 12: Week 3
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
TO-26-ATH-M/CAP1-03 | ATHLONE M/CAP1
TO-26-CBR-SVC-01 | CASTLEBAR SVC
TO-26-DND-T121-01 | DARNDALE T121
TO-26-DEN-T132-01 | DEENES T132
TO-26-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-26-GI GIS-220SA1-2CB-02 | GREAT ISLAND GIS 220SA1-2CB
TO-26-GI-T141-01 | GREAT ISLAND T141
TO-26-KLN-T2102-01 | KILLONAN T2102
TO-26-MR-T107-01 | MARINA T107
TO-26-MUL-CAP2-01 | MULLINGAR CAP2
TO-26-PB-R2001-03 | POOLBEG R2001
TO-26-SKL-M/CAP2-01 | SHANKILL M/CAP2
TO-26-TB-T2003-01 | TARBERT T2003
TO-26-THU-STATCOM-05 | THURLES STATCOM
TO-26-TRL-CAP2-01 | TRALEE CAP2

## All Works Summary
Alert Status | Outage ID | Feeder ID | From Bus | To Bus | CKT | Description | Work ID | Start Date | Finish Date | Priority | Status | Proximity | No_of_Days
CAPX2025100108505700 | TO-26-DND-T121-01 | TSO CUSTOMER TRANSFORMER - DARNDALE 110-DARNDALE 20-T121 | DARNDALE 110 | DARNDALE 20 | T121 | Darndale T121 required out to facilitate works in lead up to EI of Darndale T125. T121 to be decommissioned and replaced with new 63MVA transformer | CP1230 | 12/02/2024 | 30/09/2026 |  | Scheduled |  | 229
CAPX2025120310050100 | TO-26-GI-T141-01 | DISTRIBUTION TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND 38-T141 | GREAT ISLAND 110 | GREAT ISLAND 38 | T141 | Upgrading T141 as part of H-I-3932 works | E1680 | 02/04/2025 | 31/12/2026 |  | Reference |  | 40
CAPX2025120310050103 | TO-26-GI-T141-01 | DISTRIBUTION TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND 38-T141 | GREAT ISLAND 110 | GREAT ISLAND 38 | T141 | EI: Simultaneous 110 kV A1/B1 IN TURN @ GI + GI-T141: Interlocking checks, Energisation Instruction | E1680 | 02/04/2025 | 31/12/2026 |  | Reference |  | 2
CAPX2025120310050104 | TO-26-GI-T141-01 | DISTRIBUTION TRANSFORMER - GREAT ISLAND 110-GREAT ISLAND 38-T141 | GREAT ISLAND 110 | GREAT ISLAND 38 | T141 | EI: Simultaneous GI-T141 + GI-WAT-1: Energisation of Great Island T141 | E1680 | 02/04/2025 | 31/12/2026 |  | Reference |  | 2
TOP251022150608 | TO-26-ATH-M/CAP1-03 | CAPACITOR/SVC/REACTOR - ATHLONE 110-ATHLONE 110-M/CAP1 | ATHLONE 110 | ATHLONE 110 | M/CAP1 | FO 22-19-25 |  | 29/12/2025 | 31/12/2026 |  | Forced Out
TOP251022150320 | TO-26-CBR-SVC-01 | CAPACITOR/SVC/REACTOR - CASTLEBAR 110-CASTLEBAR 110-SVC | CASTLEBAR 110 | CASTLEBAR 110 | SVC | FO 36-40-24 |  | 29/12/2025 | 31/12/2026 |  | Forced Out
TOP251210160846 | TO-26-DEN-T132-01 | GENERATOR TRANSFORMER - DEENES 110-DEENES 33-T132 | DEENES 110 | DEENES 33 | T132 | FO 24-28-25 Mod 1 |  | 29/12/2025 | 31/12/2500 |  | Forced Out
TOP251022151423 | TO-26-GGO-220K1-2-01 | COUPLER/SECTIONALISING CB - GLANAGOW 220-GLANAGOW 220-220K1-2 | GLANAGOW 220 | GLANAGOW 220 | 220K1-2 | FO 45-14-22 |  | 29/12/2025 | 31/12/2026 |  | Forced Out
TOP251022150927 | TO-26-GI GIS-220SA1-2CB-02 | COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220-GREAT ISLAND GIS 220-220SA1-2CB | GREAT ISLAND GIS 220 | GREAT ISLAND GIS 220 | 220SA1-2CB | FO 21-19-25 |  | 29/12/2025 | 31/12/2026 |  | Forced Out
TOP251203110930 | TO-26-KLN-T2102-01 | TRANSFORMER - KILLONAN 220-KILLONAN 110-T2102 | KILLONAN 220 | KILLONAN 110 | T2102 | FO-43-25 Mod 4 |  | 29/12/2025 | 31/12/2026 |  | Forced Out
TOP251022150443 | TO-26-MUL-CAP2-01 | CAPACITOR/SVC/REACTOR - MULLINGAR 110-MULLINGAR 110-CAP2 | MULLINGAR 110 | MULLINGAR 110 | CAP2 | FO 33-48-24 |  | 29/12/2025 | 31/12/2026 |  | Forced Out
TOP251022150041 | TO-26-PB-R2001-03 | CAPACITOR/SVC/REACTOR - POOLBEG 220-POOLBEG 220-R2001 | POOLBEG 220 | POOLBEG 220 | R2001 | FO 30-42-24 |  | 29/12/2025 | 31/12/2026 |  | Forced Out
TOP251022151307 | TO-26-SKL-M/CAP2-01 | CAPACITOR/SVC/REACTOR - SHANKILL 110-SHANKILL 110-M/CAP2 | SHANKILL 110 | SHANKILL 110 | M/CAP2 | FO 32-34-25 |  | 29/12/2025 | 31/12/2026 |  | Forced Out
TOP251203111612 | TO-26-TB-T2003-01 | GENERATOR TRANSFORMER - TARBERT 220-TARBERT G3-T2003 | TARBERT 220 | TARBERT G3 | T2003 | FO 14-08-23 |  | 29/12/2025 | 31/12/2500 |  | Forced Out
TOP251203111357 | TO-26-THU-STATCOM-05 | CAPACITOR/SVC/REACTOR - THURLES 110-THURLES 110-STATCOM | THURLES 110 | THURLES 110 | STATCOM | FO 22-46-25 |  | 29/12/2025 | 31/12/2026 |  | Forced Out
TOP251210160410 | TO-26-TRL-CAP2-01 | CAPACITOR/SVC/REACTOR - TRALEE 110-TRALEE 110-CAP2 | TRALEE 110 | TRALEE 110 | CAP2 | FO 26-49-25 |  | 29/12/2025 | 31/12/2500 |  | Forced Out
CAPX2025093016214500 | TO-26-MR-T107-01 | GENERATOR TRANSFORMER - MARINA 110-MARINA GT-T107 | MARINA 110 | MARINA GT | T107 | Condition Assessment, protection settings change, relabelling GIS, DSO protection relay | CC0506 | 01/01/2026 | 27/08/2026 |  | Scheduled |  | 114
CAPX2025120508364004 | TO-26-MR-T107-01 | GENERATOR TRANSFORMER - MARINA 110-MARINA GT-T107 | MARINA 110 | MARINA GT | T107 | EI: Simultaneous MR-T107 + MR-TBG-1: EI of H5/T107 110kV Bay, new 110kV cable to new 110/38kV Trafo including NEW 38kV Module | CC0506 | 01/01/2026 | 27/08/2026 |  | Scheduled |  | 2
CAPX2025093016214503 | TO-26-MR-T107-01 | GENERATOR TRANSFORMER - MARINA 110-MARINA GT-T107 | MARINA 110 | MARINA GT | T107 | Simultaneous 110 kV A1/B1 IN TURN @ MR + MR-T107: Condition Assessment & Commissioning of H5/T107 bay | CC0506 | 01/01/2026 | 27/08/2026 |  | Scheduled |  | 65
TOP251128162121 | TO-26-110 kV A4 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110A4 | CASTLEBAGOT 110 | CASTLEBAGOT 110 | 110A4 | CBT 110 A4/B4 in turn as a consequence of OS on 110K4 bay |  | 05/01/2026 | 09/01/2026 |  | Scheduled
TOP251128162548 | TO-26-110 kV B4 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B4 | CASTLEBAGOT 110 | CASTLEBAGOT 110 | 110B4 | CBT 110 A4/B4 in turn as a consequence of OS on 110K4 bay |  | 05/01/2026 | 09/01/2026 |  | Scheduled
OD2026 | TO-26-CBT-110K4-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K4 | CASTLEBAGOT 110 | CASTLEBAGOT 110 | 110K4 | Total Maintenance Outage Duration Requested |  | 05/01/2026 | 09/01/2026 |  | Scheduled |  | 5
24EG24143 | TO-26-CBT-110K4-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K4 | CASTLEBAGOT 110 | CASTLEBAGOT 110 | 110K4 | 110kV GIS Cubicle Ordinary Service | 901542553 | 05/01/2026 | 09/01/2026 | 4 | Scheduled |  | 5 | A4/B4 110 KV IN TURN
TOP250609173530 | TO-26-CBT-110K4-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K4 | CASTLEBAGOT 110 | CASTLEBAGOT 110 | 110K4 | CBT 110 A4/B4 in turn as a consequence of OS on 110K4 bay |  | 05/01/2026 | 09/01/2026 |  | Scheduled
TOP250609173716 | TO-26-CBT-110SA2-4CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SA2-4CB | CASTLEBAGOT 110 | CASTLEBAGOT 110 | 110SA2-4CB | CBT 110 A4/B4 in turn as a consequence of OS on 110K4 bay |  | 05/01/2026 | 09/01/2026 |  | Scheduled
TOP250609173744 | TO-26-CBT-110SB2-4CB-01 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB2-4CB | CASTLEBAGOT 110 | CASTLEBAGOT 110 | 110SB2-4CB | CBT 110 A4/B4 in turn as a consequence of OS on 110K4 bay |  | 05/01/2026 | 09/01/2026 |  | Scheduled
OD0096 | TO-26-CHA-MAL-1-02 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | CHARLEVILLE 110 | MALLOW 110 | 1 | Total Maintenance Outage Duration Requested |  | 05/01/2026 | 09/01/2026 |  | Scheduled |  | 5
24CM0261 | TO-26-CHA-MAL-1-02 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | CHARLEVILLE 110 | MALLOW 110 | 1 | O-Ring Replacement to prevent SF6 leaks | 901543265 | 05/01/2026 | 09/01/2026 | 1 | Scheduled |  | 3 | N
24CM0257 | TO-26-CHA-MAL-1-02 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | CHARLEVILLE 110 | MALLOW 110 | 1 | O-Ring Replacement to prevent SF6 leaks | 901543264 | 05/01/2026 | 09/01/2026 | 1 | Scheduled |  | 3 | NO
TOP250304135754 | TO-26-CHA-MAL-1-02 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | CHARLEVILLE 110 | MALLOW 110 | 1 | Replacement of Poleset 80 & 87 due to lightning damage | 901685017 | 05/01/2026 | 09/01/2026 |  | Scheduled
24CM0170 | TO-26-CHA-MAL-1-02 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | CHARLEVILLE 110 | MALLOW 110 | 1 | O1-Protection Maintenance of 7SA & GRL | 901505666 | 05/01/2026 | 09/01/2026 | 4 | Scheduled |  | 3 | N
24LN7243 | TO-26-CHA-MAL-1-02 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | CHARLEVILLE 110 | MALLOW 110 | 1 | 2024LP-1[30]- S2 Drone (U-Bolts) | 901592678 | 05/01/2026 | 09/01/2026 | 4 | Scheduled |  | 1 | NO
25EG10145 | TO-26-CHA-MAL-1-02 | 110kV FEEDER - CHARLEVILLE 110-MALLOW 110-1 | CHARLEVILLE 110 | MALLOW 110 | 1 | 110kV SF6 Cubicle Operational Test | 901678269 | 05/01/2026 | 09/01/2026 | 4 | Scheduled |  | 1
TOP251128170050 | TO-26-220 kV A2 @ FIN-05 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220A2 | FINGLAS 220 | FINGLAS 220 | 220A2 | FIN 220 kV A2/B2 IN TURN required as consequence for 220 K2 OS |  | 05/01/2026 | 09/01/2026 |  | Scheduled |  | 7
TOP251128170234 | TO-26-220 kV B2 @ FIN-03 | BUSBAR SECTION - FINGLAS 220-FINGLAS 220-220B2 | FINGLAS 220 | FINGLAS 220 | 220B2 | FIN 220 kV A2/B2 IN TURN required as consequence for 220 K2 OS |  | 05/01/2026 | 09/01/2026 |  | Scheduled |  | 7
25EG24289 | TO-26-FIN-220K2-05 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | FINGLAS 220 | FINGLAS 220 | 220K2 | 220kV GIS Cubicle Ordinary Service | 901678229 | 05/01/2026 | 09/01/2026 | 4 | Scheduled |  | 7 | A2/B2 220 KV IN TURN
PROT25220 | TO-26-FIN-220K2-05 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | FINGLAS 220 | FINGLAS 220 | 220K2 | P3 Protection maintenance of 7SJ611 |  | 05/01/2026 | 09/01/2026 |  | Scheduled |  | 2
OD1759 | TO-26-FIN-220K2-05 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | FINGLAS 220 | FINGLAS 220 | 220K2 | Total Maintenance Outage Duration Requested |  | 05/01/2026 | 09/01/2026 |  | Scheduled |  | 7
TOP251128165923 | TO-26-FIN-220K2-05 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220K2 | FINGLAS 220 | FINGLAS 220 | 220K2 | FIN 220 kV A2/B2 IN TURN required as consequence for 220 K2 OS |  | 05/01/2026 | 09/01/2026 |  | Scheduled
TOP251201141018 | TO-26-FIN-220SA1-2CB-06 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SA1-2CB | FINGLAS 220 | FINGLAS 220 | 220SA1-2CB | FIN 220 kV A2/B2 IN TURN required as consequence for 220 K2 OS |  | 05/01/2026 | 09/01/2026 |  | Scheduled
TOP251201140920 | TO-26-FIN-220SB1-2CB-04 | COUPLER/SECTIONALISING CB - FINGLAS 220-FINGLAS 220-220SB1-2CB | FINGLAS 220 | FINGLAS 220 | 220SB1-2CB | FIN 220 kV A2/B2 IN TURN required as consequence for 220 K2 OS |  | 05/01/2026 | 09/01/2026 |  | Scheduled
CAPX2025082811210946 | TO-26-220 kV A2 @ FLA-01 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220A2 | FLAGFORD 220 | FLAGFORD 220 | 220A2 | 220 kV A2/B2 IN TURN @ FLA: civils works for construction of new F10 Louth 220kv line bay | CP0799 | 05/01/2026 | 27/02/2026 |  | Scheduled |  | 30
CAPX2025082811210947 | TO-26-220 kV B2 @ FLA-01 | BUSBAR SECTION - FLAGFORD 220-FLAGFORD 220-220B2 | FLAGFORD 220 | FLAGFORD 220 | 220B2 | 220 kV A2/B2 IN TURN @ FLA: civils works for construction of new F10 Louth 220kv line bay | CP0799 | 05/01/2026 | 27/02/2026 |  | Scheduled |  | 30
TOP251202081054 | TO-26-GWE-T102-01 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T102 | GORTAWEE 110 | GORTAWEE 10 | T102 | 110kV SF6 Cubical Ordinary Service( Excludes Busbar disconnets) | 901542818 | 05/01/2026 | 09/01/2026 |  | Scheduled |  | 5
TOP251202080842 | TO-26-GWE-T102-01 | TSO CUSTOMER TRANSFORMER - GORTAWEE 110-GORTAWEE 10-T102 | GORTAWEE 110 | GORTAWEE 10 | T102 | Total Maintenance Outage duration required |  | 05/01/2026 | 09/01/2026 |  | Scheduled |  | 5
25EG24229 | TO-26-KPG-TRL-1-01 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-1 | KILPADDOGE 110 | TRALEE 110 | 1 | Cable Insp. 110kV XLPE | 901675755 | 05/01/2026 | 09/01/2026 | 4 | Scheduled |  | 2
OD1684 | TO-26-KPG-TRL-1-01 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-1 | KILPADDOGE 110 | TRALEE 110 | 1 | Total Maintenance Outage Duration Requested |  | 05/01/2026 | 09/01/2026 |  | Scheduled |  | 5
25LN7581 | TO-26-KPG-TRL-1-01 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-1 | KILPADDOGE 110 | TRALEE 110 | 1 | 2025CM_Insp GIS Connex 5S Term_OD2Days | 901701996 | 05/01/2026 | 09/01/2026 | 2 | Scheduled |  | 2 | no
25CM0545 | TO-26-KPG-TRL-1-01 | 110kV FEEDER - KILPADDOGE 110-TRALEE 110-1 | KILPADDOGE 110 | TRALEE 110 | 1 | 01 H9 Sf6 Leak Repair | 901671167 | 05/01/2026 | 09/01/2026 |  | Scheduled
CAPX2025082811210928 | TO-26-220 kV A2 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220A2 | LOUTH 220 | LOUTH 220 | 220A2 | 220 kV A2/B2 IN TURN @ LOU: civils works for construction of new F14 Flagford 220kv line bay | CP0799 | 05/01/2026 | 27/02/2026 |  | Scheduled |  | 39
CAPX2025082811210929 | TO-26-220 kV B2 @ LOU-01 | BUSBAR SECTION - LOUTH 220-LOUTH 220-220B2 | LOUTH 220 | LOUTH 220 | 220B2 | 220 kV A2/B2 IN TURN @ LOU: civils works for construction of new F14 Flagford 220kv line bay | CP0799 | 05/01/2026 | 27/02/2026 |  | Scheduled |  | 39
CAPX2025120913292900 | TO-26-BNK-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - BARNAKYLE 110-BARNAKYLE 110-110SA1-2CB | BARNAKYLE 110 | BARNAKYLE 110 | 110SA1-2CB | 110kV A2 @ BNK: BCU verification & Sending signals back to EirGrid. Commissioning Activities to facilitate Cables work (Busbar interlocking test & VT commissioning) | CP1256 | 06/01/2026 | 19/01/2026 |  | Scheduled |  | 10
CAPX2025120913292901 | TO-26-BNK-CBT-2-02 | 110kV FEEDER - BARNAKYLE 110-CASTLEBAGOT 110-2 | BARNAKYLE 110 | CASTLEBAGOT 110 | 2 | 110kV A2 @ BNK: BCU verification & Sending signals back to EirGrid. Commissioning Activities to facilitate Cables work (Busbar interlocking test & VT commissioning) | CP1256 | 06/01/2026 | 19/01/2026 |  | Scheduled |  | 10
CAPX2025120913292902 | TO-26-BNK-T122-01 | TSO CUSTOMER TRANSFORMER - BARNAKYLE 110-BARNAKYLE 20-T122 | BARNAKYLE 110 | BARNAKYLE 20 | BNK-T122 | 110kV A2 @ BNK: BCU verification & Sending signals back to EirGrid. Commissioning Activities to facilitate Cables work (Busbar interlocking test & VT commissioning) | CP1256 | 06/01/2026 | 19/01/2026 |  | Scheduled |  | 10
25EG10090 | TO-26-BUT-CUL-1-01 | 110kV FEEDER - BUTLERSTOWN 110-CULLENAGH 110-1 | BUTLERSTOWN 110 | CULLENAGH 110 | 1 | 110kV SF6 Cubicle Operational Test | 901679047 | 06/01/2026 | 07/01/2026 | 4 | Scheduled |  | 1
24LN7210 | TO-26-BUT-CUL-1-01 | 110kV FEEDER - BUTLERSTOWN 110-CULLENAGH 110-1 | BUTLERSTOWN 110 | CULLENAGH 110 | 1 | 2024LP-1[40]Check Structure Poles | 901593232 | 06/01/2026 | 07/01/2026 | 4 | Scheduled |  | 1 | No
25EG10089 | TO-26-BUT-CUL-1-01 | 110kV FEEDER - BUTLERSTOWN 110-CULLENAGH 110-1 | BUTLERSTOWN 110 | CULLENAGH 110 | 1 | 110kV SF6 Cubicle Operational Test | 901678366 | 06/01/2026 | 07/01/2026 | 4 | Scheduled |  | 1
OD0061 | TO-26-BUT-CUL-1-01 | 110kV FEEDER - BUTLERSTOWN 110-CULLENAGH 110-1 | BUTLERSTOWN 110 | CULLENAGH 110 | 1 | Total Maintenance Outage Duration Requested |  | 06/01/2026 | 07/01/2026 |  | Scheduled |  | 2
24EG25615 | TO-26-GLN-110K1-01 | COUPLER/SECTIONALISING CB - GALLANSTOWN 110-GALLANSTOWN 110-110K1 | GALLANSTOWN 110 | GALLANSTOWN 110 | 110K1 | 110kV SF6 Cubicle Operational Test | 901678832 | 06/01/2026 | 06/01/2026 | 4 | Scheduled |  | 1
OD2052 | TO-26-GLN-110K1-01 | COUPLER/SECTIONALISING CB - GALLANSTOWN 110-GALLANSTOWN 110-110K1 | GALLANSTOWN 110 | GALLANSTOWN 110 | 110K1 | Total Maintenance Outage Duration Requested |  | 06/01/2026 | 06/01/2026 |  | Scheduled |  | 1
CAPX2025092408392500 | TO-26-MID-110SA1-02 | SECTIONALISING DISCONNECT - MIDLETON 110-MIDLETON 110-110SA1 | MIDLETON 110 | MIDLETON 110 | 110SA1 | As a consequence of MID-110SA2: 110 kV A2 @ MID: EI: Install new uprated 110 kV A2 Busbar,and new SA2. New DA for T102 and Whitegate. Install new T142 and associated bay. Protection upgrade for T102. | CP1449 | 06/01/2026 | 16/06/2026 |  | Scheduled |  | 110
CAPX2025092408392501 | TO-26-MID-110SA2-01 | SECTIONALISING DISCONNECT - MIDLETON 110-MIDLETON 110-110SA2 | MIDLETON 110 | MIDLETON 110 | 110SA2 | 110 kV A2 @ MID: EI: Install new uprated 110 kV A2 Busbar,and new SA2. New DA for T102 and Whitegate. Install new T142 and associated bay. Protection upgrade for T102. | CP1449 | 06/01/2026 | 16/06/2026 |  | Scheduled |  | 110
CAPX2025092408392502 | TO-26-MID-T102-01 | DISTRIBUTION TRANSFORMER - MIDLETON 110-MIDLETON 10-T102 | MIDLETON 110 | MIDLETON 10 | T102 | 110 kV A2 @ MID: EI: Install new uprated 110 kV A2 Busbar,and new SA2. New DA for T102 and Whitegate. Install new T142 and associated bay. Protection upgrade for T102. | CP1449 | 06/01/2026 | 16/06/2026 |  | Reference |  | 110
CAPX2025092408392503 | TO-26-MID-WHI-1-01 | 110kV FEEDER - MIDLETON 110-WHITEGATE 110-1 | MIDLETON 110 | WHITEGATE 110 | 1 | 110 kV A2 @ MID: EI: Install new uprated 110 kV A2 Busbar,and new SA2. New DA for T102 and Whitegate. Install new T142 and associated bay. Protection upgrade for T102. | CP1449 | 06/01/2026 | 16/06/2026 |  | Scheduled |  | 110
OD2297 | TO-26-AUN-110K1-01 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110K1 | AUNGIERSTOWN 110 | AUNGIERSTOWN 110 | 110K1 | Total Maintenance Outage Duration Requested |  | 07/01/2026 | 09/01/2026 |  | Scheduled |  | 1
25EG26072 | TO-26-AUN-110K1-01 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110K1 | AUNGIERSTOWN 110 | AUNGIERSTOWN 110 | 110K1 | 110kV GIS Cubicle Operational Test |  | 07/01/2026 | 09/01/2026 | 4 | Scheduled |  | 1
TOP250210170849 | TO-26-AUN-110K1-01 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110K1 | AUNGIERSTOWN 110 | AUNGIERSTOWN 110 | 110K1 | In turn with 110SA1-2CB and 110SB1-2CB |  | 07/01/2026 | 09/01/2026 |  | Scheduled
25EG26061 | TO-26-AUN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110SA1-2CB | AUNGIERSTOWN 110 | AUNGIERSTOWN 110 | 110SA1-2CB | 110kV GIS Cubicle Operational Test |  | 07/01/2026 | 09/01/2026 | 4 | Scheduled |  | 1
TOP250210170952 | TO-26-AUN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110SA1-2CB | AUNGIERSTOWN 110 | AUNGIERSTOWN 110 | 110SA1-2CB | In turn with K1 and 110SB1-2CB |  | 07/01/2026 | 09/01/2026 |  | Scheduled
OD2298 | TO-26-AUN-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110SA1-2CB | AUNGIERSTOWN 110 | AUNGIERSTOWN 110 | 110SA1-2CB | Total Maintenance Outage Duration Requested |  | 07/01/2026 | 09/01/2026 |  | Scheduled |  | 1
TOP250210171035 | TO-26-AUN-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110SB1-2CB | AUNGIERSTOWN 110 | AUNGIERSTOWN 110 | 110SB1-2CB | In turn with K1 and 110SA1-2CB |  | 07/01/2026 | 09/01/2026 |  | Scheduled
25EG26068 | TO-26-AUN-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110SB1-2CB | AUNGIERSTOWN 110 | AUNGIERSTOWN 110 | 110SB1-2CB | 110kV GIS Cubicle Operational Test |  | 07/01/2026 | 09/01/2026 | 4 | Scheduled |  | 1
OD2299 | TO-26-AUN-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110-AUNGIERSTOWN 110-110SB1-2CB | AUNGIERSTOWN 110 | AUNGIERSTOWN 110 | 110SB1-2CB | Total Maintenance Outage Duration Requested |  | 07/01/2026 | 09/01/2026 |  | Scheduled |  | 1
PROT25206 | TO-26-CLG-110K2-01 | COUPLER/SECTIONALISING CB - CLOGHRAN 110-CLOGHRAN 110-110K2 | CLOGHRAN 110 | CLOGHRAN 110 | 110K2 | P1 Protection maintenance of 7SJ611 |  | 07/01/2026 | 08/01/2026 |  | Scheduled |  | 2
TOP251128164509 | TO-26-110 kV B2 @ CBT-01 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B2 | CASTLEBAGOT 110 | CASTLEBAGOT 110 | 110B2 | CBT 110 B2/B4 in turn as a consequence of OS on 110SB2-4 bay |  | 12/01/2026 | 16/01/2026 |  | Scheduled |  | 5
TOP251128164628 | TO-26-110 kV B4 @ CBT-02 | BUSBAR SECTION - CASTLEBAGOT 110-CASTLEBAGOT 110-110B4 | CASTLEBAGOT 110 | CASTLEBAGOT 110 | 110B4 | CBT 110 B2/B4 in turn as a consequence of OS on 110SB2-4 bay |  | 12/01/2026 | 16/01/2026 |  | Scheduled |  | 5
TOP251201133705 | TO-26-CBT-110K4-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110K4 | CASTLEBAGOT 110 | CASTLEBAGOT 110 | 110K4 | CBT 110 B1/B2 and B2/B4 in turn requried as a consequence of CBT 110 SB1-2 CB and SB2-4 CB OS |  | 12/01/2026 | 16/01/2026 |  | Scheduled
OD1643 | TO-26-CBT-110SB2-4CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB2-4CB | CASTLEBAGOT 110 | CASTLEBAGOT 110 | 110SB2-4CB | Total Maintenance Outage Duration Requested |  | 12/01/2026 | 16/01/2026 |  | Scheduled |  | 5
24EG24167 | TO-26-CBT-110SB2-4CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB2-4CB | CASTLEBAGOT 110 | CASTLEBAGOT 110 | 110SB2-4CB | 110kV GIS Cubicle Ordinary Service (Including the B2 & B4 Disconnects) | 901542559 | 12/01/2026 | 16/01/2026 | 4 | Scheduled |  | 5 | B2&B4 110 KV IN TURN
TOP251128164402 | TO-26-CBT-110SB2-4CB-02 | COUPLER/SECTIONALISING CB - CASTLEBAGOT 110-CASTLEBAGOT 110-110SB2-4CB | CASTLEBAGOT 110 | CASTLEBAGOT 110 | 110SB2-4CB | CBT 110 B2/B4 in turn as a consequence of OS on 110SB2-4 bay |  | 12/01/2026 | 16/01/2026 |  | Scheduled |  | 5
25EG26206 | TO-26-LIS-LSA-1-04 | 110kV FEEDER - LISDRUM 110-LISLEA 110-1 | LISDRUM 110 | LISLEA 110 | 1 | 110kV GIS Cubicle Operational Test |  | 12/01/2026 | 21/01/2026 | 4 | Scheduled |  | 2 | A1/B1 110KV BUSBARS IN TURN
OD0213 | TO-26-LIS-LSA-1-04 | 110kV FEEDER - LISDRUM 110-LISLEA 110-1 | LISDRUM 110 | LISLEA 110 | 1 | Total Maintenance Outage Duration Requested |  | 12/01/2026 | 21/01/2026 |  | Scheduled |  | 8
25EG00641 | TO-26-LIS-LSA-1-04 | 110kV FEEDER - LISDRUM 110-LISLEA 110-1 | LISDRUM 110 | LISLEA 110 | 1 | 110KV Cubicle Condition Assessment (excludes busbar disconnects) | 901678314 | 12/01/2026 | 21/01/2026 | 4 | Scheduled |  | 3 | No
25EG00639 | TO-26-LIS-LSA-1-04 | 110kV FEEDER - LISDRUM 110-LISLEA 110-1 | LISDRUM 110 | LISLEA 110 | 1 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects) | 901678315 | 12/01/2026 | 21/01/2026 | 4 | Scheduled |  | 4 | No
25EG26218 | TO-26-LIS-LSA-1-04 | 110kV FEEDER - LISDRUM 110-LISLEA 110-1 | LISDRUM 110 | LISLEA 110 | 1 | Cable Insp. 110kV XLPE |  | 12/01/2026 | 21/01/2026 |  | Scheduled |  | 2
TOP251209103307 | TO-26-PRO-TB-1-02 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | PROSPECT 220 | TARBERT 220 | 1 | 2025FCI-1[4]Sus/Dup 220kV Replace | 901682099 | 12/01/2026 | 20/01/2026 |  | Scheduled
TOP251209103320 | TO-26-PRO-TB-1-02 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | PROSPECT 220 | TARBERT 220 | 1 | 2025CM_Rplce Cath_Prot Batt_Sys OD7Days | 901504158 | 12/01/2026 | 20/01/2026 |  | Scheduled
TOP251209103313 | TO-26-PRO-TB-1-02 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | PROSPECT 220 | TARBERT 220 | 1 | 2025CM_Rplce Cath_Prot Batt_Sys OD7Days | 901675142 | 12/01/2026 | 20/01/2026 |  | Scheduled
TOP251209103135 | TO-26-PRO-TB-1-02 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | PROSPECT 220 | TARBERT 220 | 1 | 2025FCI-1[19]Sus/Dup 220kV Replace | 901682114 | 12/01/2026 | 20/01/2026 |  | Scheduled
TOP251209103124 | TO-26-PRO-TB-1-02 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | PROSPECT 220 | TARBERT 220 | 1 | 2025FCI-1[22]Sus/Dup 220kV Replace | 901682117 | 12/01/2026 | 20/01/2026 |  | Scheduled
TOP251209103242 | TO-26-PRO-TB-1-02 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | PROSPECT 220 | TARBERT 220 | 1 | 2025FCI-1[17]Sus/Dup 220kV Replace | 901682112 | 12/01/2026 | 20/01/2026 |  | Scheduled
TOP251209103143 | TO-26-PRO-TB-1-02 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | PROSPECT 220 | TARBERT 220 | 1 | 2025FCI-1[18]Sus/Dup 220kV Replace | 901682113 | 12/01/2026 | 20/01/2026 |  | Scheduled
TOP251209103108 | TO-26-PRO-TB-1-02 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | PROSPECT 220 | TARBERT 220 | 1 | 2025FCI-1[23]Sus/Dup 220kV Replace | 901682118 | 12/01/2026 | 20/01/2026 |  | Scheduled
TOP251209103049 | TO-26-PRO-TB-1-02 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | PROSPECT 220 | TARBERT 220 | 1 | Confirm the SF6 pressure in the Tarbert Cubical in Prospect Station, No DOF required |  | 12/01/2026 | 20/01/2026 |  | Scheduled
TOP251209103257 | TO-26-PRO-TB-1-02 | 220kV FEEDER - PROSPECT 220-TARBERT 220-1 | PROSPECT 220 | TARBERT 220 | 1 | 2025FCI-1[16]Sus/Dup 220kV Replace | 901682111 | 12/01/2026 | 20/01/2026 |  | Scheduled
TOP250702121034 | TO-26-110 kV A2 @ SNU-01 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110A2 | SNUGBOROUGH 110 | SNUGBOROUGH 110 | 110A2 | SNU 110 A2/B2 IN TURN required as consequence of maintenance on SNU K2 |  | 12/01/2026 | 21/01/2026 |  | Scheduled
TOP250702121127 | TO-26-110 kV B2 @ SNU-01 | BUSBAR SECTION - SNUGBOROUGH 110-SNUGBOROUGH 110-110B2 | SNUGBOROUGH 110 | SNUGBOROUGH 110 | 110B2 | SNU 110 A2/B2 IN TURN required as consequence of maintenance on SNU K2 |  | 12/01/2026 | 21/01/2026 |  | Scheduled
TOP250702120858 | TO-26-SNU-110K2-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K2 | SNUGBOROUGH 110 | SNUGBOROUGH 110 | 110K2 | SNU 110 A2/B2 IN TURN required as consequence |  | 12/01/2026 | 21/01/2026 |  | Scheduled
23EG23696 | TO-26-SNU-110K2-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K2 | SNUGBOROUGH 110 | SNUGBOROUGH 110 | 110K2 | 110kV SF6 Cubicle Ordinary Service | 901396863 | 12/01/2026 | 21/01/2026 | 3 | Scheduled |  | 4 | A2/B2 110 KV IN TURN
OD1282 | TO-26-SNU-110K2-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K2 | SNUGBOROUGH 110 | SNUGBOROUGH 110 | 110K2 | Total Maintenance Outage Duration Requested |  | 12/01/2026 | 21/01/2026 |  | Scheduled |  | 8
PROT25273 | TO-26-SNU-110K2-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K2 | SNUGBOROUGH 110 | SNUGBOROUGH 110 | 110K2 | P3 Protection maintenance of 7SJ611 |  | 12/01/2026 | 21/01/2026 |  | Scheduled |  | 2
23EG24484 | TO-26-SNU-110K2-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110K2 | SNUGBOROUGH 110 | SNUGBOROUGH 110 | 110K2 | Inspect Densimeters on GIS Switchgear | 901397273 | 12/01/2026 | 21/01/2026 | 1 | Scheduled |  | 3 | A2/B2, SA1-2, SB1-2
TOP250526144749 | TO-26-SNU-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | SNUGBOROUGH 110 | SNUGBOROUGH 110 | 110SA1-2CB | SNU 110 A1/A2 bars required as a consequence of densimeter inspection on SNU 110 SA1-2CB |  | 12/01/2026 | 21/01/2026 |  | Scheduled
TOP250702121206 | TO-26-SNU-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | SNUGBOROUGH 110 | SNUGBOROUGH 110 | 110SA1-2CB | SNU 110 A2/B2 IN TURN required as consequence of maintenance on SNU K2 |  | 12/01/2026 | 21/01/2026 |  | Scheduled
OD1283 | TO-26-SNU-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | SNUGBOROUGH 110 | SNUGBOROUGH 110 | 110SA1-2CB | Total Maintenance Outage Duration Requested |  | 12/01/2026 | 21/01/2026 |  | Scheduled |  | 4
23EG24485 | TO-26-SNU-110SA1-2CB-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SA1-2CB | SNUGBOROUGH 110 | SNUGBOROUGH 110 | 110SA1-2CB | Inspect Densimeters on GIS Switchgear | 901406878 | 12/01/2026 | 21/01/2026 | 1 | Scheduled |  | 3 | A2/B2, SA1-2, SB1-2
TOP250702121301 | TO-26-SNU-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | SNUGBOROUGH 110 | SNUGBOROUGH 110 | 110SB1-2CB | SNU 110 A2/B2 IN TURN required as consequence of maintenance on SNU K2 |  | 12/01/2026 | 21/01/2026 |  | Scheduled
23EG23694 | TO-26-SNU-110SB1-2CB-01 | COUPLER/SECTIONALISING CB - SNUGBOROUGH 110-SNUGBOROUGH 110-110SB1-2CB | SNUGBOROUGH 110 | SNUGBOROUGH 110 | 110SB1-2CB | Inspect Densimeters on GIS Switchgear | 901406879 | 12/01/2026 | 21/01/2026 | 1 | Scheduled |  | 3
TOP251209233104 | TO-26-TTU-131-01 | GENERATOR TRANSFORMER - TULLABEG 110-TULLABEG 33-T131 | TULLABEG 110 | TULLABEG 110 | T131 | 110kV Cubical Operational test |  | 12/01/2026 | 20/01/2026 |  | Scheduled
TOP251209233108 | TO-26-TTU-131-01 | GENERATOR TRANSFORMER - TULLABEG 110-TULLABEG 33-T131 | TULLABEG 110 | TULLABEG 110 | T131 | Cable Inspection |  | 12/01/2026 | 20/01/2026 |  | Scheduled
TOP251007094724 | TO-26-TTU-131-01 | GENERATOR TRANSFORMER - TULLABEG 110-TULLABEG 33-T131 | TULLABEG 110 | TULLABEG 110 | T131 | Customer request to switch out at 08:00 on 12th Jan & switch back in at 11:00 on 20th Jan |  | 12/01/2026 | 20/01/2026 |  | Scheduled |  | 7
OD2042 | TO-26-CRU-220K1-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220K1 | CRUISERATH 220 | CRUISERATH 220 | 220K1 | Total Maintenance Outage Duration Requested |  | 13/01/2026 | 13/01/2026 |  | Scheduled |  | 1
TOP250702122650 | TO-26-CRU-220K1-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220K1 | CRUISERATH 220 | CRUISERATH 220 | 220K1 | Cruiserath 220 K1, K2, SA1-2CB and SB1-2CB IN TURN |  | 13/01/2026 | 13/01/2026 |  | Scheduled
24EG25294 | TO-26-CRU-220K1-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220K1 | CRUISERATH 220 | CRUISERATH 220 | 220K1 | 220kV SF6 Cubicle Operational Test | 901678838 | 13/01/2026 | 13/01/2026 | 4 | Scheduled |  | 1
25EG26222 | TO-26-DRY-OBE-1-02 | 110kV FEEDER - DRYBRIDGE 110-OLDBRIDGE 110-1 | DRYBRIDGE 110 | OLDBRIDGE 110 | 1 | 110kV GIS Cubicle Operational Test | 901709797 | 13/01/2026 | 16/01/2026 | 4 | Scheduled |  | 2 | A1/B1 110KV BUSBARS IN TURN
25CM0663 | TO-26-DRY-OBE-1-02 | 110kV FEEDER - DRYBRIDGE 110-OLDBRIDGE 110-1 | DRYBRIDGE 110 | OLDBRIDGE 110 | 1 | Replacement of SF6 isolation block | 901707790 | 13/01/2026 | 16/01/2026 | 3 | Scheduled |  | 4 | no
TOP251201151419 | TO-26-CAH-TIP-1-01 | 110kV FEEDER - CAHIR 110-TIPPERARY 110-1 | CAHIR 110 | TIPPERARY 110 | 1 | As a consequence of TIPPERARY 110SA2 Op. test |  | 14/01/2026 | 14/01/2026 |  | Scheduled
OD2043 | TO-26-CRU-220K2-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220K2 | CRUISERATH 220 | CRUISERATH 220 | 220K2 | Total Maintenance Outage Duration Requested |  | 14/01/2026 | 14/01/2026 |  | Scheduled |  | 1
TOP250702122806 | TO-26-CRU-220K2-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220K2 | CRUISERATH 220 | CRUISERATH 220 | 220K2 | Cruiserath 220 K1, K2, SA1-2CB and SB1-2CB IN TURN |  | 14/01/2026 | 14/01/2026 |  | Scheduled
24EG25298 | TO-26-CRU-220K2-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220K2 | CRUISERATH 220 | CRUISERATH 220 | 220K2 | 220kV SF6 Cubicle Operational Test | 901678841 | 14/01/2026 | 14/01/2026 | 4 | Scheduled |  | 1
OD2366 | TO-26-DGN-RTH-1-01 | 110kV FEEDER - DUNGARVAN 110-RATHNASKILLOGE 110-1 | DUNGARVAN 110 | RATHNASKILLOGE 110 | 1 | Total Maintenance Outage Duration Requested |  | 14/01/2026 | 14/01/2026 |  | Scheduled |  | 1
25EG10198 | TO-26-DGN-RTH-1-01 | 110kV FEEDER - DUNGARVAN 110-RATHNASKILLOGE 110-1 | DUNGARVAN 110 | RATHNASKILLOGE 110 | 1 | 110kV MO Cubicle Operational Test | 901678384 | 14/01/2026 | 14/01/2026 | 4 | Scheduled |  | 1
TOP251202103535 | TO-26-TIP-110SA1-01 | SECTIONALISING DISCONNECT - TIPPERARY 110-TIPPERARY 110-110SA1 | TIPPERARY 110 | TIPPERARY 110 | 110SA1 | As a consequence of TIPPERARY 110SA2 Op. test |  | 14/01/2026 | 14/01/2026 |  | Scheduled
25EG24324 | TO-26-TIP-110SA2-01 | SECTIONALISING DISCONNECT - TIPPERARY 110-TIPPERARY 110-110SA2 | TIPPERARY 110 | TIPPERARY 110 | 110SA2 | 110kV Sect / Dist Operational Test | 901678782 | 14/01/2026 | 14/01/2026 | 4 | Scheduled |  | 1 | NO
OD2239 | TO-26-TIP-110SA2-01 | SECTIONALISING DISCONNECT - TIPPERARY 110-TIPPERARY 110-110SA2 | TIPPERARY 110 | TIPPERARY 110 | 110SA2 | Total Maintenance Outage Duration Requested |  | 14/01/2026 | 14/01/2026 |  | Scheduled |  | 1
24EG25286 | TO-26-CRU-SA1-2CB-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SA1-2CB | CRUISERATH 220 | CRUISERATH 220 | 220SA1-2CB | 220kV SF6 Cubicle Operational Test | 901678839 | 15/01/2026 | 15/01/2026 | 4 | Scheduled |  | 1
OD2044 | TO-26-CRU-SA1-2CB-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SA1-2CB | CRUISERATH 220 | CRUISERATH 220 | 220SA1-2CB | Total Maintenance Outage Duration Requested |  | 15/01/2026 | 15/01/2026 |  | Scheduled |  | 1
TOP250702122858 | TO-26-CRU-SA1-2CB-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SA1-2CB | CRUISERATH 220 | CRUISERATH 220 | 220SA1-2CB | Cruiserath 220 K1, K2, SA1-2CB and SB1-2CB IN TURN |  | 15/01/2026 | 15/01/2026 |  | Scheduled
OD2045 | TO-26-CRU-SB1-2CB-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SB1-2CB | CRUISERATH 220 | CRUISERATH 220 | 220SB1-2CB | Total Maintenance Outage Duration Requested |  | 16/01/2026 | 16/01/2026 |  | Scheduled |  | 1
24EG25290 | TO-26-CRU-SB1-2CB-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SB1-2CB | CRUISERATH 220 | CRUISERATH 220 | 220SB1-2CB | 220kV SF6 Cubicle Operational Test | 901678840 | 16/01/2026 | 16/01/2026 | 4 | Scheduled |  | 1
TOP250702122940 | TO-26-CRU-SB1-2CB-01 | COUPLER/SECTIONALISING CB - CRUISERATH 220-CRUISERATH 220-220SB1-2CB | CRUISERATH 220 | CRUISERATH 220 | 220SB1-2CB | Cruiserath 220 K1, K2, SA1-2CB and SB1-2CB IN TURN |  | 16/01/2026 | 16/01/2026 |  | Scheduled
CAPX2025100613580124 | TO-26-110 kV A4 @ CDU-01 | BUSBAR SECTION - CORDUFF 110-CORDUFF 110-110A4 | CORDUFF 110 | CORDUFF 110 | 110A4 | Simultaneous 110 kV A4 @ CDU + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2) | CP0001 | 18/01/2026 | 18/01/2026 |  | Scheduled |  | 1
CAPX2025100613580118 | TO-26-220 kV B4 @ CDU-01 | BUSBAR SECTION - CORDUFF 220-CORDUFF 220-220B4 | CORDUFF 220 | CORDUFF 220 | 220B4 | Simultaneous 220 kV B4 @ CDU + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2) | CP0001 | 18/01/2026 | 18/01/2026 |  | Scheduled |  | 1
CAPX2025100613580127 | TO-26-CDU-T102-01 | GENERATOR TRANSFORMER - CORDUFF 110-CORDUFF 10.5-T102 | CORDUFF 110 | CORDUFF 10.5 | T102 | Simultaneous CDU-T102 + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2) | CP0001 | 18/01/2026 | 18/01/2026 |  | Scheduled |  | 1
CAPX2025100613580121 | TO-26-CDU-T2104-01 | TRANSFORMER - CORDUFF 220-CORDUFF 110-T2104 | CORDUFF 220 | CORDUFF 110 | T2104 | Simultaneous CDU-T2104 + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2) | CP0001 | 18/01/2026 | 18/01/2026 |  | Scheduled |  | 1
CAPX2025100613580115 | TO-26-CDU-WOO-1-02 | 220kV FEEDER - CORDUFF 220-WOODLAND 220-1 | CORDUFF 220 | WOODLAND 220 | 1 | Simultaneous CDU-WOO-1 + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2) | CP0001 | 18/01/2026 | 18/01/2026 |  | Scheduled |  | 1
CAPX2025100613580100 | TO-26-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | PORTAN 400 | PORTAN 260 | T4301 | Blackstart test path for EWIC to Corduff (FG2) | CP0001 | 18/01/2026 | 18/01/2026 |  | Scheduled |  | 1
CAPX2025100613580102 | TO-26-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | PORTAN 400 | PORTAN 260 | T4301 | As a consequence of PRN-WOO-1: Simultaneous PRN-T4301 + PRN-WOO-1: Blackstart test path for EWIC to Corduff (FG2) | CP0001 | 18/01/2026 | 18/01/2026 |  | Scheduled |  | 1
CAPX2025100613580103 | TO-26-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | PORTAN 400 | PORTAN 260 | T4301 | Simultaneous PRN-T4301 + PRN-WOO-1: Blackstart test path for EWIC to Corduff (FG2) | CP0001 | 18/01/2026 | 18/01/2026 |  | Scheduled |  | 1
CAPX2025100613580106 | TO-26-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | PORTAN 400 | PORTAN 260 | T4301 | Simultaneous 400 kV B1/B2 @ WOO + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2) | CP0001 | 18/01/2026 | 18/01/2026 |  | Scheduled |  | 1
CAPX2025100613580112 | TO-26-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | PORTAN 400 | PORTAN 260 | T4301 | Simultaneous 220 kV B2 @ WOO + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2) | CP0001 | 18/01/2026 | 18/01/2026 |  | Scheduled |  | 1
CAPX2025100613580109 | TO-26-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | PORTAN 400 | PORTAN 260 | T4301 | Simultaneous PRN-T4301 + WOO-T4204: Blackstart test path for EWIC to Corduff (FG2) | CP0001 | 18/01/2026 | 18/01/2026 |  | Scheduled |  | 1
CAPX2025100613580119 | TO-26-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | PORTAN 400 | PORTAN 260 | T4301 | Simultaneous 220 kV B4 @ CDU + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2) | CP0001 | 18/01/2026 | 18/01/2026 |  | Scheduled |  | 1
CAPX2025100613580122 | TO-26-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | PORTAN 400 | PORTAN 260 | T4301 | Simultaneous CDU-T2104 + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2) | CP0001 | 18/01/2026 | 18/01/2026 |  | Scheduled |  | 1
CAPX2025100613580125 | TO-26-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | PORTAN 400 | PORTAN 260 | T4301 | Simultaneous 110 kV A4 @ CDU + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2) | CP0001 | 18/01/2026 | 18/01/2026 |  | Scheduled |  | 1
CAPX2025100613580128 | TO-26-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | PORTAN 400 | PORTAN 260 | T4301 | Simultaneous CDU-T102 + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2) | CP0001 | 18/01/2026 | 18/01/2026 |  | Scheduled |  | 1
CAPX2025100613580116 | TO-26-PRN-T4301-01 | TRANSFORMER - PORTAN 400-PORTAN 260-T4301 | PORTAN 400 | PORTAN 260 | T4301 | Simultaneous CDU-WOO-1 + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2) | CP0001 | 18/01/2026 | 18/01/2026 |  | Scheduled |  | 1
CAPX2025100613580101 | TO-26-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | PORTAN 400 | WOODLAND 400 | 1 | As a consequence of PRN-T4301: Blackstart test path for EWIC to Corduff (FG2) | CP0001 | 18/01/2026 | 18/01/2026 |  | Scheduled |  | 1
CAPX2025100613580104 | TO-26-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | PORTAN 400 | WOODLAND 400 | 1 | As a consequence of PRN-T4301: Simultaneous PRN-T4301 + PRN-WOO-1: Blackstart test path for EWIC to Corduff (FG2) | CP0001 | 18/01/2026 | 18/01/2026 |  | Scheduled |  | 1
CAPX2025100613580105 | TO-26-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | PORTAN 400 | WOODLAND 400 | 1 | Simultaneous PRN-T4301 + PRN-WOO-1: Blackstart test path for EWIC to Corduff (FG2) | CP0001 | 18/01/2026 | 18/01/2026 |  | Scheduled |  | 1
CAPX2025100613580107 | TO-26-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | PORTAN 400 | WOODLAND 400 | 1 | As a consequence of PRN-T4301: Simultaneous 400 kV B1/B2 @ WOO + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2) | CP0001 | 18/01/2026 | 18/01/2026 |  | Scheduled |  | 1
CAPX2025100613580110 | TO-26-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | PORTAN 400 | WOODLAND 400 | 1 | As a consequence of PRN-T4301: Simultaneous PRN-T4301 + WOO-T4204: Blackstart test path for EWIC to Corduff (FG2) | CP0001 | 18/01/2026 | 18/01/2026 |  | Scheduled |  | 1
CAPX2025100613580113 | TO-26-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | PORTAN 400 | WOODLAND 400 | 1 | As a consequence of PRN-T4301: Simultaneous 220 kV B2 @ WOO + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2) | CP0001 | 18/01/2026 | 18/01/2026 |  | Scheduled |  | 1
CAPX2025100613580117 | TO-26-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | PORTAN 400 | WOODLAND 400 | 1 | As a consequence of PRN-T4301: Simultaneous CDU-WOO-1 + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2) | CP0001 | 18/01/2026 | 18/01/2026 |  | Scheduled |  | 1
CAPX2025100613580120 | TO-26-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | PORTAN 400 | WOODLAND 400 | 1 | As a consequence of PRN-T4301: Simultaneous 220 kV B4 @ CDU + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2) | CP0001 | 18/01/2026 | 18/01/2026 |  | Scheduled |  | 1
CAPX2025100613580123 | TO-26-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | PORTAN 400 | WOODLAND 400 | 1 | As a consequence of PRN-T4301: Simultaneous CDU-T2104 + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2) | CP0001 | 18/01/2026 | 18/01/2026 |  | Scheduled |  | 1
CAPX2025100613580126 | TO-26-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | PORTAN 400 | WOODLAND 400 | 1 | As a consequence of PRN-T4301: Simultaneous 110 kV A4 @ CDU + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2) | CP0001 | 18/01/2026 | 18/01/2026 |  | Scheduled |  | 1
CAPX2025100613580129 | TO-26-PRN-WOO-1-01 | 400kV FEEDER - PORTAN 400-WOODLAND 400-1 | PORTAN 400 | WOODLAND 400 | 1 | As a consequence of PRN-T4301: Simultaneous CDU-T102 + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2) | CP0001 | 18/01/2026 | 18/01/2026 |  | Scheduled |  | 1
CAPX2025100613580114 | TO-26-220 kV B2 @ WOO-02 | BUSBAR SECTION - WOODLAND 220-WOODLAND 220-220B2 | WOODLAND 220 | WOODLAND 220 | 220B2 | Simultaneous 220 kV B2 @ WOO + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2) | CP0001 | 18/01/2026 | 18/01/2026 |  | Scheduled |  | 1
CAPX2025100613580108 | TO-26-400 kV B1/B2 @ WOO-01 | BUSBAR SECTION - WOODLAND 400-WOODLAND 400-400B1-B2 | WOODLAND 400 | WOODLAND 400 | 400B1-B2 | Simultaneous 400 kV B1/B2 @ WOO + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2) | CP0001 | 18/01/2026 | 18/01/2026 |  | Scheduled |  | 1
CAPX2025100613580111 | TO-26-WOO-T4204-04 | TRANSFORMER - WOODLAND 400-WOODLAND 220-T4204 | WOODLAND 400 | WOODLAND 220 | T4204 | Simultaneous PRN-T4301 + WOO-T4204: Blackstart test path for EWIC to Corduff (FG2) | CP0001 | 18/01/2026 | 18/01/2026 |  | Scheduled |  | 1

## All
TSO CUSTOMER TRANSFORMER - DARNDALE T121 [Amazon (Darndale)]
TO-26-DND-T121-01 ISO [year]week: [24]7mo - 40we Date: 12 Feb 24 - 30 Sep Duration: 962 Days (680 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1230 | DO | 229 |  | Darndale T121 required out to facilitate works in lead up to EI of Darndale T125. T121 to be decommissioned and replaced with new 63MVA transformer
DISTRIBUTION TRANSFORMER - GREAT ISLAND T141 [SDCC]
TO-26-GI-T141-01 ISO [year]week: [25]14we - 53th Date: 02 Apr 25 - 31 Dec Duration: 639 Days (447 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | E1680 | DO | 40 |  | Upgrading T141 as part of H-I-3932 works
CAPX |  |  | E1680 | DO | 2 |  | EI: Simultaneous 110 kV A1/B1 IN TURN @ GI + GI-T141: Interlocking checks, Energisation Instruction
CAPX |  |  | E1680 | DO | 2 |  | EI: Simultaneous GI-T141 + GI-WAT-1: Energisation of Great Island T141
CAPACITOR/SVC/REACTOR - ATHLONE M/CAP1
TO-26-ATH-M/CAP1-03 ISO week: 1mo - 53th Date: 29 Dec - 31 Dec Duration: 368 Days (254 WD) Status: Forced Out
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | FO 22-19-25
CAPACITOR/SVC/REACTOR - CASTLEBAR SVC
TO-26-CBR-SVC-01 ISO week: 1mo - 53th Date: 29 Dec - 31 Dec Duration: 368 Days (254 WD) Status: Forced Out
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | FO 36-40-24
GENERATOR TRANSFORMER - DEENES T132 [Gaskinstown Solar (DE1)]
TO-26-DEN-T132-01 ISO [year]week: 1mo - N/A Date: 29 Dec - N/A Status: Forced Out
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FO 24-28-25 Mod 1
COUPLER/SECTIONALISING CB - GLANAGOW 220K1-2
TO-26-GGO-220K1-2-01 ISO week: 1mo - 53th Date: 29 Dec - 31 Dec Duration: 368 Days (254 WD) Status: Forced Out
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | FO 45-14-22
COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220SA1-2CB
TO-26-GI GIS-220SA1-2CB-02 ISO week: 1mo - 53th Date: 29 Dec - 31 Dec Duration: 368 Days (254 WD) Status: Forced Out
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | FO 21-19-25
TRANSFORMER - KILLONAN T2102
TO-26-KLN-T2102-01 ISO week: 1mo - 53th Date: 29 Dec - 31 Dec Duration: 368 Days (254 WD) Status: Forced Out
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | FO-43-25 Mod 4
CAPACITOR/SVC/REACTOR - MULLINGAR CAP2
TO-26-MUL-CAP2-01 ISO week: 1mo - 53th Date: 29 Dec - 31 Dec Duration: 368 Days (254 WD) Status: Forced Out
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | FO 33-48-24
CAPACITOR/SVC/REACTOR - POOLBEG R2001
TO-26-PB-R2001-03 ISO week: 1mo - 53th Date: 29 Dec - 31 Dec Duration: 368 Days (254 WD) Status: Forced Out
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | FO 30-42-24
CAPACITOR/SVC/REACTOR - SHANKILL M/CAP2
TO-26-SKL-M/CAP2-01 ISO week: 1mo - 53th Date: 29 Dec - 31 Dec Duration: 368 Days (254 WD) Status: Forced Out
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | FO 32-34-25
GENERATOR TRANSFORMER - TARBERT T2003 [Tarbert TB3]
TO-26-TB-T2003-01 ISO [year]week: 1mo - N/A Date: 29 Dec - N/A Status: Forced Out
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | FO 14-08-23
CAPACITOR/SVC/REACTOR - THURLES STATCOM
TO-26-THU-STATCOM-05 ISO week: 1mo - 53th Date: 29 Dec - 31 Dec Duration: 368 Days (254 WD) Status: Forced Out
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | FO |  |  | FO 22-46-25
CAPACITOR/SVC/REACTOR - TRALEE CAP2
TO-26-TRL-CAP2-01 ISO [year]week: 1mo - N/A Date: 29 Dec - N/A Status: Forced Out
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | FO 26-49-25
GENERATOR TRANSFORMER - MARINA T107
TO-26-MR-T107-01 ISO week: 1th - 35th Date: 01 Jan - 27 Aug Duration: 239 Days (163 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CC0506 | DO | 114 |  | Condition Assessment, protection settings change, relabelling GIS, DSO protection relay
CAPX |  |  | CC0506 | DO | 65 |  | Simultaneous 110 kV A1/B1 IN TURN @ MR + MR-T107: Condition Assessment & Commissioning of H5/T107 bay
CAPX |  |  | CC0506 | DO | 2 |  | EI: Simultaneous MR-T107 + MR-TBG-1: EI of H5/T107 110kV Bay, new 110kV cable to new 110/38kV Trafo including NEW 38kV Module
BUSBAR SECTION - CASTLEBAGOT 110 kV A4
TO-26-110 kV A4 @ CBT-01 ISO week: 2mo - 2fr Date: 05 Jan - 09 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | CBT 110 A4/B4 in turn as a consequence of OS on 110K4 bay
BUSBAR SECTION - CASTLEBAGOT 110 kV B4
TO-26-110 kV B4 @ CBT-01 ISO week: 2mo - 2fr Date: 05 Jan - 09 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | CBT 110 A4/B4 in turn as a consequence of OS on 110K4 bay
COUPLER/SECTIONALISING CB - CASTLEBAGOT 110K4
TO-26-CBT-110K4-01 ISO week: 2mo - 2fr Date: 05 Jan - 09 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | CBT 110 A4/B4 in turn as a consequence of OS on 110K4 bay
N/A | - | - |  | DO | 5 |  | Total Maintenance Outage Duration Requested
OS | CBT | - | 901542553 | DO | 5 | 4 | 110kV GIS Cubicle Ordinary Service
COUPLER/SECTIONALISING CB - CASTLEBAGOT 110SA2-4CB
TO-26-CBT-110SA2-4CB-01 ISO week: 2mo - 2fr Date: 05 Jan - 09 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | CBT 110 A4/B4 in turn as a consequence of OS on 110K4 bay
COUPLER/SECTIONALISING CB - CASTLEBAGOT 110SB2-4CB
TO-26-CBT-110SB2-4CB-01 ISO week: 2mo - 2fr Date: 05 Jan - 09 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | CBT 110 A4/B4 in turn as a consequence of OS on 110K4 bay
110kV FEEDER - CHARLEVILLE MALLOW
TO-26-CHA-MAL-1-02 ISO week: 2mo - 2fr Date: 05 Jan - 09 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  | 901685017 | DO |  |  | Replacement of Poleset 80 & 87 due to lightning damage
N/A | - | - |  | DO | 5 |  | Total Maintenance Outage Duration Requested
| CHA | - | 901543264 | DO | 3 | 1 | O-Ring Replacement to prevent SF6 leaks
OPT | CHA | - | 901678269 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
CORRECT | MAL | - | 901505666 | DO | 3 | 4 | O1-Protection Maintenance of 7SA & GRL
| MAL | - | 901543265 | DO | 3 | 1 | O-Ring Replacement to prevent SF6 leaks
| STH | CK | 901592678 | DO | 1 | 4 | 2024LP-1[30]- S2 Drone (U-Bolts)
BUSBAR SECTION - FINGLAS 220 kV A2
TO-26-220 kV A2 @ FIN-05 ISO week: 2mo - 2fr Date: 05 Jan - 09 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO | 7 |  | FIN 220 kV A2/B2 IN TURN required as consequence for 220 K2 OS
BUSBAR SECTION - FINGLAS 220 kV B2
TO-26-220 kV B2 @ FIN-03 ISO week: 2mo - 2fr Date: 05 Jan - 09 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO | 7 |  | FIN 220 kV A2/B2 IN TURN required as consequence for 220 K2 OS
COUPLER/SECTIONALISING CB - FINGLAS 220K2
TO-26-FIN-220K2-05 ISO week: 2mo - 2fr Date: 05 Jan - 09 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FIN 220 kV A2/B2 IN TURN required as consequence for 220 K2 OS
N/A | - | - |  | DO | 7 |  | Total Maintenance Outage Duration Requested
OS220 | FIN | - | 901678229 | DO | 7 | 4 | 220kV GIS Cubicle Ordinary Service
| FIN |  |  | DO | 2 |  | P3 Protection maintenance of 7SJ611
COUPLER/SECTIONALISING CB - FINGLAS 220SA1-2CB
TO-26-FIN-220SA1-2CB-06 ISO week: 2mo - 2fr Date: 05 Jan - 09 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | FIN 220 kV A2/B2 IN TURN required as consequence for 220 K2 OS
COUPLER/SECTIONALISING CB - FINGLAS 220SB1-2CB
TO-26-FIN-220SB1-2CB-04 ISO week: 2mo - 2fr Date: 05 Jan - 09 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | FIN 220 kV A2/B2 IN TURN required as consequence for 220 K2 OS
BUSBAR SECTION - FLAGFORD 220 kV A2
TO-26-220 kV A2 @ FLA-01 ISO week: 2mo - 9fr Date: 05 Jan - 27 Feb Duration: 54 Days (39 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0799 | DO | 30 |  | 220 kV A2/B2 IN TURN @ FLA: civils works for construction of new F10 Louth 220kv line bay
BUSBAR SECTION - FLAGFORD 220 kV B2
TO-26-220 kV B2 @ FLA-01 ISO week: 2mo - 9fr Date: 05 Jan - 27 Feb Duration: 54 Days (39 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0799 | DO | 30 |  | 220 kV A2/B2 IN TURN @ FLA: civils works for construction of new F10 Louth 220kv line bay
TSO CUSTOMER TRANSFORMER - GORTAWEE T102 [Mannok]
TO-26-GWE-T102-01 ISO week: 2mo - 2fr Date: 05 Jan - 09 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO | 5 |  | Total Maintenance Outage duration required
|  |  | 901542818 | DO | 5 |  | 110kV SF6 Cubical Ordinary Service( Excludes Busbar disconnets)
110kV FEEDER - KILPADDOGE TRALEE 1
TO-26-KPG-TRL-1-01 ISO week: 2mo - 2fr Date: 05 Jan - 09 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
N/A | - | - |  | DO | 5 |  | Total Maintenance Outage Duration Requested
| - | - | 901701996 | DO | 2 | 2 | 2025CM_Insp GIS Connex 5S Term_OD2Days
AMCAB | KPG | - | 901675755 | DO | 2 | 4 | Cable Insp. 110kV XLPE
| KPG | - | 901671167 | DO |  |  | 01 H9 Sf6 Leak Repair
BUSBAR SECTION - LOUTH 220 kV A2
TO-26-220 kV A2 @ LOU-01 ISO week: 2mo - 9fr Date: 05 Jan - 27 Feb Duration: 54 Days (39 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0799 | DO | 39 |  | 220 kV A2/B2 IN TURN @ LOU: civils works for construction of new F14 Flagford 220kv line bay
BUSBAR SECTION - LOUTH 220 kV B2
TO-26-220 kV B2 @ LOU-01 ISO week: 2mo - 9fr Date: 05 Jan - 27 Feb Duration: 54 Days (39 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0799 | DO | 39 |  | 220 kV A2/B2 IN TURN @ LOU: civils works for construction of new F14 Flagford 220kv line bay
COUPLER/SECTIONALISING CB - BARNAKYLE 110SA1-2CB
TO-26-BNK-110SA1-2CB-01 ISO week: 2tu - 4mo Date: 06 Jan - 19 Jan Duration: 14 Days (10 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1256 | DO | 10 |  | 110kV A2 @ BNK: BCU verification & Sending signals back to EirGrid. Commissioning Activities to facilitate Cables work (Busbar interlocking test & VT commissioning)
110kV FEEDER - BARNAKYLE CASTLEBAGOT 2 [Google]
TO-26-BNK-CBT-2-02 ISO week: 2tu - 4mo Date: 06 Jan - 19 Jan Duration: 14 Days (10 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1256 | DO | 10 |  | 110kV A2 @ BNK: BCU verification & Sending signals back to EirGrid. Commissioning Activities to facilitate Cables work (Busbar interlocking test & VT commissioning)
TSO CUSTOMER TRANSFORMER - BARNAKYLE T122 [Google]
TO-26-BNK-T122-01 ISO week: 2tu - 4mo Date: 06 Jan - 19 Jan Duration: 14 Days (10 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1256 | DO | 10 |  | 110kV A2 @ BNK: BCU verification & Sending signals back to EirGrid. Commissioning Activities to facilitate Cables work (Busbar interlocking test & VT commissioning)
110kV FEEDER - BUTLERSTOWN CULLENAGH
TO-26-BUT-CUL-1-01 ISO week: 2tu - 2we Date: 06 Jan - 07 Jan Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
N/A | - | - |  | DO | 2 |  | Total Maintenance Outage Duration Requested
| - | - | 901593232 | DO | 1 | 4 | 2024LP-1[40]Check Structure Poles
OPT | BUT | - | 901678366 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | CUL | - | 901679047 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
COUPLER/SECTIONALISING CB - GALLANSTOWN 110K1
TO-26-GLN-110K1-01 ISO week: 2tu Date: 06 Jan Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
N/A | - | - |  | DO | 1 |  | Total Maintenance Outage Duration Requested
| GLN | - | 901678832 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
SECTIONALISING DISCONNECT - MIDLETON 110SA1
TO-26-MID-110SA1-02 ISO week: 2tu - 25tu Date: 06 Jan - 16 Jun Duration: 162 Days (110 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1449 | DO | 110 |  | As a consequence of MID-110SA2: 110 kV A2 @ MID: EI: Install new uprated 110 kV A2 Busbar,and new SA2. New DA for T102 and Whitegate. Install new T142 and associated bay. Protection upgrade for T102.
SECTIONALISING DISCONNECT - MIDLETON 110SA2
TO-26-MID-110SA2-01 ISO week: 2tu - 25tu Date: 06 Jan - 16 Jun Duration: 162 Days (110 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1449 | DO | 110 |  | 110 kV A2 @ MID: EI: Install new uprated 110 kV A2 Busbar,and new SA2. New DA for T102 and Whitegate. Install new T142 and associated bay. Protection upgrade for T102.
DISTRIBUTION TRANSFORMER - MIDLETON T102 [SDCC]
TO-26-MID-T102-01 ISO week: 2tu - 25tu Date: 06 Jan - 16 Jun Duration: 162 Days (110 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1449 | DO | 110 |  | 110 kV A2 @ MID: EI: Install new uprated 110 kV A2 Busbar,and new SA2. New DA for T102 and Whitegate. Install new T142 and associated bay. Protection upgrade for T102.
110kV FEEDER - MIDLETON WHITEGATE [Irving Oil]
TO-26-MID-WHI-1-01 ISO week: 2tu - 25tu Date: 06 Jan - 16 Jun Duration: 162 Days (110 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1449 | DO | 110 |  | 110 kV A2 @ MID: EI: Install new uprated 110 kV A2 Busbar,and new SA2. New DA for T102 and Whitegate. Install new T142 and associated bay. Protection upgrade for T102.
COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110K1
TO-26-AUN-110K1-01 ISO week: 2we - 2fr Date: 07 Jan - 09 Jan Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | In turn with 110SA1-2CB and 110SB1-2CB
N/A | - | - |  | DO | 1 |  | Total Maintenance Outage Duration Requested
N/A | AUN | 110-K1 |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110SA1-2CB
TO-26-AUN-110SA1-2CB-01 ISO week: 2we - 2fr Date: 07 Jan - 09 Jan Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | In turn with K1 and 110SB1-2CB
N/A | - | - |  | DO | 1 |  | Total Maintenance Outage Duration Requested
N/A | AUN | 110-SA1-2 |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110SB1-2CB
TO-26-AUN-110SB1-2CB-01 ISO week: 2we - 2fr Date: 07 Jan - 09 Jan Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | In turn with K1 and 110SA1-2CB
N/A | - | - |  | DO | 1 |  | Total Maintenance Outage Duration Requested
N/A | AUN | 110-SB1-2 |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
COUPLER/SECTIONALISING CB - CLOGHRAN 110K2
TO-26-CLG-110K2-01 ISO week: 2we - 2th Date: 07 Jan - 08 Jan Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| CLG |  |  | DO | 2 |  | P1 Protection maintenance of 7SJ611
BUSBAR SECTION - CASTLEBAGOT 110 kV B2
TO-26-110 kV B2 @ CBT-01 ISO week: 3mo - 3fr Date: 12 Jan - 16 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO | 5 |  | CBT 110 B2/B4 in turn as a consequence of OS on 110SB2-4 bay
BUSBAR SECTION - CASTLEBAGOT 110 kV B4
TO-26-110 kV B4 @ CBT-02 ISO week: 3mo - 3fr Date: 12 Jan - 16 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO | 5 |  | CBT 110 B2/B4 in turn as a consequence of OS on 110SB2-4 bay
COUPLER/SECTIONALISING CB - CASTLEBAGOT 110K4
TO-26-CBT-110K4-02 ISO week: 3mo - 3fr Date: 12 Jan - 16 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | CBT 110 B1/B2 and B2/B4 in turn requried as a consequence of CBT 110 SB1-2 CB and SB2-4 CB OS
COUPLER/SECTIONALISING CB - CASTLEBAGOT 110SB2-4CB
TO-26-CBT-110SB2-4CB-02 ISO week: 3mo - 3fr Date: 12 Jan - 16 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO | 5 |  | CBT 110 B2/B4 in turn as a consequence of OS on 110SB2-4 bay
N/A | - | - |  | DO | 5 |  | Total Maintenance Outage Duration Requested
OS | CBT | SB2-4 | 901542559 | DO | 5 | 4 | 110kV GIS Cubicle Ordinary Service (Including the B2 & B4 Disconnects)
110kV FEEDER - LISDRUM LISLEA
TO-26-LIS-LSA-1-04 ISO week: 3mo - 4we Date: 12 Jan - 21 Jan Duration: 10 Days (8 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
N/A | - | - |  | DO | 8 |  | Total Maintenance Outage Duration Requested
OS | LIS | - | 901678315 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects)
CA_110 | LIS | - | 901678314 | DO | 3 | 4 | 110KV Cubicle Condition Assessment (excludes busbar disconnects)
OPT | LSA | - |  | DO | 2 | 4 | 110kV GIS Cubicle Operational Test
| LSA | - |  | DO | 2 |  | Cable Insp. 110kV XLPE
220kV FEEDER - PROSPECT TARBERT
TO-26-PRO-TB-1-02 ISO week: 3mo - 4tu Date: 12 Jan - 20 Jan Duration: 9 Days (7 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | Confirm the SF6 pressure in the Tarbert Cubical in Prospect Station, No DOF required
|  |  | 901504158 | DO |  |  | 2025CM_Rplce Cath_Prot Batt_Sys OD7Days
|  |  | 901675142 | DO |  |  | 2025CM_Rplce Cath_Prot Batt_Sys OD7Days
|  |  | 901682099 | DO |  |  | 2025FCI-1[4]Sus/Dup 220kV Replace
|  |  | 901682111 | DO |  |  | 2025FCI-1[16]Sus/Dup 220kV Replace
|  |  | 901682112 | DO |  |  | 2025FCI-1[17]Sus/Dup 220kV Replace
|  |  | 901682113 | DO |  |  | 2025FCI-1[18]Sus/Dup 220kV Replace
|  |  | 901682114 | DO |  |  | 2025FCI-1[19]Sus/Dup 220kV Replace
|  |  | 901682117 | DO |  |  | 2025FCI-1[22]Sus/Dup 220kV Replace
|  |  | 901682118 | DO |  |  | 2025FCI-1[23]Sus/Dup 220kV Replace
BUSBAR SECTION - SNUGBOROUGH 110 kV A2
TO-26-110 kV A2 @ SNU-01 ISO week: 3mo - 4we Date: 12 Jan - 21 Jan Duration: 10 Days (8 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | SNU 110 A2/B2 IN TURN required as consequence of maintenance on SNU K2
BUSBAR SECTION - SNUGBOROUGH 110 kV B2
TO-26-110 kV B2 @ SNU-01 ISO week: 3mo - 4we Date: 12 Jan - 21 Jan Duration: 10 Days (8 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | SNU 110 A2/B2 IN TURN required as consequence of maintenance on SNU K2
COUPLER/SECTIONALISING CB - SNUGBOROUGH 110K2
TO-26-SNU-110K2-01 ISO week: 3mo - 4we Date: 12 Jan - 21 Jan Duration: 10 Days (8 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | SNU 110 A2/B2 IN TURN required as consequence
N/A | - | - |  | DO | 8 |  | Total Maintenance Outage Duration Requested
OSSF6110 | SNU | - | 901396863 | DO | 4 | 3 | 110kV SF6 Cubicle Ordinary Service
SF6 | SNU | - | 901397273 | DO | 3 | 1 | Inspect Densimeters on GIS Switchgear
| SNU |  |  | DO | 2 |  | P3 Protection maintenance of 7SJ611
COUPLER/SECTIONALISING CB - SNUGBOROUGH 110SA1-2CB
TO-26-SNU-110SA1-2CB-01 ISO week: 3mo - 4we Date: 12 Jan - 21 Jan Duration: 10 Days (8 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | SNU 110 A1/A2 bars required as a consequence of densimeter inspection on SNU 110 SA1-2CB
|  |  |  | DO |  |  | SNU 110 A2/B2 IN TURN required as consequence of maintenance on SNU K2
N/A | - | - |  | DO | 4 |  | Total Maintenance Outage Duration Requested
SF6 | SNU | - | 901406878 | DO | 3 | 1 | Inspect Densimeters on GIS Switchgear
COUPLER/SECTIONALISING CB - SNUGBOROUGH 110SB1-2CB
TO-26-SNU-110SB1-2CB-01 ISO week: 3mo - 4we Date: 12 Jan - 21 Jan Duration: 10 Days (8 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  | 901406879 | DO | 3 | 1 | Inspect Densimeters on GIS Switchgear
|  |  |  | DO |  |  | SNU 110 A2/B2 IN TURN required as consequence of maintenance on SNU K2
GENERATOR TRANSFORMER - TULLABEG T131 [Tullabeg SF (TL1)]
TO-26-TTU-131-01 ISO week: 3mo - 4tu Date: 12 Jan - 20 Jan Duration: 9 Days (7 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO | 7 |  | Customer request to switch out at 08:00 on 12th Jan & switch back in at 11:00 on 20th Jan
|  |  |  | DO |  |  | 110kV Cubical Operational test
|  |  |  | DO |  |  | Cable Inspection
COUPLER/SECTIONALISING CB - CRUISERATH 220K1
TO-26-CRU-220K1-01 ISO week: 3tu Date: 13 Jan Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | Cruiserath 220 K1, K2, SA1-2CB and SB1-2CB IN TURN
N/A | - | - |  | DO | 1 |  | Total Maintenance Outage Duration Requested
| CRU | - | 901678838 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
110kV FEEDER - DRYBRIDGE OLDBRIDGE [Amazon (Oldbridge)]
TO-26-DRY-OBE-1-02 ISO week: 3tu - 3fr Date: 13 Jan - 16 Jan Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| DRY | - | 901707790 | DO | 4 | 3 | Replacement of SF6 isolation block
OPT | OBE | - | 901709797 | DO | 2 | 4 | 110kV GIS Cubicle Operational Test
110kV FEEDER - CAHIR TIPPERARY
TO-26-CAH-TIP-1-01 ISO week: 3we Date: 14 Jan Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | As a consequence of TIPPERARY 110SA2 Op. test
COUPLER/SECTIONALISING CB - CRUISERATH 220K2
TO-26-CRU-220K2-01 ISO week: 3we Date: 14 Jan Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | Cruiserath 220 K1, K2, SA1-2CB and SB1-2CB IN TURN
N/A | - | - |  | DO | 1 |  | Total Maintenance Outage Duration Requested
| CRU | - | 901678841 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
110kV FEEDER - DUNGARVAN RATHNASKILLOGE
TO-26-DGN-RTH-1-01 ISO week: 3we Date: 14 Jan Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
N/A | - | - |  | DO | 1 |  | Total Maintenance Outage Duration Requested
OPT | DGN | - | 901678384 | DO | 1 | 4 | 110kV MO Cubicle Operational Test
SECTIONALISING DISCONNECT - TIPPERARY 110SA1
TO-26-TIP-110SA1-01 ISO week: 3we Date: 14 Jan Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | As a consequence of TIPPERARY 110SA2 Op. test
SECTIONALISING DISCONNECT - TIPPERARY 110SA2
TO-26-TIP-110SA2-01 ISO week: 3we Date: 14 Jan Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
N/A | - | - |  | DO | 1 |  | Total Maintenance Outage Duration Requested
OPT | TIP | SA2 | 901678782 | DO | 1 | 4 | 110kV Sect / Dist Operational Test
COUPLER/SECTIONALISING CB - CRUISERATH 220SA1-2CB
TO-26-CRU-SA1-2CB-01 ISO week: 3th Date: 15 Jan Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | Cruiserath 220 K1, K2, SA1-2CB and SB1-2CB IN TURN
N/A | - | - |  | DO | 1 |  | Total Maintenance Outage Duration Requested
| CRU | - | 901678839 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
COUPLER/SECTIONALISING CB - CRUISERATH 220SB1-2CB
TO-26-CRU-SB1-2CB-01 ISO week: 3fr Date: 16 Jan Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | Cruiserath 220 K1, K2, SA1-2CB and SB1-2CB IN TURN
N/A | - | - |  | DO | 1 |  | Total Maintenance Outage Duration Requested
| CRU | - | 901678840 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
BUSBAR SECTION - CORDUFF 110 kV A4
TO-26-110 kV A4 @ CDU-01 ISO week: 3su Date: 18 Jan Duration: 1 Day (0 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous 110 kV A4 @ CDU + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
BUSBAR SECTION - CORDUFF 220 kV B4
TO-26-220 kV B4 @ CDU-01 ISO week: 3su Date: 18 Jan Duration: 1 Day (0 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous 220 kV B4 @ CDU + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
GENERATOR TRANSFORMER - CORDUFF T102 [Corduff Flexgen (FG2)]
TO-26-CDU-T102-01 ISO week: 3su Date: 18 Jan Duration: 1 Day (0 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous CDU-T102 + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
TRANSFORMER - CORDUFF T2104
TO-26-CDU-T2104-01 ISO week: 3su Date: 18 Jan Duration: 1 Day (0 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous CDU-T2104 + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
220kV FEEDER - CORDUFF WOODLAND
TO-26-CDU-WOO-1-02 ISO week: 3su Date: 18 Jan Duration: 1 Day (0 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous CDU-WOO-1 + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
TRANSFORMER - PORTAN T4301
TO-26-PRN-T4301-01 ISO week: 3su Date: 18 Jan Duration: 1 Day (0 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0001 | DO | 1 |  | Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | As a consequence of PRN-WOO-1: Simultaneous PRN-T4301 + PRN-WOO-1: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous PRN-T4301 + PRN-WOO-1: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous 400 kV B1/B2 @ WOO + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous PRN-T4301 + WOO-T4204: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous 220 kV B2 @ WOO + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous CDU-WOO-1 + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous 220 kV B4 @ CDU + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous CDU-T2104 + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous 110 kV A4 @ CDU + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous CDU-T102 + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
400kV FEEDER - PORTAN WOODLAND
TO-26-PRN-WOO-1-01 ISO week: 3su Date: 18 Jan Duration: 1 Day (0 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0001 | DO | 1 |  | As a consequence of PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | As a consequence of PRN-T4301: Simultaneous PRN-T4301 + PRN-WOO-1: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous PRN-T4301 + PRN-WOO-1: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | As a consequence of PRN-T4301: Simultaneous 400 kV B1/B2 @ WOO + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | As a consequence of PRN-T4301: Simultaneous PRN-T4301 + WOO-T4204: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | As a consequence of PRN-T4301: Simultaneous 220 kV B2 @ WOO + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | As a consequence of PRN-T4301: Simultaneous CDU-WOO-1 + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | As a consequence of PRN-T4301: Simultaneous 220 kV B4 @ CDU + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | As a consequence of PRN-T4301: Simultaneous CDU-T2104 + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | As a consequence of PRN-T4301: Simultaneous 110 kV A4 @ CDU + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | As a consequence of PRN-T4301: Simultaneous CDU-T102 + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
BUSBAR SECTION - WOODLAND 220 kV B2
TO-26-220 kV B2 @ WOO-02 ISO week: 3su Date: 18 Jan Duration: 1 Day (0 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous 220 kV B2 @ WOO + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
BUSBAR SECTION - WOODLAND 400 kV B1/B2
TO-26-400 kV B1/B2 @ WOO-01 ISO week: 3su Date: 18 Jan Duration: 1 Day (0 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous 400 kV B1/B2 @ WOO + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
TRANSFORMER - WOODLAND T4204
TO-26-WOO-T4204-04 ISO week: 3su Date: 18 Jan Duration: 1 Day (0 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous PRN-T4301 + WOO-T4204: Blackstart test path for EWIC to Corduff (FG2)

## WATERFORD (Rgn)
110kV FEEDER - BUTLERSTOWN CULLENAGH
TO-26-BUT-CUL-1-01 ISO week: 2tu - 2we Date: 06 Jan - 07 Jan Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
N/A | - | - |  | DO | 2 |  | Total Maintenance Outage Duration Requested
| - | - | 901593232 | DO | 1 | 4 | 2024LP-1[40]Check Structure Poles
OPT | BUT | - | 901678366 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
OPT | CUL | - | 901679047 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
110kV FEEDER - CAHIR TIPPERARY
TO-26-CAH-TIP-1-01 ISO week: 3we Date: 14 Jan Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | As a consequence of TIPPERARY 110SA2 Op. test
110kV FEEDER - DUNGARVAN RATHNASKILLOGE
TO-26-DGN-RTH-1-01 ISO week: 3we Date: 14 Jan Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
N/A | - | - |  | DO | 1 |  | Total Maintenance Outage Duration Requested
OPT | DGN | - | 901678384 | DO | 1 | 4 | 110kV MO Cubicle Operational Test

## TRALEE (Rgn)
GENERATOR TRANSFORMER - TARBERT T2003 [Tarbert TB3]
TO-26-TB-T2003-01 ISO [year]week: 1mo - N/A Date: 29 Dec - N/A Status: Forced Out
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | FO 14-08-23
CAPACITOR/SVC/REACTOR - TRALEE CAP2
TO-26-TRL-CAP2-01 ISO [year]week: 1mo - N/A Date: 29 Dec - N/A Status: Forced Out
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | FO 26-49-25
110kV FEEDER - KILPADDOGE TRALEE 1
TO-26-KPG-TRL-1-01 ISO week: 2mo - 2fr Date: 05 Jan - 09 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
N/A | - | - |  | DO | 5 |  | Total Maintenance Outage Duration Requested
| - | - | 901701996 | DO | 2 | 2 | 2025CM_Insp GIS Connex 5S Term_OD2Days
AMCAB | KPG | - | 901675755 | DO | 2 | 4 | Cable Insp. 110kV XLPE
| KPG | - | 901671167 | DO |  |  | 01 H9 Sf6 Leak Repair
220kV FEEDER - PROSPECT TARBERT
TO-26-PRO-TB-1-02 ISO week: 3mo - 4tu Date: 12 Jan - 20 Jan Duration: 9 Days (7 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | Confirm the SF6 pressure in the Tarbert Cubical in Prospect Station, No DOF required
|  |  | 901504158 | DO |  |  | 2025CM_Rplce Cath_Prot Batt_Sys OD7Days
|  |  | 901675142 | DO |  |  | 2025CM_Rplce Cath_Prot Batt_Sys OD7Days
|  |  | 901682099 | DO |  |  | 2025FCI-1[4]Sus/Dup 220kV Replace
|  |  | 901682111 | DO |  |  | 2025FCI-1[16]Sus/Dup 220kV Replace
|  |  | 901682112 | DO |  |  | 2025FCI-1[17]Sus/Dup 220kV Replace
|  |  | 901682113 | DO |  |  | 2025FCI-1[18]Sus/Dup 220kV Replace
|  |  | 901682114 | DO |  |  | 2025FCI-1[19]Sus/Dup 220kV Replace
|  |  | 901682117 | DO |  |  | 2025FCI-1[22]Sus/Dup 220kV Replace
|  |  | 901682118 | DO |  |  | 2025FCI-1[23]Sus/Dup 220kV Replace

## SOLAR (Rgn)
GENERATOR TRANSFORMER - DEENES T132 [Gaskinstown Solar (DE1)]
TO-26-DEN-T132-01 ISO [year]week: 1mo - N/A Date: 29 Dec - N/A Status: Forced Out
WORK | LOCATION | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FO 24-28-25 Mod 1
GENERATOR TRANSFORMER - TULLABEG T131 [Tullabeg SF (TL1)]
TO-26-TTU-131-01 ISO week: 3mo - 4tu Date: 12 Jan - 20 Jan Duration: 9 Days (7 WD) Status: Scheduled
WORK | LOCATION | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  | DO | 7 |  | Customer request to switch out at 08:00 on 12th Jan & switch back in at 11:00 on 20th Jan
|  |  | DO |  |  | 110kV Cubical Operational test
|  |  | DO |  |  | Cable Inspection

## SLIGO (Rgn)
BUSBAR SECTION - FLAGFORD 220 kV A2
TO-26-220 kV A2 @ FLA-01 ISO week: 2mo - 9fr Date: 05 Jan - 27 Feb Duration: 54 Days (39 WD) Status: Scheduled
WORK | LOCATION | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  | CP0799 | DO | 30 |  | 220 kV A2/B2 IN TURN @ FLA: civils works for construction of new F10 Louth 220kv line bay
BUSBAR SECTION - FLAGFORD 220 kV B2
TO-26-220 kV B2 @ FLA-01 ISO week: 2mo - 9fr Date: 05 Jan - 27 Feb Duration: 54 Days (39 WD) Status: Scheduled
WORK | LOCATION | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  | CP0799 | DO | 30 |  | 220 kV A2/B2 IN TURN @ FLA: civils works for construction of new F10 Louth 220kv line bay

## SDCC (Rgn)
DISTRIBUTION TRANSFORMER - GREAT ISLAND T141 [SDCC]
TO-26-GI-T141-01 ISO [year]week: [25]14we - 53th Date: 02 Apr 25 - 31 Dec Duration: 639 Days (447 WD) Status: Reference
WORK | LOCATION | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  | E1680 | DO | 40 |  | Upgrading T141 as part of H-I-3932 works
CAPX |  | E1680 | DO | 2 |  | EI: Simultaneous 110 kV A1/B1 IN TURN @ GI + GI-T141: Interlocking checks, Energisation Instruction
CAPX |  | E1680 | DO | 2 |  | EI: Simultaneous GI-T141 + GI-WAT-1: Energisation of Great Island T141
DISTRIBUTION TRANSFORMER - MIDLETON T102 [SDCC]
TO-26-MID-T102-01 ISO week: 2tu - 25tu Date: 06 Jan - 16 Jun Duration: 162 Days (110 WD) Status: Reference
WORK | LOCATION | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  | CP1449 | DO | 110 |  | 110 kV A2 @ MID: EI: Install new uprated 110 kV A2 Busbar,and new SA2. New DA for T102 and Whitegate. Install new T142 and associated bay. Protection upgrade for T102.

## OUTTURN - TSO (Rgn)
GENERATOR TRANSFORMER - DEENES T132 [Gaskinstown Solar (DE1)]
TO-26-DEN-T132-01 ISO [year]week: 1mo - N/A Date: 29 Dec - N/A Status: Forced Out
WORK | LOCATION | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FO 24-28-25 Mod 1
GENERATOR TRANSFORMER - TULLABEG T131 [Tullabeg SF (TL1)]
TO-26-TTU-131-01 ISO week: 3mo - 4tu Date: 12 Jan - 20 Jan Duration: 9 Days (7 WD) Status: Scheduled
WORK | LOCATION | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  | DO | 7 |  | Customer request to switch out at 08:00 on 12th Jan & switch back in at 11:00 on 20th Jan
|  |  | DO |  |  | 110kV Cubical Operational test
|  |  | DO |  |  | Cable Inspection
GENERATOR TRANSFORMER - CORDUFF T102 [Corduff Flexgen (FG2)]
TO-26-CDU-T102-01 ISO week: 3su Date: 18 Jan Duration: 1 Day (0 WD) Status: Scheduled
WORK | LOCATION | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  | CP0001 | DO | 1 |  | Simultaneous CDU-T102 + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)

## LIMERICK (Rgn)
TRANSFORMER - KILLONAN T2102
TO-26-KLN-T2102-01 ISO week: 1mo - 53th Date: 29 Dec - 31 Dec Duration: 368 Days (254 WD) Status: Forced Out
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | FO-43-25 Mod 4
CAPACITOR/SVC/REACTOR - THURLES STATCOM
TO-26-THU-STATCOM-05 ISO week: 1mo - 53th Date: 29 Dec - 31 Dec Duration: 368 Days (254 WD) Status: Forced Out
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | FO |  |  | FO 22-46-25
110kV FEEDER - CHARLEVILLE MALLOW
TO-26-CHA-MAL-1-02 ISO week: 2mo - 2fr Date: 05 Jan - 09 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  | 901685017 | DO |  |  | Replacement of Poleset 80 & 87 due to lightning damage
N/A | - | - |  | DO | 5 |  | Total Maintenance Outage Duration Requested
| CHA | - | 901543264 | DO | 3 | 1 | O-Ring Replacement to prevent SF6 leaks
OPT | CHA | - | 901678269 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
CORRECT | MAL | - | 901505666 | DO | 3 | 4 | O1-Protection Maintenance of 7SA & GRL
| MAL | - | 901543265 | DO | 3 | 1 | O-Ring Replacement to prevent SF6 leaks
| STH | CK | 901592678 | DO | 1 | 4 | 2024LP-1[30]- S2 Drone (U-Bolts)
220kV FEEDER - PROSPECT TARBERT
TO-26-PRO-TB-1-02 ISO week: 3mo - 4tu Date: 12 Jan - 20 Jan Duration: 9 Days (7 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | Confirm the SF6 pressure in the Tarbert Cubical in Prospect Station, No DOF required
|  |  | 901504158 | DO |  |  | 2025CM_Rplce Cath_Prot Batt_Sys OD7Days
|  |  | 901675142 | DO |  |  | 2025CM_Rplce Cath_Prot Batt_Sys OD7Days
|  |  | 901682099 | DO |  |  | 2025FCI-1[4]Sus/Dup 220kV Replace
|  |  | 901682111 | DO |  |  | 2025FCI-1[16]Sus/Dup 220kV Replace
|  |  | 901682112 | DO |  |  | 2025FCI-1[17]Sus/Dup 220kV Replace
|  |  | 901682113 | DO |  |  | 2025FCI-1[18]Sus/Dup 220kV Replace
|  |  | 901682114 | DO |  |  | 2025FCI-1[19]Sus/Dup 220kV Replace
|  |  | 901682117 | DO |  |  | 2025FCI-1[22]Sus/Dup 220kV Replace
|  |  | 901682118 | DO |  |  | 2025FCI-1[23]Sus/Dup 220kV Replace
110kV FEEDER - CAHIR TIPPERARY
TO-26-CAH-TIP-1-01 ISO week: 3we Date: 14 Jan Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | As a consequence of TIPPERARY 110SA2 Op. test
SECTIONALISING DISCONNECT - TIPPERARY 110SA1
TO-26-TIP-110SA1-01 ISO week: 3we Date: 14 Jan Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | As a consequence of TIPPERARY 110SA2 Op. test
SECTIONALISING DISCONNECT - TIPPERARY 110SA2
TO-26-TIP-110SA2-01 ISO week: 3we Date: 14 Jan Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
N/A | - | - |  | DO | 1 |  | Total Maintenance Outage Duration Requested
OPT | TIP | SA2 | 901678782 | DO | 1 | 4 | 110kV Sect / Dist Operational Test

## GALWAY (Rgn)
CAPACITOR/SVC/REACTOR - CASTLEBAR SVC
TO-26-CBR-SVC-01 ISO week: 1mo - 53th Date: 29 Dec - 31 Dec Duration: 368 Days (254 WD) Status: Forced Out
WORK | LOCATION | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  | DO |  |  | FO 36-40-24

## ENNISCORTHY (Rgn)
DISTRIBUTION TRANSFORMER - GREAT ISLAND T141 [SDCC]
TO-26-GI-T141-01 ISO [year]week: [25]14we - 53th Date: 02 Apr 25 - 31 Dec Duration: 639 Days (447 WD) Status: Reference
WORK | LOCATION | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  | E1680 | DO | 40 |  | Upgrading T141 as part of H-I-3932 works
CAPX |  | E1680 | DO | 2 |  | EI: Simultaneous 110 kV A1/B1 IN TURN @ GI + GI-T141: Interlocking checks, Energisation Instruction
CAPX |  | E1680 | DO | 2 |  | EI: Simultaneous GI-T141 + GI-WAT-1: Energisation of Great Island T141
COUPLER/SECTIONALISING CB - GREAT ISLAND GIS 220SA1-2CB
TO-26-GI GIS-220SA1-2CB-02 ISO week: 1mo - 53th Date: 29 Dec - 31 Dec Duration: 368 Days (254 WD) Status: Forced Out
WORK | LOCATION | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  | DO |  |  | FO 21-19-25
GENERATOR TRANSFORMER - TULLABEG T131 [Tullabeg SF (TL1)]
TO-26-TTU-131-01 ISO week: 3mo - 4tu Date: 12 Jan - 20 Jan Duration: 9 Days (7 WD) Status: Scheduled
WORK | LOCATION | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  | DO | 7 |  | Customer request to switch out at 08:00 on 12th Jan & switch back in at 11:00 on 20th Jan
|  |  | DO |  |  | 110kV Cubical Operational test
|  |  | DO |  |  | Cable Inspection

## DUNDALK (Rgn)
GENERATOR TRANSFORMER - DEENES T132 [Gaskinstown Solar (DE1)]
TO-26-DEN-T132-01 ISO [year]week: 1mo - N/A Date: 29 Dec - N/A Status: Forced Out
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FO 24-28-25 Mod 1
BUSBAR SECTION - LOUTH 220 kV A2
TO-26-220 kV A2 @ LOU-01 ISO week: 2mo - 9fr Date: 05 Jan - 27 Feb Duration: 54 Days (39 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0799 | DO | 39 |  | 220 kV A2/B2 IN TURN @ LOU: civils works for construction of new F14 Flagford 220kv line bay
BUSBAR SECTION - LOUTH 220 kV B2
TO-26-220 kV B2 @ LOU-01 ISO week: 2mo - 9fr Date: 05 Jan - 27 Feb Duration: 54 Days (39 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0799 | DO | 39 |  | 220 kV A2/B2 IN TURN @ LOU: civils works for construction of new F14 Flagford 220kv line bay
110kV FEEDER - DRYBRIDGE OLDBRIDGE [Amazon (Oldbridge)]
TO-26-DRY-OBE-1-02 ISO week: 3tu - 3fr Date: 13 Jan - 16 Jan Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| DRY | - | 901707790 | DO | 4 | 3 | Replacement of SF6 isolation block
OPT | OBE | - | 901709797 | DO | 2 | 4 | 110kV GIS Cubicle Operational Test

## DUBLIN (Rgn)
TSO CUSTOMER TRANSFORMER - DARNDALE T121 [Amazon (Darndale)]
TO-26-DND-T121-01 ISO [year]week: [24]7mo - 40we Date: 12 Feb 24 - 30 Sep Duration: 962 Days (680 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1230 | DO | 229 |  | Darndale T121 required out to facilitate works in lead up to EI of Darndale T125. T121 to be decommissioned and replaced with new 63MVA transformer
CAPACITOR/SVC/REACTOR - POOLBEG R2001
TO-26-PB-R2001-03 ISO week: 1mo - 53th Date: 29 Dec - 31 Dec Duration: 368 Days (254 WD) Status: Forced Out
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | FO 30-42-24
BUSBAR SECTION - CASTLEBAGOT 110 kV A4
TO-26-110 kV A4 @ CBT-01 ISO week: 2mo - 2fr Date: 05 Jan - 09 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | CBT 110 A4/B4 in turn as a consequence of OS on 110K4 bay
BUSBAR SECTION - CASTLEBAGOT 110 kV B4
TO-26-110 kV B4 @ CBT-01 ISO week: 2mo - 2fr Date: 05 Jan - 09 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | CBT 110 A4/B4 in turn as a consequence of OS on 110K4 bay
COUPLER/SECTIONALISING CB - CASTLEBAGOT 110K4
TO-26-CBT-110K4-01 ISO week: 2mo - 2fr Date: 05 Jan - 09 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | CBT 110 A4/B4 in turn as a consequence of OS on 110K4 bay
N/A | - | - |  | DO | 5 |  | Total Maintenance Outage Duration Requested
OS | CBT | - | 901542553 | DO | 5 | 4 | 110kV GIS Cubicle Ordinary Service
COUPLER/SECTIONALISING CB - CASTLEBAGOT 110SA2-4CB
TO-26-CBT-110SA2-4CB-01 ISO week: 2mo - 2fr Date: 05 Jan - 09 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | CBT 110 A4/B4 in turn as a consequence of OS on 110K4 bay
COUPLER/SECTIONALISING CB - CASTLEBAGOT 110SB2-4CB
TO-26-CBT-110SB2-4CB-01 ISO week: 2mo - 2fr Date: 05 Jan - 09 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | CBT 110 A4/B4 in turn as a consequence of OS on 110K4 bay
BUSBAR SECTION - FINGLAS 220 kV A2
TO-26-220 kV A2 @ FIN-05 ISO week: 2mo - 2fr Date: 05 Jan - 09 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO | 7 |  | FIN 220 kV A2/B2 IN TURN required as consequence for 220 K2 OS
BUSBAR SECTION - FINGLAS 220 kV B2
TO-26-220 kV B2 @ FIN-03 ISO week: 2mo - 2fr Date: 05 Jan - 09 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO | 7 |  | FIN 220 kV A2/B2 IN TURN required as consequence for 220 K2 OS
COUPLER/SECTIONALISING CB - FINGLAS 220K2
TO-26-FIN-220K2-05 ISO week: 2mo - 2fr Date: 05 Jan - 09 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
FIN 220 kV A2/B2 IN TURN required as consequence for 220 K2 OS
N/A | - | - |  | DO | 7 |  | Total Maintenance Outage Duration Requested
OS220 | FIN | - | 901678229 | DO | 7 | 4 | 220kV GIS Cubicle Ordinary Service
| FIN |  |  | DO | 2 |  | P3 Protection maintenance of 7SJ611
COUPLER/SECTIONALISING CB - FINGLAS 220SA1-2CB
TO-26-FIN-220SA1-2CB-06 ISO week: 2mo - 2fr Date: 05 Jan - 09 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | FIN 220 kV A2/B2 IN TURN required as consequence for 220 K2 OS
COUPLER/SECTIONALISING CB - FINGLAS 220SB1-2CB
TO-26-FIN-220SB1-2CB-04 ISO week: 2mo - 2fr Date: 05 Jan - 09 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | FIN 220 kV A2/B2 IN TURN required as consequence for 220 K2 OS
COUPLER/SECTIONALISING CB - BARNAKYLE 110SA1-2CB
TO-26-BNK-110SA1-2CB-01 ISO week: 2tu - 4mo Date: 06 Jan - 19 Jan Duration: 14 Days (10 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1256 | DO | 10 |  | 110kV A2 @ BNK: BCU verification & Sending signals back to EirGrid. Commissioning Activities to facilitate Cables work (Busbar interlocking test & VT commissioning)
110kV FEEDER - BARNAKYLE CASTLEBAGOT 2 [Google]
TO-26-BNK-CBT-2-02 ISO week: 2tu - 4mo Date: 06 Jan - 19 Jan Duration: 14 Days (10 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1256 | DO | 10 |  | 110kV A2 @ BNK: BCU verification & Sending signals back to EirGrid. Commissioning Activities to facilitate Cables work (Busbar interlocking test & VT commissioning)
TSO CUSTOMER TRANSFORMER - BARNAKYLE T122 [Google]
TO-26-BNK-T122-01 ISO week: 2tu - 4mo Date: 06 Jan - 19 Jan Duration: 14 Days (10 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1256 | DO | 10 |  | 110kV A2 @ BNK: BCU verification & Sending signals back to EirGrid. Commissioning Activities to facilitate Cables work (Busbar interlocking test & VT commissioning)
COUPLER/SECTIONALISING CB - GALLANSTOWN 110K1
TO-26-GLN-110K1-01 ISO week: 2tu Date: 06 Jan Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
N/A | - | - |  | DO | 1 |  | Total Maintenance Outage Duration Requested
| GLN | - | 901678832 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110K1
TO-26-AUN-110K1-01 ISO week: 2we - 2fr Date: 07 Jan - 09 Jan Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | In turn with 110SA1-2CB and 110SB1-2CB
N/A | - | - |  | DO | 1 |  | Total Maintenance Outage Duration Requested
N/A | AUN | 110-K1 |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110SA1-2CB
TO-26-AUN-110SA1-2CB-01 ISO week: 2we - 2fr Date: 07 Jan - 09 Jan Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | In turn with K1 and 110SB1-2CB
N/A | - | - |  | DO | 1 |  | Total Maintenance Outage Duration Requested
N/A | AUN | 110-SA1-2 |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
COUPLER/SECTIONALISING CB - AUNGIERSTOWN 110SB1-2CB
TO-26-AUN-110SB1-2CB-01 ISO week: 2we - 2fr Date: 07 Jan - 09 Jan Duration: 3 Days (3 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | In turn with K1 and 110SA1-2CB
N/A | - | - |  | DO | 1 |  | Total Maintenance Outage Duration Requested
N/A | AUN | 110-SB1-2 |  | DO | 1 | 4 | 110kV GIS Cubicle Operational Test
COUPLER/SECTIONALISING CB - CLOGHRAN 110K2
TO-26-CLG-110K2-01 ISO week: 2we - 2th Date: 07 Jan - 08 Jan Duration: 2 Days (2 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| CLG |  |  | DO | 2 |  | P1 Protection maintenance of 7SJ611
BUSBAR SECTION - CASTLEBAGOT 110 kV B2
TO-26-110 kV B2 @ CBT-01 ISO week: 3mo - 3fr Date: 12 Jan - 16 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO | 5 |  | CBT 110 B2/B4 in turn as a consequence of OS on 110SB2-4 bay
BUSBAR SECTION - CASTLEBAGOT 110 kV B4
TO-26-110 kV B4 @ CBT-02 ISO week: 3mo - 3fr Date: 12 Jan - 16 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO | 5 |  | CBT 110 B2/B4 in turn as a consequence of OS on 110SB2-4 bay
COUPLER/SECTIONALISING CB - CASTLEBAGOT 110K4
TO-26-CBT-110K4-02 ISO week: 3mo - 3fr Date: 12 Jan - 16 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | CBT 110 B1/B2 and B2/B4 in turn requried as a consequence of CBT 110 SB1-2 CB and SB2-4 CB OS
COUPLER/SECTIONALISING CB - CASTLEBAGOT 110SB2-4CB
TO-26-CBT-110SB2-4CB-02 ISO week: 3mo - 3fr Date: 12 Jan - 16 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO | 5 |  | CBT 110 B2/B4 in turn as a consequence of OS on 110SB2-4 bay
N/A | - | - |  | DO | 5 |  | Total Maintenance Outage Duration Requested
OS | CBT | SB2-4 | 901542559 | DO | 5 | 4 | 110kV GIS Cubicle Ordinary Service (Including the B2 & B4 Disconnects)
BUSBAR SECTION - SNUGBOROUGH 110 kV A2
TO-26-110 kV A2 @ SNU-01 ISO week: 3mo - 4we Date: 12 Jan - 21 Jan Duration: 10 Days (8 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | SNU 110 A2/B2 IN TURN required as consequence of maintenance on SNU K2
BUSBAR SECTION - SNUGBOROUGH 110 kV B2
TO-26-110 kV B2 @ SNU-01 ISO week: 3mo - 4we Date: 12 Jan - 21 Jan Duration: 10 Days (8 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | SNU 110 A2/B2 IN TURN required as consequence of maintenance on SNU K2
COUPLER/SECTIONALISING CB - SNUGBOROUGH 110K2
TO-26-SNU-110K2-01 ISO week: 3mo - 4we Date: 12 Jan - 21 Jan Duration: 10 Days (8 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | SNU 110 A2/B2 IN TURN required as consequence
N/A | - | - |  | DO | 8 |  | Total Maintenance Outage Duration Requested
OSSF6110 | SNU | - | 901396863 | DO | 4 | 3 | 110kV SF6 Cubicle Ordinary Service
SF6 | SNU | - | 901397273 | DO | 3 | 1 | Inspect Densimeters on GIS Switchgear
| SNU |  |  | DO | 2 |  | P3 Protection maintenance of 7SJ611
COUPLER/SECTIONALISING CB - SNUGBOROUGH 110SA1-2CB
TO-26-SNU-110SA1-2CB-01 ISO week: 3mo - 4we Date: 12 Jan - 21 Jan Duration: 10 Days (8 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | SNU 110 A1/A2 bars required as a consequence of densimeter inspection on SNU 110 SA1-2CB
|  |  |  | DO |  |  | SNU 110 A2/B2 IN TURN required as consequence of maintenance on SNU K2
N/A | - | - |  | DO | 4 |  | Total Maintenance Outage Duration Requested
SF6 | SNU | - | 901406878 | DO | 3 | 1 | Inspect Densimeters on GIS Switchgear
COUPLER/SECTIONALISING CB - SNUGBOROUGH 110SB1-2CB
TO-26-SNU-110SB1-2CB-01 ISO week: 3mo - 4we Date: 12 Jan - 21 Jan Duration: 10 Days (8 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  | 901406879 | DO | 3 | 1 | Inspect Densimeters on GIS Switchgear
|  |  |  | DO |  |  | SNU 110 A2/B2 IN TURN required as consequence of maintenance on SNU K2
COUPLER/SECTIONALISING CB - CRUISERATH 220K1
TO-26-CRU-220K1-01 ISO week: 3tu Date: 13 Jan Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | Cruiserath 220 K1, K2, SA1-2CB and SB1-2CB IN TURN
N/A | - | - |  | DO | 1 |  | Total Maintenance Outage Duration Requested
| CRU | - | 901678838 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
COUPLER/SECTIONALISING CB - CRUISERATH 220K2
TO-26-CRU-220K2-01 ISO week: 3we Date: 14 Jan Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | Cruiserath 220 K1, K2, SA1-2CB and SB1-2CB IN TURN
N/A | - | - |  | DO | 1 |  | Total Maintenance Outage Duration Requested
| CRU | - | 901678841 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
COUPLER/SECTIONALISING CB - CRUISERATH 220SA1-2CB
TO-26-CRU-SA1-2CB-01 ISO week: 3th Date: 15 Jan Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | Cruiserath 220 K1, K2, SA1-2CB and SB1-2CB IN TURN
N/A | - | - |  | DO | 1 |  | Total Maintenance Outage Duration Requested
| CRU | - | 901678839 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
COUPLER/SECTIONALISING CB - CRUISERATH 220SB1-2CB
TO-26-CRU-SB1-2CB-01 ISO week: 3fr Date: 16 Jan Duration: 1 Day (1 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | Cruiserath 220 K1, K2, SA1-2CB and SB1-2CB IN TURN
N/A | - | - |  | DO | 1 |  | Total Maintenance Outage Duration Requested
| CRU | - | 901678840 | DO | 1 | 4 | 220kV SF6 Cubicle Operational Test
BUSBAR SECTION - CORDUFF 110 kV A4
TO-26-110 kV A4 @ CDU-01 ISO week: 3su Date: 18 Jan Duration: 1 Day (0 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous 110 kV A4 @ CDU + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
BUSBAR SECTION - CORDUFF 220 kV B4
TO-26-220 kV B4 @ CDU-01 ISO week: 3su Date: 18 Jan Duration: 1 Day (0 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous 220 kV B4 @ CDU + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
GENERATOR TRANSFORMER - CORDUFF T102 [Corduff Flexgen (FG2)]
TO-26-CDU-T102-01 ISO week: 3su Date: 18 Jan Duration: 1 Day (0 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous CDU-T102 + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
TRANSFORMER - CORDUFF T2104
TO-26-CDU-T2104-01 ISO week: 3su Date: 18 Jan Duration: 1 Day (0 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous CDU-T2104 + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
220kV FEEDER - CORDUFF WOODLAND
TO-26-CDU-WOO-1-02 ISO week: 3su Date: 18 Jan Duration: 1 Day (0 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous CDU-WOO-1 + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
TRANSFORMER - PORTAN T4301
TO-26-PRN-T4301-01 ISO week: 3su Date: 18 Jan Duration: 1 Day (0 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0001 | DO | 1 |  | Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | As a consequence of PRN-WOO-1: Simultaneous PRN-T4301 + PRN-WOO-1: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous PRN-T4301 + PRN-WOO-1: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous 400 kV B1/B2 @ WOO + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous PRN-T4301 + WOO-T4204: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous 220 kV B2 @ WOO + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous CDU-WOO-1 + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous 220 kV B4 @ CDU + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous CDU-T2104 + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous 110 kV A4 @ CDU + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous CDU-T102 + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
400kV FEEDER - PORTAN WOODLAND
TO-26-PRN-WOO-1-01 ISO week: 3su Date: 18 Jan Duration: 1 Day (0 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0001 | DO | 1 |  | As a consequence of PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | As a consequence of PRN-T4301: Simultaneous PRN-T4301 + PRN-WOO-1: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous PRN-T4301 + PRN-WOO-1: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | As a consequence of PRN-T4301: Simultaneous 400 kV B1/B2 @ WOO + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | As a consequence of PRN-T4301: Simultaneous PRN-T4301 + WOO-T4204: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | As a consequence of PRN-T4301: Simultaneous 220 kV B2 @ WOO + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | As a consequence of PRN-T4301: Simultaneous CDU-WOO-1 + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | As a consequence of PRN-T4301: Simultaneous 220 kV B4 @ CDU + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | As a consequence of PRN-T4301: Simultaneous CDU-T2104 + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | As a consequence of PRN-T4301: Simultaneous 110 kV A4 @ CDU + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
CAPX |  |  | CP0001 | DO | 1 |  | As a consequence of PRN-T4301: Simultaneous CDU-T102 + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
BUSBAR SECTION - WOODLAND 220 kV B2
TO-26-220 kV B2 @ WOO-02 ISO week: 3su Date: 18 Jan Duration: 1 Day (0 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous 220 kV B2 @ WOO + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
BUSBAR SECTION - WOODLAND 400 kV B1/B2
TO-26-400 kV B1/B2 @ WOO-01 ISO week: 3su Date: 18 Jan Duration: 1 Day (0 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous 400 kV B1/B2 @ WOO + PRN-T4301: Blackstart test path for EWIC to Corduff (FG2)
TRANSFORMER - WOODLAND T4204
TO-26-WOO-T4204-04 ISO week: 3su Date: 18 Jan Duration: 1 Day (0 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP0001 | DO | 1 |  | Simultaneous PRN-T4301 + WOO-T4204: Blackstart test path for EWIC to Corduff (FG2)

## DEMAND (Rgn)
TSO CUSTOMER TRANSFORMER - DARNDALE T121 [Amazon (Darndale)]
TO-26-DND-T121-01 ISO [year]week: [24]7mo - 40we Date: 12 Feb 24 - 30 Sep Duration: 962 Days (680 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1230 | DO | 229 |  | Darndale T121 required out to facilitate works in lead up to EI of Darndale T125. T121 to be decommissioned and replaced with new 63MVA transformer
TSO CUSTOMER TRANSFORMER - GORTAWEE T102 [Mannok]
TO-26-GWE-T102-01 ISO week: 2mo - 2fr Date: 05 Jan - 09 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO | 5 |  | Total Maintenance Outage duration required
|  |  | 901542818 | DO | 5 |  | 110kV SF6 Cubical Ordinary Service( Excludes Busbar disconnets)
110kV FEEDER - BARNAKYLE CASTLEBAGOT 2 [Google]
TO-26-BNK-CBT-2-02 ISO week: 2tu - 4mo Date: 06 Jan - 19 Jan Duration: 14 Days (10 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1256 | DO | 10 |  | 110kV A2 @ BNK: BCU verification & Sending signals back to EirGrid. Commissioning Activities to facilitate Cables work (Busbar interlocking test & VT commissioning)
TSO CUSTOMER TRANSFORMER - BARNAKYLE T122 [Google]
TO-26-BNK-T122-01 ISO week: 2tu - 4mo Date: 06 Jan - 19 Jan Duration: 14 Days (10 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1256 | DO | 10 |  | 110kV A2 @ BNK: BCU verification & Sending signals back to EirGrid. Commissioning Activities to facilitate Cables work (Busbar interlocking test & VT commissioning)
110kV FEEDER - MIDLETON WHITEGATE [Irving Oil]
TO-26-MID-WHI-1-01 ISO week: 2tu - 25tu Date: 06 Jan - 16 Jun Duration: 162 Days (110 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1449 | DO | 110 |  | 110 kV A2 @ MID: EI: Install new uprated 110 kV A2 Busbar,and new SA2. New DA for T102 and Whitegate. Install new T142 and associated bay. Protection upgrade for T102.
110kV FEEDER - DRYBRIDGE OLDBRIDGE [Amazon (Oldbridge)]
TO-26-DRY-OBE-1-02 ISO week: 3tu - 3fr Date: 13 Jan - 16 Jan Duration: 4 Days (4 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
| DRY | - | 901707790 | DO | 4 | 3 | Replacement of SF6 isolation block
OPT | OBE | - | 901709797 | DO | 2 | 4 | 110kV GIS Cubicle Operational Test

## CORK (Rgn)
COUPLER/SECTIONALISING CB - GLANAGOW 220K1-2
TO-26-GGO-220K1-2-01 ISO week: 1mo - 53th Date: 29 Dec - 31 Dec Duration: 368 Days (254 WD) Status: Forced Out
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | FO 45-14-22
GENERATOR TRANSFORMER - MARINA T107
TO-26-MR-T107-01 ISO week: 1th - 35th Date: 01 Jan - 27 Aug Duration: 239 Days (163 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CC0506 | DO | 114 |  | Condition Assessment, protection settings change, relabelling GIS, DSO protection relay
CAPX |  |  | CC0506 | DO | 65 |  | Simultaneous 110 kV A1/B1 IN TURN @ MR + MR-T107: Condition Assessment & Commissioning of H5/T107 bay
CAPX |  |  | CC0506 | DO | 2 |  | EI: Simultaneous MR-T107 + MR-TBG-1: EI of H5/T107 110kV Bay, new 110kV cable to new 110/38kV Trafo including NEW 38kV Module
110kV FEEDER - CHARLEVILLE MALLOW
TO-26-CHA-MAL-1-02 ISO week: 2mo - 2fr Date: 05 Jan - 09 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  | 901685017 | DO |  |  | Replacement of Poleset 80 & 87 due to lightning damage
N/A | - | - |  | DO | 5 |  | Total Maintenance Outage Duration Requested
| CHA | - | 901543264 | DO | 3 | 1 | O-Ring Replacement to prevent SF6 leaks
OPT | CHA | - | 901678269 | DO | 1 | 4 | 110kV SF6 Cubicle Operational Test
CORRECT | MAL | - | 901505666 | DO | 3 | 4 | O1-Protection Maintenance of 7SA & GRL
| MAL | - | 901543265 | DO | 3 | 1 | O-Ring Replacement to prevent SF6 leaks
| STH | CK | 901592678 | DO | 1 | 4 | 2024LP-1[30]- S2 Drone (U-Bolts)
SECTIONALISING DISCONNECT - MIDLETON 110SA1
TO-26-MID-110SA1-02 ISO week: 2tu - 25tu Date: 06 Jan - 16 Jun Duration: 162 Days (110 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1449 | DO | 110 |  | As a consequence of MID-110SA2: 110 kV A2 @ MID: EI: Install new uprated 110 kV A2 Busbar,and new SA2. New DA for T102 and Whitegate. Install new T142 and associated bay. Protection upgrade for T102.
SECTIONALISING DISCONNECT - MIDLETON 110SA2
TO-26-MID-110SA2-01 ISO week: 2tu - 25tu Date: 06 Jan - 16 Jun Duration: 162 Days (110 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1449 | DO | 110 |  | 110 kV A2 @ MID: EI: Install new uprated 110 kV A2 Busbar,and new SA2. New DA for T102 and Whitegate. Install new T142 and associated bay. Protection upgrade for T102.
DISTRIBUTION TRANSFORMER - MIDLETON T102 [SDCC]
TO-26-MID-T102-01 ISO week: 2tu - 25tu Date: 06 Jan - 16 Jun Duration: 162 Days (110 WD) Status: Reference
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1449 | DO | 110 |  | 110 kV A2 @ MID: EI: Install new uprated 110 kV A2 Busbar,and new SA2. New DA for T102 and Whitegate. Install new T142 and associated bay. Protection upgrade for T102.
110kV FEEDER - MIDLETON WHITEGATE [Irving Oil]
TO-26-MID-WHI-1-01 ISO week: 2tu - 25tu Date: 06 Jan - 16 Jun Duration: 162 Days (110 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
CAPX |  |  | CP1449 | DO | 110 |  | 110 kV A2 @ MID: EI: Install new uprated 110 kV A2 Busbar,and new SA2. New DA for T102 and Whitegate. Install new T142 and associated bay. Protection upgrade for T102.

## CAVAN (Rgn)
CAPACITOR/SVC/REACTOR - SHANKILL M/CAP2
TO-26-SKL-M/CAP2-01 ISO week: 1mo - 53th Date: 29 Dec - 31 Dec Duration: 368 Days (254 WD) Status: Forced Out
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO |  |  | FO 32-34-25
TSO CUSTOMER TRANSFORMER - GORTAWEE T102 [Mannok]
TO-26-GWE-T102-01 ISO week: 2mo - 2fr Date: 05 Jan - 09 Jan Duration: 5 Days (5 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  |  | DO | 5 |  | Total Maintenance Outage duration required
|  |  | 901542818 | DO | 5 |  | 110kV SF6 Cubical Ordinary Service( Excludes Busbar disconnets)
110kV FEEDER - LISDRUM LISLEA
TO-26-LIS-LSA-1-04 ISO week: 3mo - 4we Date: 12 Jan - 21 Jan Duration: 10 Days (8 WD) Status: Scheduled
WORK | LOCATION |  | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
N/A | - | - |  | DO | 8 |  | Total Maintenance Outage Duration Requested
OS | LIS | - | 901678315 | DO | 4 | 4 | 110kV SF6 Cubicle Ordinary Service (excludes busbar disconnects)
CA_110 | LIS | - | 901678314 | DO | 3 | 4 | 110KV Cubicle Condition Assessment (excludes busbar disconnects)
OPT | LSA | - |  | DO | 2 | 4 | 110kV GIS Cubicle Operational Test
| LSA | - |  | DO | 2 |  | Cable Insp. 110kV XLPE

## ATHLONE (Rgn)
CAPACITOR/SVC/REACTOR - ATHLONE M/CAP1
TO-26-ATH-M/CAP1-03 ISO week: 1mo - 53th Date: 29 Dec - 31 Dec Duration: 368 Days (254 WD) Status: Forced Out
WORK | LOCATION | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  | DO |  |  | FO 22-19-25
CAPACITOR/SVC/REACTOR - MULLINGAR CAP2
TO-26-MUL-CAP2-01 ISO week: 1mo - 53th Date: 29 Dec - 31 Dec Duration: 368 Days (254 WD) Status: Forced Out
WORK | LOCATION | WORK ID | STATUS | DAYS | PRIORITY | DESCRIPTION/COMMENTS
|  |  | DO |  |  | FO 33-48-24