## Wks 10 - 11
Report covers outages commencing/returning/spanning the period: 02/03/2026 - 15/03/2026
Outages commencing/returning in Week 10
OUTAGE ID | PLANT |  | Week 10 | [6 empty] | Week 11
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
TO-26-110 kV A2 @ LOU-04 | LOUTH 110 kV A2
TO-26-LOU-T2104-02 | LOUTH T2104
TO-26-BAG-T101-01 | BARNAGEERAGH T101
TO-26-CLO-CRD-1-01 | CLOGHER CROAGHONAGH
TO-26-CRD-T131-01 | CROAGHONAGH T131
TO-26-KBY-MR-2-01 | KILBARRY MARINA 2
TO-26-BAG 110 - CLG 110 - 1-02 | BARNAGEERAGH CLOGHRAN | bar: Week 10 Sa 7 to Week 11 Fr 13
TO-26-110 kV A1 @ CLG-01 | CLOGHRAN 110 kV A1 | bar: Week 10 Sa 7 to Week 11 Fr 13
TO-26-110 kV B1 @ CLG-01 | CLOGHRAN 110 kV B1 | bar: Week 10 Sa 7 to Week 11 Fr 13
TO-26-CLG-110K1-04 | CLOGHRAN 110K1 | bar: Week 10 Sa 7 to Week 11 Fr 13
TO-26-CLG-110SA1-2CB-02 | CLOGHRAN 110SA1-2CB | bar: Week 10 Sa 7 to Week 11 Fr 13
TO-26-CLG-110SB1-2CB-02 | CLOGHRAN 110SB1-2CB | bar: Week 10 Sa 7 to Week 11 Fr 13
TO-26-KLN-T2103-01 | KILLONAN T2103 | bar: Week 10 Sa 7 to Week 11 Fr 13
TO-26-220 kV A1 @ MAY-01 | MAYNOOTH 220 kV A1 | bar: Week 10 Sa 7 to Week 11 Fr 13
TO-26-220 kV B1 @ MAY-01 | MAYNOOTH 220 kV B1 | bar: Week 10 Sa 7 to Week 11 Fr 13
TO-26-MAY-TH-1-01 | MAYNOOTH TURLOUGH HILL | bar: Week 10 Sa 7 to Week 11 Fr 13
TO-26-220 kV A2 @ TH-01 | TURLOUGH HILL 220 kV A2 | bar: Week 10 Sa 7 to Week 11 Fr 13
TO-26-220 kV B2 @ TH-01 | TURLOUGH HILL 220 kV B2 | bar: Week 10 Sa 7 to Week 11 Fr 13
TO-26-110 kV A1 @ BVK-02 | BALLYVOUSKILL 110 kV A1 | bar: Week 10 Sa 7 to Week 11 Mo 16
TO-26-110 kV B1 @ BVK-01 | BALLYVOUSKILL 110 kV B1 | bar: Week 10 Sa 7 to Week 11 Mo 16
TO-26-BVK-110K1-01 | BALLYVOUSKILL 110K1 | bar: Week 10 Sa 7 to Week 11 Mo 16
TO-26-BVK-110SA1-2CB-06 | BALLYVOUSKILL 110SA1-2CB | bar: Week 10 Sa 7 to Week 11 Mo 16
TO-26-BVK-110SB1-2CB-04 | BALLYVOUSKILL 110SB1-2CB | bar: Week 10 Sa 7 to Week 11 Mo 16
TO-26-220 kV A1 @ BVK-01 | BALLYVOUSKILL 220 kV A1 | bar: Week 10 Sa 7 to Week 11 Mo 16
TO-26-220 kV B1 @ BVK-01 | BALLYVOUSKILL 220 kV B1 | bar: Week 10 Sa 7 to Week 11 Mo 16
TO-26-BVK-220K1-01 | BALLYVOUSKILL 220K1 | bar: Week 10 Sa 7 to Week 11 Mo 16
TO-26-BVK-220SA1-2CB-05 | BALLYVOUSKILL 220SA1-2CB | bar: Week 10 Sa 7 to Week 11 Mo 16
TO-26-BVK-220SB1-2CB-05 | BALLYVOUSKILL 220SB1-2CB | bar: Week 10 Sa 7 to Week 11 Mo 16
TO-26-BVK-T2101-02 | BALLYVOUSKILL T2101 | bar: Week 10 Sa 7 to Week 11 Mo 16
TO-26-CTN-TIP-1-01 | CAUTEEN TIPPERARY | bar: Su 1
TO-26-DMY-MAC-1-04 | DUNMANWAY MACROOM | bar: Su 1
TO-26-GAR-110K1-01 | GARBALLAGH 110K1
TO-26-AUG-CFM-1-01 | AUGHINISH CASTLEFARM 1
TO-26-CFM-T101-01 | CASTLEFARM T101
TO-26-AA GIS-DRU-1-03 | ARDNACRUSHA GIS DRUMLINE
TO-26-110 kV B1 @ CSH-04 | CASHLA 110 kV B1 | bar: Su 1
TO-26-CSH-T2101-01 | CASHLA T2101 | bar: Su 1
TO-26-CUL-RTH-1-01 | CULLENAGH RATHNASKILLOGE | bar: Su 1
TO-26-KPG-KNR-1-01 | KILPADDOGE KNOCKANURE 1
TO-26-110 kV B2 @ LOU-04 | LOUTH 110 kV B2
TO-26-RTH-T133-01 | RATHNASKILLOGE T133
TO-26-220 kV A2 @ ARK-01 | ARKLOW 220 kV A2 | bar: Su 1
TO-26-220 kV B2 @ ARK-01 | ARKLOW 220 kV B2 | bar: Su 1
TO-26-ARK-CKM GIS-1-01 | ARKLOW CARRICKMINES GIS | bar: Su 1
TO-26-BEG-CKM GIS-1-01 | BALLYBEG CARRICKMINES GIS | bar: Su 1
TO-26-220 kV A3 @ CKM GIS-01 | CARRICKMINES GIS 220 kV A3 | bar: Su 1
TO-26-220 kV B3 @ CKM GIS-01 | CARRICKMINES GIS 220 kV B3 | bar: Su 1
TO-26-CKM GIS-220K3-02 | CARRICKMINES GIS 220K3 | bar: Su 1
TO-26-CKM GIS-220SA1-3CB-05 | CARRICKMINES GIS 220SA1-3CB | bar: Su 1
TO-26-CKM GIS-220SB1-3CB-03 | CARRICKMINES GIS 220SB1-3CB | bar: Su 1
TO-26-CDU-FIN-1-01 | CORDUFF FINGLAS 1 | bar: Su 1
TO-26-220 kV A1 @ FIN-01 | FINGLAS 220 kV A1 | bar: Su 1
TO-26-220 kV B1 @ FIN-01 | FINGLAS 220 kV B1 | bar: Su 1
TO-26-FIN-220K1-01 | FINGLAS 220K1 | bar: Su 1
TO-26-FIN-220SA1-2CB-05 | FINGLAS 220SA1-2CB | bar: Su 1
TO-26-FIN-220SB1-2CB-02 | FINGLAS 220SB1-2CB | bar: Su 1
TO-26-GLN-PLA-1-01 | GALLANSTOWN PLATIN | bar: Su 1
TO-26-220 kV A2 @ INC-01 | INCHICORE 220 kV A2 | bar: Su 1
TO-26-220 kV B2 @ INC-01 | INCHICORE 220 kV B2 | bar: Su 1
TO-26-INC-PB-2-02 | INCHICORE POOLBEG 2 | bar: Su 1
TO-26-PLA-110SA1-02 | PLATIN 110SA1 | bar: Su 1
Report covers outages commencing/returning/spanning the period: 02/03/2026 - 15/03/2026
Outages commencing/returning in Week 10
OUTAGE ID | PLANT | Week 10 Mo 2: Week 10; Week 11 Mo 9: Week 11
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
TO-26-PLA-110SA2-02 | PLATIN 110SA2 | bar: Su 1 to Week 10 Fr 6
TO-26-PLA-T105-01 | PLATIN T105 | bar: Su 1 to Week 10 Fr 6
TO-26-220 kV A3 @ PB-01 | POOLBEG 220 kV A3 | bar: Su 1 to Week 10 Fr 6
TO-26-220 kV B3 @ PB-01 | POOLBEG 220 kV B3 | bar: Su 1 to Week 10 Fr 6
TO-26-220 kV A1/A2 @ PB-02 | POOLBEG 220 kV A1/A2 | bar: Week 10 Sa 7 to Week 11 Mo 16
Outages commencing/returning in Week 11
OUTAGE ID | PLANT | Week 10 Mo 2: Week 10; Week 11 Mo 9: Week 11
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
TO-26-LSA-110K1-02 | LISLEA 110K1 | bar: Week 11 Mo 9
TO-26-TEN-T132-01 | TIMAHOE T132 | bar: Week 11 Mo 9 to Week 11 Tu 10
TO-26-BAG-T103-01 | BARNAGEERAGH T103 | bar: Week 11 Mo 9 to Week 11 Fr 13
TO-26-CVW-KRA-1-03 | CASTLEVIEW KNOCKRAHA | bar: Week 11 Mo 9 to Week 11 Fr 13
TO-26-110 kV A1 @ CUL-02 | CULLENAGH 110 kV A1 | bar: Week 11 Mo 9 to Week 11 Fr 13
TO-26-110 kV A2 @ CUL-01 | CULLENAGH 110 kV A2 | bar: Week 11 Mo 9 to Week 11 Fr 13
TO-26-110 kV B1 @ CUL-02 | CULLENAGH 110 kV B1 | bar: Week 11 Mo 9 to Week 11 Fr 13
TO-26-110 kV B2 @ CUL-01 | CULLENAGH 110 kV B2 | bar: Week 11 Mo 9 to Week 11 Fr 13
TO-26-CUL-110K1-2-01 | CULLENAGH 110K1-2 | bar: Week 11 Mo 9 to Week 11 Fr 13
TO-26-KPG-KNR-2-01 | KILPADDOGE KNOCKANURE 2 | bar: Week 11 Mo 9 to Week 11 Fr 13
TO-26-ROP-WEX-1-01 | ROSSPILE WEXFORD | bar: Week 11 Mo 9 to Week 11 Fr 13
TO-26-CBT-INC-2-05 | CASTLEBAGOT INCHICORE 2 | bar: Week 11 Mo 9 to Week 11 Mo 16
TO-26-CLE-WOO-1-02 | CLONEE WOODLAND | bar: Week 11 Mo 9 to Week 11 Mo 16
TO-26-DEN-DRY-1-03 | DEENES DRYBRIDGE | bar: Week 11 Mo 9 to Week 11 Mo 16
TO-26-220 kV A2 @ DSN-01 | DUNSTOWN 220 kV A2 | bar: Week 11 Mo 9 to Week 11 Mo 16
TO-26-220 kV A2 @ FLA-02 | FLAGFORD 220 kV A2 | bar: Week 11 Mo 9 to Week 11 Mo 16
TO-26-220 kV B2 @ FLA-02 | FLAGFORD 220 kV B2 | bar: Week 11 Mo 9 to Week 11 Mo 16
TO-26-INC-220K4-6-01 | INCHICORE 220K4-6 | bar: Week 11 Mo 9 to Week 11 Mo 16
TO-26-INC-T2106-01 | INCHICORE T2106 | bar: Week 11 Mo 9 to Week 11 Mo 16
TO-26-220 kV A2 @ LOU-02 | LOUTH 220 kV A2 | bar: Week 11 Mo 9 to Week 11 Mo 16
TO-26-220 kV B2 @ LOU-02 | LOUTH 220 kV B2 | bar: Week 11 Mo 9 to Week 11 Mo 16
TO-26-220 kV B1 @ WOO-01 | WOODLAND 220 kV B1 | bar: Week 11 Mo 9 to Week 11 Mo 16
TO-26-GOR-NAV-1-02 | GORMAN NAVAN 1 | bar: Week 11 Tu 10
TO-26-TB-110K1-2-01 | TARBERT 110K1-2 | bar: Week 11 Tu 10 to Week 11 We 11
TO-26-TH-T2001/2-02 | TURLOUGH HILL T2001/2 | bar: Week 11 Tu 10 to Week 11 We 11
TO-26-BLC-DND-1-02 | BELCAMP DARNDALE 1 | bar: Week 11 Tu 10 to Week 11 Th 12
TO-26-220 kV A2 @ CSH-01 | CASHLA 220 kV A2 | bar: Week 11 Tu 10 to Week 11 Mo 16
TO-26-220 kV A4 @ CSH-01 | CASHLA 220 kV A4 | bar: Week 11 Tu 10 to Week 11 Mo 16
TO-26-220 kV B2 @ CSH-02 | CASHLA 220 kV B2 | bar: Week 11 Tu 10 to Week 11 Mo 16
TO-26-220 kV B4 @ CSH-02 | CASHLA 220 kV B4 | bar: Week 11 Tu 10 to Week 11 Mo 16
TO-26-CSH-220K2-4-01 | CASHLA 220K2-4 | bar: Week 11 Tu 10 to Week 11 Mo 16
TO-26-110 kV A2 @ DEY-01 | DERRYCARNEY 110 kV A2 | bar: Week 11 We 11 to Week 11 Th 12
TO-26-110 kV B2 @ DEY-01 | DERRYCARNEY 110 kV B2 | bar: Week 11 We 11 to Week 11 Th 12
TO-26-DEY-110K2-02 | DERRYCARNEY 110K2 | bar: Week 11 We 11 to Week 11 Th 12
TO-26-DEY-T134-02 | DERRYCARNEY T134 | bar: Week 11 We 11 to Week 11 Th 12
TO-26-TH-T2003/4-02 | TURLOUGH HILL T2003/4 | bar: Week 11 Th 12 to Week 11 Fr 13
TO-26-110 kV A2 @ ARV-01 | ARVA 110 kV A2 | bar: Week 11 Th 12 to Week 11 Mo 16
TO-26-110 kV B2 @ ARV-01 | ARVA 110 kV B2 | bar: Week 11 Th 12 to Week 11 Mo 16
TO-26-220 kV A1 @ TB-01 | TARBERT 220 kV A1 | bar: Su 1 to Week 11 Fr 13
TO-26-220 kV B1 @ TB-01 | TARBERT 220 kV B1 | bar: Su 1 to Week 11 Fr 13
TO-26-400 kV A1 @ WOO-02 | WOODLAND 400 kV A1 | bar: Su 1 to Week 11 Fr 13
TO-26-400 kV B1 @ WOO-02 | WOODLAND 400 kV B1 | bar: Su 1 to Week 11 Fr 13
TO-26-GI-WAT-1-05 | GREAT ISLAND WATERFORD 1 | bar: Week 11 Sa 14
TO-26-GI-WAT-2-03 | GREAT ISLAND WATERFORD 2 | bar: Week 11 Sa 14
Outages spanning Weeks 10-11
OUTAGE ID | PLANT | Week 10 Mo 2: Week 10; Week 11 Mo 9: Week 11
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
TO-26-ATH-M/CAP1-03 | ATHLONE M/CAP1
Report covers outages commencing/returning/spanning the period: 02/03/2026 - 15/03/2026
Outages spanning Weeks 10-11
OUTAGE ID | PLANT | Week 10 Mo 2: Week 10; Week 11 Mo 9: Week 11
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
TO-26-CBR-SVC-01 | CASTLEBAR SVC
TO-26-DND-T121-01 | DARNDALE T121
TO-26-DEN-T132-01 | DEENES T132
TO-26-DJG-110K2-01 | DROMBEG 110K2
TO-26-DSN-MP GIS-1-03 | DUNSTOWN MONEYPOINT GIS
TO-26-GAR-PLA-1-02 | GARBALLAGH PLATIN
TO-26-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-26-110 kV A1 @ GOR-05 | GORMAN 110 kV A1
TO-26-110 kV A2 @ GOR-01 | GORMAN 110 kV A2
TO-26-GI GIS-220SA1-2CB-02 | GREAT ISLAND GIS 220SA1-2CB
TO-26-GI-T141-01 | GREAT ISLAND T141
TO-26-KLS-110K1-2-01 | KELLIS 110K1-2
TO-26-220 kV A4 @ KRA-01 | KNOCKRAHA 220 kV A4
TO-26-220 kV B4 @ KRA-01 | KNOCKRAHA 220 kV B4
TO-26-KRA-220K4-01 | KNOCKRAHA 220K4
TO-26-KRA-220SA2-4CB-03 | KNOCKRAHA 220SA2-4CB
TO-26-KRA-220SB2-4CB-03 | KNOCKRAHA 220SB2-4CB
TO-26-LET-SVC-02 | LETTERKENNY SVC
TO-26-MR-T107-01 | MARINA T107
TO-26-MID-110SA1-01 | MIDLETON 110SA1
TO-26-MID-110SA2-01 | MIDLETON 110SA2
TO-26-MID-T102-01 | MIDLETON T102
TO-26-MID-WHI-1-01 | MIDLETON WHITEGATE
TO-26-NEW-PLS-1-01 | NEWBRIDGE PORTLAOISE
TO-26-PB-R2001-02 | POOLBEG R2001
TO-26-PB-R2001-03
TO-26-110 kV A1 @ PLS-05 | PORTLAOISE 110 kV A1
TO-26-RAF-110K1-2-03 | RAFFEEN 110K1-2
TO-26-SKL-M/CAP2-01 | SHANKILL M/CAP2
TO-26-SH-T2102-02 | SHANNONBRIDGE T2102
TO-26-TB-T2003-01 | TARBERT T2003
TO-26-TRL-CAP2-01 | TRALEE CAP2