## Wks 12 - 13
Report covers outages commencing/returning/spanning the period: 16/03/2026 - 29/03/2026
Outages commencing/returning in Week 12
OUTAGE ID | PLANT |  | Week 12 | [6 empty] | Week 13
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
TO-26-220 kV A1 @ CDU-04 | CORDUFF 220 kV A1 | bar: Week 12 Mo 16 to Week 12 Tu 17
TO-26-220 kV A3 @ CDU-02 | CORDUFF 220 kV A3 | bar: Week 12 Mo 16 to Week 12 Tu 17
TO-26-CDU-220K1-3-01 | CORDUFF 220K1-3 | bar: Week 12 Mo 16 to Week 12 Tu 17
TO-26-110 kV A2 @ RAT-01 | RATHKEALE 110 kV A2 | bar: Week 12 Mo 16 to Week 12 Tu 17
TO-26-RAT-110SA1-02 | RATHKEALE 110SA1 | bar: Week 12 Mo 16 to Week 12 Tu 17
TO-26-RAT-110SA2-01 | RATHKEALE 110SA2 | bar: Week 12 Mo 16 to Week 12 Tu 17
TO-26-RAT-T142-01 | RATHKEALE T142 | bar: Week 12 Mo 16 to Week 12 Tu 17
TO-26-LIM-RAT-1-01 | LIMERICK RATHKEALE | bar: Week 12 Mo 16 to Week 12 Tu 17; Week 12 Fr 20
TO-26-BDN-CUL-1-05 | BALLYDINE CULLENAGH | bar: Week 12 Mo 16 to Week 12 Tu 17; Week 12 Fr 20 to Week 12 Sa 21
TO-26-220 kV A2 @ CLE-01 | CLONEE 220 kV A2 | bar: Week 12 Mo 16 to Week 12 Tu 17; Week 12 Fr 20 to Week 13 Th 26
TO-26-220 kV B2 @ CLE-01 | CLONEE 220 kV B2 | bar: Week 12 Mo 16 to Week 12 Tu 17; Week 12 Fr 20 to Week 13 Th 26
TO-26-CLE-220K2-02 | CLONEE 220K2 | bar: Week 12 Mo 16 to Week 12 Tu 17; Week 12 Fr 20 to Week 13 Th 26
TO-26-CLE-220SA1-2CB-02 | CLONEE 220SA1-2CB | bar: Week 12 Mo 16 to Week 12 Tu 17; Week 12 Fr 20 to Week 13 Th 26
TO-26-CLE-220SB1-2CB-02 | CLONEE 220SB1-2CB | bar: Week 12 Mo 16 to Week 12 Tu 17; Week 12 Fr 20 to Week 13 Th 26
TO-26-CLE-WOO-1-03 | CLONEE WOODLAND | bar: Week 12 Mo 16 to Week 12 Tu 17; Week 12 Fr 20 to Week 13 Th 26
TO-26-110 kV A3 @ KPG-01 | KILPADDOGE 110 kV A3 | bar: Week 12 Mo 16 to Week 12 Tu 17; Week 12 Fr 20 to Week 13 Fr 27
TO-26-110 kV A4 @ KPG-01 | KILPADDOGE 110 kV A4 | bar: Week 12 Mo 16 to Week 12 Tu 17; Week 12 Fr 20 to Week 13 Fr 27
TO-26-110 kV B2 @ KPG-02 | KILPADDOGE 110 kV B2 | bar: Week 12 Mo 16 to Week 12 Tu 17; Week 12 Fr 20 to Week 13 Fr 27
TO-26-110 kV B3 @ KPG-01 | KILPADDOGE 110 kV B3 | bar: Week 12 Mo 16 to Week 12 Tu 17; Week 12 Fr 20 to Week 13 Fr 27
TO-26-110 kV B4 @ KPG-01 | KILPADDOGE 110 kV B4 | bar: Week 12 Mo 16 to Week 12 Tu 17; Week 12 Fr 20 to Week 13 Fr 27
TO-26-KPG-110K3-01 | KILPADDOGE 110K3 | bar: Week 12 Mo 16 to Week 12 Tu 17; Week 12 Fr 20 to Week 13 Fr 27
TO-26-KPG-110K4-02 | KILPADDOGE 110K4 | bar: Week 12 Mo 16 to Week 12 Tu 17; Week 12 Fr 20 to Week 13 Fr 27
TO-26-KPG-110SA1-3CB-02 | KILPADDOGE 110SA1-3CB | bar: Week 12 Mo 16 to Week 12 Tu 17; Week 12 Fr 20 to Week 13 Fr 27
TO-26-KPG-110SA2-4CB-02 | KILPADDOGE 110SA2-4CB | bar: Week 12 Mo 16 to Week 12 Tu 17; Week 12 Fr 20 to Week 13 Fr 27
TO-26-KPG-110SB1-3CB-03 | KILPADDOGE 110SB1-3CB | bar: Week 12 Mo 16 to Week 12 Tu 17; Week 12 Fr 20 to Week 13 Fr 27
TO-26-KPG-110SB2-4CB-03 | KILPADDOGE 110SB2-4CB | bar: Week 12 Mo 16 to Week 12 Tu 17; Week 12 Fr 20 to Week 13 Fr 27
TO-26-SH-220K1-2-02 | SHANNONBRIDGE 220K1-2 | bar: Week 12 Mo 16 to Week 12 Tu 17; Week 12 Fr 20 to Week 13 Mo 30
TO-26-CKM GIS-220K3-03 | CARRICKMINES GIS 220K3
TO-26-RYB GIS-T105-01 | RYEBROOK GIS T105
TO-26-MID-WHI-1-02 | MIDLETON WHITEGATE | bar: Week 12 Fr 20 to Week 13 Th 26
TO-26-WHI-110SA1-01 | WHITEGATE 110SA1 | bar: Week 12 Fr 20 to Week 13 Th 26
TO-26-WHI-110SA2-01 | WHITEGATE 110SA2 | bar: Week 12 Fr 20 to Week 13 Th 26
TO-26-WHI-CKB-T101-01 | WHITEGATE CKB-T101 | bar: Week 12 Fr 20 to Week 13 Th 26
TO-26-LET-PST-04 | LETTERKENNY STRABANE PST | bar: Su 15 to Week 12 Tu 17
TO-26-BVK-CLA-1-02 | BALLYVOUSKILL CLASHAVOON | bar: Week 12 Fr 20
TO-26-110 kV A1 @ BVK-02 | BALLYVOUSKILL 110 kV A1 | bar: Su 15 to Week 12 Tu 17; Week 12 Fr 20
TO-26-110 kV B1 @ BVK-01 | BALLYVOUSKILL 110 kV B1 | bar: Su 15 to Week 12 Tu 17; Week 12 Fr 20
TO-26-BVK-110K1-01 | BALLYVOUSKILL 110K1 | bar: Su 15 to Week 12 Tu 17; Week 12 Fr 20
TO-26-BVK-110SA1-2CB-06 | BALLYVOUSKILL 110SA1-2CB | bar: Su 15 to Week 12 Tu 17; Week 12 Fr 20
TO-26-BVK-110SB1-2CB-04 | BALLYVOUSKILL 110SB1-2CB | bar: Su 15 to Week 12 Tu 17; Week 12 Fr 20
TO-26-220 kV A1 @ BVK-01 | BALLYVOUSKILL 220 kV A1 | bar: Su 15 to Week 12 Tu 17; Week 12 Fr 20
TO-26-220 kV B1 @ BVK-01 | BALLYVOUSKILL 220 kV B1 | bar: Su 15 to Week 12 Tu 17; Week 12 Fr 20
TO-26-BVK-220K1-01 | BALLYVOUSKILL 220K1 | bar: Su 15 to Week 12 Tu 17; Week 12 Fr 20
TO-26-BVK-220SA1-2CB-05 | BALLYVOUSKILL 220SA1-2CB | bar: Su 15 to Week 12 Tu 17; Week 12 Fr 20
TO-26-BVK-220SB1-2CB-05 | BALLYVOUSKILL 220SB1-2CB | bar: Su 15 to Week 12 Tu 17; Week 12 Fr 20
TO-26-BVK-T2101-02 | BALLYVOUSKILL T2101 | bar: Su 15 to Week 12 Tu 17; Week 12 Fr 20
Outages commencing/returning in Week 13
OUTAGE ID | PLANT | Week 12 Mo 16: Week 12; Week 13 Mo 23: Week 13
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
TO-26-CUL-220K1-2-01 | CULLENAGH 220K1-2 | bar: Week 13 Mo 23
TO-26-GLN-T133-01 | GALLANSTOWN T133 | bar: Week 13 Mo 23
TO-26-ATH-LA-1-10 | ATHLONE LANESBORO | bar: Week 13 Mo 23; Week 13 Fr 27
TO-26-DJG-110K2-02 | DROMBEG 110K2 | bar: Week 13 Mo 23; Week 13 Fr 27
TO-26-DJG-KPG-1-05 | DROMBEG KILPADDOGE | bar: Week 13 Mo 23; Week 13 Fr 27
TO-26-DJG-T134-02 | DROMBEG T134 | bar: Week 13 Mo 23; Week 13 Fr 27
TO-26-DJG-T142-01 | DROMBEG T142 | bar: Week 13 Mo 23; Week 13 Fr 27
TO-26-DJG-TRL-1-04 | DROMBEG TRALEE | bar: Week 13 Mo 23; Week 13 Fr 27
TO-26-DSN-TH-1-02 | DUNSTOWN TURLOUGH HILL | bar: Week 13 Mo 23; Week 13 Fr 27
TO-26-GOR-NAV-2-02 | GORMAN NAVAN 2 | bar: Week 13 Mo 23; Week 13 Fr 27
TO-26-KPG-RAT-1-03 | KILPADDOGE RATHKEALE | bar: Week 13 Mo 23; Week 13 Fr 27
TO-26-KRA-WOH-1-07 | KNOCKRAHA WOODHOUSE | bar: Week 13 Mo 23; Week 13 Fr 27
Report covers outages commencing/returning/spanning the period: 16/03/2026 - 29/03/2026
Outages commencing/returning in Week 13
OUTAGE ID | PLANT | Week 12 Mo 16: Week 12; Week 13 Mo 23: Week 13
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
TO-26-RAT-110SA1-01 | RATHKEALE 110SA1 | bar: Week 13 Mo 23; Week 13 Fr 27
TO-26-RAT-110SA2-02 | RATHKEALE 110SA2 | bar: Week 13 Mo 23; Week 13 Fr 27
TO-26-RAT-T141-01 | RATHKEALE T141 | bar: Week 13 Mo 23; Week 13 Fr 27
TO-26-220 kV A1 @ CDU-01 | CORDUFF 220 kV A1 | bar: Week 13 Mo 23; Week 13 Fr 27 to Week 13 Mo 30
TO-26-220 kV A2 @ CDU-02 | CORDUFF 220 kV A2 | bar: Week 13 Mo 23; Week 13 Fr 27 to Week 13 Mo 30
TO-26-220 kV B1 @ CDU-01 | CORDUFF 220 kV B1 | bar: Week 13 Mo 23; Week 13 Fr 27 to Week 13 Mo 30
TO-26-220 kV B2 @ CDU-02 | CORDUFF 220 kV B2 | bar: Week 13 Mo 23; Week 13 Fr 27 to Week 13 Mo 30
TO-26-CDU-220K1-2-01 | CORDUFF 220K1-2 | bar: Week 13 Mo 23; Week 13 Fr 27 to Week 13 Mo 30
TO-26-CDU-220SA2-4CB-02 | CORDUFF 220SA2-4CB | bar: Week 13 Mo 23; Week 13 Fr 27 to Week 13 Mo 30
TO-26-CDU-220SB2-4CB-02 | CORDUFF 220SB2-4CB | bar: Week 13 Mo 23; Week 13 Fr 27 to Week 13 Mo 30
TO-26-KPG-RAT-1-02 | KILPADDOGE RATHKEALE | bar: Week 13 Mo 23; Week 13 Fr 27 to Week 13 Mo 30
TO-26-110 kV A2 @ KRA-01 | KNOCKRAHA 110 kV A2 | bar: Week 13 Mo 23; Week 13 Fr 27 to Week 13 Mo 30
TO-26-110 kV B2 @ KRA-01 | KNOCKRAHA 110 kV B2 | bar: Week 13 Mo 23; Week 13 Fr 27 to Week 13 Mo 30
TO-26-220 kV A2 @ DSN-01 | DUNSTOWN 220 kV A2 | bar: Su 15 to Week 13 Mo 23
TO-26-DND-110SA1-2CB-02 | DARNDALE 110SA1-2CB
TO-26-CLU-T124-01 | CLUTTERLAND T124
TO-26-BLC-DND-3-01 | BELCAMP DARNDALE 3
TO-26-RYB GIS-T104-01 | RYEBROOK GIS T104
TO-26-110 kV A1 @ KNR-01 | KNOCKANURE 110 kV A1 | bar: Week 13 Fr 27 to Week 13 Mo 30
TO-26-110 kV B1 @ KNR-01 | KNOCKANURE 110 kV B1 | bar: Week 13 Fr 27 to Week 13 Mo 30
TO-26-KNR-110K1-01 | KNOCKANURE 110K1 | bar: Week 13 Fr 27 to Week 13 Mo 30
TO-26-KNR-110SA1-2CB-01 | KNOCKANURE 110SA1-2CB | bar: Week 13 Fr 27 to Week 13 Mo 30
TO-26-KNR-110SB1-2CB-01 | KNOCKANURE 110SB1-2CB | bar: Week 13 Fr 27 to Week 13 Mo 30
TO-26-220 kV A1 @ KNR-01 | KNOCKANURE 220 kV A1 | bar: Week 13 Fr 27 to Week 13 Mo 30
TO-26-220 kV B1 @ KNR-01 | KNOCKANURE 220 kV B1 | bar: Week 13 Fr 27 to Week 13 Mo 30
TO-26-KNR-220K1-01 | KNOCKANURE 220K1 | bar: Week 13 Fr 27 to Week 13 Mo 30
TO-26-KNR-220SA1-2CB-01 | KNOCKANURE 220SA1-2CB | bar: Week 13 Fr 27 to Week 13 Mo 30
TO-26-KNR-220SB1-2CB-01 | KNOCKANURE 220SB1-2CB | bar: Week 13 Fr 27 to Week 13 Mo 30
TO-26-KNR-T2101-01 | KNOCKANURE T2101 | bar: Week 13 Fr 27 to Week 13 Mo 30
TO-26-CLA-CKN-1-01 | CLASHAVOON CLONKEEN
TO-26-BAN-RAF-1-02 | BANDON RAFFEEN | bar: Week 13 Fr 27 to Week 13 Mo 30
TO-26-110 kV B2 @ RAF-02 | RAFFEEN 110 kV B2 | bar: Week 13 Fr 27 to Week 13 Mo 30
TO-26-DEN-DRY-1-03 | DEENES DRYBRIDGE | bar: Su 15 to Week 13 Mo 23
Outages spanning Weeks 12-13
OUTAGE ID | PLANT | Week 12 Mo 16: Week 12; Week 13 Mo 23: Week 13
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
TO-26-ATH-M/CAP1-03 | ATHLONE M/CAP1
TO-26-CBT-INC-2-05 | CASTLEBAGOT INCHICORE 2
TO-26-CBR-SVC-02 | CASTLEBAR SVC
TO-26-CBR-SVC-01
TO-26-CLE-WOO-1-02 | CLONEE WOODLAND
TO-26-CRA-T122-02 | CRANE T122
TO-26-DND-T121-01 | DARNDALE T121
TO-26-DND-T124-03 | DARNDALE T124
TO-26-110 kV B2 @ DJG-01 | DROMBEG 110 kV B2
TO-26-DJG-110K2-01 | DROMBEG 110K2
TO-26-DSN-MP GIS-1-03 | DUNSTOWN MONEYPOINT GIS
TO-26-220 kV A2 @ FLA-02 | FLAGFORD 220 kV A2
TO-26-220 kV B2 @ FLA-02 | FLAGFORD 220 kV B2
TO-26-GAR-PLA-1-02 | GARBALLAGH PLATIN
TO-26-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-26-110 kV A1 @ GOR-05 | GORMAN 110 kV A1
TO-26-110 kV A2 @ GOR-01 | GORMAN 110 kV A2
TO-26-GI GIS-220SA1-2CB-02 | GREAT ISLAND GIS 220SA1-2CB
TO-26-GI-T141-01 | GREAT ISLAND T141
TO-26-220 kV A6 @ INC-03 | INCHICORE 220 kV A6
TO-26-220 kV B6 @ INC-03 | INCHICORE 220 kV B6
TO-26-INC-220K4-6-01 | INCHICORE 220K4-6
TO-26-INC-T2106-01 | INCHICORE T2106
TO-26-KLS-110K1-2-01 | KELLIS 110K1-2
TO-26-220 kV A4 @ KRA-01 | KNOCKRAHA 220 kV A4
TO-26-220 kV B4 @ KRA-01 | KNOCKRAHA 220 kV B4
Report covers outages commencing/returning/spanning the period: 16/03/2026 - 29/03/2026
Outages spanning Weeks 12-13
OUTAGE ID | PLANT | Week 12 Mo 16: Week 12; Week 13 Mo 23: Week 13
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
TO-26-KRA-220K4-01 | KNOCKRAHA 220K4
TO-26-KRA-220SA2-4CB-03 | KNOCKRAHA 220SA2-4CB
TO-26-KRA-220SB2-4CB-03 | KNOCKRAHA 220SB2-4CB
TO-26-LET-SVC-02 | LETTERKENNY SVC
TO-26-220 kV A2 @ LOU-02 | LOUTH 220 kV A2
TO-26-220 kV B2 @ LOU-02 | LOUTH 220 kV B2
TO-26-MR-T107-01 | MARINA T107
TO-26-MID-110SA1-01 | MIDLETON 110SA1
TO-26-MID-110SA2-01 | MIDLETON 110SA2
TO-26-MID-T102-01 | MIDLETON T102
TO-26-MID-WHI-1-01 | MIDLETON WHITEGATE
TO-26-NAV-M/CAP1-01 | NAVAN M/CAP1
TO-26-NEW-PLS-1-01 | NEWBRIDGE PORTLAOISE
TO-26-220 kV A1/A2 @ PB-02 | POOLBEG 220 kV A1/A2
TO-26-PB-R2001-02 | POOLBEG R2001
TO-26-PB-R2001-03
TO-26-110 kV A1 @ PLS-05 | PORTLAOISE 110 kV A1
TO-26-RAF-110K1-2-03 | RAFFEEN 110K1-2
TO-26-SKL-M/CAP2-01 | SHANKILL M/CAP2
TO-26-SH-T2102-02 | SHANNONBRIDGE T2102
TO-26-TB-T2003-01 | TARBERT T2003
TO-26-TRL-CAP2-01 | TRALEE CAP2
TO-26-220 kV B1 @ WOO-01 | WOODLAND 220 kV B1