## Wks 14 - 15
Report covers outages commencing/returning/spanning the period: 30/03/2026 - 12/04/2026
Outages commencing/returning in Week 14
OUTAGE ID | PLANT |  | Week 14 | [6 empty] | Week 15
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
TO-26-ATH-110SA1-2CB-01 | ATHLONE 110SA1-2CB
TO-26-ATH-SH-1-02 | ATHLONE SHANNONBRIDGE
TO-26-ATH-T142-01 | ATHLONE T142
TO-26-LSA-SKL-1-02 | LISLEA SHANKILL
TO-26-BDN-DOO-1-02 | BALLYDINE DOON
TO-26-220 kV B1 @ BYH-01 | BALLYNAHULLA 220 kV B1
TO-26-220 kV B2 @ BYH-01 | BALLYNAHULLA 220 kV B2
TO-26-BYH-220K1-01 | BALLYNAHULLA 220K1
TO-26-BYH-220K2-01 | BALLYNAHULLA 220K2
TO-26-BYH-220SA1-2CB-01 | BALLYNAHULLA 220SA1-2CB
TO-26-BYH-220SB1-2CB-01 | BALLYNAHULLA 220SB1-2CB
TO-26-CBT-CKG-2-01 | CASTLEBAGOT CORKAGH 2
TO-26-CDK-LWD-1-01 | CASTLEDOCKRELL LODGEWOOD
TO-26-CDK-T121-02 | CASTLEDOCKRELL T121
TO-26-110 kV A1 @ CKG-01 | CORKAGH 110 kV A1
TO-26-110 kV A2 @ CKG-02 | CORKAGH 110 kV A2
TO-26-110 kV B1 @ CKG-01 | CORKAGH 110 kV B1
TO-26-110 kV B2 @ CKG-02 | CORKAGH 110 kV B2
TO-26-CKG-110K2-03 | CORKAGH 110K2
TO-26-CKG-110SA1-2CB-02 | CORKAGH 110SA1-2CB
TO-26-CKG-110SA1-3CB-01 | CORKAGH 110SA1-3CB
TO-26-CKG-110SB1-2CB-02 | CORKAGH 110SB1-2CB
TO-26-CKG-110SB1-3CB-01 | CORKAGH 110SB1-3CB
TO-26-LWD-110K1-2-01 | LODGEWOOD 110K1-2
TO-26-LWD-T2102-01 | LODGEWOOD T2102
TO-26-OBE-T121-01 | OLDBRIDGE T121 | bar: Week 14 Fr 3
TO-26-220 kV A2 @ DSN-02 | DUNSTOWN 220 kV A2 | bar: Week 14 Fr 3 to Week 15 Tu 7
TO-26-220 kV A4 @ INC-01 | INCHICORE 220 kV A4 | bar: Week 14 Fr 3 to Week 15 We 8
TO-26-CHA-MAL-1-01 | CHARLEVILLE MALLOW | bar: Week 14 Fr 3 to Week 15 Mo 13
TO-26-CLA-MAC-1-02 | CLASHAVOON MACROOM 1 | bar: Week 14 Fr 3 to Week 15 Mo 13
TO-26-220 kV A2 @ CLE-01 | CLONEE 220 kV A2 | bar: Su 29
TO-26-220 kV B2 @ CLE-01 | CLONEE 220 kV B2 | bar: Su 29
TO-26-CLE-220K2-02 | CLONEE 220K2 | bar: Su 29
TO-26-CLE-220SA1-2CB-02 | CLONEE 220SA1-2CB | bar: Su 29
TO-26-CLE-220SB1-2CB-02 | CLONEE 220SB1-2CB | bar: Su 29
TO-26-AD-220K1-01 | AGHADA 220K1
TO-26-AD-SB1-2CB-01 | AGHADA 220SB1-2CB
TO-26-KPG-T2102-02 | KILPADDOGE T2102
TO-26-FIN GIS-T2101-01 | FINGLAS GIS T2101
TO-26-CLO-DRM-1-01 | CLOGHER DRUMKEEN
TO-26-CKN-KER-1-02 | CLONKEEN KNOCKEARAGH
TO-26-GOL-T101-01 | GOLAGH T101
TO-26-GOL,T-CLO-1-01 | GOLAGH tee CLOGHER
TO-26-GOL,T-GOL-1-03 | GOLAGH tee GOLAGH
TO-26-GOL,T-LET-1-03 | GOLAGH tee LETTERKENNY
TO-26-FLA-110K1-2-01 | FLAGFORD 110K1-2
TO-26-220 kV B2 @ KPG-01 | KILPADDOGE 220 kV B2
TO-26-AD-SA1-2CB-01 | AGHADA 220SA1-2CB
TO-26-RYB GIS-T107-01 | RYEBROOK GIS T107
TO-26-DEN-T132-02 | DEENES T132
TO-26-GI-T141-02 | GREAT ISLAND T141 | bar: Week 14 Fr 3
TO-26-DSN-MP GIS-1-03 | DUNSTOWN MONEYPOINT GIS | bar: Su 29
TO-26-400 kV A3 @ MP GIS-01 | MONEYPOINT GIS 400 kV A3 | bar: Su 29
TO-26-400 kV B3 @ MP GIS-01 | MONEYPOINT GIS 400 kV B3 | bar: Su 29
TO-26-MP GIS-400K3-04 | MONEYPOINT GIS 400K3 | bar: Su 29
TO-26-MP GIS-400SA1-3CB-05 | MONEYPOINT GIS 400SA1-3CB | bar: Su 29
TO-26-MP GIS-400SB1-3CB-05 | MONEYPOINT GIS 400SB1-3CB | bar: Su 29
TO-26-MP GIS-T4003-01 | MONEYPOINT GIS T4003 | bar: Su 29
TO-26-220 kV A1 @ CDU-01 | CORDUFF 220 kV A1 | bar: Su 29; Week 14 Fr 3
TO-26-220 kV A2 @ CDU-02 | CORDUFF 220 kV A2 | bar: Su 29; Week 14 Fr 3
TO-26-220 kV B1 @ CDU-01 | CORDUFF 220 kV B1 | bar: Su 29; Week 14 Fr 3
TO-26-220 kV B2 @ CDU-02 | CORDUFF 220 kV B2 | bar: Su 29; Week 14 Fr 3
TO-26-CDU-220K1-2-01 | CORDUFF 220K1-2 | bar: Su 29; Week 14 Fr 3
TO-26-CDU-220SA2-4CB-02 | CORDUFF 220SA2-4CB | bar: Su 29; Week 14 Fr 3
Report covers outages commencing/returning/spanning the period: 30/03/2026 - 12/04/2026
Outages commencing/returning in Week 14
OUTAGE ID | PLANT | Week 14 Mo 30: Week 14; Week 15 Mo 6: Week 15
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
TO-26-CDU-220SB2-4CB-02 | CORDUFF 220SB2-4CB | bar: Su 29 to Week 14 Fr 3
TO-26-110 kV A1 @ GOR-05 | GORMAN 110 kV A1 | bar: Su 29 to Week 14 Fr 3
TO-26-110 kV A2 @ GOR-01 | GORMAN 110 kV A2 | bar: Su 29 to Week 14 Fr 3
TO-26-GRI-T141-02 | GRIFFINRATH T141 | bar: Su 29 to Week 14 Fr 3
TO-26-GRI,T-GRI-1-02 | GRIFFINRATH tee GRIFFINRATH | bar: Su 29 to Week 14 Fr 3
TO-26-GRI,T-MAY-1-03 | GRIFFINRATH tee MAYNOOTH | bar: Su 29 to Week 14 Fr 3
TO-26-KPG-RAT-1-02 | KILPADDOGE RATHKEALE | bar: Su 29 to Week 14 Fr 3
Outages commencing/returning in Week 15
OUTAGE ID | PLANT | Week 14 Mo 30: Week 14; Week 15 Mo 6: Week 15
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
TO-26-BVK-110SA1-2CB-03 | BALLYVOUSKILL 110SA1-2CB | bar: Week 15 Tu 7
TO-26-BVK-110SB1-2CB-03 | BALLYVOUSKILL 110SB1-2CB | bar: Week 15 Tu 7
TO-26-220 kV A2 @ SH-01 | SHANNONBRIDGE 220 kV A2 | bar: Week 15 Tu 7
TO-26-220 kV B2 @ SH-01 | SHANNONBRIDGE 220 kV B2 | bar: Week 15 Tu 7
TO-26-SH-220K1-2-01 | SHANNONBRIDGE 220K1-2 | bar: Week 15 Tu 7
TO-26-CRA-LWD-1-01 | CRANE LODGEWOOD | bar: Week 15 Tu 7
TO-26-220 kV A1 @ BVK-02 | BALLYVOUSKILL 220 kV A1 | bar: Week 15 Tu 7
TO-26-BVK-T2101-03 | BALLYVOUSKILL T2101 | bar: Week 15 Tu 7
TO-26-LOU-MLN-1-02 | LOUTH MULLAGHARLIN | bar: Week 15 Tu 7
TO-26-MLN-110SA1-2CB-02 | MULLAGHARLIN 110SA1-2CB | bar: Week 15 Tu 7
TO-26-MLN-T122-01 | MULLAGHARLIN T122 | bar: Week 15 Tu 7
TO-26-MLN-T124-02 | MULLAGHARLIN T124 | bar: Week 15 Tu 7
TO-26-AA GIS-ENN-1-03 | ARDNACRUSHA GIS ENNIS | bar: Week 15 Tu 7; Week 15 Sa 11 to Week 15 Mo 13
TO-26-220 kV A2 @ FIN-07 | FINGLAS 220 kV A2 | bar: Week 15 Tu 7; Week 15 Sa 11 to Week 15 Mo 13
TO-26-220 kV B2 @ FIN-05 | FINGLAS 220 kV B2 | bar: Week 15 Tu 7; Week 15 Sa 11 to Week 15 Mo 13
TO-26-FIN-220K2-10 | FINGLAS 220K2 | bar: Week 15 Tu 7; Week 15 Sa 11 to Week 15 Mo 13
TO-26-FIN-220SA1-2CB-13 | FINGLAS 220SA1-2CB | bar: Week 15 Tu 7; Week 15 Sa 11 to Week 15 Mo 13
TO-26-FIN-220SB1-2CB-10 | FINGLAS 220SB1-2CB | bar: Week 15 Tu 7; Week 15 Sa 11 to Week 15 Mo 13
TO-26-110 kV A3 @ FIN GIS-01 | FINGLAS GIS 110 kV A3 | bar: Week 15 Tu 7; Week 15 Sa 11 to Week 15 Mo 13
TO-26-110 kV B3 @ FIN GIS-01 | FINGLAS GIS 110 kV B3 | bar: Week 15 Tu 7; Week 15 Sa 11 to Week 15 Mo 13
TO-26-FIN GIS-110SA1-3CB-02 | FINGLAS GIS 110SA1-3CB | bar: Week 15 Tu 7; Week 15 Sa 11 to Week 15 Mo 13
TO-26-FIN GIS-110SA3-5CB-03 | FINGLAS GIS 110SA3-5CB | bar: Week 15 Tu 7; Week 15 Sa 11 to Week 15 Mo 13
TO-26-FIN GIS-110SB1-3CB-01 | FINGLAS GIS 110SB1-3CB | bar: Week 15 Tu 7; Week 15 Sa 11 to Week 15 Mo 13
TO-26-FIN GIS-110SB3-5CB-03 | FINGLAS GIS 110SB3-5CB | bar: Week 15 Tu 7; Week 15 Sa 11 to Week 15 Mo 13
TO-26-FIN GIS-T2106-01 | FINGLAS GIS T2106 | bar: Week 15 Tu 7; Week 15 Sa 11 to Week 15 Mo 13
TO-26-KPG-KNR-1-110-01 | KILPADDOGE KNOCKANURE 110 | bar: Week 15 Tu 7; Week 15 Sa 11 to Week 15 Mo 13
TO-26-RYB GIS-T108-01 | RYEBROOK GIS T108 | bar: Week 15 Tu 7; Week 15 Sa 11 to Week 15 Mo 13
TO-26-TAW-T1/T2-01 | TAWNAGHMORE T1/T2 | bar: Week 15 Tu 7; Week 15 Sa 11 to Week 15 Mo 13
TO-26-TAW-T3-02 | TAWNAGHMORE T3 | bar: Week 15 Tu 7; Week 15 Sa 11 to Week 15 Mo 13
TO-26-FLA-TON-1-01 | FLAGFORD TONROE | bar: Week 15 Sa 11 to Week 15 Mo 13
TO-26-KLN-KRA-1-06 | KILLONAN KNOCKRAHA | bar: Week 15 Sa 11 to Week 15 Mo 13
TO-26-220 kV A1 @ KRA-03 | KNOCKRAHA 220 kV A1 | bar: Week 15 Sa 11 to Week 15 Mo 13
TO-26-220 kV B1 @ KRA-03 | KNOCKRAHA 220 kV B1 | bar: Week 15 Sa 11 to Week 15 Mo 13
TO-26-KRA-220K1-06 | KNOCKRAHA 220K1 | bar: Week 15 Sa 11 to Week 15 Mo 13
TO-26-KRA-220K1-05 | bar: Week 15 Sa 11 to Week 15 Mo 13
TO-26-KRA-220SA1-2CB-06 | KNOCKRAHA 220SA1-2CB | bar: Week 15 Sa 11 to Week 15 Mo 13
TO-26-KRA-220SB1-2CB-06 | KNOCKRAHA 220SB1-2CB | bar: Week 15 Sa 11 to Week 15 Mo 13
TO-26-MTH-T141-01 | MEATH HILL T141 | bar: Week 15 Sa 11 to Week 15 Mo 13
TO-26-TON-T142-01 | TONROE T142 | bar: Week 15 Sa 11 to Week 15 Mo 13
TO-26-SH-220K1-2-02 | SHANNONBRIDGE 220K1-2 | bar: Su 29 to Week 15 Tu 7
TO-26-110 kV A2 @ SH-01 | SHANNONBRIDGE 110 kV A2
TO-26-110 kV B2 @ SH-01 | SHANNONBRIDGE 110 kV B2
TO-26-SH-110K1-2-01 | SHANNONBRIDGE 110K1-2
TO-26-CRA-T122-02 | CRANE T122 | bar: Su 29 to Week 15 Tu 7
TO-26-110 kV A1 @ KNR-01 | KNOCKANURE 110 kV A1 | bar: Su 29 to Week 15 Tu 7
TO-26-110 kV B1 @ KNR-01 | KNOCKANURE 110 kV B1 | bar: Su 29 to Week 15 Tu 7
TO-26-KNR-110K1-01 | KNOCKANURE 110K1 | bar: Su 29 to Week 15 Tu 7
TO-26-KNR-110SA1-2CB-01 | KNOCKANURE 110SA1-2CB | bar: Su 29 to Week 15 Tu 7
TO-26-KNR-110SB1-2CB-01 | KNOCKANURE 110SB1-2CB | bar: Su 29 to Week 15 Tu 7
TO-26-220 kV A1 @ KNR-01 | KNOCKANURE 220 kV A1 | bar: Su 29 to Week 15 Tu 7
TO-26-220 kV B1 @ KNR-01 | KNOCKANURE 220 kV B1 | bar: Su 29 to Week 15 Tu 7
Report covers outages commencing/returning/spanning the period: 30/03/2026 - 12/04/2026
Outages commencing/returning in Week 15
OUTAGE ID | PLANT | Week 14 Mo 30: Week 14; Week 15 Mo 6: Week 15
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
TO-26-KNR-220K1-01 | KNOCKANURE 220K1
TO-26-KNR-220SA1-2CB-01 | KNOCKANURE 220SA1-2CB
TO-26-KNR-220SB1-2CB-01 | KNOCKANURE 220SB1-2CB
TO-26-KNR-T2101-01 | KNOCKANURE T2101
Outages spanning Weeks 14-15
OUTAGE ID | PLANT | Week 14 Mo 30: Week 14; Week 15 Mo 6: Week 15
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
TO-26-BAN-RAF-1-02 | BANDON RAFFEEN
TO-26-CBT-INC-2-05 | CASTLEBAGOT INCHICORE 2
TO-26-CBR-SVC-02 | CASTLEBAR SVC
TO-26-CBR-SVC-01
TO-26-CLE-WOO-1-02 | CLONEE WOODLAND
TO-26-DND-T121-01 | DARNDALE T121
TO-26-110 kV B2 @ DJG-01 | DROMBEG 110 kV B2
TO-26-DJG-110K2-01 | DROMBEG 110K2
TO-26-220 kV A2 @ FLA-02 | FLAGFORD 220 kV A2
TO-26-220 kV B2 @ FLA-02 | FLAGFORD 220 kV B2
TO-26-GAR-PLA-1-02 | GARBALLAGH PLATIN
TO-26-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-26-GI GIS-220SA1-2CB-02 | GREAT ISLAND GIS 220SA1-2CB
TO-26-GI-T141-01 | GREAT ISLAND T141
TO-26-220 kV A6 @ INC-03 | INCHICORE 220 kV A6
TO-26-220 kV B6 @ INC-03 | INCHICORE 220 kV B6
TO-26-INC-220K4-6-01 | INCHICORE 220K4-6
TO-26-INC-T2106-01 | INCHICORE T2106
TO-26-KLS-110K1-2-01 | KELLIS 110K1-2
TO-26-110 kV A2 @ KRA-01 | KNOCKRAHA 110 kV A2
TO-26-110 kV B2 @ KRA-01 | KNOCKRAHA 110 kV B2
TO-26-220 kV A4 @ KRA-01 | KNOCKRAHA 220 kV A4
TO-26-220 kV B4 @ KRA-01 | KNOCKRAHA 220 kV B4
TO-26-KRA-220K4-01 | KNOCKRAHA 220K4
TO-26-KRA-220SA2-4CB-03 | KNOCKRAHA 220SA2-4CB
TO-26-KRA-220SB2-4CB-03 | KNOCKRAHA 220SB2-4CB
TO-26-LET-SVC-02 | LETTERKENNY SVC
TO-26-220 kV A2 @ LOU-02 | LOUTH 220 kV A2
TO-26-220 kV B2 @ LOU-02 | LOUTH 220 kV B2
TO-26-MR-T107-01 | MARINA T107
TO-26-MID-110SA1-01 | MIDLETON 110SA1
TO-26-MID-110SA2-01 | MIDLETON 110SA2
TO-26-MID-T102-01 | MIDLETON T102
TO-26-MID-WHI-1-01 | MIDLETON WHITEGATE
TO-26-NAV-M/CAP1-01 | NAVAN M/CAP1
TO-26-NEW-PLS-1-01 | NEWBRIDGE PORTLAOISE
TO-26-220 kV A1/A2 @ PB-02 | POOLBEG 220 kV A1/A2
TO-26-PB-R2001-02 | POOLBEG R2001
TO-26-PB-R2001-03
TO-26-110 kV A1 @ PLS-06 | PORTLAOISE 110 kV A1
TO-26-110 kV B2 @ RAF-02 | RAFFEEN 110 kV B2
TO-26-SKL-M/CAP2-01 | SHANKILL M/CAP2
TO-26-SH-T2102-02 | SHANNONBRIDGE T2102
TO-26-TB-T2003-01 | TARBERT T2003
TO-26-TRL-CAP2-01 | TRALEE CAP2
TO-26-220 kV B1 @ WOO-01 | WOODLAND 220 kV B1