## Wks 16 - 17
Report covers outages commencing/returning/spanning the period: 13/04/2026 - 26/04/2026
Outages commencing/returning in Week 16
OUTAGE ID | PLANT |  | Week 16 | [6 empty] | Week 17
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
TO-26-MLN-T123-02 | MULLAGHARLIN T123 | bar: Week 16 Mo 13
TO-26-LSA-T131-02 | LISLEA T131 | bar: Week 16 Mo 13; Week 16 Th 16
TO-26-BVK-T2102-06 | BALLYVOUSKILL T2102 | bar: Week 16 Mo 13; Week 16 Th 16 to Week 16 Fr 17
TO-26-BDA-T102-02 | BARODA T102 | bar: Week 16 Mo 13; Week 16 Th 16 to Week 16 Fr 17
TO-26-CLE-T224-02 | CLONEE T224 | bar: Week 16 Mo 13; Week 16 Th 16 to Week 16 Fr 17
TO-26-220 kV B2 @ DSN-02 | DUNSTOWN 220 kV B2 | bar: Week 16 Mo 13; Week 16 Th 16 to Week 16 Fr 17
TO-26-MAY-TEN-1-01 | MAYNOOTH TIMAHOE | bar: Week 16 Mo 13; Week 16 Th 16 to Week 16 Fr 17
TO-26-RRU-T122-01 | RATRUSSAN T122 | bar: Week 16 Mo 13; Week 16 Th 16 to Week 16 Fr 17
TO-26-220 kV B4 @ INC-01 | INCHICORE 220 kV B4 | bar: Week 16 Mo 13; Week 16 Th 16 to Week 17 Mo 20
TO-26-AGP-TIV-1-01 | ARDNAGAPPARY TIEVEBRACK | bar: Week 16 Mo 13; Week 16 Th 16 to Week 17 Th 23
TO-26-BIN-TIV-1-01 | BINBANE TIEVEBRACK | bar: Week 16 Mo 13; Week 16 Th 16 to Week 17 Th 23
TO-26-TIV-110SA1-2CB-01 | TIEVEBRACK 110SA1-2CB | bar: Week 16 Mo 13; Week 16 Th 16 to Week 17 Th 23
TO-26-CLE-T224-01 | CLONEE T224 | bar: Week 16 Mo 13; Week 16 Th 16 to Week 17 Mo 27
TO-26-KIN-T101-02 | KINNEGAD T101
TO-26-CBT-T2101-01 | CASTLEBAGOT T2101
TO-26-DDK-MLN-1-02 | DUNDALK MULLAGHARLIN
TO-26-GOR-T122-01 | GORMAN T122
TO-26-PRN-T4301-02 | PORTAN T4301 | bar: Week 16 Th 16 to Week 16 Sa 18
TO-26-PRN-WOO-1-02 | PORTAN WOODLAND | bar: Week 16 Th 16 to Week 16 Sa 18
TO-26-WOO-400K1-2-01 | WOODLAND 400K1-2 | bar: Week 16 Th 16 to Week 16 Sa 18
TO-26-LOU-AT3-01 | LOUTH AT3 | bar: Week 16 Th 16 to Week 17 Th 23
TO-26-PRN-T4301-03 | PORTAN T4301 | bar: Week 16 Th 16 to Week 17 Mo 27
TO-26-PRN-WOO-1-03 | PORTAN WOODLAND | bar: Week 16 Th 16 to Week 17 Mo 27
TO-26-SRA-110K1-2-01 | SRANANAGH 110K1-2 | bar: Week 16 Th 16 to Week 17 Mo 27
TO-26-220 kV A1 @ WOO-04 | WOODLAND 220 kV A1 | bar: Week 16 Th 16 to Week 17 Mo 27
TO-26-220 kV B1 @ WOO-04 | WOODLAND 220 kV B1 | bar: Week 16 Th 16 to Week 17 Mo 27
TO-26-400 kV A1 @ WOO-04 | WOODLAND 400 kV A1 | bar: Week 16 Th 16 to Week 17 Mo 27
TO-26-400 kV B1 @ WOO-04 | WOODLAND 400 kV B1 | bar: Week 16 Th 16 to Week 17 Mo 27
TO-26-WOO-T4201-02 | WOODLAND T4201 | bar: Week 16 Th 16 to Week 17 Mo 27
TO-26-ATY-T101-02 | ATHY T101 | bar: Week 16 Th 16 to Week 17 Fr 24
TO-26-DEN-DRY-1-03 | DEENES DRYBRIDGE | bar: Su 12 to Week 16 Mo 13
TO-26-KLS-110K1-2-01 | KELLIS 110K1-2 | bar: Su 12 to Week 16 Mo 13
TO-26-AA GIS-ENN-1-03 | ARDNACRUSHA GIS ENNIS | bar: Su 12 to Week 16 Mo 13; Week 16 Th 16 to Week 16 Fr 17
TO-26-KLN-KRA-1-06 | KILLONAN KNOCKRAHA | bar: Su 12 to Week 16 Mo 13; Week 16 Th 16 to Week 16 Fr 17
TO-26-KPG-KNR-1-110-01 | KILPADDOGE KNOCKANURE 110 | bar: Su 12 to Week 16 Mo 13; Week 16 Th 16 to Week 16 Fr 17
TO-26-220 kV A1 @ KRA-03 | KNOCKRAHA 220 kV A1 | bar: Su 12 to Week 16 Mo 13; Week 16 Th 16 to Week 16 Fr 17
TO-26-220 kV B1 @ KRA-03 | KNOCKRAHA 220 kV B1 | bar: Su 12 to Week 16 Mo 13; Week 16 Th 16 to Week 16 Fr 17
TO-26-KRA-220K1-06 | KNOCKRAHA 220K1 | bar: Su 12 to Week 16 Mo 13; Week 16 Th 16 to Week 16 Fr 17
TO-26-KRA-220SA1-2CB-06 | KNOCKRAHA 220SA1-2CB | bar: Su 12 to Week 16 Mo 13; Week 16 Th 16 to Week 16 Fr 17
TO-26-KRA-220SB1-2CB-06 | KNOCKRAHA 220SB1-2CB | bar: Su 12 to Week 16 Mo 13; Week 16 Th 16 to Week 16 Fr 17
TO-26-220 kV A2 @ LOU-06 | LOUTH 220 kV A2 | bar: Su 12 to Week 16 Mo 13; Week 16 Th 16 to Week 16 Fr 17
TO-26-220 kV B2 @ LOU-06 | LOUTH 220 kV B2 | bar: Su 12 to Week 16 Mo 13; Week 16 Th 16 to Week 16 Fr 17
TO-26-110 kV B2 @ RAF-02 | RAFFEEN 110 kV B2 | bar: Su 12 to Week 16 Mo 13; Week 16 Th 16 to Week 16 Fr 17
TO-26-RYB GIS-T108-01 | RYEBROOK GIS T108 | bar: Su 12 to Week 16 Mo 13; Week 16 Th 16 to Week 16 Fr 17
Outages commencing/returning in Week 17
OUTAGE ID | PLANT | Week 16 Mo 13: Week 16; Week 17 Mo 20: Week 17
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
TO-26-CBT-CLU-1-02 | CASTLEBAGOT CLUTTERLAND | bar: Week 17 Mo 20 to Week 17 Tu 21
TO-26-BVK-220SB1-2CB-03 | BALLYVOUSKILL 220SB1-2CB | bar: Week 17 Mo 20 to Week 17 Tu 21
TO-26-110 kV A2 @ LOU-09 | LOUTH 110 kV A2 | bar: Week 17 Mo 20 to Week 17 Tu 21
TO-26-110 kV B2 @ LOU-09 | LOUTH 110 kV B2 | bar: Week 17 Mo 20 to Week 17 Tu 21
TO-26-CDK-LWD-1-01 | CASTLEDOCKRELL LODGEWOOD | bar: Week 17 Mo 20 to Week 17 Tu 21; Week 17 Fr 24
TO-26-CDK-T121-02 | CASTLEDOCKRELL T121 | bar: Week 17 Mo 20 to Week 17 Tu 21; Week 17 Fr 24
TO-26-400 kV A2 @ DSN-01 | DUNSTOWN 400 kV A2 | bar: Week 17 Mo 20 to Week 17 Tu 21; Week 17 Fr 24
TO-26-110 kV A2 @ KLS-02 | KELLIS 110 kV A2 | bar: Week 17 Mo 20 to Week 17 Tu 21; Week 17 Fr 24
TO-26-110 kV B2 @ KLS-03 | KELLIS 110 kV B2 | bar: Week 17 Mo 20 to Week 17 Tu 21; Week 17 Fr 24
TO-26-KLS-110K1-2-02 | KELLIS 110K1-2 | bar: Week 17 Mo 20 to Week 17 Tu 21; Week 17 Fr 24
TO-26-LWD-110K1-2-01 | LODGEWOOD 110K1-2 | bar: Week 17 Mo 20 to Week 17 Tu 21; Week 17 Fr 24
Report covers outages commencing/returning/spanning the period: 13/04/2026 - 26/04/2026
Outages commencing/returning in Week 17
OUTAGE ID | PLANT | Week 16 Mo 13: Week 16; Week 17 Mo 20: Week 17
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
TO-26-LWD-T2102-01 | LODGEWOOD T2102 | bar: Week 17 Mo 20 to Week 17 Tu 21
TO-26-AD-RAF-1-03 | AGHADA RAFFEEN | bar: Week 17 Mo 20 to Week 17 Tu 21; Week 17 Sa 25 to Week 17 Mo 27
TO-26-AA GIS-T102-01 | ARDNACRUSHA GIS T102 | bar: Week 17 Mo 20 to Week 17 Tu 21; Week 17 Sa 25 to Week 17 Mo 27
TO-26-AA GIS-T103-02 | ARDNACRUSHA GIS T103 | bar: Week 17 Mo 20 to Week 17 Tu 21; Week 17 Sa 25 to Week 17 Mo 27
TO-26-DDK-LOU-1-01 | DUNDALK LOUTH | bar: Week 17 Mo 20 to Week 17 Tu 21; Week 17 Sa 25 to Week 17 Mo 27
TO-26-IA-T101-01 | INNISCARRA T101 | bar: Week 17 Mo 20 to Week 17 Tu 21; Week 17 Sa 25 to Week 17 Mo 27
TO-26-KRA-RAF-1-06 | KNOCKRAHA RAFFEEN | bar: Week 17 Mo 20 to Week 17 Tu 21; Week 17 Sa 25 to Week 17 Mo 27
TO-26-PRO-TB-1-03 | PROSPECT TARBERT | bar: Week 17 Mo 20 to Week 17 Tu 21; Week 17 Sa 25 to Week 17 Mo 27
TO-26-110 kV A2 @ RAF-01 | RAFFEEN 110 kV A2 | bar: Week 17 Mo 20 to Week 17 Tu 21; Week 17 Sa 25 to Week 17 Mo 27
TO-26-110 kV B2 @ RAF-01 | RAFFEEN 110 kV B2 | bar: Week 17 Mo 20 to Week 17 Tu 21; Week 17 Sa 25 to Week 17 Mo 27
TO-26-CBT-T2102-02 | CASTLEBAGOT T2102 | bar: Week 17 Tu 21
TO-26-KTL-CAP1-01 | KILTEEL CAP1 | bar: Week 17 Tu 21
TO-26-110 kV A1 @ CDU-02 | CORDUFF 110 kV A1 | bar: Week 17 Tu 21; Week 17 Sa 25 to Week 17 Mo 27
TO-26-110 kV B1 @ CDU-02 | CORDUFF 110 kV B1 | bar: Week 17 Tu 21; Week 17 Sa 25 to Week 17 Mo 27
TO-26-220 kV A1 @ CDU-05 | CORDUFF 220 kV A1 | bar: Week 17 Tu 21; Week 17 Sa 25 to Week 17 Mo 27
TO-26-220 kV B1 @ CDU-02 | CORDUFF 220 kV B1 | bar: Week 17 Tu 21; Week 17 Sa 25 to Week 17 Mo 27
TO-26-CDU-T2101-01 | CORDUFF T2101 | bar: Week 17 Tu 21; Week 17 Sa 25 to Week 17 Mo 27
TO-26-MTH-T141-01 | MEATH HILL T141 | bar: Su 12 to Week 17 Tu 21
TO-26-TTU-110K1-02 | TULLABEG 110K1
TO-26-AA GIS-110K3-02 | ARDNACRUSHA GIS 110K3
TO-26-220 kV A1 @ BVK-03 | BALLYVOUSKILL 220 kV A1
TO-26-220 kV A2 @ BVK-04 | BALLYVOUSKILL 220 kV A2
TO-26-BVK-220K1-03 | BALLYVOUSKILL 220K1
TO-26-BVK-220K2-05 | BALLYVOUSKILL 220K2
TO-26-BVK-220SA1-2CB-03 | BALLYVOUSKILL 220SA1-2CB
TO-26-220 kV B1 @ WOO-01 | WOODLAND 220 kV B1 | bar: Su 12 to Week 17 Tu 21
TO-26-PRN-T4301-05 | PORTAN T4301
TO-26-AA GIS-110SA1-2CB-01 | ARDNACRUSHA GIS 110SA1-2CB
TO-26-SHL-T2016-02 | SHELLYBANKS T2016 | bar: Week 17 Sa 25 to Week 17 Mo 27
TO-26-MID-110SA1-01 | MIDLETON 110SA1 | bar: Su 12 to Week 17 Tu 21
TO-26-MID-110SA2-01 | MIDLETON 110SA2 | bar: Su 12 to Week 17 Tu 21
TO-26-MID-T102-01 | MIDLETON T102 | bar: Su 12 to Week 17 Tu 21
TO-26-MID-WHI-1-01 | MIDLETON WHITEGATE | bar: Su 12 to Week 17 Tu 21
TO-26-ATY-110SA1-03 | ATHY 110SA1 | bar: Week 17 Sa 25 to Week 17 Mo 27
TO-26-ATY-110SA2-03 | ATHY 110SA2 | bar: Week 17 Sa 25 to Week 17 Mo 27
TO-26-ATY-CLW-1-05 | ATHY CARLOW | bar: Week 17 Sa 25 to Week 17 Mo 27
TO-26-ATY-T101-01 | ATHY T101 | bar: Week 17 Sa 25 to Week 17 Mo 27
TO-26-220 kV A2 @ FIN-07 | FINGLAS 220 kV A2 | bar: Su 12 to Week 17 Tu 21
TO-26-220 kV B2 @ FIN-05 | FINGLAS 220 kV B2 | bar: Su 12 to Week 17 Tu 21
TO-26-FIN-220K2-10 | FINGLAS 220K2 | bar: Su 12 to Week 17 Tu 21
TO-26-FIN-220SA1-2CB-13 | FINGLAS 220SA1-2CB | bar: Su 12 to Week 17 Tu 21
TO-26-FIN-220SB1-2CB-10 | FINGLAS 220SB1-2CB | bar: Su 12 to Week 17 Tu 21
TO-26-110 kV A3 @ FIN GIS-01 | FINGLAS GIS 110 kV A3 | bar: Su 12 to Week 17 Tu 21
TO-26-110 kV B3 @ FIN GIS-01 | FINGLAS GIS 110 kV B3 | bar: Su 12 to Week 17 Tu 21
TO-26-FIN GIS-110SA1-3CB-02 | FINGLAS GIS 110SA1-3CB | bar: Su 12 to Week 17 Tu 21
TO-26-FIN GIS-110SA3-5CB-03 | FINGLAS GIS 110SA3-5CB | bar: Su 12 to Week 17 Tu 21
TO-26-FIN GIS-110SB1-3CB-01 | FINGLAS GIS 110SB1-3CB | bar: Su 12 to Week 17 Tu 21
TO-26-FIN GIS-110SB3-5CB-03 | FINGLAS GIS 110SB3-5CB | bar: Su 12 to Week 17 Tu 21
TO-26-FIN GIS-T2106-01 | FINGLAS GIS T2106 | bar: Su 12 to Week 17 Tu 21
TO-26-220 kV A1 @ TB-01 | TARBERT 220 kV A1 | bar: Su 12 to Week 17 Tu 21
TO-26-220 kV B1 @ TB-01 | TARBERT 220 kV B1 | bar: Su 12 to Week 17 Tu 21
Outages spanning Weeks 16-17
OUTAGE ID | PLANT | Week 16 Mo 13: Week 16; Week 17 Mo 20: Week 17
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
TO-26-AD-LPT-1-01 | AGHADA LONG POINT
TO-26-BAN-RAF-1-02 | BANDON RAFFEEN
TO-26-CAH-DOO-1-01 | CAHIR DOON
TO-26-CBT-INC-2-05 | CASTLEBAGOT INCHICORE 2
Report covers outages commencing/returning/spanning the period: 13/04/2026 - 26/04/2026
Outages spanning Weeks 16-17 | PLANT | Week 16 Mo 13: Week 16; Week 17 Mo 20: Week 17
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
TO-26-CBR-SVC-01 | CASTLEBAR SVC
TO-26-CBR-SVC-02
TO-26-CHA-MAL-1-01 | CHARLEVILLE MALLOW
TO-26-CLA-MAC-1-02 | CLASHAVOON MACROOM 1
TO-26-CLE-WOO-1-02 | CLONEE WOODLAND
TO-26-DND-T121-01 | DARNDALE T121
TO-26-220 kV A2 @ FLA-02 | FLAGFORD 220 kV A2
TO-26-220 kV B2 @ FLA-02 | FLAGFORD 220 kV B2
TO-26-FLA-LOU-1-06 | FLAGFORD LOUTH
TO-26-FLA-TON-1-01 | FLAGFORD TONROE
TO-26-GAR-PLA-1-02 | GARBALLAGH PLATIN
TO-26-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-26-GI GIS-220SA1-2CB-02 | GREAT ISLAND GIS 220SA1-2CB
TO-26-GI-T141-01 | GREAT ISLAND T141
TO-26-220 kV A6 @ INC-03 | INCHICORE 220 kV A6
TO-26-220 kV B6 @ INC-03 | INCHICORE 220 kV B6
TO-26-INC-220K4-6-01 | INCHICORE 220K4-6
TO-26-INC-T2106-01 | INCHICORE T2106
TO-26-110 kV A2 @ KRA-01 | KNOCKRAHA 110 kV A2
TO-26-110 kV B2 @ KRA-01 | KNOCKRAHA 110 kV B2
TO-26-220 kV A4 @ KRA-01 | KNOCKRAHA 220 kV A4
TO-26-220 kV B4 @ KRA-01 | KNOCKRAHA 220 kV B4
TO-26-KRA-220K4-01 | KNOCKRAHA 220K4
TO-26-KRA-220SA2-4CB-03 | KNOCKRAHA 220SA2-4CB
TO-26-KRA-220SB2-4CB-03 | KNOCKRAHA 220SB2-4CB
TO-26-LET-SVC-02 | LETTERKENNY SVC
TO-26-LPT-T2002-01 | LONG POINT T2002
TO-26-220 kV A2 @ LOU-02 | LOUTH 220 kV A2
TO-26-220 kV B2 @ LOU-02 | LOUTH 220 kV B2
TO-26-MR-T107-01 | MARINA T107
TO-26-NAV-M/CAP1-01 | NAVAN M/CAP1
TO-26-NEW-PLS-1-01 | NEWBRIDGE PORTLAOISE
TO-26-220 kV A1/A2 @ PB-02 | POOLBEG 220 kV A1/A2
TO-26-PB-R2001-03 | POOLBEG R2001
TO-26-PB-R2001-02
TO-26-110 kV A1 @ PLS-06 | PORTLAOISE 110 kV A1
TO-26-SKL-M/CAP2-01 | SHANKILL M/CAP2
TO-26-SH-T2102-02 | SHANNONBRIDGE T2102
TO-26-TB-T2003-01 | TARBERT T2003
TO-26-TAW-T1/T2-01 | TAWNAGHMORE T1/T2
TO-26-TAW-T3-02 | TAWNAGHMORE T3
TO-26-TON-T142-01 | TONROE T142
TO-26-TRL-CAP2-01 | TRALEE CAP2