## Wks 18 - 19
Report covers outages commencing/returning/spanning the period: 27/04/2026 - 10/05/2026
Outages commencing/returning in Week 18
OUTAGE ID | PLANT |  | Week 18 | [6 empty] | Week 19
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
TO-26-110 kV A2 @ SH-01 | SHANNONBRIDGE 110 kV A2 | bar: Week 18 Mo 27 to Week 18 Tu 28
TO-26-110 kV B2 @ SH-01 | SHANNONBRIDGE 110 kV B2 | bar: Week 18 Mo 27 to Week 18 Tu 28
TO-26-SH-110K1-2-01 | SHANNONBRIDGE 110K1-2 | bar: Week 18 Mo 27 to Week 18 Tu 28
TO-26-KDN-T131-01 | KNOCKDRIN T131 | bar: Week 18 Mo 27 to Week 18 Th 30
TO-26-110 kV A2 @ DND-02 | DARNDALE 110 kV A2 | bar: Week 18 Mo 27 to Week 18 Fr 1
TO-26-110 kV B2 @ DND-02 | DARNDALE 110 kV B2 | bar: Week 18 Mo 27 to Week 18 Fr 1
TO-26-DND-110K2-04 | DARNDALE 110K2 | bar: Week 18 Mo 27 to Week 18 Fr 1
TO-26-DND-110SA1-2CB-08 | DARNDALE 110SA1-2CB | bar: Week 18 Mo 27 to Week 18 Fr 1
TO-26-DND-110SB1-2CB-07 | DARNDALE 110SB1-2CB | bar: Week 18 Mo 27 to Week 18 Fr 1
TO-26-DND-T122-01 | DARNDALE T122 | bar: Week 18 Mo 27 to Week 18 Fr 1
TO-26-WOH-T122-01 | WOODHOUSE T122 | bar: Week 18 Mo 27 to Week 18 Fr 1
TO-26-MP GIS-220K1-01 | MONEYPOINT GIS 220K1 | bar: Week 18 Mo 27 to Week 19 We 6
TO-26-MP GIS-220K2-01 | MONEYPOINT GIS 220K2 | bar: Week 18 Mo 27 to Week 19 We 6
TO-26-MP GIS-220SA1-2CB-01 | MONEYPOINT GIS 220SA1-2CB | bar: Week 18 Mo 27 to Week 19 We 6
TO-26-MP GIS-220SB1-2CB-01 | MONEYPOINT GIS 220SB1-2CB | bar: Week 18 Mo 27 to Week 19 We 6
TO-26-220 kV A1 @ WOO-03 | WOODLAND 220 kV A1 | bar: Week 18 Mo 27 to Week 19 Th 7
TO-26-220 kV B1 @ WOO-03 | WOODLAND 220 kV B1 | bar: Week 18 Mo 27 to Week 19 Th 7
TO-26-DER-TSB-1-04 | DERRYIRON THORNSBERRY
TO-26-DER-TSB-1-01
TO-26-GAR-PLA-1-02 | GARBALLAGH PLATIN | bar: Su 26 to Week 18 Mo 27
TO-26-220 kV B4 @ INC-01 | INCHICORE 220 kV B4 | bar: Su 26 to Week 18 Mo 27
TO-26-PRN-T4301-03 | PORTAN T4301 | bar: Su 26 to Week 18 Mo 27
TO-26-PRN-WOO-1-03 | PORTAN WOODLAND | bar: Su 26 to Week 18 Mo 27
TO-26-CDU-RYB GIS-1-02 | CORDUFF RYEBROOK GIS | bar: Week 18 Tu 28
TO-26-CRA-LWD-1-01 | CRANE LODGEWOOD | bar: Week 18 Tu 28 to Week 18 Th 30
TO-26-KLS-KKY-1-01 | KELLIS KILKENNY | bar: Week 18 Tu 28 to Week 18 Th 30
TO-26-KPG-220K4-01 | KILPADDOGE 220K4 | bar: Week 18 Tu 28 to Week 18 Th 30
TO-26-KPG-220SA2-4CB-01 | KILPADDOGE 220SA2-4CB | bar: Week 18 Tu 28 to Week 18 Th 30
TO-26-KPG-220SB2-4CB-01 | KILPADDOGE 220SB2-4CB | bar: Week 18 Tu 28 to Week 18 Th 30
TO-26-CBT-INC-2-05 | CASTLEBAGOT INCHICORE 2 | bar: Su 26 to Week 18 Tu 28
TO-26-CHA-MAL-1-01 | CHARLEVILLE MALLOW | bar: Su 26 to Week 18 Tu 28
TO-26-220 kV A6 @ INC-03 | INCHICORE 220 kV A6 | bar: Su 26 to Week 18 Tu 28
TO-26-220 kV B6 @ INC-03 | INCHICORE 220 kV B6 | bar: Su 26 to Week 18 Tu 28
TO-26-INC-220K4-6-01 | INCHICORE 220K4-6 | bar: Su 26 to Week 18 Tu 28
TO-26-INC-T2106-01 | INCHICORE T2106 | bar: Su 26 to Week 18 Tu 28
TO-26-220 kV A2 @ SH-01 | SHANNONBRIDGE 220 kV A2 | bar: Week 18 We 29
TO-26-220 kV B2 @ SH-01 | SHANNONBRIDGE 220 kV B2 | bar: Week 18 We 29
TO-26-SH-220K1-2-01 | SHANNONBRIDGE 220K1-2 | bar: Week 18 We 29
TO-26-CBT-INC-2-02 | CASTLEBAGOT INCHICORE 2 | bar: Week 18 We 29 to Week 19 Mo 11
TO-26-220 kV A4 @ INC-03 | INCHICORE 220 kV A4 | bar: Week 18 We 29 to Week 19 Mo 11
TO-26-220 kV A6 @ INC-04 | INCHICORE 220 kV A6 | bar: Week 18 We 29 to Week 19 Mo 11
TO-26-220 kV B4 @ INC-03 | INCHICORE 220 kV B4 | bar: Week 18 We 29 to Week 19 Mo 11
TO-26-220 kV B6 @ INC-04 | INCHICORE 220 kV B6 | bar: Week 18 We 29 to Week 19 Mo 11
TO-26-INC-220K4-6-03 | INCHICORE 220K4-6 | bar: Week 18 We 29 to Week 19 Mo 11
TO-26-INC-T2106-02 | INCHICORE T2106 | bar: Week 18 We 29 to Week 19 Mo 11
TO-26-SHL-T2016-02 | SHELLYBANKS T2016 | bar: Su 26 to Week 18 We 29
TO-26-SHL-D1/CB2-04 | SHELLYBANKS D1/CB2 | bar: Week 18 Th 30
TO-26-SHL-D1/CB3-02 | SHELLYBANKS D1/CB3 | bar: Week 18 Th 30
TO-26-SHL-D1/CB1-04 | SHELLYBANKS D1/CB1 | bar: Week 18 Th 30 to Week 19 Th 7
TO-26-SHL-D2/CB1-03 | SHELLYBANKS D2/CB1 | bar: Week 18 Th 30 to Week 19 Th 7
TO-26-SHL-T2016-01 | SHELLYBANKS T2016 | bar: Week 18 Th 30 to Week 19 Th 7
TO-26-SHL-T2014-03 | SHELLYBANKS T2014 | bar: Week 18 Th 30 to Week 19 Fr 8
TO-26-AA GIS-T102-01 | ARDNACRUSHA GIS T102 | bar: Su 26 to Week 18 Th 30
TO-26-CDU-GLN-1-01 | CORDUFF GALLANSTOWN | bar: Week 18 Fr 1 to Week 19 Tu 5
TO-26-MP GIS-T4002-02 | MONEYPOINT GIS T4002 | bar: Week 18 Fr 1 to Week 19 Mo 11
TO-26-400 kV A1 @ DSN-01 | DUNSTOWN 400 kV A1 | bar: Su 26 to Week 18 Fr 1
TO-26-400 kV A2 @ DSN-01 | DUNSTOWN 400 kV A2 | bar: Su 26 to Week 18 Fr 1
TO-26-IA-T101-01 | INNISCARRA T101 | bar: Su 26 to Week 18 Fr 1
TO-26-KRA-RAF-1-06 | KNOCKRAHA RAFFEEN | bar: Su 26 to Week 18 Fr 1
TO-26-MID-110SA1-01 | MIDLETON 110SA1 | bar: Su 26 to Week 18 Fr 1
Report covers outages commencing/returning/spanning the period: 27/04/2026 - 10/05/2026
Outages commencing/returning in Week 18
OUTAGE ID | PLANT | Week 18 Mo 27: Week 18; Week 19 Mo 4: Week 19
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
TO-26-MID-110SA2-01 | MIDLETON 110SA2 | bar: Su 26 to Week 18 Fr 1
TO-26-MID-T102-01 | MIDLETON T102 | bar: Su 26 to Week 18 Fr 1
TO-26-MID-WHI-1-01 | MIDLETON WHITEGATE | bar: Su 26 to Week 18 Fr 1
TO-26-PRO-TB-1-03 | PROSPECT TARBERT | bar: Su 26 to Week 18 Fr 1
TO-26-SH-T2102-02 | SHANNONBRIDGE T2102 | bar: Su 26 to Week 18 Fr 1
TO-26-220 kV A1 @ WOO-04 | WOODLAND 220 kV A1 | bar: Su 26 to Week 18 Fr 1
TO-26-220 kV B1 @ WOO-04 | WOODLAND 220 kV B1 | bar: Su 26 to Week 18 Fr 1
TO-26-400 kV A1 @ WOO-04 | WOODLAND 400 kV A1 | bar: Su 26 to Week 18 Fr 1
TO-26-400 kV B1 @ WOO-04 | WOODLAND 400 kV B1 | bar: Su 26 to Week 18 Fr 1
TO-26-WOO-T4201-02 | WOODLAND T4201 | bar: Su 26 to Week 18 Fr 1
Outages commencing/returning in Week 19
OUTAGE ID | PLANT | Week 18 Mo 27: Week 18; Week 19 Mo 4: Week 19
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
TO-26-KLS-220K1-2-02 | KELLIS 220K1-2
TO-26-CLW-KLS-2-04 | CARLOW KELLIS 2 | bar: Week 19 Th 7
TO-26-CLH-T122-01 | CLAHANE T122 | bar: Week 19 Th 7
TO-26-KLS-110K1-2-03 | KELLIS 110K1-2 | bar: Week 19 Th 7
TO-26-KLS-KKY-1-02 | KELLIS KILKENNY | bar: Week 19 Th 7
TO-26-KLS-T2102-06 | KELLIS T2102 | bar: Week 19 Th 7
TO-26-THU-STATCOM-02 | THURLES STATCOM | bar: Week 19 Th 7
TO-26-DRM-LET-1-01 | DRUMKEEN LETTERKENNY | bar: Week 19 Th 7; Week 19 Sa 9 to Week 19 Mo 11
TO-26-400 kV B2 @ DSN-02 | DUNSTOWN 400 kV B2 | bar: Week 19 Th 7; Week 19 Sa 9 to Week 19 Mo 11
TO-26-220 kV A1 @ MP GIS-01 | MONEYPOINT GIS 220 kV A1 | bar: Week 19 Th 7; Week 19 Sa 9 to Week 19 Mo 11
TO-26-220 kV B1 @ MP GIS-01 | MONEYPOINT GIS 220 kV B1 | bar: Week 19 Th 7; Week 19 Sa 9 to Week 19 Mo 11
TO-26-MP GIS-220K1-05 | MONEYPOINT GIS 220K1 | bar: Week 19 Th 7; Week 19 Sa 9 to Week 19 Mo 11
TO-26-MP GIS-220SA1-2CB-03 | MONEYPOINT GIS 220SA1-2CB | bar: Week 19 Th 7; Week 19 Sa 9 to Week 19 Mo 11
TO-26-MP GIS-220SB1-2CB-02 | MONEYPOINT GIS 220SB1-2CB | bar: Week 19 Th 7; Week 19 Sa 9 to Week 19 Mo 11
TO-26-400 kV A1 @ MP GIS-02 | MONEYPOINT GIS 400 kV A1 | bar: Week 19 Th 7; Week 19 Sa 9 to Week 19 Mo 11
TO-26-400 kV B1 @ MP GIS-02 | MONEYPOINT GIS 400 kV B1 | bar: Week 19 Th 7; Week 19 Sa 9 to Week 19 Mo 11
TO-26-MP GIS-400SA1-2CB-03 | MONEYPOINT GIS 400SA1-2CB | bar: Week 19 Th 7; Week 19 Sa 9 to Week 19 Mo 11
TO-26-MP GIS-400SA1-3CB-06 | MONEYPOINT GIS 400SA1-3CB | bar: Week 19 Th 7; Week 19 Sa 9 to Week 19 Mo 11
TO-26-MP GIS-400SB1-2CB-03 | MONEYPOINT GIS 400SB1-2CB | bar: Week 19 Th 7; Week 19 Sa 9 to Week 19 Mo 11
TO-26-MP GIS-400SB1-3CB-06 | MONEYPOINT GIS 400SB1-3CB | bar: Week 19 Th 7; Week 19 Sa 9 to Week 19 Mo 11
TO-26-MP GIS-T4201-01 | MONEYPOINT GIS T4201 | bar: Week 19 Th 7; Week 19 Sa 9 to Week 19 Mo 11
TO-26-RAF-TBG-2-03 | RAFFEEN TRABEG 2 | bar: Week 19 Th 7; Week 19 Sa 9 to Week 19 Mo 11
TO-26-RYB GIS-T109-01 | RYEBROOK GIS T109 | bar: Week 19 Th 7; Week 19 Sa 9 to Week 19 Mo 11
TO-26-110 kV A1 @ SNU-01 | SNUGBOROUGH 110 kV A1 | bar: Week 19 Th 7; Week 19 Sa 9 to Week 19 Mo 11
TO-26-110 kV A2 @ SNU-01 | SNUGBOROUGH 110 kV A2 | bar: Week 19 Th 7; Week 19 Sa 9 to Week 19 Mo 11
TO-26-110 kV B1 @ SNU-01 | SNUGBOROUGH 110 kV B1 | bar: Week 19 Th 7; Week 19 Sa 9 to Week 19 Mo 11
TO-26-110 kV B2 @ SNU-01 | SNUGBOROUGH 110 kV B2 | bar: Week 19 Th 7; Week 19 Sa 9 to Week 19 Mo 11
TO-26-SNU-110K1-01 | SNUGBOROUGH 110K1 | bar: Week 19 Th 7; Week 19 Sa 9 to Week 19 Mo 11
TO-26-SNU-110K2-01 | SNUGBOROUGH 110K2 | bar: Week 19 Th 7; Week 19 Sa 9 to Week 19 Mo 11
TO-26-SNU-110SA1-2CB-01 | SNUGBOROUGH 110SA1-2CB | bar: Week 19 Th 7; Week 19 Sa 9 to Week 19 Mo 11
TO-26-SNU-110SB1-2CB-01 | SNUGBOROUGH 110SB1-2CB | bar: Week 19 Th 7; Week 19 Sa 9 to Week 19 Mo 11
TO-26-110 kV A1 @ TBG-01 | TRABEG 110 kV A1 | bar: Week 19 Th 7; Week 19 Sa 9 to Week 19 Mo 11
TO-26-110 kV B1 @ TBG-01 | TRABEG 110 kV B1 | bar: Week 19 Th 7; Week 19 Sa 9 to Week 19 Mo 11
TO-26-BEG-T101-01 | BALLYBEG T101 | bar: Week 19 Th 7
TO-26-DND-T125-01 | DARNDALE T125 | bar: Week 19 Th 7
TO-26-AUG-MTN-1-01 | AUGHINISH MONETEEN | bar: Week 19 Th 7
TO-26-AD-LPT-1-01 | AGHADA LONG POINT | bar: Su 26 to Week 19 Mo 4
TO-26-CLA-MAC-1-02 | CLASHAVOON MACROOM 1 | bar: Su 26 to Week 19 Mo 4
TO-26-GOR-MTH-1-03 | GORMAN MEATH HILL | bar: Su 26 to Week 19 Mo 4
TO-26-LPT-T2002-01 | LONG POINT T2002 | bar: Su 26 to Week 19 Mo 4
TO-26-NEW-PLS-1-01 | NEWBRIDGE PORTLAOISE | bar: Su 26 to Week 19 Mo 4
TO-26-110 kV A1 @ PLS-06 | PORTLAOISE 110 kV A1 | bar: Su 26 to Week 19 Mo 4
TO-26-KHL-T131-01 | KILL HILL T131 | bar: Week 19 Th 7
TO-26-LOU-MTH-1-01 | LOUTH MEATH HILL | bar: Week 19 Th 7; Week 19 Sa 9 to Week 19 Mo 11
TO-26-PHT-131-01 | PHILIPSTOWN T131
TO-26-SHL-D1/CB2-05 | SHELLYBANKS D1/CB2
Report covers outages commencing/returning/spanning the period: 27/04/2026 - 10/05/2026
Outages commencing/returning in Week 19
OUTAGE ID | PLANT | Week 18 Mo 27: Week 18; Week 19 Mo 4: Week 19
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
TO-26-SHL-D1/CB3-03 | SHELLYBANKS D1/CB3
TO-26-GI GIS-T2004-03 | GREAT ISLAND GIS T2004
TO-26-AD-RAF-1-03 | AGHADA RAFFEEN
TO-26-ATY-110SA1-03 | ATHY 110SA1
TO-26-ATY-110SA2-03 | ATHY 110SA2
TO-26-ATY-CLW-1-05 | ATHY CARLOW
TO-26-ATY-T101-01 | ATHY T101
TO-26-110 kV A1 @ CUL-03 | CULLENAGH 110 kV A1
TO-26-CUL-WAT-1-01 | CULLENAGH WATERFORD
Outages spanning Weeks 18-19
OUTAGE ID | PLANT | Week 18 Mo 27: Week 18; Week 19 Mo 4: Week 19
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
TO-26-AA GIS-T103-02 | ARDNACRUSHA GIS T103
TO-26-BAN-RAF-1-02 | BANDON RAFFEEN
TO-26-CAH-DOO-1-01 | CAHIR DOON
TO-26-CBR-SVC-01 | CASTLEBAR SVC
TO-26-CBR-SVC-02
TO-26-CLE-T224-01 | CLONEE T224
TO-26-CLE-WOO-1-02 | CLONEE WOODLAND
TO-26-110 kV A1 @ CDU-02 | CORDUFF 110 kV A1
TO-26-110 kV B1 @ CDU-02 | CORDUFF 110 kV B1
TO-26-220 kV A1 @ CDU-05 | CORDUFF 220 kV A1
TO-26-220 kV B1 @ CDU-02 | CORDUFF 220 kV B1
TO-26-CDU-T2101-01 | CORDUFF T2101
TO-26-DND-T121-01 | DARNDALE T121
TO-26-DDK-LOU-1-01 | DUNDALK LOUTH
TO-26-110 kV A1 @ FLA-01 | FLAGFORD 110 kV A1
TO-26-110 kV B1 @ FLA-01 | FLAGFORD 110 kV B1
TO-26-220 kV A2 @ FLA-02 | FLAGFORD 220 kV A2
TO-26-220 kV B2 @ FLA-02 | FLAGFORD 220 kV B2
TO-26-FLA-LOU-1-06 | FLAGFORD LOUTH
TO-26-FLA-TON-1-01 | FLAGFORD TONROE
TO-26-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-26-GI GIS-220SA1-2CB-02 | GREAT ISLAND GIS 220SA1-2CB
TO-26-GI-T141-01 | GREAT ISLAND T141
TO-26-110 kV A2 @ KRA-01 | KNOCKRAHA 110 kV A2
TO-26-110 kV B2 @ KRA-01 | KNOCKRAHA 110 kV B2
TO-26-220 kV A4 @ KRA-01 | KNOCKRAHA 220 kV A4
TO-26-220 kV B4 @ KRA-01 | KNOCKRAHA 220 kV B4
TO-26-KRA-220K4-01 | KNOCKRAHA 220K4
TO-26-KRA-220SA2-4CB-03 | KNOCKRAHA 220SA2-4CB
TO-26-KRA-220SB2-4CB-03 | KNOCKRAHA 220SB2-4CB
TO-26-LET-SVC-02 | LETTERKENNY SVC
TO-26-220 kV A2 @ LOU-02 | LOUTH 220 kV A2
TO-26-220 kV B2 @ LOU-02 | LOUTH 220 kV B2
TO-26-MR-T107-01 | MARINA T107
TO-26-NAV-M/CAP1-01 | NAVAN M/CAP1
TO-26-220 kV A1/A2 @ PB-02 | POOLBEG 220 kV A1/A2
TO-26-PB-R2001-02 | POOLBEG R2001
TO-26-PB-R2001-03
TO-26-110 kV A2 @ RAF-01 | RAFFEEN 110 kV A2
TO-26-110 kV B2 @ RAF-01 | RAFFEEN 110 kV B2
TO-26-SKL-M/CAP2-01 | SHANKILL M/CAP2
TO-26-SRA-110K1-2-01 | SRANANAGH 110K1-2
TO-26-TB-T2003-01 | TARBERT T2003
TO-26-TAW-T1/T2-01 | TAWNAGHMORE T1/T2
TO-26-TAW-T3-02 | TAWNAGHMORE T3
TO-26-TON-T142-01 | TONROE T142
TO-26-TRL-CAP2-01 | TRALEE CAP2