## Wks 22 - 23
Report covers outages commencing/returning/spanning the period: 25/05/2026 - 07/06/2026
Outages commencing/returning in Week 22
OUTAGE ID | PLANT |  | Week 22 | [6 empty] | Week 23
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
TO-26-KRA-T2101-01 | KNOCKRAHA T2101
TO-26-BYH-STATCOM-04 | BALLYNAHULLA STATCOM
TO-26-BOG-110SA1-02 | BANOGE 110SA1
TO-26-BOG-110SA2-01 | BANOGE 110SA2
TO-26-BOG-T122-01 | BANOGE T122
TO-26-220 kV A2 @ KPG-01 | KILPADDOGE 220 kV A2
TO-26-220 kV B2 @ KPG-02 | KILPADDOGE 220 kV B2
TO-26-KPG-220SA1-2CB-01 | KILPADDOGE 220SA1-2CB
TO-26-KPG-220SA2-4CB-04 | KILPADDOGE 220SA2-4CB
TO-26-KPG-220SB1-2CB-01 | KILPADDOGE 220SB1-2CB
TO-26-KPG-220SB2-4CB-04 | KILPADDOGE 220SB2-4CB
TO-26-KPG-TB-2-01 | KILPADDOGE TARBERT 2
TO-26-220 kV A2 @ TB-02 | TARBERT 220 kV A2
TO-26-220 kV B2 @ TB-02 | TARBERT 220 kV B2
TO-26-ARK-BOG-1-04 | ARKLOW BANOGE | bar: Week 22 Sa 30 to Week 23 Tu 2
TO-26-220 kV A1 @ CSH-01 | CASHLA 220 kV A1 | bar: Week 22 Sa 30 to Week 23 Mo 8
TO-26-220 kV A2 @ CSH-02 | CASHLA 220 kV A2 | bar: Week 22 Sa 30 to Week 23 Mo 8
TO-26-220 kV B1 @ CSH-01 | CASHLA 220 kV B1 | bar: Week 22 Sa 30 to Week 23 Mo 8
TO-26-220 kV B2 @ CSH-03 | CASHLA 220 kV B2 | bar: Week 22 Sa 30 to Week 23 Mo 8
TO-26-CSH-220K1-2-01 | CASHLA 220K1-2 | bar: Week 22 Sa 30 to Week 23 Mo 8
TO-26-DER-TEN-1-01 | DERRYIRON TIMAHOE | bar: Week 22 Sa 30 to Week 23 Mo 8
TO-26-MP GIS-T4001-05 | MONEYPOINT GIS T4001 | bar: Week 22 Sa 30 to Week 23 Mo 8
TO-26-TRL-CAP2-03 | TRALEE CAP2 | bar: Week 22 Sa 30 to Week 23 Mo 8
TO-26-CBT-CKG-2-03 | CASTLEBAGOT CORKAGH 2
TO-26-DOO-T141-01 | DOON T141 | bar: Week 22 Sa 30 to Week 23 Mo 8
TO-26-SRA-110K1-2-01 | SRANANAGH 110K1-2 | bar: Su 24
TO-26-LOU-MTH-1-03 | LOUTH MEATH HILL | bar: Su 24
TO-26-MTH-110SA1-01 | MEATH HILL 110SA1 | bar: Su 24
TO-26-MTH-110SA2-01 | MEATH HILL 110SA2 | bar: Su 24
TO-26-MTH-T141-02 | MEATH HILL T141 | bar: Su 24
TO-26-NEW-PLS-1-01 | NEWBRIDGE PORTLAOISE | bar: Su 24
TO-26-110 kV A1 @ PLS-06 | PORTLAOISE 110 kV A1 | bar: Su 24
TO-26-GOR-MTH-1-04 | GORMAN MEATH HILL | bar: Week 22 Sa 30 to Week 23 Th 4
TO-26-MTH-110SA1-03 | MEATH HILL 110SA1 | bar: Week 22 Sa 30 to Week 23 Th 4
TO-26-MTH-110SA2-02 | MEATH HILL 110SA2 | bar: Week 22 Sa 30 to Week 23 Th 4
TO-26-MTH-T142-03 | MEATH HILL T142 | bar: Week 22 Sa 30 to Week 23 Th 4
TO-26-MTH-T142-01 | bar: Week 22 Sa 30 to Week 23 Mo 8
TO-26-CLE-WOO-1-02 | CLONEE WOODLAND | bar: Su 24
TO-26-220 kV A1 @ WOO-01 | WOODLAND 220 kV A1 | bar: Su 24
TO-26-220 kV B1 @ WOO-02 | WOODLAND 220 kV B1 | bar: Su 24
TO-26-SHL-D2/CB2-03 | SHELLYBANKS D2/CB2
TO-26-SHL-D2/CB3-03 | SHELLYBANKS D2/CB3
TO-26-110 kV A1 @ BLC-03 | BELCAMP 110 kV A1 | bar: Su 24
TO-26-110 kV A3 @ BLC-03 | BELCAMP 110 kV A3 | bar: Su 24
TO-26-110 kV B1 @ BLC-03 | BELCAMP 110 kV B1 | bar: Su 24
TO-26-110 kV B3 @ BLC-03 | BELCAMP 110 kV B3 | bar: Su 24
TO-26-BLC-110K1-03 | BELCAMP 110K1 | bar: Su 24
TO-26-BLC-110K3-03 | BELCAMP 110K3 | bar: Su 24
TO-26-BLC-110SA1-3CB-06 | BELCAMP 110SA1-3CB | bar: Su 24
TO-26-BLC-110SB1-3CB-04 | BELCAMP 110SB1-3CB | bar: Su 24
TO-26-CLE-T224-01 | CLONEE T224 | bar: Su 24
TO-26-220 kV A1 @ CUL-02 | CULLENAGH 220 kV A1 | bar: Su 24
TO-26-220 kV B1 @ CUL-02 | CULLENAGH 220 kV B1 | bar: Su 24
TO-26-CUL-GI GIS-1-01 | CULLENAGH GREAT ISLAND GIS | bar: Su 24
TO-26-DER-T1/T2-02 | DERRYIRON RHODE T1/T2 | bar: Su 24
TO-26-RAF-TBG-2-03 | RAFFEEN TRABEG 2 | bar: Su 24
TO-26-SHL-T2015-02 | SHELLYBANKS T2015 | bar: Su 24
TO-26-GI-WAT-1-05 | GREAT ISLAND WATERFORD 1 | bar: Week 22 Sa 30
TO-26-GI-WAT-2-03 | GREAT ISLAND WATERFORD 2 | bar: Week 22 Sa 30
Report covers outages commencing/returning/spanning the period: 25/05/2026 - 07/06/2026
Outages commencing/returning in Week 23
OUTAGE ID | PLANT | Week 22 Mo 25: Week 22; Week 23 Mo 1: Week 23
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
TO-26-CUS-KIR-1-01 | CUSHALING KILCUMBER
TO-26-KIR-T131-01 | KILCUMBER T131
TO-26-LLA-T133-01 | LENALEA T133
TO-26-CBT-CKG-1-03 | CASTLEBAGOT CORKAGH 1 | bar: Week 23 Fr 5
TO-26-110 kV A3 @ CKG-02 | CORKAGH 110 kV A3 | bar: Week 23 Fr 5
TO-26-110 kV B3 @ CKG-03 | CORKAGH 110 kV B3 | bar: Week 23 Fr 5
TO-26-CKG-110K3-02 | CORKAGH 110K3 | bar: Week 23 Fr 5
TO-26-CKG-110SA1-3CB-04 | CORKAGH 110SA1-3CB | bar: Week 23 Fr 5
TO-26-CKG-110SB1-3CB-04 | CORKAGH 110SB1-3CB | bar: Week 23 Fr 5
TO-26-KLN-T2101-03 | KILLONAN T2101 | bar: Week 23 Fr 5
TO-26-SHL-D1/CB1-02 | SHELLYBANKS D1/CB1 | bar: Week 23 Fr 5
TO-26-SHL-D1/CB2-03 | SHELLYBANKS D1/CB2 | bar: Week 23 Fr 5
TO-26-BYH-CDL-1-01 | BALLYNAHULLA CORDAL | bar: Week 23 Fr 5 to Week 23 Mo 8
TO-26-CDL-110SA1-01 | CORDAL 110SA1 | bar: Week 23 Fr 5 to Week 23 Mo 8
TO-26-CDL-110SA2-01 | CORDAL 110SA2 | bar: Week 23 Fr 5 to Week 23 Mo 8
TO-26-CDL-T132-02 | CORDAL T132 | bar: Week 23 Fr 5 to Week 23 Mo 8
TO-26-CDL-T141-01 | CORDAL T141 | bar: Week 23 Fr 5 to Week 23 Mo 8
TO-26-FIN-HN-1-01 | FINGLAS HUNTSTOWN | bar: Week 23 Fr 5 to Week 23 Mo 8
TO-26-FIN-SHL-1-02 | FINGLAS SHELLYBANKS | bar: Week 23 Fr 5 to Week 23 Mo 8
TO-26-HN-T2010/11-01 | HUNTSTOWN T2010/11 | bar: Week 23 Fr 5 to Week 23 Mo 8
TO-26-KLN-KPG-1-02 | KILLONAN KILPADDOGE | bar: Week 23 Fr 5 to Week 23 Mo 8
TO-26-MP GIS-T4202-01 | MONEYPOINT GIS T4202 | bar: Week 23 Fr 5 to Week 23 Mo 8
TO-26-110 kV A1 @ PLS-07 | PORTLAOISE 110 kV A1 | bar: Week 23 Fr 5 to Week 23 Mo 8
TO-26-110 kV A2 @ PLS-01 | PORTLAOISE 110 kV A2 | bar: Week 23 Fr 5 to Week 23 Mo 8
TO-26-110 kV B1 @ PLS-06 | PORTLAOISE 110 kV B1 | bar: Week 23 Fr 5 to Week 23 Mo 8
TO-26-110 kV B2 @ PLS-01 | PORTLAOISE 110 kV B2 | bar: Week 23 Fr 5 to Week 23 Mo 8
TO-26-PLS-110K1-2-03 | PORTLAOISE 110K1-2 | bar: Week 23 Fr 5 to Week 23 Mo 8
TO-26-110 kV A2 @ CDU-03 | CORDUFF 110 kV A2 | bar: Su 24 to Week 23 Mo 1
TO-26-110 kV A4 @ CDU-04 | CORDUFF 110 kV A4 | bar: Su 24 to Week 23 Mo 1
TO-26-110 kV B2 @ CDU-03 | CORDUFF 110 kV B2 | bar: Su 24 to Week 23 Mo 1
TO-26-110 kV B4 @ CDU-03 | CORDUFF 110 kV B4 | bar: Su 24 to Week 23 Mo 1
TO-26-CDU-110SA2-4CB-03 | CORDUFF 110SA2-4CB | bar: Su 24 to Week 23 Mo 1
TO-26-CDU-110SB2-4CB-03 | CORDUFF 110SB2-4CB | bar: Su 24 to Week 23 Mo 1
TO-26-220 kV A2 @ CDU-03 | CORDUFF 220 kV A2 | bar: Su 24 to Week 23 Mo 1
TO-26-220 kV A4 @ CDU-02 | CORDUFF 220 kV A4 | bar: Su 24 to Week 23 Mo 1
TO-26-220 kV B2 @ CDU-03 | CORDUFF 220 kV B2 | bar: Su 24 to Week 23 Mo 1
TO-26-220 kV B4 @ CDU-03 | CORDUFF 220 kV B4 | bar: Su 24 to Week 23 Mo 1
TO-26-CDU-220SA2-4CB-03 | CORDUFF 220SA2-4CB | bar: Su 24 to Week 23 Mo 1
TO-26-CDU-220SB2-4CB-03 | CORDUFF 220SB2-4CB | bar: Su 24 to Week 23 Mo 1
TO-26-COR-PST-03 | CORRACLASSY ENNISKILLEN PST | bar: Su 24 to Week 23 Mo 1
TO-26-CKM GIS-220K4-01 | CARRICKMINES GIS 220K4
TO-26-MR-T106-01 | MARINA T106
TO-26-110 kV A1 @ ARK-01 | ARKLOW 110 kV A1 | bar: Week 23 Fr 5 to Week 23 Mo 8
TO-26-110 kV B1 @ ARK-01 | ARKLOW 110 kV B1 | bar: Week 23 Fr 5 to Week 23 Mo 8
TO-26-220 kV A1 @ ARK-01 | ARKLOW 220 kV A1 | bar: Week 23 Fr 5 to Week 23 Mo 8
TO-26-220 kV B1 @ ARK-01 | ARKLOW 220 kV B1 | bar: Week 23 Fr 5 to Week 23 Mo 8
TO-26-ARK-T2101-03 | ARKLOW T2101 | bar: Week 23 Fr 5 to Week 23 Mo 8
TO-26-CF-110K1-2-01 | CATHALEENS FALL 110K1-2 | bar: Week 23 Fr 5 to Week 23 Mo 8
TO-26-CAH-DOO-1-01 | CAHIR DOON | bar: Su 24 to Week 23 Mo 1
TO-26-DSN-T4202-01 | DUNSTOWN T4202 | bar: Week 23 Fr 5 to Week 23 Mo 8
TO-26-GLE-KCR-1-01 | GLENLARA KNOCKACUMMER | bar: Su 24 to Week 23 Mo 1; Week 23 Fr 5
TO-26-KCR-T121-01 | KNOCKACUMMER T121 | bar: Su 24 to Week 23 Mo 1; Week 23 Fr 5
TO-26-LLA-LET-1-01 | LENALEA LETTERKENNY | bar: Su 24 to Week 23 Mo 1; Week 23 Fr 5
TO-26-LET-110SA1-3CB-02 | LETTERKENNY 110SA1-3CB | bar: Su 24 to Week 23 Mo 1; Week 23 Fr 5
TO-26-LET-TLK-1-01 | LETTERKENNY TRILLICK | bar: Su 24 to Week 23 Mo 1; Week 23 Fr 5
TO-26-SOR-T122-01 | SORNE HILL T122 | bar: Su 24 to Week 23 Mo 1; Week 23 Fr 5
TO-26-SOR-T124-01 | SORNE HILL T124 | bar: Su 24 to Week 23 Mo 1; Week 23 Fr 5
TO-26-SOR-TLK-1-01 | SORNE HILL TRILLICK | bar: Su 24 to Week 23 Mo 1; Week 23 Fr 5
TO-26-TLK-T141-01 | TRILLICK T141 | bar: Su 24 to Week 23 Mo 1; Week 23 Fr 5
TO-26-TLK-T142-01 | TRILLICK T142 | bar: Su 24 to Week 23 Mo 1; Week 23 Fr 5
Report covers outages commencing/returning/spanning the period: 25/05/2026 - 07/06/2026
Outages spanning Weeks 22-23
OUTAGE ID | PLANT | Week 22 Mo 25: Week 22; Week 23 Mo 1: Week 23
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
TO-26-AA GIS-T103-02 | ARDNACRUSHA GIS T103
TO-26-ATY-PLS-1-01 | ATHY PORTLAOISE
TO-26-BAN-RAF-1-02 | BANDON RAFFEEN
TO-26-CLW-KLS-1-03 | CARLOW KELLIS 1
TO-26-110 kV B1/B2 @ CSH-01 | CASHLA 110 kV B1/B2
TO-26-CSH-110K1-2-01 | CASHLA 110K1-2
TO-26-CBT-INC-2-02 | CASTLEBAGOT INCHICORE 2
TO-26-CBR-SVC-01 | CASTLEBAR SVC
TO-26-CBR-SVC-02
TO-26-CDU-T2102-02 | CORDUFF T2102
TO-26-DND-T121-01 | DARNDALE T121
TO-26-DER-TSB-1-01 | DERRYIRON THORNSBERRY
TO-26-DER-TSB-1-04
TO-26-DDK-LOU-1-01 | DUNDALK LOUTH
TO-26-110 kV A1 @ FLA-01 | FLAGFORD 110 kV A1
TO-26-110 kV B1 @ FLA-01 | FLAGFORD 110 kV B1
TO-26-220 kV A2 @ FLA-02 | FLAGFORD 220 kV A2
TO-26-220 kV B2 @ FLA-02 | FLAGFORD 220 kV B2
TO-26-FLA-LOU-1-06 | FLAGFORD LOUTH
TO-26-FLA-TON-1-01 | FLAGFORD TONROE
TO-26-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-26-GI GIS-220SA1-2CB-02 | GREAT ISLAND GIS 220SA1-2CB
TO-26-GI-T141-01 | GREAT ISLAND T141
TO-26-220 kV A4 @ INC-03 | INCHICORE 220 kV A4
TO-26-220 kV B4 @ INC-03 | INCHICORE 220 kV B4
TO-26-INC-220K4-6-03 | INCHICORE 220K4-6
TO-26-INC-T2106-02 | INCHICORE T2106
TO-26-110 kV A2 @ KRA-01 | KNOCKRAHA 110 kV A2
TO-26-110 kV B2 @ KRA-01 | KNOCKRAHA 110 kV B2
TO-26-220 kV A4 @ KRA-01 | KNOCKRAHA 220 kV A4
TO-26-220 kV B4 @ KRA-01 | KNOCKRAHA 220 kV B4
TO-26-KRA-220K4-01 | KNOCKRAHA 220K4
TO-26-KRA-220SA2-4CB-03 | KNOCKRAHA 220SA2-4CB
TO-26-KRA-220SB2-4CB-03 | KNOCKRAHA 220SB2-4CB
TO-26-LET-SVC-02 | LETTERKENNY SVC
TO-26-220 kV A2 @ LOU-02 | LOUTH 220 kV A2
TO-26-220 kV B2 @ LOU-02 | LOUTH 220 kV B2
TO-26-MR-T107-01 | MARINA T107
TO-26-MP GIS-T4002-02 | MONEYPOINT GIS T4002
TO-26-NAV-M/CAP1-01 | NAVAN M/CAP1
TO-26-220 kV A1/A2 @ PB-02 | POOLBEG 220 kV A1/A2
TO-26-PB-R2001-03 | POOLBEG R2001
TO-26-PB-R2001-02
TO-26-110 kV A2 @ RAF-01 | RAFFEEN 110 kV A2
TO-26-110 kV B2 @ RAF-01 | RAFFEEN 110 kV B2
TO-26-SKL-M/CAP2-01 | SHANKILL M/CAP2
TO-26-TB-T2003-01 | TARBERT T2003
TO-26-TAW-T1/T2-01 | TAWNAGHMORE T1/T2
TO-26-TAW-T3-02 | TAWNAGHMORE T3
TO-26-TON-T142-01 | TONROE T142
TO-26-TRL-CAP2-01 | TRALEE CAP2