## Wks 26 - 27
Report covers outages commencing/returning/spanning the period: 22/06/2026 - 05/07/2026
Outages commencing/returning in Week 26
OUTAGE ID | PLANT |  | Week 26 | [6 empty] | Week 27
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6
TO-26-CDU-CRU-2-02 | CORDUFF CRUISERATH 2 | bar: Week 26 Th 25 to Week 26 Fr 26
TO-26-DRY-LOU-1-04 | DRYBRIDGE LOUTH | bar: Week 26 Th 25 to Week 26 Fr 26
TO-26-KPG-T122-01 | KILPADDOGE T122 | bar: Week 26 Th 25 to Week 26 Fr 26
TO-26-LOU-RRU-1-02 | LOUTH RATRUSSAN | bar: Week 26 Th 25 to Week 26 Fr 26
TO-26-220 kV A2 @ AD-02 | AGHADA 220 kV A2 | bar: Week 26 Th 25 to Week 27 Fr 3
TO-26-220 kV B2 @ AD-01 | AGHADA 220 kV B2 | bar: Week 26 Th 25 to Week 27 Fr 3
TO-26-AD-GGO-1-01 | AGHADA GLANAGOW | bar: Week 26 Th 25 to Week 27 Fr 3
TO-26-110 kV A1 @ FIN GIS-01 | FINGLAS GIS 110 kV A1 | bar: Week 26 Th 25 to Week 27 Fr 3
TO-26-110 kV A2 @ FIN GIS-02 | FINGLAS GIS 110 kV A2 | bar: Week 26 Th 25 to Week 27 Fr 3
TO-26-FIN GIS-110K1-02 | FINGLAS GIS 110K1 | bar: Week 26 Th 25 to Week 27 Fr 3
TO-26-FIN GIS-110K2-03 | FINGLAS GIS 110K2 | bar: Week 26 Th 25 to Week 27 Fr 3
TO-26-FIN GIS-110SA1-2CB-01 | FINGLAS GIS 110SA1-2CB | bar: Week 26 Th 25 to Week 27 Fr 3
TO-26-FIN GIS-110SA1-3CB-03 | FINGLAS GIS 110SA1-3CB | bar: Week 26 Th 25 to Week 27 Fr 3
TO-26-FIN GIS-110SA2-4CB-04 | FINGLAS GIS 110SA2-4CB | bar: Week 26 Th 25 to Week 27 Fr 3
TO-26-BOL-ENN-1-01 | BOOLTIAGH ENNIS | bar: Week 26 Th 25 to Week 27 Mo 6
TO-26-GI GIS-LON-1-03 | GREAT ISLAND GIS LOUGHTOWN | bar: Week 26 Th 25 to Week 27 Mo 6
TO-26-LON-T2401-02 | LOUGHTOWN T2401 | bar: Week 26 Th 25 to Week 27 Mo 6
TO-26-110 kV A2 @ MAY-02 | MAYNOOTH 110 kV A2 | bar: Week 26 Th 25 to Week 27 Mo 6
TO-26-110 kV A3 @ MAY-01 | MAYNOOTH 110 kV A3 | bar: Week 26 Th 25 to Week 27 Mo 6
TO-26-110 kV B2 @ MAY-01 | MAYNOOTH 110 kV B2 | bar: Week 26 Th 25 to Week 27 Mo 6
TO-26-110 kV B3 @ MAY-01 | MAYNOOTH 110 kV B3 | bar: Week 26 Th 25 to Week 27 Mo 6
TO-26-220 kV A1 @ MAY-02 | MAYNOOTH 220 kV A1 | bar: Week 26 Th 25 to Week 27 Mo 6
TO-26-220 kV B1 @ MAY-02 | MAYNOOTH 220 kV B1 | bar: Week 26 Th 25 to Week 27 Mo 6
TO-26-MAY-T2102-01 | MAYNOOTH T2102 | bar: Week 26 Th 25 to Week 27 Mo 6
TO-26-CDU-T2104-02 | CORDUFF T2104
TO-26-CKM GIS-220SB1-2CB-01 | CARRICKMINES GIS 220SB1-2CB | bar: Week 26 Th 25
TO-26-CKM GIS-220SB1-3CB-01 | CARRICKMINES GIS 220SB1-3CB | bar: Week 26 Th 25
TO-26-CKM GIS-220SB2-4CB-01 | CARRICKMINES GIS 220SB2-4CB | bar: Week 26 Th 25
TO-26-FLA-T2102-02 | FLAGFORD T2102 | bar: Week 26 Th 25
TO-26-110 kV A1 @ KLN-02 | KILLONAN 110 kV A1 | bar: Week 26 Th 25 to Week 26 Fr 26
TO-26-110 kV B1 @ KLN-02 | KILLONAN 110 kV B1 | bar: Week 26 Th 25 to Week 26 Fr 26
TO-26-220 kV A2 @ KLN-01 | KILLONAN 220 kV A2 | bar: Week 26 Th 25 to Week 26 Fr 26
TO-26-220 kV B2 @ KLN-01 | KILLONAN 220 kV B2 | bar: Week 26 Th 25 to Week 26 Fr 26
TO-26-BAR-T141-04 | BARRYMORE T141 | bar: Week 26 Th 25 to Week 27 We 1
TO-26-BAR,T-BAR-1-04 | BARRYMORE tee BARRYMORE | bar: Week 26 Th 25 to Week 27 We 1
TO-26-BAR,T-CAH-1-04 | BARRYMORE tee CAHIR | bar: Week 26 Th 25 to Week 27 We 1
TO-26-BAR,T-KRA-1-04 | BARRYMORE tee KNOCKRAHA | bar: Week 26 Th 25 to Week 27 We 1
TO-26-BNK-CBT-1-03 | BARNAKYLE CASTLEBAGOT 1 | bar: Su 21
TO-26-110 kV A1 @ CBT-02 | CASTLEBAGOT 110 kV A1 | bar: Su 21
TO-26-110 kV B1 @ CBT-02 | CASTLEBAGOT 110 kV B1 | bar: Su 21
TO-26-CBT-110K1-04 | CASTLEBAGOT 110K1 | bar: Su 21
TO-26-CBT-110SA1-2CB-02 | CASTLEBAGOT 110SA1-2CB | bar: Su 21
TO-26-CBT-110SB1-2CB-02 | CASTLEBAGOT 110SB1-2CB | bar: Su 21
TO-26-GRO-T122-02 | GARROW T122
TO-26-220 kV A1 @ FIN-06 | FINGLAS 220 kV A1 | bar: Su 21
TO-26-220 kV B1 @ FIN-06 | FINGLAS 220 kV B1 | bar: Su 21
TO-26-FIN-220K1-05 | FINGLAS 220K1 | bar: Su 21
TO-26-FIN-220SA1-2CB-15 | FINGLAS 220SA1-2CB | bar: Su 21
TO-26-FIN-220SB1-2CB-12 | FINGLAS 220SB1-2CB | bar: Su 21
TO-26-FIN-HN-1-01 | FINGLAS HUNTSTOWN | bar: Su 21
TO-26-HN-T2010/11-01 | HUNTSTOWN T2010/11 | bar: Su 21
TO-26-CBT-INC-2-02 | CASTLEBAGOT INCHICORE 2 | bar: Su 21; Week 26 Th 25
TO-26-CDU-T2102-02 | CORDUFF T2102 | bar: Su 21; Week 26 Th 25
TO-26-220 kV A4 @ INC-03 | INCHICORE 220 kV A4 | bar: Su 21; Week 26 Th 25
TO-26-220 kV B4 @ INC-03 | INCHICORE 220 kV B4 | bar: Su 21; Week 26 Th 25
TO-26-INC-220K4-6-03 | INCHICORE 220K4-6 | bar: Su 21; Week 26 Th 25
TO-26-INC-T2106-02 | INCHICORE T2106 | bar: Su 21; Week 26 Th 25
TO-26-CDL-T132-01 | CORDAL T132 | bar: Week 26 Fr 26
TO-26-220 kV A2 @ LOU-07 | LOUTH 220 kV A2 | bar: Week 26 Fr 26 to Week 27 Mo 6
TO-26-220 kV B2 @ LOU-07 | LOUTH 220 kV B2 | bar: Week 26 Fr 26 to Week 27 Mo 6
TO-26-220 kV A2 @ CSH-01 | CASHLA 220 kV A2 | bar: Su 21; Week 26 Th 25 to Week 26 Fr 26
Report covers outages commencing/returning/spanning the period: 22/06/2026 - 05/07/2026
Outages commencing/returning in Week 26
OUTAGE ID | PLANT | Week 26 Mo 22: Week 26; Week 27 Mo 29: Week 27
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6
TO-26-220 kV A4 @ CSH-01 | CASHLA 220 kV A4 | bar: Su 21 to Week 26 Fr 26
TO-26-220 kV B2 @ CSH-02 | CASHLA 220 kV B2 | bar: Su 21 to Week 26 Fr 26
TO-26-220 kV B4 @ CSH-02 | CASHLA 220 kV B4 | bar: Su 21 to Week 26 Fr 26
TO-26-CSH-220K2-4-01 | CASHLA 220K2-4 | bar: Su 21 to Week 26 Fr 26
TO-26-CF-CLO-2-02 | CATHALEENS FALL CLOGHER 2 | bar: Su 21 to Week 26 Fr 26
TO-26-220 kV A1/A2 @ LOU-01 | LOUTH 220 kV A1/A2 | bar: Su 21 to Week 26 Fr 26
TO-26-LOU-220K1-2-03 | LOUTH 220K1-2 | bar: Su 21 to Week 26 Fr 26
Outages commencing/returning in Week 27
OUTAGE ID | PLANT | Week 26 Mo 22: Week 26; Week 27 Mo 29: Week 27
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6
TO-26-220 kV A2 @ CBT-02 | CASTLEBAGOT 220 kV A2
TO-26-220 kV B2 @ CBT-02 | CASTLEBAGOT 220 kV B2
TO-26-CBT-220K2-01 | CASTLEBAGOT 220K2
TO-26-CBT-220SA1-2CB-03 | CASTLEBAGOT 220SA1-2CB
TO-26-AUG-SK-4-02 | AUGHINISH SEALROCK 4 | bar: Week 27 Fr 3
TO-26-COS-FLA-1-01 | CARRICK ON SHANNON FLAGFORD 1 | bar: Week 27 Fr 3
TO-26-COT-T132-01 | COOMATAGGART T132 | bar: Week 27 Fr 3
TO-26-110 kV A1 @ FLA-03 | FLAGFORD 110 kV A1 | bar: Week 27 Fr 3
TO-26-110 kV B1 @ FLA-04 | FLAGFORD 110 kV B1 | bar: Week 27 Fr 3
TO-26-SK-T104-04 | SEALROCK T104 | bar: Week 27 Fr 3
TO-26-AGP-T141-01 | ARDNAGAPPARY T141 | bar: Week 27 Fr 3 to Week 27 Mo 6
TO-26-AGP-TIV-1-01 | ARDNAGAPPARY TIEVEBRACK | bar: Week 27 Fr 3 to Week 27 Mo 6
TO-26-BVK-COT-1-01 | BALLYVOUSKILL COOMATAGGART | bar: Week 27 Fr 3 to Week 27 Mo 6
TO-26-BIN-TIV-1-01 | BINBANE TIEVEBRACK | bar: Week 27 Fr 3 to Week 27 Mo 6
TO-26-CLW-KLS-1-01 | CARLOW KELLIS 1 | bar: Week 27 Fr 3 to Week 27 Mo 6
TO-26-COT-110SA1-01 | COOMATAGGART 110SA1 | bar: Week 27 Fr 3 to Week 27 Mo 6
TO-26-COT-110SA2-01 | COOMATAGGART 110SA2 | bar: Week 27 Fr 3 to Week 27 Mo 6
TO-26-COT-FILTER1-01 | COOMATAGGART FILTER1 | bar: Week 27 Fr 3 to Week 27 Mo 6
TO-26-COT-T132-02 | COOMATAGGART T132 | bar: Week 27 Fr 3 to Week 27 Mo 6
TO-26-COT-T141-01 | COOMATAGGART T141 | bar: Week 27 Fr 3 to Week 27 Mo 6
TO-26-220 kV A2 @ DSN-05 | DUNSTOWN 220 kV A2 | bar: Week 27 Fr 3 to Week 27 Mo 6
TO-26-220 kV B2 @ DSN-04 | DUNSTOWN 220 kV B2 | bar: Week 27 Fr 3 to Week 27 Mo 6
TO-26-400 kV A2 @ DSN-04 | DUNSTOWN 400 kV A2 | bar: Week 27 Fr 3 to Week 27 Mo 6
TO-26-400 kV B2 @ DSN-06 | DUNSTOWN 400 kV B2 | bar: Week 27 Fr 3 to Week 27 Mo 6
TO-26-DSN-T4202-02 | DUNSTOWN T4202 | bar: Week 27 Fr 3 to Week 27 Mo 6
TO-26-220 kV A1 @ INC-01 | INCHICORE 220 kV A1 | bar: Week 27 Fr 3 to Week 27 Mo 6
TO-26-220 kV B1 @ INC-02 | INCHICORE 220 kV B1 | bar: Week 27 Fr 3 to Week 27 Mo 6
TO-26-INC-PB-1-05 | INCHICORE POOLBEG 1 | bar: Week 27 Fr 3 to Week 27 Mo 6
TO-26-LOU-T2102-07 | LOUTH T2102 | bar: Week 27 Fr 3 to Week 27 Mo 6
TO-26-220 kV A1 @ PB-02 | POOLBEG 220 kV A1 | bar: Week 27 Fr 3 to Week 27 Mo 6
TO-26-220 kV B1 @ PB-03 | POOLBEG 220 kV B1 | bar: Week 27 Fr 3 to Week 27 Mo 6
TO-26-110 kV A2 @ RAF-03 | RAFFEEN 110 kV A2 | bar: Week 27 Fr 3 to Week 27 Mo 6
TO-26-110 kV B2 @ RAF-05 | RAFFEEN 110 kV B2 | bar: Week 27 Fr 3 to Week 27 Mo 6
TO-26-RAF-CAP2-02 | RAFFEEN CAP2 | bar: Week 27 Fr 3 to Week 27 Mo 6
TO-26-TIV-110SA1-2CB-01 | TIEVEBRACK 110SA1-2CB | bar: Week 27 Fr 3 to Week 27 Mo 6
TO-26-TSB-110SA1-01 | THORNSBERRY 110SA1 | bar: Week 27 Fr 3
TO-26-TSB-110SA2-01 | THORNSBERRY 110SA2 | bar: Week 27 Fr 3
TO-26-TSB-T142-04 | THORNSBERRY T142 | bar: Week 27 Fr 3
TO-26-GWE-CAP1-01 | GORTAWEE CAP1 | bar: Week 27 Fr 3 to Week 27 Mo 6
TO-26-INC-T2101-01 | INCHICORE T2101 | bar: Week 27 Fr 3 to Week 27 Mo 6
TO-26-DSN-T4201-03 | DUNSTOWN T4201 | bar: Su 21 to Week 27 Tu 30
TO-26-KYT-T233-03 | KELLYSTOWN T233 | bar: Su 21 to Week 26 Su 28
TO-26-KHL-THU-1-02 | KILL HILL THURLES
TO-26-CBA-110SA1-01 | CLOGHBOOLA 110SA1 | bar: Su 21 to Week 26 Su 28
TO-26-CBA-110SA2-01 | CLOGHBOOLA 110SA2 | bar: Su 21 to Week 26 Su 28
TO-26-CBA-T122-01 | CLOGHBOOLA T122 | bar: Su 21 to Week 26 Su 28
TO-26-CBA-T131-01 | CLOGHBOOLA T131 | bar: Su 21 to Week 26 Su 28
TO-26-CBA-TRI-1-01 | CLOGHBOOLA TRIEN | bar: Su 21 to Week 26 Su 28
TO-26-BYH-CDL-1-01 | BALLYNAHULLA CORDAL | bar: Su 21 to Week 26 Su 28; Week 27 Fr 3
Report covers outages commencing/returning/spanning the period: 22/06/2026 - 05/07/2026
Outages commencing/returning in Week 27
OUTAGE ID | PLANT | Week 26 Mo 22: Week 26; Week 27 Mo 29: Week 27
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6
TO-26-BVK-T2102-05 | BALLYVOUSKILL T2102
TO-26-CDL-110SA1-01 | CORDAL 110SA1
TO-26-CDL-110SA2-01 | CORDAL 110SA2
TO-26-CDL-T132-02 | CORDAL T132
TO-26-CDL-T141-01 | CORDAL T141
Outages spanning Weeks 26-27
OUTAGE ID | PLANT | Week 26 Mo 22: Week 26; Week 27 Mo 29: Week 27
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6
TO-26-AA GIS-T103-02 | ARDNACRUSHA GIS T103
TO-26-ATH-M/CAP1-03 | ATHLONE M/CAP1
TO-26-ATY-PLS-1-01 | ATHY PORTLAOISE
TO-26-BAN-RAF-1-02 | BANDON RAFFEEN
TO-26-CLW-KLS-1-03 | CARLOW KELLIS 1
TO-26-110 kV B1/B2 @ CSH-01 | CASHLA 110 kV B1/B2
TO-26-CSH-110K1-2-01 | CASHLA 110K1-2
TO-26-CBR-SVC-02 | CASTLEBAR SVC
TO-26-CBR-SVC-01
TO-26-CF-110K1-2-01 | CATHALEENS FALL 110K1-2
TO-26-CHA-KLN-1-02 | CHARLEVILLE KILLONAN
TO-26-CRA-T122-02 | CRANE T122
TO-26-DND-T121-01 | DARNDALE T121
TO-26-DER-TSB-1-01 | DERRYIRON THORNSBERRY
TO-26-DOO-T141-01 | DOON T141
TO-26-DDK-LOU-1-01 | DUNDALK LOUTH
TO-26-DSN-MP GIS-1-10 | DUNSTOWN MONEYPOINT GIS
TO-26-DSN-T4202-01 | DUNSTOWN T4202
TO-26-FIN GIS-SVN-1-03 | FINGLAS GIS STEPHENSTOWN
TO-26-FIN GIS-T2106-02 | FINGLAS GIS T2106
TO-26-FIN-SHL-1-02 | FINGLAS SHELLYBANKS
TO-26-110 kV A1 @ FLA-01 | FLAGFORD 110 kV A1
TO-26-110 kV B1 @ FLA-01 | FLAGFORD 110 kV B1
TO-26-220 kV A2 @ FLA-02 | FLAGFORD 220 kV A2
TO-26-220 kV B2 @ FLA-02 | FLAGFORD 220 kV B2
TO-26-FLA-TON-1-01 | FLAGFORD TONROE
TO-26-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-26-GI GIS-220SA1-2CB-02 | GREAT ISLAND GIS 220SA1-2CB
TO-26-GI-T141-01 | GREAT ISLAND T141
TO-26-ISH-T2001-01 | IRISHTOWN T2001
TO-26-KLN-KPG-1-02 | KILLONAN KILPADDOGE
TO-26-KLN-T2102-05 | KILLONAN T2102
TO-26-220 kV A4 @ KRA-01 | KNOCKRAHA 220 kV A4
TO-26-220 kV B4 @ KRA-01 | KNOCKRAHA 220 kV B4
TO-26-KRA-220K4-01 | KNOCKRAHA 220K4
TO-26-KRA-220SA2-4CB-03 | KNOCKRAHA 220SA2-4CB
TO-26-KRA-220SB2-4CB-03 | KNOCKRAHA 220SB2-4CB
TO-26-LET-SVC-02 | LETTERKENNY SVC
TO-26-MR-T107-01 | MARINA T107
TO-26-MP GIS-T4002-02 | MONEYPOINT GIS T4002
TO-26-NAV-M/CAP1-01 | NAVAN M/CAP1
TO-26-220 kV A1/A2 @ PB-02 | POOLBEG 220 kV A1/A2
TO-26-PB-R2001-03 | POOLBEG R2001
TO-26-PB-R2001-02
TO-26-110 kV A2 @ RAF-01 | RAFFEEN 110 kV A2
TO-26-110 kV B2 @ RAF-01 | RAFFEEN 110 kV B2
TO-26-SKL-M/CAP2-01 | SHANKILL M/CAP2
TO-26-SHL-D1/CB1-01 | SHELLYBANKS D1/CB1
TO-26-SHL-D1/CB2-06 | SHELLYBANKS D1/CB2
TO-26-TB-T2003-01 | TARBERT T2003
TO-26-TAW-T1/T2-01 | TAWNAGHMORE T1/T2
Report covers outages commencing/returning/spanning the period: 22/06/2026 - 05/07/2026
Outages spanning Weeks 26-27
OUTAGE ID | PLANT | Week 26 Mo 22: Week 26; Week 27 Mo 29: Week 27
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6
TO-26-TAW-T3-02 | TAWNAGHMORE T3
TO-26-TON-T142-01 | TONROE T142
TO-26-TRL-CAP2-01 | TRALEE CAP2