## Wks 30 - 31
Report covers outages commencing/returning/spanning the period: 20/07/2026 - 02/08/2026
Outages commencing/returning in Week 30
OUTAGE ID | PLANT |  | Week 30 | [6 empty] | Week 31
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3
TO-26-BOT-MLC-1-01 | BOGTOWN MOUNTLUCAS
TO-26-BOT-T131-02 | BOGTOWN T131
TO-26-110 kV B2 @ LOU-05 | LOUTH 110 kV B2
TO-26-LOU-T2104-03 | LOUTH T2104
TO-26-CAH-CAP2/4-01 | CAHIR CAP2/4
TO-26-110 kV A2 @ CLG-02 | CLOGHRAN 110 kV A2
TO-26-110 kV B2 @ CLG-02 | CLOGHRAN 110 kV B2
TO-26-CLG-110K2-01 | CLOGHRAN 110K2
TO-26-CLG-110SA1-2CB-03 | CLOGHRAN 110SA1-2CB
TO-26-CLG-110SB1-2CB-03 | CLOGHRAN 110SB1-2CB
TO-26-220 kV A4 @ KRA-08 | KNOCKRAHA 220 kV A4
TO-26-220 kV B4 @ KRA-10 | KNOCKRAHA 220 kV B4
TO-26-KRA-220K4-04 | KNOCKRAHA 220K4
TO-26-KRA-220SA2-4CB-09 | KNOCKRAHA 220SA2-4CB
TO-26-KRA-220SB2-4CB-09 | KNOCKRAHA 220SB2-4CB
TO-26-LET-PST-01 | LETTERKENNY STRABANE PST
TO-26-220 kV A1 @ DSN-01 | DUNSTOWN 220 kV A1
TO-26-220 kV B1 @ DSN-02 | DUNSTOWN 220 kV B1
TO-26-220 kV A1 @ MAY-03 | MAYNOOTH 220 kV A1
TO-26-220 kV B1 @ MAY-03 | MAYNOOTH 220 kV B1
TO-26-110 kV A2 @ ARV-01 | ARVA 110 kV A2
TO-26-110 kV B2 @ ARV-01 | ARVA 110 kV B2
TO-26-ARV-COS-1-07 | ARVA CARRICK ON SHANNON
TO-26-AA GIS-LIM-1-01 | ARDNACRUSHA GIS LIMERICK
TO-26-ARK-CKM GIS-1-05 | ARKLOW CARRICKMINES GIS
TO-26-110 kV A5 @ FIN GIS-01 | FINGLAS GIS 110 kV A5
TO-26-110 kV B5 @ FIN GIS-01 | FINGLAS GIS 110 kV B5
TO-26-FIN GIS-110K5-02 | FINGLAS GIS 110K5
TO-26-FIN GIS-110SA3-5CB-02 | FINGLAS GIS 110SA3-5CB
TO-26-FIN GIS-110SB3-5CB-02 | FINGLAS GIS 110SB3-5CB
TO-26-FIN GIS-MCE-1-01 | FINGLAS GIS MACETOWN
TO-26-220 kV A2 @ INC-02 | INCHICORE 220 kV A2
TO-26-220 kV A4 @ INC-04 | INCHICORE 220 kV A4
TO-26-220 kV B2 @ INC-02 | INCHICORE 220 kV B2
TO-26-220 kV B4 @ INC-04 | INCHICORE 220 kV B4
TO-26-220 kV B4 @ INC-05
TO-26-INC-220K2-4-01 | INCHICORE 220K2-4
TO-26-110 kV B1 @ LLA-01 | LENALEA 110 kV B1
TO-26-LLA-110K1-02 | LENALEA 110K1
TO-26-LOU-TAN-2-03 | LOUTH TANDRAGEE 2
TO-26-OUG-T141-01 | OUGHTRAGH T141
TO-26-OUG,T-KER-1-02 | OUGHTRAGH tee KNOCKEARAGH
TO-26-OUG,T-OUG-1-02 | OUGHTRAGH tee OUGHTRAGH
TO-26-OUG,T-TRL-1-01 | OUGHTRAGH tee TRALEE
TO-26-TRL-110SA1-2CB-02 | TRALEE 110SA1-2CB
TO-26-TRL-T142-01 | TRALEE T142
TO-26-DSN-MAY-1-01 | DUNSTOWN MAYNOOTH 1
TO-26-220 kV A1 @ LOU-01 | LOUTH 220 kV A1
TO-26-220 kV B1 @ LOU-01 | LOUTH 220 kV B1
TO-26-LOU-AT2-02 | LOUTH AT2
TO-26-ARK-220K1-2-01 | ARKLOW 220K1-2
TO-26-DEY-T134-03 | DERRYCARNEY T134
TO-26-LA-SLB-1-01 | LANESBORO SLIABH BAWN
TO-26-KBY-MR-1-01 | KILBARRY MARINA 1
TO-26-LA-110SA1-2CB-04 | LANESBORO 110SA1-2CB
TO-26-DJG-TRL-1-01 | DROMBEG TRALEE
TO-26-BDN-MRK1-04 | BALLYDINE MRK1
TO-26-MEE-T121-02 | MEENTYCAT T121
TO-26-THU-CAP1-01 | THURLES CAP1
TO-26-BAN-RAF-1-02 | BANDON RAFFEEN
TO-26-BRT-T222-03 | BRACETOWN T222
Report covers outages commencing/returning/spanning the period: 20/07/2026 - 02/08/2026
Outages commencing/returning in Week 30
OUTAGE ID | PLANT | Week 30 Mo 20: Week 30; Week 31 Mo 27: Week 31
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3
TO-26-CSH-ENN-1-03 | CASHLA ENNIS | bar: Week 30 Th 23
TO-26-GAL GIS-T142-01 | GALWAY GIS T142 | bar: Week 30 Th 23
TO-26-CKG-T124-01 | CORKAGH T124 | bar: Week 30 Th 23 to Week 31 Mo 3
TO-26-110 kV A1 @ RAF-03 | RAFFEEN 110 kV A1 | bar: Week 30 Th 23 to Week 31 Mo 3
TO-26-110 kV B1 @ RAF-02 | RAFFEEN 110 kV B1 | bar: Week 30 Th 23 to Week 31 Mo 3
TO-26-RAF-TBG-1-04 | RAFFEEN TRABEG 1 | bar: Week 30 Th 23 to Week 31 Mo 3
TO-26-110 kV A2 @ TBG-02 | TRABEG 110 kV A2 | bar: Week 30 Th 23 to Week 31 Mo 3
TO-26-110 kV B2 @ TBG-02 | TRABEG 110 kV B2 | bar: Week 30 Th 23 to Week 31 Mo 3
TO-26-110 kV B1/B2 @ CSH-01 | CASHLA 110 kV B1/B2 | bar: Su 19 to Week 30 Th 23
TO-26-CSH-110K1-2-01 | CASHLA 110K1-2 | bar: Su 19 to Week 30 Th 23
TO-26-CLN-110SA1-06 | CLOON 110SA1 | bar: Su 19 to Week 30 Th 23
TO-26-CLN-110SA2-04 | CLOON 110SA2 | bar: Su 19 to Week 30 Th 23
TO-26-CLN-LA-1-03 | CLOON LANESBORO | bar: Su 19 to Week 30 Th 23
TO-26-CLN-T142-02 | CLOON T142 | bar: Su 19 to Week 30 Th 23
TO-26-LA-T104-01 | LANESBORO T104 | bar: Su 19 to Week 30 Th 23
TO-26-CSH-GAL GIS-4-03 | CASHLA GALWAY GIS 4 | bar: Week 30 Fr 24
TO-26-110 kV A1 @ FLA-02 | FLAGFORD 110 kV A1 | bar: Week 30 Fr 24 to Week 31 Th 30
TO-26-110 kV B1 @ FLA-03 | FLAGFORD 110 kV B1 | bar: Week 30 Fr 24 to Week 31 Th 30
TO-26-FIN GIS-SVN-1-03 | FINGLAS GIS STEPHENSTOWN | bar: Su 19 to Week 30 Fr 24
Outages commencing/returning in Week 31
OUTAGE ID | PLANT | Week 30 Mo 20: Week 30; Week 31 Mo 27: Week 31
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3
TO-26-110 kV A1 @ KBY-01 | KILBARRY 110 kV A1 | bar: Week 31 Mo 27 to Week 31 Tu 28
TO-26-110 kV B1 @ KBY-01 | KILBARRY 110 kV B1 | bar: Week 31 Mo 27 to Week 31 Tu 28
TO-26-DGY-FIN GIS-1-01 | DUNSOGHLY FINGLAS GIS | bar: Week 31 Mo 27 to Week 31 We 29
TO-26-DGY-T101-01 | DUNSOGHLY T101 | bar: Week 31 Mo 27 to Week 31 We 29
TO-26-BDN-110SA1-01 | BALLYDINE 110SA1 | bar: Week 31 Mo 27 to Week 31 Th 30
TO-26-BDN-CUL-1-06 | BALLYDINE CULLENAGH | bar: Week 31 Mo 27 to Week 31 Th 30
TO-26-CLA-DMY-1-01 | CLASHAVOON DUNMANWAY | bar: Week 31 Mo 27 to Week 31 Fr 31
TO-26-110 kV A2 @ DEY-03 | DERRYCARNEY 110 kV A2 | bar: Week 31 Mo 27 to Week 31 Fr 31
TO-26-110 kV B2 @ DEY-03 | DERRYCARNEY 110 kV B2 | bar: Week 31 Mo 27 to Week 31 Fr 31
TO-26-DEY-110K2-04 | DERRYCARNEY 110K2 | bar: Week 31 Mo 27 to Week 31 Fr 31
TO-26-KRA-220SB2-4CB-05 | KNOCKRAHA 220SB2-4CB | bar: Week 31 Mo 27 to Week 31 Fr 31
TO-26-LIS-CAP2-05 | LISDRUM CAP2 | bar: Week 31 Mo 27 to Week 31 Fr 31
TO-26-220 kV A1 @ WOO-04 | WOODLAND 220 kV A1 | bar: Week 31 Mo 27 to Week 31 Fr 31
TO-26-220 kV B1 @ WOO-04 | WOODLAND 220 kV B1 | bar: Week 31 Mo 27 to Week 31 Fr 31
TO-26-WOO-T4201-03 | WOODLAND T4201 | bar: Week 31 Mo 27 to Week 31 Fr 31
TO-26-CD-KBY-1-01 | CARRIGADROHID KILBARRY | bar: Week 31 Mo 27 to Week 31 Mo 3
TO-26-CD-KBY-1-03 | bar: Week 31 Mo 27 to Week 31 Mo 3
TO-26-DRY-T141-01 | DRYBRIDGE T141 | bar: Week 31 Mo 27 to Week 31 Mo 3
TO-26-KBY-KRA-2-03 | KILBARRY KNOCKRAHA 2 | bar: Week 31 Mo 27 to Week 31 Mo 3
TO-26-NEW-T141-04 | NEWBRIDGE T141 | bar: Week 31 Mo 27 to Week 31 Mo 3
TO-26-SHL-D1/CB1-07 | SHELLYBANKS D1/CB1 | bar: Week 31 Mo 27 to Week 31 Mo 3
TO-26-SHL-D1/CB2-07 | SHELLYBANKS D1/CB2 | bar: Week 31 Mo 27 to Week 31 Mo 3
TO-26-KKY-T141-01 | KILKENNY T141 | bar: Week 31 Tu 28 to Week 31 We 29
TO-26-CLG-T121-01 | CLOGHRAN T121 | bar: Week 31 Tu 28 to Week 31 Th 30
TO-26-CLU-KUD-1-02 | CLUTTERLAND KILMAHUD | bar: Week 31 Tu 28 to Week 31 Th 30
TO-26-LA-RIC-2-08 | LANESBORO RICHMOND 2 | bar: Su 19 to Week 31 Tu 28
TO-26-MP GIS-T4002-02 | MONEYPOINT GIS T4002 | bar: Su 19 to Week 31 Tu 28
TO-26-KKY-CAP2-02 | KILKENNY CAP2 | bar: Week 31 We 29 to Week 31 Th 30
TO-26-CLN-LA-1-04 | CLOON LANESBORO | bar: Week 31 We 29 to Week 31 Fr 31
TO-26-LA-110SA1-2CB-02 | LANESBORO 110SA1-2CB | bar: Week 31 We 29 to Week 31 Fr 31
TO-26-LA-RIC-2-03 | LANESBORO RICHMOND 2 | bar: Week 31 We 29 to Week 31 Fr 31
TO-26-LA-SLB-1-02 | LANESBORO SLIABH BAWN | bar: Week 31 We 29 to Week 31 Fr 31
TO-26-LA-T104-02 | LANESBORO T104 | bar: Week 31 We 29 to Week 31 Fr 31
TO-26-110 kV A1 @ KBY-02 | KILBARRY 110 kV A1 | bar: Week 31 We 29 to Week 31 Mo 3
TO-26-KLT-RGR-1-02 | KILLAPHORT RAGHRA | bar: Week 31 We 29 to Week 31 Mo 3
TO-26-KPT-T2001/2-02 | KILLAPHORT T2001/2 | bar: Week 31 We 29 to Week 31 Mo 3
TO-26-RGR-SH-1-01 | RAGHRA SHANNONBRIDGE | bar: Week 31 We 29 to Week 31 Mo 3
Report covers outages commencing/returning/spanning the period: 20/07/2026 - 02/08/2026
Outages commencing/returning in Week 31
OUTAGE ID | PLANT | Week 30 Mo 20: Week 30; Week 31 Mo 27: Week 31
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3
TO-26-CHA-KLN-1-02 | CHARLEVILLE KILLONAN
TO-26-KLN-KPG-1-02 | KILLONAN KILPADDOGE
TO-26-110 kV A2 @ FLA-02 | FLAGFORD 110 kV A2
TO-26-110 kV B2 @ FLA-02 | FLAGFORD 110 kV B2
TO-26-FLA-SLI-1-04 | FLAGFORD SLIGO
TO-26-CLN-T141-04 | CLOON T141
TO-26-FIN-220SB1-2CB-14 | FINGLAS 220SB1-2CB
TO-26-FLA-TON-1-01 | FLAGFORD TONROE
TO-26-TON-T142-01 | TONROE T142
TO-26-110 kV B1 @ KLS-01 | KELLIS 110 kV B1
TO-26-110 kV B2 @ KLS-06 | KELLIS 110 kV B2
TO-26-KLS-KKY-1-06 | KELLIS KILKENNY
TO-26-CLW-KLS-1-03 | CARLOW KELLIS 1
TO-26-110 kV A1 @ KLS-01 | KELLIS 110 kV A1
TO-26-110 kV B1 @ KLS-02 | KELLIS 110 kV B1
Outages spanning Weeks 30-31
OUTAGE ID | PLANT | Week 30 Mo 20: Week 30; Week 31 Mo 27: Week 31
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3
TO-26-AD-T2014-04 | AGHADA T2014
TO-26-AA GIS-T103-02 | ARDNACRUSHA GIS T103
TO-26-ATH-M/CAP1-03 | ATHLONE M/CAP1
TO-26-ATY-PLS-1-01 | ATHY PORTLAOISE
TO-26-CBR-SVC-02 | CASTLEBAR SVC
TO-26-CBR-SVC-01
TO-26-110 kV A1 @ CF-02 | CATHALEENS FALL 110 kV A1
TO-26-110 kV A2 @ CF-01 | CATHALEENS FALL 110 kV A2
TO-26-110 kV B1 @ CF-01 | CATHALEENS FALL 110 kV B1
TO-26-110 kV B2 @ CF-01 | CATHALEENS FALL 110 kV B2
TO-26-CF-110K1-2-02 | CATHALEENS FALL 110K1-2
TO-26-DND-T121-01 | DARNDALE T121
TO-26-DER-TSB-1-01 | DERRYIRON THORNSBERRY
TO-26-DOO-T141-01 | DOON T141
TO-26-DRY-LOU-1-01 | DRYBRIDGE LOUTH
TO-26-DRY-LOU-1-02
TO-26-DDK-LOU-1-01 | DUNDALK LOUTH
TO-26-DSN-400K1-2-04 | DUNSTOWN 400K1-2
TO-26-DSN-MP GIS-1-10 | DUNSTOWN MONEYPOINT GIS
TO-26-DSN-T4201-03 | DUNSTOWN T4201
TO-26-DSN-T4202-01 | DUNSTOWN T4202
TO-26-FIN-FIN GIS-2-01 | FINGLAS FINGLAS GIS 2
TO-26-FIN-SHL-1-02 | FINGLAS SHELLYBANKS
TO-26-FIN-T2104-01 | FINGLAS T2104
TO-26-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-26-GI GIS-220SA1-2CB-02 | GREAT ISLAND GIS 220SA1-2CB
TO-26-GI-T141-01 | GREAT ISLAND T141
TO-26-ISH-T2001-01 | IRISHTOWN T2001
TO-26-KYT-T237-03 | KELLYSTOWN T237
TO-26-KKY-CAP2-03 | KILKENNY CAP2
TO-26-220 kV A4 @ KRA-01 | KNOCKRAHA 220 kV A4
TO-26-220 kV B4 @ KRA-01 | KNOCKRAHA 220 kV B4
TO-26-KRA-220K4-01 | KNOCKRAHA 220K4
TO-26-KRA-220SA2-4CB-03 | KNOCKRAHA 220SA2-4CB
TO-26-KRA-220SB2-4CB-03 | KNOCKRAHA 220SB2-4CB
TO-26-KRA-LYT-1-01 | KNOCKRAHA LYSAGHTSTOWN
TO-26-LET-SVC-02 | LETTERKENNY SVC
TO-26-110 kV A1 @ LOU-01 | LOUTH 110 kV A1
TO-26-110 kV B1 @ LOU-01 | LOUTH 110 kV B1
TO-26-MR-T107-01 | MARINA T107
TO-26-NAV-M/CAP1-01 | NAVAN M/CAP1
Report covers outages commencing/returning/spanning the period: 20/07/2026 - 02/08/2026
Outages spanning Weeks 30-31
OUTAGE ID | PLANT | Week 30 Mo 20: Week 30; Week 31 Mo 27: Week 31
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3
TO-26-220 kV A1/A2 @ PB-02 | POOLBEG 220 kV A1/A2
TO-26-PB-R2001-02 | POOLBEG R2001
TO-26-PB-R2001-03
TO-26-110 kV A2 @ RAF-01 | RAFFEEN 110 kV A2
TO-26-110 kV B2 @ RAF-01 | RAFFEEN 110 kV B2
TO-26-SKL-M/CAP2-01 | SHANKILL M/CAP2
TO-26-TB-T2003-01 | TARBERT T2003
TO-26-TAW-T1/T2-01 | TAWNAGHMORE T1/T2
TO-26-TAW-T3-02 | TAWNAGHMORE T3
TO-26-TRL-CAP2-01 | TRALEE CAP2
TO-26-WEX-CAP4-06 | WEXFORD CAP4