## Wks 32 - 33
Report covers outages commencing/returning/spanning the period: 03/08/2026 - 16/08/2026
Outages commencing/returning in Week 32
OUTAGE ID | PLANT |  | Week 32 | [6 empty] | Week 33
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
TO-26-AA GIS-SNG-1-01 | ARDNACRUSHA GIS SINGLAND | bar: Week 32 Tu 4
TO-26-FLA-T2102-05 | FLAGFORD T2102 | bar: Week 32 Tu 4
TO-26-BNK-110SA1-2CB-02 | BARNAKYLE 110SA1-2CB | bar: Week 32 Tu 4; Week 32 Th 6
TO-26-BNK-CBT-2-03 | BARNAKYLE CASTLEBAGOT 2 | bar: Week 32 Tu 4; Week 32 Th 6
TO-26-BNK-T122-02 | BARNAKYLE T122 | bar: Week 32 Tu 4; Week 32 Th 6
TO-26-CBT-KUD-1-02 | CASTLEBAGOT KILMAHUD | bar: Week 32 Tu 4; Week 32 Th 6
TO-26-GRO-T122-01 | GARROW T122 | bar: Week 32 Tu 4; Week 32 Th 6 to Week 32 Fr 7
TO-26-110 kV A2 @ SH-04 | SHANNONBRIDGE 110 kV A2 | bar: Week 32 Tu 4; Week 32 Th 6 to Week 33 Mo 10
TO-26-110 kV B2 @ SH-04 | SHANNONBRIDGE 110 kV B2 | bar: Week 32 Tu 4; Week 32 Th 6 to Week 33 Mo 10
TO-26-SOM,T-CSH-1-01 | SOMERSET tee CASHLA | bar: Week 32 Tu 4; Week 32 Th 6 to Week 33 Mo 10
TO-26-SOM,T-SH-1-01 | SOMERSET tee SHANNONBRIDGE | bar: Week 32 Tu 4; Week 32 Th 6 to Week 33 Mo 10
TO-26-SOM,T-SOM-1-01 | SOMERSET tee SOMERSET | bar: Week 32 Tu 4; Week 32 Th 6 to Week 33 Mo 10
TO-26-SOM-T142-01 | SOMERSET T142 | bar: Week 32 Tu 4; Week 32 Th 6 to Week 33 Tu 11
TO-26-KLS-KKY-1-04 | KELLIS KILKENNY | bar: Week 32 Tu 4; Week 32 Th 6 to Week 33 Fr 14
TO-26-CLW-KLS-2-01 | CARLOW KELLIS 2 | bar: Week 32 Tu 4; Week 32 Th 6 to Week 33 Mo 17
TO-26-220 kV A1 @ CLE-01 | CLONEE 220 kV A1 | bar: Week 32 Tu 4; Week 32 Th 6 to Week 33 Mo 17
TO-26-220 kV A2 @ CLE-02 | CLONEE 220 kV A2 | bar: Week 32 Tu 4; Week 32 Th 6 to Week 33 Mo 17
TO-26-220 kV B1 @ CLE-01 | CLONEE 220 kV B1 | bar: Week 32 Tu 4; Week 32 Th 6 to Week 33 Mo 17
TO-26-220 kV B2 @ CLE-02 | CLONEE 220 kV B2 | bar: Week 32 Tu 4; Week 32 Th 6 to Week 33 Mo 17
TO-26-CLE-220K1-01 | CLONEE 220K1 | bar: Week 32 Tu 4; Week 32 Th 6 to Week 33 Mo 17
TO-26-CLE-220K2-03 | CLONEE 220K2 | bar: Week 32 Tu 4; Week 32 Th 6 to Week 33 Mo 17
TO-26-CLE-220SA1-2CB-01 | CLONEE 220SA1-2CB | bar: Week 32 Tu 4; Week 32 Th 6 to Week 33 Mo 17
TO-26-CLE-220SB1-2CB-01 | CLONEE 220SB1-2CB | bar: Week 32 Tu 4; Week 32 Th 6 to Week 33 Mo 17
TO-26-CKN-GRO-1-01 | CLONKEEN GARROW | bar: Week 32 Tu 4; Week 32 Th 6 to Week 33 Mo 17
TO-26-CLN-T141-01 | CLOON T141 | bar: Week 32 Tu 4; Week 32 Th 6 to Week 33 Mo 17
TO-26-110 kV A1 @ CF-02 | CATHALEENS FALL 110 kV A1 | bar: Su 2 to Week 32 Tu 4
TO-26-110 kV A2 @ CF-01 | CATHALEENS FALL 110 kV A2 | bar: Su 2 to Week 32 Tu 4
TO-26-110 kV B1 @ CF-01 | CATHALEENS FALL 110 kV B1 | bar: Su 2 to Week 32 Tu 4
TO-26-110 kV B2 @ CF-01 | CATHALEENS FALL 110 kV B2 | bar: Su 2 to Week 32 Tu 4
TO-26-CF-110K1-2-02 | CATHALEENS FALL 110K1-2 | bar: Su 2 to Week 32 Tu 4
TO-26-DRY-110SA1-02 | DRYBRIDGE 110SA1 | bar: Su 2 to Week 32 Tu 4
TO-26-DRY-110SA2-03 | DRYBRIDGE 110SA2 | bar: Su 2 to Week 32 Tu 4
TO-26-DRY-OBE-1-01 | DRYBRIDGE OLDBRIDGE | bar: Su 2 to Week 32 Tu 4
TO-26-110 kV B1 @ AA GIS-03 | ARDNACRUSHA GIS 110 kV B1
TO-26-110 kV B2 @ AA GIS-01 | ARDNACRUSHA GIS 110 kV B2
TO-26-AA GIS-110K2-02 | ARDNACRUSHA GIS 110K2
TO-26-AA GIS-110SB1-2CB-04 | ARDNACRUSHA GIS 110SB1-2CB
TO-26-AA GIS-T102-03 | ARDNACRUSHA GIS T102
TO-26-220 kV A2 @ FLA-07 | FLAGFORD 220 kV A2
TO-26-220 kV B2 @ FLA-07 | FLAGFORD 220 kV B2
TO-26-CLG-T122-01 | CLOGHRAN T122 | bar: Week 32 Th 6
TO-26-110 kV B1 @ CUL-03 | CULLENAGH 110 kV B1 | bar: Week 32 Th 6
TO-26-110 kV B2 @ CUL-02 | CULLENAGH 110 kV B2 | bar: Week 32 Th 6
TO-26-CUL-110K1-2-02 | CULLENAGH 110K1-2 | bar: Week 32 Th 6
TO-26-110 kV A1 @ SRA-02 | SRANANAGH 110 kV A1 | bar: Week 32 Th 6 to Week 33 We 12
TO-26-110 kV A2 @ SRA-01 | SRANANAGH 110 kV A2 | bar: Week 32 Th 6 to Week 33 We 12
TO-26-110 kV B1 @ SRA-02 | SRANANAGH 110 kV B1 | bar: Week 32 Th 6 to Week 33 We 12
TO-26-110 kV B2 @ SRA-01 | SRANANAGH 110 kV B2 | bar: Week 32 Th 6 to Week 33 We 12
TO-26-SRA-110K1-2-03 | SRANANAGH 110K1-2 | bar: Week 32 Th 6 to Week 33 We 12
TO-26-110 kV A1 @ CLO-01 | CLOGHER 110 kV A1 | bar: Week 32 Th 6 to Week 33 Fr 14
TO-26-110 kV B1 @ CLO-01 | CLOGHER 110 kV B1 | bar: Week 32 Th 6 to Week 33 Fr 14
TO-26-CLO-DRM-1-05 | CLOGHER DRUMKEEN | bar: Week 32 Th 6 to Week 33 Fr 14
TO-26-GOR-NAV-1-03 | GORMAN NAVAN 1 | bar: Week 32 Th 6 to Week 33 Fr 14
TO-26-DSN-MP GIS-1-02 | DUNSTOWN MONEYPOINT GIS | bar: Week 32 Th 6 to Week 33 Mo 17
TO-26-MP GIS-PRO-1-02 | MONEYPOINT GIS PROSPECT | bar: Week 32 Th 6 to Week 33 Mo 17
TO-26-CBT-INC-2-02 | CASTLEBAGOT INCHICORE 2 | bar: Su 2 to Week 32 Tu 4
TO-26-CKG-T124-01 | CORKAGH T124 | bar: Su 2 to Week 32 Tu 4
TO-26-INC-220K4-6-03 | INCHICORE 220K4-6 | bar: Su 2 to Week 32 Tu 4
TO-26-INC-T2106-02 | INCHICORE T2106 | bar: Su 2 to Week 32 Tu 4
TO-26-CLH-TRI-1-02 | CLAHANE TRIEN | bar: Week 32 Th 6 to Week 32 Fr 7
TO-26-BDN-MRK1-04 | BALLYDINE MRK1 | bar: Su 2 to Week 32 Tu 4; Week 32 Th 6
TO-26-DRY-LOU-1-02 | DRYBRIDGE LOUTH | bar: Su 2 to Week 32 Tu 4; Week 32 Th 6
TO-26-110 kV A1 @ LOU-04 | LOUTH 110 kV A1 | bar: Week 32 Fr 7
TO-26-110 kV B1 @ LOU-04 | LOUTH 110 kV B1 | bar: Week 32 Fr 7
Report covers outages commencing/returning/spanning the period: 03/08/2026 - 16/08/2026
Outages commencing/returning in Week 32
OUTAGE ID | PLANT | Week 32 Mo 3: Week 32; Week 33 Mo 10: Week 33
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
TO-26-CHA-KLN-1-02 | CHARLEVILLE KILLONAN | bar: Su 2 to Week 32 Fr 7
TO-26-DSN-MAY-1-01 | DUNSTOWN MAYNOOTH 1 | bar: Su 2 to Week 32 Fr 7
TO-26-KLT-RGR-1-02 | KILLAPHORT RAGHRA | bar: Su 2 to Week 32 Fr 7
TO-26-KPT-T2001/2-02 | KILLAPHORT T2001/2 | bar: Su 2 to Week 32 Fr 7
TO-26-KLN-KPG-1-02 | KILLONAN KILPADDOGE | bar: Su 2 to Week 32 Fr 7
TO-26-110 kV A1 @ RAF-03 | RAFFEEN 110 kV A1 | bar: Su 2 to Week 32 Fr 7
TO-26-110 kV B1 @ RAF-02 | RAFFEEN 110 kV B1 | bar: Su 2 to Week 32 Fr 7
TO-26-RAF-TBG-1-04 | RAFFEEN TRABEG 1 | bar: Su 2 to Week 32 Fr 7
TO-26-RGR-SH-1-01 | RAGHRA SHANNONBRIDGE | bar: Su 2 to Week 32 Fr 7
TO-26-110 kV A2 @ TBG-02 | TRABEG 110 kV A2 | bar: Su 2 to Week 32 Fr 7
TO-26-110 kV B2 @ TBG-02 | TRABEG 110 kV B2 | bar: Su 2 to Week 32 Fr 7
TO-26-FIN-SHL-1-02 | FINGLAS SHELLYBANKS | bar: Su 2 to Week 32 Su 9
Outages commencing/returning in Week 33
OUTAGE ID | PLANT | Week 32 Mo 3: Week 32; Week 33 Mo 10: Week 33
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
TO-26-110 kV A1/A2 @ LOU-01 | LOUTH 110 kV A1/A2
TO-26-LOU-CAP1-04 | LOUTH CAP1
TO-26-TRI-110SA1-2CB-01 | TRIEN 110SA1-2CB
TO-26-CLH-TRI-1-01 | CLAHANE TRIEN
TO-26-UGL-T131-01 | UGGOOL T131
TO-26-UGL-T132-01 | UGGOOL T132
TO-26-UGL-T134-01 | UGGOOL T134
TO-26-AUG-SK-3-01 | AUGHINISH SEALROCK 3 | bar: Week 33 Fr 14
TO-26-BAL-110SA1-04 | BALTRASNA 110SA1 | bar: Week 33 Fr 14
TO-26-BAL-110SA2-05 | BALTRASNA 110SA2 | bar: Week 33 Fr 14
TO-26-BAL-DEN-1-01 | BALTRASNA DEENES | bar: Week 33 Fr 14
TO-26-BAL-T121-02 | BALTRASNA T121 | bar: Week 33 Fr 14
TO-26-FLA-GIL-1-03 | FLAGFORD GILRA | bar: Week 33 Fr 14
TO-26-GRV-T121-01 | GARVAGH T121 | bar: Week 33 Fr 14
TO-26-GIL-T121-01 | GILRA T121 | bar: Week 33 Fr 14
TO-26-KBY-MAL-1-02 | KILBARRY MALLOW | bar: Week 33 Fr 14
TO-26-SK-T103-01 | SEALROCK T103 | bar: Week 33 Fr 14
TO-26-BGH-110SA1-01 | BOGGERAGH 110SA1 | bar: Week 33 Fr 14 to Week 33 Mo 17
TO-26-BGH-110SA2-01 | BOGGERAGH 110SA2 | bar: Week 33 Fr 14 to Week 33 Mo 17
TO-26-BGH-CLA-1-01 | BOGGERAGH CLASHAVOON | bar: Week 33 Fr 14 to Week 33 Mo 17
TO-26-BGH-T121-01 | BOGGERAGH T121 | bar: Week 33 Fr 14 to Week 33 Mo 17
TO-26-BGH-T132-01 | BOGGERAGH T132 | bar: Week 33 Fr 14 to Week 33 Mo 17
TO-26-BGH-T142-01 | BOGGERAGH T142 | bar: Week 33 Fr 14 to Week 33 Mo 17
TO-26-220 kV A1 @ CDU-06 | CORDUFF 220 kV A1 | bar: Week 33 Fr 14 to Week 33 Mo 17
TO-26-220 kV B1 @ CDU-03 | CORDUFF 220 kV B1 | bar: Week 33 Fr 14 to Week 33 Mo 17
TO-26-CDU-HN-1-01 | CORDUFF HUNTSTOWN | bar: Week 33 Fr 14 to Week 33 Mo 17
TO-26-HN-T2002-01 | HUNTSTOWN T2002 | bar: Week 33 Fr 14 to Week 33 Mo 17
TO-26-220 kV A1 @ INC-02 | INCHICORE 220 kV A1 | bar: Week 33 Fr 14 to Week 33 Mo 17
TO-26-220 kV A2 @ INC-03 | INCHICORE 220 kV A2 | bar: Week 33 Fr 14 to Week 33 Mo 17
TO-26-220 kV B1 @ INC-01 | INCHICORE 220 kV B1 | bar: Week 33 Fr 14 to Week 33 Mo 17
TO-26-220 kV B2 @ INC-03 | INCHICORE 220 kV B2 | bar: Week 33 Fr 14 to Week 33 Mo 17
TO-26-INC-220K1-2-01 | INCHICORE 220K1-2 | bar: Week 33 Fr 14 to Week 33 Mo 17
TO-26-220 kV A1 @ KLN-01 | KILLONAN 220 kV A1 | bar: Week 33 Fr 14 to Week 33 Mo 17
TO-26-220 kV A2 @ KLN-02 | KILLONAN 220 kV A2 | bar: Week 33 Fr 14 to Week 33 Mo 17
TO-26-KLN-220K1-2-01 | KILLONAN 220K1-2 | bar: Week 33 Fr 14 to Week 33 Mo 17
TO-26-KLN-SNG-1-01 | KILLONAN SINGLAND | bar: Week 33 Fr 14 to Week 33 Mo 17
TO-26-110 kV A1 @ MR-02 | MARINA 110 kV A1 | bar: Week 33 Fr 14 to Week 33 Mo 17
TO-26-110 kV A2 @ MR-02 | MARINA 110 kV A2 | bar: Week 33 Fr 14 to Week 33 Mo 17
TO-26-110 kV B1 @ MR-02 | MARINA 110 kV B1 | bar: Week 33 Fr 14 to Week 33 Mo 17
TO-26-110 kV B2 @ MR-02 | MARINA 110 kV B2 | bar: Week 33 Fr 14 to Week 33 Mo 17
TO-26-MR-110K1-2-02 | MARINA 110K1-2 | bar: Week 33 Fr 14 to Week 33 Mo 17
TO-26-NEW-T141-04 | NEWBRIDGE T141 | bar: Week 33 Fr 14 to Week 33 Mo 17
TO-26-110 kV A2 @ RAF-03 | RAFFEEN 110 kV A2 | bar: Week 33 Fr 14 to Week 33 Mo 17
TO-26-110 kV B2 @ RAF-05 | RAFFEEN 110 kV B2 | bar: Week 33 Fr 14 to Week 33 Mo 17
TO-26-RAF-CAP2-02 | RAFFEEN CAP2 | bar: Week 33 Fr 14 to Week 33 Mo 17
TO-26-110 kV B1/B2 @ LOU-01 | LOUTH 110 kV B1/B2
TO-26-CKG-110K2-02 | CORKAGH 110K2
Report covers outages commencing/returning/spanning the period: 03/08/2026 - 16/08/2026
Outages commencing/returning in Week 33
OUTAGE ID | PLANT | Week 32 Mo 3: Week 32; Week 33 Mo 10: Week 33
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
TO-26-CKG-110SA1-2CB-05 | CORKAGH 110SA1-2CB
TO-26-CKG-110SB1-2CB-05 | CORKAGH 110SB1-2CB
TO-26-KIN-T101-02 | KINNEGAD T101
TO-26-CLG-T123-01 | CLOGHRAN T123
TO-26-220 kV A1 @ CSH-02 | CASHLA 220 kV A1
TO-26-220 kV B1 @ CSH-02 | CASHLA 220 kV B1
TO-26-CSH-FLA-1-03 | CASHLA FLAGFORD
TO-26-220 kV A1 @ FLA-02 | FLAGFORD 220 kV A1
TO-26-220 kV B1 @ FLA-01 | FLAGFORD 220 kV B1
TO-26-KIN-T102-05 | KINNEGAD T102
TO-26-CSH-SAL-1-01 | CASHLA SALTHILL
TO-26-DDK-LOU-1-01 | DUNDALK LOUTH
TO-26-CBT-KSG-1-02 | CASTLEBAGOT KISHOGE
TO-26-220 kV A1 @ LOU-01 | LOUTH 220 kV A1
TO-26-220 kV B1 @ LOU-01 | LOUTH 220 kV B1
TO-26-LOU-AT2-02 | LOUTH AT2
Outages spanning Weeks 32-33
OUTAGE ID | PLANT | Week 32 Mo 3: Week 32; Week 33 Mo 10: Week 33
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
TO-26-AA GIS-T103-02 | ARDNACRUSHA GIS T103
TO-26-ATH-M/CAP1-03 | ATHLONE M/CAP1
TO-26-ATY-PLS-1-01 | ATHY PORTLAOISE
TO-26-CD-KBY-1-03 | CARRIGADROHID KILBARRY
TO-26-CBR-SVC-02 | CASTLEBAR SVC
TO-26-CBR-SVC-01
TO-26-DND-T121-01 | DARNDALE T121
TO-26-DER-TSB-1-01 | DERRYIRON THORNSBERRY
TO-26-DOO-T141-01 | DOON T141
TO-26-DRY-LOU-1-01 | DRYBRIDGE LOUTH
TO-26-DRY-T141-01 | DRYBRIDGE T141
TO-26-DSN-400K1-2-04 | DUNSTOWN 400K1-2
TO-26-DSN-MP GIS-1-10 | DUNSTOWN MONEYPOINT GIS
TO-26-DSN-T4201-03 | DUNSTOWN T4201
TO-26-DSN-T4202-01 | DUNSTOWN T4202
TO-26-FIN-FIN GIS-2-01 | FINGLAS FINGLAS GIS 2
TO-26-FIN-T2104-01 | FINGLAS T2104
TO-26-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-26-GI GIS-220SA1-2CB-02 | GREAT ISLAND GIS 220SA1-2CB
TO-26-GI-T141-01 | GREAT ISLAND T141
TO-26-ISH-T2001-01 | IRISHTOWN T2001
TO-26-KYT-T237-03 | KELLYSTOWN T237
TO-26-110 kV A1 @ KBY-02 | KILBARRY 110 kV A1
TO-26-KBY-KRA-2-03 | KILBARRY KNOCKRAHA 2
TO-26-KKY-CAP2-03 | KILKENNY CAP2
TO-26-220 kV A4 @ KRA-01 | KNOCKRAHA 220 kV A4
TO-26-220 kV B4 @ KRA-01 | KNOCKRAHA 220 kV B4
TO-26-KRA-220K4-01 | KNOCKRAHA 220K4
TO-26-KRA-220SA2-4CB-03 | KNOCKRAHA 220SA2-4CB
TO-26-KRA-220SB2-4CB-03 | KNOCKRAHA 220SB2-4CB
TO-26-KRA-LYT-1-01 | KNOCKRAHA LYSAGHTSTOWN
TO-26-LET-SVC-02 | LETTERKENNY SVC
TO-26-110 kV A1 @ LOU-01 | LOUTH 110 kV A1
TO-26-110 kV B1 @ LOU-01 | LOUTH 110 kV B1
TO-26-MR-T107-01 | MARINA T107
TO-26-MAY-TEN-1-05 | MAYNOOTH TIMAHOE
TO-26-NAV-M/CAP1-01 | NAVAN M/CAP1
TO-26-PB-R2001-02 | POOLBEG R2001
TO-26-PB-R2001-03
TO-26-110 kV A2 @ RAF-01 | RAFFEEN 110 kV A2
TO-26-110 kV B2 @ RAF-01 | RAFFEEN 110 kV B2
TO-26-TB-T2003-01 | TARBERT T2003
Report covers outages commencing/returning/spanning the period: 03/08/2026 - 16/08/2026
Outages spanning Weeks 32-33
OUTAGE ID | PLANT | Week 32 Mo 3: Week 32; Week 33 Mo 10: Week 33
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
TO-26-TAW-T1/T2-01 | TAWNAGHMORE T1/T2
TO-26-TAW-T3-02 | TAWNAGHMORE T3
TO-26-TRL-CAP2-01 | TRALEE CAP2
TO-26-WEX-CAP4-06 | WEXFORD CAP4