## Wks 34 - 35
Report covers outages commencing/returning/spanning the period: 17/08/2026 - 30/08/2026
Outages commencing/returning in Week 34
OUTAGE ID | PLANT |  | Week 34 | [6 empty] | Week 35
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
TO-26-110 kV B1 @ KLS-01 | KELLIS 110 kV B1
TO-26-110 kV B2 @ KLS-06 | KELLIS 110 kV B2
TO-26-KLS-KKY-1-06 | KELLIS KILKENNY
TO-26-220 kV B3 @ KYT-02 | KELLYSTOWN 220 kV B3
TO-26-KYT-220K3-02 | KELLYSTOWN 220K3
TO-26-KYT-220SB1-3CB-01 | KELLYSTOWN 220SB1-3CB
TO-26-KYT-MAY-1-03 | KELLYSTOWN MAYNOOTH
TO-26-KYT-T237-04 | KELLYSTOWN T237
TO-26-BVK-COT-1-01 | BALLYVOUSKILL COOMATAGGART
TO-26-COT-110SA1-01 | COOMATAGGART 110SA1
TO-26-COT-110SA2-01 | COOMATAGGART 110SA2
TO-26-COT-FILTER1-01 | COOMATAGGART FILTER1
TO-26-COT-T132-01 | COOMATAGGART T132
TO-26-COT-T141-01 | COOMATAGGART T141
TO-26-IKE,T-THU-1-05 | IKERRIN tee THURLES
TO-26-220 kV A1/A2 @ PB-02 | POOLBEG 220 kV A1/A2
TO-26-THU-110SA1-2CB-02 | THURLES 110SA1-2CB
TO-26-THU-STATCOM-03 | THURLES STATCOM
TO-26-THU-T142-06 | THURLES T142
TO-26-WEX-CAP4-02 | WEXFORD CAP4
TO-26-DCL-T136-01 | DRUMCAMILL T136
TO-26-BAN-110SA1-02 | BANDON 110SA1
TO-26-BAN-110SA2-02 | BANDON 110SA2
TO-26-BAN-BRI-1-02 | BANDON BRINNY 1
TO-26-BAN-CAP1-02 | BANDON CAP1
TO-26-BAN-DMY-1-03 | BANDON DUNMANWAY
TO-26-BAN-T101-01 | BANDON T101
TO-26-BAN-T141-02 | BANDON T141
TO-26-BRI-T101-01 | BRINNY T101
TO-26-KSG-T121-01 | KISHOGE T121
TO-26-110 kV A2 @ ARK-01 | ARKLOW 110 kV A2
TO-26-110 kV B2 @ ARK-01 | ARKLOW 110 kV B2
TO-26-220 kV A2 @ ARK-02 | ARKLOW 220 kV A2
TO-26-220 kV B2 @ ARK-02 | ARKLOW 220 kV B2
TO-26-ARK-T2102-01 | ARKLOW T2102
TO-26-CD-MAC-1-02 | CARRIGADROHID MACROOM
TO-26-CD-T103-02 | CARRIGADROHID T103
TO-26-KNY-SAL-1-01 | KNOCKRANNY SALTHILL
TO-26-220 kV A2 @ LOU-09 | LOUTH 220 kV A2
TO-26-220 kV B2 @ LOU-09 | LOUTH 220 kV B2
TO-26-220 kV A1 @ MAY-04 | MAYNOOTH 220 kV A1
TO-26-220 kV B1 @ MAY-04 | MAYNOOTH 220 kV B1
TO-26-MAY-T2102-03 | MAYNOOTH T2102
TO-26-RAF-TBG-2-05 | RAFFEEN TRABEG 2
TO-26-SAL-110SA1-2CB-01 | SALTHILL 110SA1-2CB
TO-26-SAL-T102-01 | SALTHILL T102
TO-26-GOL-T101-02 | GOLAGH T101
TO-26-GOL,T-CLO-1-02 | GOLAGH tee CLOGHER
TO-26-GOL,T-GOL-1-01 | GOLAGH tee GOLAGH
TO-26-GOL,T-LET-1-01 | GOLAGH tee LETTERKENNY
TO-26-LSN-110SA1-2-03 | LISHEEN 110SA1-2
TO-26-LSN-110SA2-4-03 | LISHEEN 110SA2-4
TO-26-LSN-T122-03 | LISHEEN T122
TO-26-LSN-T131-03 | LISHEEN T131
TO-26-LSN-T142-03 | LISHEEN T142
TO-26-LSN-THU-1-03 | LISHEEN THURLES
TO-26-110 kV A1 @ PLS-02 | PORTLAOISE 110 kV A1
TO-26-110 kV B1 @ PLS-02 | PORTLAOISE 110 kV B1
TO-26-CLW-KLS-1-03 | CARLOW KELLIS 1
TO-26-110 kV A1 @ KLS-01 | KELLIS 110 kV A1
TO-26-110 kV B1 @ KLS-02 | KELLIS 110 kV B1
Report covers outages commencing/returning/spanning the period: 17/08/2026 - 30/08/2026
Outages commencing/returning in Week 34
OUTAGE ID | PLANT | Week 34 Mo 17: Week 34; Week 35 Mo 24: Week 35
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
TO-26-KYT-T237-03 | KELLYSTOWN T237 | bar: Su 16 to Week 34 Mo 17
TO-26-220 kV A1 @ KRA-04 | KNOCKRAHA 220 kV A1 | bar: Week 34 Tu 18 to Week 35 Fr 28
TO-26-220 kV B1 @ KRA-04 | KNOCKRAHA 220 kV B1 | bar: Week 34 Tu 18 to Week 35 Fr 28
TO-26-KRA-220K1-03 | KNOCKRAHA 220K1 | bar: Week 34 Tu 18 to Week 35 Fr 28
TO-26-KRA-220SA1-2CB-07 | KNOCKRAHA 220SA1-2CB | bar: Week 34 Tu 18 to Week 35 Fr 28
TO-26-KRA-220SB1-2CB-07 | KNOCKRAHA 220SB1-2CB | bar: Week 34 Tu 18 to Week 35 Fr 28
TO-26-CLW-KLS-2-01 | CARLOW KELLIS 2 | bar: Week 34 Tu 18 to Week 35 Mo 31
TO-26-CBT-INC-2-02 | CASTLEBAGOT INCHICORE 2 | bar: Su 16 to Week 34 Tu 18
TO-26-CDU-HN-1-01 | CORDUFF HUNTSTOWN | bar: Su 16 to Week 34 Tu 18
TO-26-HN-T2002-01 | HUNTSTOWN T2002 | bar: Su 16 to Week 34 Tu 18
TO-26-INC-220K4-6-03 | INCHICORE 220K4-6 | bar: Su 16 to Week 34 Tu 18
TO-26-INC-T2106-02 | INCHICORE T2106 | bar: Su 16 to Week 34 Tu 18
TO-26-DOO-CAP1-01 | DOON CAP1 | bar: Week 34 We 19
TO-26-DJG-KPG-1-01 | DROMBEG KILPADDOGE | bar: Week 34 We 19 to Week 34 Th 20
TO-26-TB-T102-01 | TARBERT T102 | bar: Week 34 We 19 to Week 34 Th 20
TO-26-TRI-T143-01 | TRIEN T143 | bar: Week 34 We 19 to Week 34 Th 20
TO-26-CDY-GRV-1-01 | CORDERRY GARVAGH | bar: Su 16 to Week 34 We 19
TO-26-DOO-T141-01 | DOON T141 | bar: Su 16 to Week 34 We 19
TO-26-GRV-110K1-01 | GARVAGH 110K1 | bar: Su 16 to Week 34 We 19
TO-26-GRV-T121-01 | GARVAGH T121 | bar: Su 16 to Week 34 We 19
TO-26-GRV-T141-01 | GARVAGH T141 | bar: Su 16 to Week 34 We 19
TO-26-BGH-110SA1-01 | BOGGERAGH 110SA1 | bar: Su 16 to Week 34 Fr 21
TO-26-BGH-110SA2-01 | BOGGERAGH 110SA2 | bar: Su 16 to Week 34 Fr 21
TO-26-BGH-CLA-1-01 | BOGGERAGH CLASHAVOON | bar: Su 16 to Week 34 Fr 21
TO-26-BGH-T121-01 | BOGGERAGH T121 | bar: Su 16 to Week 34 Fr 21
TO-26-BGH-T132-01 | BOGGERAGH T132 | bar: Su 16 to Week 34 Fr 21
TO-26-BGH-T142-01 | BOGGERAGH T142 | bar: Su 16 to Week 34 Fr 21
TO-26-220 kV A1 @ CLE-01 | CLONEE 220 kV A1 | bar: Su 16 to Week 34 Fr 21
TO-26-220 kV A2 @ CLE-02 | CLONEE 220 kV A2 | bar: Su 16 to Week 34 Fr 21
TO-26-220 kV B1 @ CLE-01 | CLONEE 220 kV B1 | bar: Su 16 to Week 34 Fr 21
TO-26-220 kV B2 @ CLE-02 | CLONEE 220 kV B2 | bar: Su 16 to Week 34 Fr 21
TO-26-CLE-220K1-01 | CLONEE 220K1 | bar: Su 16 to Week 34 Fr 21
TO-26-CLE-220K2-03 | CLONEE 220K2 | bar: Su 16 to Week 34 Fr 21
TO-26-CLE-220SA1-2CB-01 | CLONEE 220SA1-2CB | bar: Su 16 to Week 34 Fr 21
TO-26-CLE-220SB1-2CB-01 | CLONEE 220SB1-2CB | bar: Su 16 to Week 34 Fr 21
TO-26-110 kV A1 @ MR-02 | MARINA 110 kV A1 | bar: Su 16 to Week 34 Fr 21
TO-26-110 kV A2 @ MR-02 | MARINA 110 kV A2 | bar: Su 16 to Week 34 Fr 21
TO-26-110 kV B1 @ MR-02 | MARINA 110 kV B1 | bar: Su 16 to Week 34 Fr 21
TO-26-110 kV B2 @ MR-02 | MARINA 110 kV B2 | bar: Su 16 to Week 34 Fr 21
TO-26-MR-110K1-2-02 | MARINA 110K1-2 | bar: Su 16 to Week 34 Fr 21
TO-26-110 kV A2 @ RAF-03 | RAFFEEN 110 kV A2 | bar: Su 16 to Week 34 Fr 21
TO-26-110 kV B2 @ RAF-05 | RAFFEEN 110 kV B2 | bar: Su 16 to Week 34 Fr 21
TO-26-RAF-CAP2-02 | RAFFEEN CAP2 | bar: Su 16 to Week 34 Fr 21
TO-26-TSB-110SA1-03 | THORNSBERRY 110SA1 | bar: Su 16 to Week 34 Fr 21
TO-26-TSB-110SA2-04 | THORNSBERRY 110SA2 | bar: Su 16 to Week 34 Fr 21
TO-26-TSB-T142-05 | THORNSBERRY T142 | bar: Su 16 to Week 34 Fr 21
Outages commencing/returning in Week 35
OUTAGE ID | PLANT | Week 34 Mo 17: Week 34; Week 35 Mo 24: Week 35
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
TO-26-DER-110SA1-2CB-01 | DERRYIRON 110SA1-2CB | bar: Week 35 Mo 24
TO-26-DER-T1/T2-01 | DERRYIRON RHODE T1/T2 | bar: Week 35 Mo 24
TO-26-DER-TEN-1-02 | DERRYIRON TIMAHOE | bar: Week 35 Mo 24
TO-26-CGL-T122-01 | COOMAGEARLAHY T122 | bar: Week 35 Mo 24 to Week 35 Th 27
TO-26-BK-SKY-1-01 | BELLACORICK SRAHNAKILLY | bar: Week 35 Mo 24 to Week 35 Fr 28
TO-26-SKY-110SA1-01 | SRAHNAKILLY 110SA1 | bar: Week 35 Mo 24 to Week 35 Fr 28
TO-26-SKY-110SA2-01 | SRAHNAKILLY 110SA2 | bar: Week 35 Mo 24 to Week 35 Fr 28
TO-26-SKY-T131-02 | SRAHNAKILLY T131 | bar: Week 35 Mo 24 to Week 35 Fr 28
TO-26-SKY-T132-01 | SRAHNAKILLY T132 | bar: Week 35 Mo 24 to Week 35 Fr 28
TO-26-THU-CAP1-01 | THURLES CAP1 | bar: Week 35 Mo 24 to Week 35 Fr 28
Report covers outages commencing/returning/spanning the period: 17/08/2026 - 30/08/2026
Outages commencing/returning in Week 35
OUTAGE ID | PLANT | Week 34 Mo 17: Week 34; Week 35 Mo 24: Week 35
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
TO-26-WEX-CAP2-02 | WEXFORD CAP2 | bar: Week 35 Mo 24 to Week 35 Th 27
TO-26-AGL-SH-1-02 | AGANNYGAL SHANNONBRIDGE | bar: Week 35 Mo 24 to Week 35 Th 27; Week 35 Sa 29 to Week 35 Mo 31
TO-26-220 kV A1 @ CSH-01 | CASHLA 220 kV A1 | bar: Week 35 Mo 24 to Week 35 Th 27; Week 35 Sa 29 to Week 35 Mo 31
TO-26-220 kV A2 @ CSH-02 | CASHLA 220 kV A2 | bar: Week 35 Mo 24 to Week 35 Th 27; Week 35 Sa 29 to Week 35 Mo 31
TO-26-220 kV B1 @ CSH-01 | CASHLA 220 kV B1 | bar: Week 35 Mo 24 to Week 35 Th 27; Week 35 Sa 29 to Week 35 Mo 31
TO-26-220 kV B2 @ CSH-03 | CASHLA 220 kV B2 | bar: Week 35 Mo 24 to Week 35 Th 27; Week 35 Sa 29 to Week 35 Mo 31
TO-26-CSH-220K1-2-01 | CASHLA 220K1-2 | bar: Week 35 Mo 24 to Week 35 Th 27; Week 35 Sa 29 to Week 35 Mo 31
TO-26-110 kV A2 @ SH-05 | SHANNONBRIDGE 110 kV A2 | bar: Week 35 Mo 24 to Week 35 Th 27; Week 35 Sa 29 to Week 35 Mo 31
TO-26-110 kV B2 @ SH-05 | SHANNONBRIDGE 110 kV B2 | bar: Week 35 Mo 24 to Week 35 Th 27; Week 35 Sa 29 to Week 35 Mo 31
TO-26-DER-TSB-1-01 | DERRYIRON THORNSBERRY | bar: Su 16 to Week 35 Mo 24
TO-26-MLN-110SA1-2CB-02 | MULLAGHARLIN 110SA1-2CB | bar: Week 35 Tu 25
TO-26-MLN-T121-01 | MULLAGHARLIN T121 | bar: Week 35 Tu 25
TO-26-BRA-NEW-1-01 | BRACKLONE NEWBRIDGE | bar: Week 35 Tu 25 to Week 35 Th 27
TO-26-CUS-NEW-1-05 | CUSHALING NEWBRIDGE | bar: Week 35 Tu 25 to Week 35 Th 27
TO-26-MLN-T124-02 | MULLAGHARLIN T124 | bar: Week 35 Tu 25 to Week 35 Th 27
TO-26-NEW-110SA1-04 | NEWBRIDGE 110SA1 | bar: Week 35 Tu 25 to Week 35 Th 27
TO-26-NEW-110SA2-05 | NEWBRIDGE 110SA2 | bar: Week 35 Tu 25 to Week 35 Th 27
TO-26-CTN-KLN-1-01 | CAUTEEN KILLONAN | bar: Week 35 Tu 25 to Week 35 Th 27; Week 35 Sa 29 to Week 35 Mo 31
TO-26-LOU-MLN-1-02 | LOUTH MULLAGHARLIN | bar: Week 35 We 26 to Week 35 Th 27
TO-26-KRA-LYT-1-01 | KNOCKRAHA LYSAGHTSTOWN | bar: Su 16 to Week 35 We 26
TO-26-CSH-GAL GIS-1-01 | CASHLA GALWAY GIS 1 | bar: Week 35 Th 27
TO-26-CSH-SAL-1-05 | CASHLA SALTHILL | bar: Week 35 Th 27
TO-26-KTL-T142-01 | KILTEEL T142 | bar: Week 35 Th 27
TO-26-CSH-GAL GIS-1-04 | CASHLA GALWAY GIS 1 | bar: Week 35 Th 27; Week 35 Sa 29 to Week 35 Mo 31
TO-26-BLK-T142-03 | BLAKE T142 | bar: Week 35 Sa 29 to Week 35 Su 30
TO-26-BLK,T-BLK-1-04 | BLAKE tee BLAKE | bar: Week 35 Sa 29 to Week 35 Su 30
TO-26-BLK,T-MAY-1-05 | BLAKE tee MAYNOOTH | bar: Week 35 Sa 29 to Week 35 Su 30
TO-26-BLK,T-NEW-1-05 | BLAKE tee NEWBRIDGE | bar: Week 35 Sa 29 to Week 35 Su 30
TO-26-AA GIS-T101-03 | ARDNACRUSHA GIS T101 | bar: Su 16 to Week 35 Th 27
TO-26-CSH-SAL-1-01 | CASHLA SALTHILL | bar: Su 16 to Week 35 Th 27
Outages spanning Weeks 34-35
OUTAGE ID | PLANT | Week 34 Mo 17: Week 34; Week 35 Mo 24: Week 35
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
TO-26-AA GIS-T103-02 | ARDNACRUSHA GIS T103
TO-26-ATH-M/CAP1-03 | ATHLONE M/CAP1
TO-26-ATY-PLS-1-01 | ATHY PORTLAOISE
TO-26-CD-KBY-1-03 | CARRIGADROHID KILBARRY
TO-26-CBR-SVC-02 | CASTLEBAR SVC
TO-26-CBR-SVC-01
TO-26-CKN-GRO-1-01 | CLONKEEN GARROW
TO-26-DND-T121-01 | DARNDALE T121
TO-26-DRY-LOU-1-01 | DRYBRIDGE LOUTH
TO-26-DRY-T141-01 | DRYBRIDGE T141
TO-26-DSN-400K1-2-04 | DUNSTOWN 400K1-2
TO-26-DSN-MP GIS-1-02 | DUNSTOWN MONEYPOINT GIS
TO-26-DSN-MP GIS-1-10
TO-26-DSN-T4201-03 | DUNSTOWN T4201
TO-26-DSN-T4202-01 | DUNSTOWN T4202
TO-26-FIN-FIN GIS-2-01 | FINGLAS FINGLAS GIS 2
TO-26-FIN-SHL-1-02 | FINGLAS SHELLYBANKS
TO-26-FIN-T2104-01 | FINGLAS T2104
TO-26-220 kV A2 @ FLA-06 | FLAGFORD 220 kV A2
TO-26-220 kV B2 @ FLA-06 | FLAGFORD 220 kV B2
TO-26-FLA-LOU-1-01 | FLAGFORD LOUTH
TO-26-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-26-GI GIS-220SA1-2CB-02 | GREAT ISLAND GIS 220SA1-2CB
TO-26-GI-T141-01 | GREAT ISLAND T141
TO-26-INC-PB-2-01 | INCHICORE POOLBEG 2
TO-26-ISH-T2001-01 | IRISHTOWN T2001
Report covers outages commencing/returning/spanning the period: 17/08/2026 - 30/08/2026
Outages spanning Weeks 34-35
OUTAGE ID | PLANT | Week 34 Mo 17: Week 34; Week 35 Mo 24: Week 35
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
TO-26-110 kV A1 @ KBY-02 | KILBARRY 110 kV A1
TO-26-KBY-KRA-2-03 | KILBARRY KNOCKRAHA 2
TO-26-KKY-CAP2-03 | KILKENNY CAP2
TO-26-KLN-SNG-1-01 | KILLONAN SINGLAND
TO-26-220 kV A4 @ KRA-01 | KNOCKRAHA 220 kV A4
TO-26-220 kV B4 @ KRA-01 | KNOCKRAHA 220 kV B4
TO-26-KRA-220K4-01 | KNOCKRAHA 220K4
TO-26-KRA-220SA2-4CB-03 | KNOCKRAHA 220SA2-4CB
TO-26-KRA-220SB2-4CB-03 | KNOCKRAHA 220SB2-4CB
TO-26-LET-SVC-02 | LETTERKENNY SVC
TO-26-110 kV A1 @ LOU-01 | LOUTH 110 kV A1
TO-26-110 kV B1 @ LOU-01 | LOUTH 110 kV B1
TO-26-MR-T107-01 | MARINA T107
TO-26-MAY-TEN-1-05 | MAYNOOTH TIMAHOE
TO-26-MP GIS-PRO-1-02 | MONEYPOINT GIS PROSPECT
TO-26-NAV-M/CAP1-01 | NAVAN M/CAP1
TO-26-NEW-T141-04 | NEWBRIDGE T141
TO-26-PB-R2001-03 | POOLBEG R2001
TO-26-PB-R2001-02
TO-26-110 kV A2 @ RAF-01 | RAFFEEN 110 kV A2
TO-26-110 kV B2 @ RAF-01 | RAFFEEN 110 kV B2
TO-26-SHL-D1/CB1-01 | SHELLYBANKS D1/CB1
TO-26-SHL-D1/CB2-06 | SHELLYBANKS D1/CB2
TO-26-TB-T2003-01 | TARBERT T2003
TO-26-TAW-T1/T2-01 | TAWNAGHMORE T1/T2
TO-26-TAW-T3-02 | TAWNAGHMORE T3
TO-26-TRL-CAP2-01 | TRALEE CAP2
TO-26-WEX-CAP4-06 | WEXFORD CAP4