## Wks 36 - 37
Report covers outages commencing/returning/spanning the period: 31/08/2026 - 13/09/2026
Outages commencing/returning in Week 36
OUTAGE ID | PLANT |  | Week 36 | [6 empty] | Week 37
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
TO-26-220 kV A2 @ AD-03 | AGHADA 220 kV A2 | bar: Week 36 Mo 31 to Week 36 Fr 4
TO-26-AD-SA1-2CB-04 | AGHADA 220SA1-2CB | bar: Week 36 Mo 31 to Week 36 Fr 4
TO-26-CLG-T124-01 | CLOGHRAN T124 | bar: Week 36 Mo 31 to Week 36 Fr 4
TO-26-DMY-MAC-1-05 | DUNMANWAY MACROOM | bar: Week 36 Mo 31 to Week 36 Fr 4
TO-26-220 kV A1 @ ISH-02 | IRISHTOWN 220 kV A1 | bar: Week 36 Mo 31 to Week 36 Fr 4
TO-26-220 kV B1 @ ISH-02 | IRISHTOWN 220 kV B1 | bar: Week 36 Mo 31 to Week 36 Fr 4
TO-26-ISH-220K1-2-03 | IRISHTOWN 220K1-2 | bar: Week 36 Mo 31 to Week 36 Fr 4
TO-26-WHI-CKB-T102-01 | WHITEGATE CKB-T102 | bar: Week 36 Mo 31 to Week 36 Fr 4
TO-26-MUL-CAP1-01 | MULLINGAR CAP1 | bar: Week 36 Mo 31 to Week 37 Th 10
TO-26-110 kV A1 @ LLA-02 | LENALEA 110 kV A1 | bar: Week 36 Mo 31 to Week 37 Fr 11
TO-26-LLA-110K1-03 | LENALEA 110K1 | bar: Week 36 Mo 31 to Week 37 Fr 11
TO-26-220 kV A2 @ WOO-01 | WOODLAND 220 kV A2 | bar: Week 36 Mo 31 to Week 37 Fr 11
TO-26-AD-KRA-1-03 | AGHADA KNOCKRAHA 1
TO-26-AD-KRA-2-03 | AGHADA KNOCKRAHA 2
TO-26-DOO-CAP1-04 | DOON CAP1
TO-26-MAY-TH-1-04 | MAYNOOTH TURLOUGH HILL
TO-26-WOO-220K1-2-01 | WOODLAND 220K1-2
TO-26-DER-TSB-1-01 | DERRYIRON THORNSBERRY | bar: Su 30 to Week 36 Mo 31
TO-26-MLN-110SA1-2CB-02 | MULLAGHARLIN 110SA1-2CB | bar: Week 36 Tu 1
TO-26-MLN-T121-01 | MULLAGHARLIN T121 | bar: Week 36 Tu 1
TO-26-AUN-T123-02 | AUNGIERSTOWN T123 | bar: Week 36 Tu 1 to Week 36 We 2
TO-26-FLA-LOU-1-02 | FLAGFORD LOUTH | bar: Week 36 Tu 1 to Week 37 Fr 11
TO-26-220 kV A2 @ LOU-09 | LOUTH 220 kV A2 | bar: Week 36 Tu 1 to Week 37 Fr 11
TO-26-220 kV B2 @ LOU-09 | LOUTH 220 kV B2 | bar: Week 36 Tu 1 to Week 37 Fr 11
TO-26-LOU-AT1-02 | LOUTH AT1 | bar: Week 36 Tu 1 to Week 37 Fr 11
TO-26-LOU-AT3-02 | LOUTH AT3 | bar: Week 36 Tu 1 to Week 37 Fr 11
TO-26-LOU-TAN-1-01 | LOUTH TANDRAGEE 1 | bar: Week 36 Tu 1 to Week 37 Fr 11
TO-26-220 kV A1 @ TB-02 | TARBERT 220 kV A1 | bar: Week 36 Tu 1 to Week 37 Mo 14
TO-26-220 kV B1 @ TB-02 | TARBERT 220 kV B1 | bar: Week 36 Tu 1 to Week 37 Mo 14
TO-26-CBT-T2103-02 | CASTLEBAGOT T2103 | bar: Week 36 We 2
TO-26-DER-T132-03 | DERRYIRON T132 | bar: Week 36 We 2
TO-26-LOU-MLN-1-02 | LOUTH MULLAGHARLIN | bar: Week 36 We 2 to Week 36 Fr 4
TO-26-MLN-T124-02 | MULLAGHARLIN T124 | bar: Week 36 We 2 to Week 36 Fr 4
TO-26-CSH-GAL GIS-1-04 | CASHLA GALWAY GIS 1 | bar: Su 30 to Week 36 We 2
TO-26-110 kV A2 @ RAF-01 | RAFFEEN 110 kV A2 | bar: Su 30 to Week 36 We 2
TO-26-110 kV B2 @ RAF-01 | RAFFEEN 110 kV B2 | bar: Su 30 to Week 36 We 2
TO-26-CSH-GAL GIS-4-03 | CASHLA GALWAY GIS 4 | bar: Week 36 Th 3
TO-26-LA-T141-01 | LANESBORO T141 | bar: Week 36 Th 3 to Week 36 Fr 4
TO-26-WOO-T4202-01 | WOODLAND T4202 | bar: Week 36 Th 3 to Week 36 Fr 4
TO-26-AD-T2011/12-01 | AGHADA T2011/12 | bar: Week 36 Th 3 to Week 37 Mo 14
TO-26-GAL GIS-T142-01 | GALWAY GIS T142 | bar: Week 36 Fr 4
TO-26-CKN-GRO-1-01 | CLONKEEN GARROW | bar: Su 30 to Week 36 Fr 4
TO-26-GOL-T101-02 | GOLAGH T101 | bar: Su 30 to Week 36 Fr 4
TO-26-GOL,T-CLO-1-02 | GOLAGH tee CLOGHER | bar: Su 30 to Week 36 Fr 4
TO-26-GOL,T-GOL-1-01 | GOLAGH tee GOLAGH | bar: Su 30 to Week 36 Fr 4
TO-26-GOL,T-LET-1-01 | GOLAGH tee LETTERKENNY | bar: Su 30 to Week 36 Fr 4
TO-26-SHL-D1/CB1-01 | SHELLYBANKS D1/CB1 | bar: Su 30 to Week 36 Fr 4
TO-26-SHL-D1/CB2-06 | SHELLYBANKS D1/CB2 | bar: Su 30 to Week 36 Fr 4
TO-26-ISH-SHL-1-03 | IRISHTOWN SHELLYBANKS | bar: Week 36 Sa 5
TO-26-ISH-T2001-01 | IRISHTOWN T2001 | bar: Su 30 to Week 36 Sa 5
Outages commencing/returning in Week 37
OUTAGE ID | PLANT | Week 36 Mo 31: Week 36; Week 37 Mo 7: Week 37
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
TO-26-AUG-CFM-2-03 | AUGHINISH CASTLEFARM 2 | bar: Week 37 Mo 7; Week 37 Th 10 to Week 37 Fr 11
TO-26-CFM-T102-02 | CASTLEFARM T102 | bar: Week 37 Mo 7; Week 37 Th 10 to Week 37 Fr 11
TO-26-110 kV A2 @ CLG-03 | CLOGHRAN 110 kV A2 | bar: Week 37 Mo 7; Week 37 Th 10 to Week 37 Fr 11
TO-26-110 kV B2 @ CLG-03 | CLOGHRAN 110 kV B2 | bar: Week 37 Mo 7; Week 37 Th 10 to Week 37 Fr 11
TO-26-CLG-110K2-06 | CLOGHRAN 110K2 | bar: Week 37 Mo 7; Week 37 Th 10 to Week 37 Fr 11
Report covers outages commencing/returning/spanning the period: 31/08/2026 - 13/09/2026
Outages commencing/returning in Week 37
OUTAGE ID | PLANT | Week 36 Mo 31: Week 36; Week 37 Mo 7: Week 37
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
TO-26-CLG-110SA1-2CB-04 | CLOGHRAN 110SA1-2CB | bar: Week 37 Mo 7; Week 37 Th 10 to Week 37 Fr 11
TO-26-CLG-110SB1-2CB-04 | CLOGHRAN 110SB1-2CB | bar: Week 37 Mo 7; Week 37 Th 10 to Week 37 Fr 11
TO-26-CLG-T126-01 | CLOGHRAN T126 | bar: Week 37 Mo 7; Week 37 Th 10 to Week 37 Fr 11
TO-26-WHI-CKB-T101-02 | WHITEGATE CKB-T101 | bar: Week 37 Mo 7; Week 37 Th 10 to Week 37 Fr 11
TO-26-BDA-T101-01 | BARODA T101 | bar: Week 37 Mo 7; Week 37 Th 10 to Week 37 Mo 14
TO-26-220kV A2 @ BRT-02 | BRACETOWN 220 kV A2 | bar: Week 37 Mo 7; Week 37 Th 10 to Week 37 Mo 14
TO-26-220kV B2 @ BRT-02 | BRACETOWN 220 kV B2 | bar: Week 37 Mo 7; Week 37 Th 10 to Week 37 Mo 14
TO-26-BRT-220K2-02 | BRACETOWN 220K2 | bar: Week 37 Mo 7; Week 37 Th 10 to Week 37 Mo 14
TO-26-BRT-110SA1-2CB-01 | BRACETOWN 220SA1-2CB | bar: Week 37 Mo 7; Week 37 Th 10 to Week 37 Mo 14
TO-26-BRT-110SB1-2CB-01 | BRACETOWN 220SB1-2CB | bar: Week 37 Mo 7; Week 37 Th 10 to Week 37 Mo 14
TO-26-CSH-SAL-1-01 | CASHLA SALTHILL | bar: Week 37 Mo 7; Week 37 Th 10 to Week 37 Mo 14
TO-26-CF-SRA-1-04 | CATHALEENS FALL SRANANAGH 1 | bar: Week 37 Mo 7; Week 37 Th 10 to Week 37 Mo 14
TO-26-CLO-110K1-2-01 | CLOGHER 110K1-2
TO-26-SLB-110K2-01 | SLIABH BAWN 110K2
TO-26-220 kV B1/B2 @ AD-01 | AGHADA 220 kV B1/B2 | bar: Week 37 Th 10
TO-26-AD-220K1-02 | AGHADA 220K1 | bar: Week 37 Th 10
TO-26-AD-SB1-2CB-02 | AGHADA 220SB1-2CB | bar: Week 37 Th 10
TO-26-CSH-CAP2-02 | CASHLA CAP2 | bar: Week 37 Th 10
TO-26-DJG-TRL-1-06 | DROMBEG TRALEE | bar: Week 37 Th 10
TO-26-OUG,T-TRL-1-03 | OUGHTRAGH tee TRALEE | bar: Week 37 Th 10
TO-26-TRL-110SA1-2CB-02 | TRALEE 110SA1-2CB | bar: Week 37 Th 10
TO-26-TRL-CAP2-04 | TRALEE CAP2 | bar: Week 37 Th 10
TO-26-TRL-T142-02 | TRALEE T142 | bar: Week 37 Th 10
TO-26-GGO-T2001-02 | GLANAGOW T2001 | bar: Su 30 to Week 37 Mo 7
TO-26-BVK-220K2-03 | BALLYVOUSKILL 220K2 | bar: Week 37 Th 10
TO-26-KNY-SAL-1-01 | KNOCKRANNY SALTHILL | bar: Week 37 Th 10 to Week 37 Mo 14
TO-26-SAL-110SA1-2CB-01 | SALTHILL 110SA1-2CB | bar: Week 37 Th 10 to Week 37 Mo 14
TO-26-SAL-T102-01 | SALTHILL T102 | bar: Week 37 Th 10 to Week 37 Mo 14
TO-26-110 kV A1 @ LSN-01 | LISHEEN 110 kV A1 | bar: Su 30 to Week 37 Mo 7
TO-26-LSN-110SA1-2-03 | LISHEEN 110SA1-2 | bar: Su 30 to Week 37 Mo 7
TO-26-LSN-110SA2-4-03 | LISHEEN 110SA2-4 | bar: Su 30 to Week 37 Mo 7
TO-26-LSN-T122-03 | LISHEEN T122 | bar: Su 30 to Week 37 Mo 7
TO-26-LSN-T131-03 | LISHEEN T131 | bar: Su 30 to Week 37 Mo 7
TO-26-LSN-T142-03 | LISHEEN T142 | bar: Su 30 to Week 37 Mo 7
TO-26-LSN-THU-1-03 | LISHEEN THURLES | bar: Su 30 to Week 37 Mo 7
TO-26-KLN-110K1-2-01 | KILLONAN 110K1-2 | bar: Week 37 Th 10
TO-26-AGL-SH-1-02 | AGANNYGAL SHANNONBRIDGE | bar: Su 30 to Week 37 Mo 7; Week 37 Th 10 to Week 37 Fr 11
TO-26-220 kV B1 @ CSH-01 | CASHLA 220 kV B1 | bar: Su 30 to Week 37 Mo 7; Week 37 Th 10 to Week 37 Fr 11
TO-26-110 kV A2 @ SH-05 | SHANNONBRIDGE 110 kV A2 | bar: Su 30 to Week 37 Mo 7; Week 37 Th 10 to Week 37 Fr 11
TO-26-110 kV B2 @ SH-05 | SHANNONBRIDGE 110 kV B2 | bar: Su 30 to Week 37 Mo 7; Week 37 Th 10 to Week 37 Fr 11
Outages spanning Weeks 36-37
OUTAGE ID | PLANT | Week 36 Mo 31: Week 36; Week 37 Mo 7: Week 37
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
TO-26-AA GIS-T103-02 | ARDNACRUSHA GIS T103
TO-26-ATH-M/CAP1-03 | ATHLONE M/CAP1
TO-26-ATY-PLS-1-01 | ATHY PORTLAOISE
TO-26-BRT-T222-05 | BRACETOWN T222
TO-26-CLW-KLS-2-01 | CARLOW KELLIS 2
TO-26-CD-KBY-1-03 | CARRIGADROHID KILBARRY
TO-26-CBT-INC-1-02 | CASTLEBAGOT INCHICORE 1
TO-26-CBR-SVC-01 | CASTLEBAR SVC
TO-26-CBR-SVC-02
TO-26-CTN-KLN-1-01 | CAUTEEN KILLONAN
TO-26-DND-T121-01 | DARNDALE T121
TO-26-DRY-LOU-1-01 | DRYBRIDGE LOUTH
TO-26-DRY-T141-01 | DRYBRIDGE T141
TO-26-DSN-400K1-2-04 | DUNSTOWN 400K1-2
TO-26-DSN-MP GIS-1-02 | DUNSTOWN MONEYPOINT GIS
TO-26-DSN-MP GIS-1-10
Report covers outages commencing/returning/spanning the period: 31/08/2026 - 13/09/2026
Outages spanning Weeks 36-37
OUTAGE ID | PLANT | Week 36 Mo 31: Week 36; Week 37 Mo 7: Week 37
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
TO-26-DSN-T4201-03 | DUNSTOWN T4201
TO-26-DSN-T4202-01 | DUNSTOWN T4202
TO-26-FIN-FIN GIS-2-01 | FINGLAS FINGLAS GIS 2
TO-26-FIN-SHL-1-02 | FINGLAS SHELLYBANKS
TO-26-FIN-T2104-01 | FINGLAS T2104
TO-26-220 kV A2 @ FLA-06 | FLAGFORD 220 kV A2
TO-26-220 kV B2 @ FLA-06 | FLAGFORD 220 kV B2
TO-26-FLA-LOU-1-01 | FLAGFORD LOUTH
TO-26-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-26-GI GIS-220SA1-2CB-02 | GREAT ISLAND GIS 220SA1-2CB
TO-26-GI-T141-01 | GREAT ISLAND T141
TO-26-INC-220K10-01 | INCHICORE 220K10
TO-26-INC-SA6-8CB-03 | INCHICORE 220SA6-8CB
TO-26-INC-SA8-10CB-01 | INCHICORE 220SA8-10CB
TO-26-INC-SB6-8CB-03 | INCHICORE 220SB6-8CB
TO-26-INC-SB8-10CB-01 | INCHICORE 220SB8-10CB
TO-26-INC-PB-2-01 | INCHICORE POOLBEG 2
TO-26-110 kV A1 @ KBY-02 | KILBARRY 110 kV A1
TO-26-KBY-KRA-2-03 | KILBARRY KNOCKRAHA 2
TO-26-KKY-CAP2-03 | KILKENNY CAP2
TO-26-KLN-SNG-1-01 | KILLONAN SINGLAND
TO-26-220 kV A4 @ KRA-01 | KNOCKRAHA 220 kV A4
TO-26-220 kV B4 @ KRA-01 | KNOCKRAHA 220 kV B4
TO-26-KRA-220K4-01 | KNOCKRAHA 220K4
TO-26-KRA-220SA2-4CB-03 | KNOCKRAHA 220SA2-4CB
TO-26-KRA-220SB2-4CB-03 | KNOCKRAHA 220SB2-4CB
TO-26-LET-SVC-02 | LETTERKENNY SVC
TO-26-110 kV A1 @ LOU-01 | LOUTH 110 kV A1
TO-26-110 kV B1 @ LOU-01 | LOUTH 110 kV B1
TO-26-220 kV A2 @ LOU-10 | LOUTH 220 kV A2
TO-26-220 kV B2 @ LOU-10 | LOUTH 220 kV B2
TO-26-MR-T107-01 | MARINA T107
TO-26-MP GIS-PRO-1-01 | MONEYPOINT GIS PROSPECT
TO-26-NAV-M/CAP1-01 | NAVAN M/CAP1
TO-26-NEW-T141-04 | NEWBRIDGE T141
TO-26-PB-R2001-03 | POOLBEG R2001
TO-26-PB-R2001-02
TO-26-110 kV A1 @ PLS-02 | PORTLAOISE 110 kV A1
TO-26-110 kV B1 @ PLS-02 | PORTLAOISE 110 kV B1
TO-26-TB-T2003-01 | TARBERT T2003
TO-26-TAW-T1/T2-01 | TAWNAGHMORE T1/T2
TO-26-TAW-T3-02 | TAWNAGHMORE T3
TO-26-TRL-CAP2-01 | TRALEE CAP2
TO-26-WEX-CAP4-06 | WEXFORD CAP4