## Wks 38 - 39
Report covers outages commencing/returning/spanning the period: 14/09/2026 - 27/09/2026
Outages commencing/returning in Week 38
OUTAGE ID | PLANT |  | Week 38 | [6 empty] | Week 39
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
TO-26-ISH-SHL-1-03 | IRISHTOWN SHELLYBANKS | bar: Week 38 Mo 14
TO-26-220 kV A2 @ FLA-04 | FLAGFORD 220 kV A2 | bar: Week 38 Mo 14 to Week 38 Tu 15
TO-26-220 kV B2 @ FLA-04 | FLAGFORD 220 kV B2 | bar: Week 38 Mo 14 to Week 38 Tu 15
TO-26-FLA-T2102-01 | FLAGFORD T2102 | bar: Week 38 Mo 14 to Week 38 Tu 15
TO-26-ROP-T131-02 | ROSSPILE T131 | bar: Week 38 Mo 14 to Week 38 Tu 15
TO-26-UGL-T131-01 | UGGOOL T131 | bar: Week 38 Mo 14 to Week 38 Tu 15
TO-26-UGL-T132-01 | UGGOOL T132 | bar: Week 38 Mo 14 to Week 38 Tu 15
TO-26-UGL-T134-01 | UGGOOL T134 | bar: Week 38 Mo 14 to Week 38 Tu 15
TO-26-MUL-CAP2-02 | MULLINGAR CAP2 | bar: Week 38 Mo 14 to Week 38 Tu 15
TO-26-220 kV A1/A2 @ PB-03 | POOLBEG 220 kV A1/A2 | bar: Week 38 Mo 14 to Week 38 Tu 15
TO-26-110 kV A1 @ AA GIS-02 | ARDNACRUSHA GIS 110 kV A1 | bar: Week 38 Mo 14 to Week 38 Tu 15; Week 38 Sa 19 to Week 39 Tu 22
TO-26-110 kV B1 @ AA GIS-02 | ARDNACRUSHA GIS 110 kV B1 | bar: Week 38 Mo 14 to Week 38 Tu 15; Week 38 Sa 19 to Week 39 Tu 22
TO-26-AA GIS-110SA1-2CB-03 | ARDNACRUSHA GIS 110SA1-2CB | bar: Week 38 Mo 14 to Week 38 Tu 15; Week 38 Sa 19 to Week 39 Tu 22
TO-26-AA GIS-110SA1-3CB-03 | ARDNACRUSHA GIS 110SA1-3CB | bar: Week 38 Mo 14 to Week 38 Tu 15; Week 38 Sa 19 to Week 39 Tu 22
TO-26-AA GIS-110SB1-2CB-03 | ARDNACRUSHA GIS 110SB1-2CB | bar: Week 38 Mo 14 to Week 38 Tu 15; Week 38 Sa 19 to Week 39 Tu 22
TO-26-AA GIS-110SB1-3CB-04 | ARDNACRUSHA GIS 110SB1-3CB | bar: Week 38 Mo 14 to Week 38 Tu 15; Week 38 Sa 19 to Week 39 Tu 22
TO-26-AA GIS-T101-01 | ARDNACRUSHA GIS T101 | bar: Week 38 Mo 14 to Week 38 Tu 15; Week 38 Sa 19 to Week 39 Tu 22
TO-26-CHA-110SA1-2CB-01 | CHARLEVILLE 110SA1-2CB | bar: Week 38 Mo 14 to Week 38 Tu 15; Week 38 Sa 19 to Week 39 We 23
TO-26-CHA-MAL-1-05 | CHARLEVILLE MALLOW | bar: Week 38 Mo 14 to Week 38 Tu 15; Week 38 Sa 19 to Week 39 We 23
TO-26-CHA-T142-01 | CHARLEVILLE T142 | bar: Week 38 Mo 14 to Week 38 Tu 15; Week 38 Sa 19 to Week 39 We 23
TO-26-BAN-T141-01 | BANDON T141 | bar: Week 38 Mo 14 to Week 38 Tu 15; Week 38 Sa 19 to Week 39 Fr 25
TO-26-BRT-CLE-2-01 | BRACETOWN CLONEE 2 | bar: Week 38 Mo 14 to Week 38 Tu 15; Week 38 Sa 19 to Week 39 Fr 25
TO-26-110 kV B1 @ LLA-02 | LENALEA 110 kV B1 | bar: Week 38 Mo 14 to Week 38 Tu 15; Week 38 Sa 19 to Week 39 Fr 25
TO-26-LLA-110K1-04 | LENALEA 110K1 | bar: Week 38 Mo 14 to Week 38 Tu 15; Week 38 Sa 19 to Week 39 Fr 25
TO-26-GI-WAT-1-04 | GREAT ISLAND WATERFORD 1 | bar: Week 38 Mo 14 to Week 38 Tu 15; Week 38 Sa 19 to Week 39 Sa 26
TO-26-110 kV B1 @ KBY-02 | KILBARRY 110 kV B1 | bar: Week 38 Mo 14 to Week 38 Tu 15; Week 38 Sa 19 to Week 39 Sa 26
TO-26-DFR-T122-10 | DUNFIRTH T122 | bar: Week 38 Mo 14 to Week 38 Tu 15; Week 38 Sa 19 to Week 39 Mo 28
TO-26-DFR,T-DFR-1-11 | DUNFIRTH tee DUNFIRTH | bar: Week 38 Mo 14 to Week 38 Tu 15; Week 38 Sa 19 to Week 39 Mo 28
TO-26-DFR,T-KIN-1-11 | DUNFIRTH tee KINNEGAD | bar: Week 38 Mo 14 to Week 38 Tu 15; Week 38 Sa 19 to Week 39 Mo 28
TO-26-DFR,T-RNW-1-11 | DUNFIRTH tee RINAWADE | bar: Week 38 Mo 14 to Week 38 Tu 15; Week 38 Sa 19 to Week 39 Mo 28
TO-26-110 kV A1 @ KBY-03 | KILBARRY 110 kV A1 | bar: Week 38 Mo 14 to Week 38 Tu 15; Week 38 Sa 19 to Week 39 Mo 28
TO-26-ISH-T2001-01 | IRISHTOWN T2001 | bar: Su 13 to Week 38 Mo 14
TO-26-110 kV A1 @ KBY-02 | KILBARRY 110 kV A1 | bar: Su 13 to Week 38 Mo 14
TO-26-CRU-T224-02 | CRUISERATH T224 | bar: Week 38 Tu 15
TO-26-KNY-SAL-1-01 | KNOCKRANNY SALTHILL | bar: Week 38 Tu 15; Week 38 Sa 19 to Week 39 Th 24
TO-26-SAL-110SA1-2CB-01 | SALTHILL 110SA1-2CB | bar: Week 38 Tu 15; Week 38 Sa 19 to Week 39 Th 24
TO-26-SAL-T102-01 | SALTHILL T102 | bar: Week 38 Tu 15; Week 38 Sa 19 to Week 39 Th 24
TO-26-220 kV A1/A2 @ LOU-02 | LOUTH 220 kV A1/A2
TO-26-220 kV A1 @ FLA-03 | FLAGFORD 220 kV A1
TO-26-220 kV A2 @ FLA-03 | FLAGFORD 220 kV A2
TO-26-220 kV B2 @ FLA-03 | FLAGFORD 220 kV B2
TO-26-FLA-220K1-2-01 | FLAGFORD 220K1-2
TO-26-LOU-220K1-2-05 | LOUTH 220K1-2
TO-26-LOU-T2103-07 | LOUTH T2103
TO-26-220 kV B1/B2 @ LOU-01 | LOUTH 220 kV B1/B2
TO-26-AD-T2011/12-01 | AGHADA T2011/12 | bar: Su 13 to Week 38 Tu 15
TO-26-CKM GIS-DSN-1-04 | CARRICKMINES GIS DUNSTOWN
TO-26-DSN-400K1-2-01 | DUNSTOWN 400K1-2
TO-26-110 kV A1 @ BLC-01 | BELCAMP 110 kV A1 | bar: Week 38 Sa 19
TO-26-110 kV B1 @ BLC-01 | BELCAMP 110 kV B1 | bar: Week 38 Sa 19
TO-26-BLC-110K1-01 | BELCAMP 110K1 | bar: Week 38 Sa 19
TO-26-BLC-110SA1-3CB-01 | BELCAMP 110SA1-3CB | bar: Week 38 Sa 19
TO-26-BLC-110SB1-3CB-01 | BELCAMP 110SB1-3CB | bar: Week 38 Sa 19
TO-26-AD-KRA-1-03 | AGHADA KNOCKRAHA 1 | bar: Su 13 to Week 38 Tu 15
TO-26-AD-KRA-2-03 | AGHADA KNOCKRAHA 2 | bar: Su 13 to Week 38 Tu 15
TO-26-AA GIS-T103-02 | ARDNACRUSHA GIS T103 | bar: Su 13 to Week 38 Tu 15
TO-26-BDA-T101-01 | BARODA T101 | bar: Su 13 to Week 38 Tu 15
TO-26-BRT-T224-02 | BRACETOWN T224 | bar: Su 13 to Week 38 Fr 18
TO-26-CF-SRA-1-04 | CATHALEENS FALL SRANANAGH 1 | bar: Su 13 to Week 38 Tu 15
TO-26-DSN-400K1-2-04 | DUNSTOWN 400K1-2 | bar: Su 13 to Week 38 Tu 15
TO-26-DSN-MP GIS-1-02 | DUNSTOWN MONEYPOINT GIS | bar: Su 13 to Week 38 Tu 15
Report covers outages commencing/returning/spanning the period: 14/09/2026 - 27/09/2026
Outages commencing/returning in Week 38
OUTAGE ID | PLANT | Week 38 Mo 14: Week 38; Week 39 Mo 21: Week 39
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
TO-26-DSN-T4202-01 | DUNSTOWN T4202 | bar: Su 13 to Week 38 Fr 18
TO-26-MP GIS-PRO-1-01 | MONEYPOINT GIS PROSPECT | bar: Su 13 to Week 38 Fr 18
TO-26-110 kV A2 @ CSH-05 | CASHLA 110 kV A2 | bar: Week 38 Sa 19 to Week 38 Su 20
TO-26-SOM-T142-01 | SOMERSET T142 | bar: Week 38 Sa 19 to Week 38 Su 20
TO-26-SOM,T-CSH-1-03 | SOMERSET tee CASHLA | bar: Week 38 Sa 19 to Week 38 Su 20
TO-26-SOM,T-SH-1-04 | SOMERSET tee SHANNONBRIDGE | bar: Week 38 Sa 19 to Week 38 Su 20
TO-26-SOM,T-SOM-1-01 | SOMERSET tee SOMERSET | bar: Week 38 Sa 19 to Week 38 Su 20
Outages commencing/returning in Week 39
OUTAGE ID | PLANT | Week 38 Mo 14: Week 38; Week 39 Mo 21: Week 39
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
TO-26-CF-CLO-1-01 | CATHALEENS FALL CLOGHER 1 | bar: Week 39 Mo 21
TO-26-OBE-110K1-01 | OLDBRIDGE 110K1 | bar: Week 39 Mo 21
TO-26-OBE-110K2-01 | OLDBRIDGE 110K2 | bar: Week 39 Mo 21
TO-26-OBE-110SA1-2CB-01 | OLDBRIDGE 110SA1-2CB | bar: Week 39 Mo 21
TO-26-OBE-110SB1-2CB-01 | OLDBRIDGE 110SB1-2CB | bar: Week 39 Mo 21
TO-26-CVW-KRA-1-01 | CASTLEVIEW KNOCKRAHA | bar: Week 39 Mo 21; Week 39 Fr 25
TO-26-CF-T103-01 | CATHALEENS FALL T103 | bar: Week 39 Mo 21; Week 39 Fr 25
TO-26-DND-T124-01 | DARNDALE T124 | bar: Week 39 Mo 21; Week 39 Fr 25
TO-26-220 kV A4 @ KRA-02 | KNOCKRAHA 220 kV A4 | bar: Week 39 Mo 21; Week 39 Fr 25
TO-26-220 kV B4 @ KRA-02 | KNOCKRAHA 220 kV B4 | bar: Week 39 Mo 21; Week 39 Fr 25
TO-26-KRA-220K4-02 | KNOCKRAHA 220K4 | bar: Week 39 Mo 21; Week 39 Fr 25
TO-26-KRA-220SA2-4CB-04 | KNOCKRAHA 220SA2-4CB | bar: Week 39 Mo 21; Week 39 Fr 25
TO-26-KRA-220SB2-4CB-04 | KNOCKRAHA 220SB2-4CB | bar: Week 39 Mo 21; Week 39 Fr 25
TO-26-KRA-WOH-1-01 | KNOCKRAHA WOODHOUSE | bar: Week 39 Mo 21; Week 39 Fr 25
TO-26-AD-T2014-05 | AGHADA T2014 | bar: Week 39 Mo 21; Week 39 Fr 25 to Week 39 Mo 28
TO-26-AUG-KPG-1-04 | AUGHINISH KILPADDOGE | bar: Week 39 Mo 21; Week 39 Fr 25 to Week 39 Mo 28
TO-26-AUG-KPG-1-02 | bar: Week 39 Mo 21; Week 39 Fr 25 to Week 39 Mo 28
TO-26-FIN GIS-SVN-1-01 | FINGLAS GIS STEPHENSTOWN | bar: Week 39 Mo 21; Week 39 Fr 25 to Week 39 Mo 28
TO-26-220 kV A6 @ INC-05 | INCHICORE 220 kV A6 | bar: Week 39 Mo 21; Week 39 Fr 25 to Week 39 Mo 28
TO-26-220 kV B6 @ INC-05 | INCHICORE 220 kV B6 | bar: Week 39 Mo 21; Week 39 Fr 25 to Week 39 Mo 28
TO-26-INC-SA6-8CB-06 | INCHICORE 220SA6-8CB | bar: Week 39 Mo 21; Week 39 Fr 25 to Week 39 Mo 28
TO-26-INC-SB6-8CB-06 | INCHICORE 220SB6-8CB | bar: Week 39 Mo 21; Week 39 Fr 25 to Week 39 Mo 28
TO-26-MAY-RYB GIS-1-02 | MAYNOOTH RYEBROOK GIS | bar: Week 39 Mo 21; Week 39 Fr 25 to Week 39 Mo 28
TO-26-110 kV A1 @ RYB GIS-01 | RYEBROOK GIS 110 kV A1 | bar: Week 39 Mo 21; Week 39 Fr 25 to Week 39 Mo 28
TO-26-110 kV B1 @ RYB GIS-02 | RYEBROOK GIS 110 kV B1 | bar: Week 39 Mo 21; Week 39 Fr 25 to Week 39 Mo 28
TO-26-RYB GIS-110SA1-2CB-02 | RYEBROOK GIS 110SA1-2CB | bar: Week 39 Mo 21; Week 39 Fr 25 to Week 39 Mo 28
TO-26-RYB GIS-110SA1-3CB-01 | RYEBROOK GIS 110SA1-3CB | bar: Week 39 Mo 21; Week 39 Fr 25 to Week 39 Mo 28
TO-26-RYB GIS-110SB1-2CB-02 | RYEBROOK GIS 110SB1-2CB | bar: Week 39 Mo 21; Week 39 Fr 25 to Week 39 Mo 28
TO-26-RYB GIS-110SB1-3CB-01 | RYEBROOK GIS 110SB1-3CB | bar: Week 39 Mo 21; Week 39 Fr 25 to Week 39 Mo 28
TO-26-110 kV A1 @ SH-02 | SHANNONBRIDGE 110 kV A1 | bar: Week 39 Mo 21; Week 39 Fr 25 to Week 39 Mo 28
TO-26-110 kV A2 @ SH-03 | SHANNONBRIDGE 110 kV A2 | bar: Week 39 Mo 21; Week 39 Fr 25 to Week 39 Mo 28
TO-26-110 kV B1 @ SH-02 | SHANNONBRIDGE 110 kV B1 | bar: Week 39 Mo 21; Week 39 Fr 25 to Week 39 Mo 28
TO-26-110 kV B2 @ SH-03 | SHANNONBRIDGE 110 kV B2 | bar: Week 39 Mo 21; Week 39 Fr 25 to Week 39 Mo 28
TO-26-SH-110K1-2-02 | SHANNONBRIDGE 110K1-2 | bar: Week 39 Mo 21; Week 39 Fr 25 to Week 39 Mo 28
TO-26-GOR-LOU-1-02 | GORMAN LOUTH
TO-26-220 kV A2 @ LOU-04 | LOUTH 220 kV A2
TO-26-220 kV B2 @ LOU-04 | LOUTH 220 kV B2
TO-26-DRU-CAP2-01 | DRUMLINE CAP2 | bar: Week 39 Fr 25 to Week 39 Mo 28
TO-26-220 kV A2 @ FLA-06 | FLAGFORD 220 kV A2 | bar: Su 13 to Week 39 Mo 21
TO-26-220 kV B2 @ FLA-06 | FLAGFORD 220 kV B2 | bar: Su 13 to Week 39 Mo 21
TO-26-FLA-LOU-1-01 | FLAGFORD LOUTH | bar: Su 13 to Week 39 Mo 21
TO-26-220 kV A2 @ LOU-10 | LOUTH 220 kV A2 | bar: Su 13 to Week 39 Mo 21
TO-26-220 kV B2 @ LOU-10 | LOUTH 220 kV B2 | bar: Su 13 to Week 39 Mo 21
TO-26-110 kV A1 @ PLS-01 | PORTLAOISE 110 kV A1 | bar: Week 39 Fr 25
TO-26-110 kV B1 @ PLS-01 | PORTLAOISE 110 kV B1 | bar: Week 39 Fr 25
TO-26-220 kV A1 @ CSH-02 | CASHLA 220 kV A1 | bar: Week 39 Fr 25 to Week 39 Mo 28
TO-26-220 kV B1 @ CSH-02 | CASHLA 220 kV B1 | bar: Week 39 Fr 25 to Week 39 Mo 28
TO-26-CSH-FLA-1-03 | CASHLA FLAGFORD | bar: Week 39 Fr 25 to Week 39 Mo 28
TO-26-220 kV A1 @ FLA-02 | FLAGFORD 220 kV A1 | bar: Week 39 Fr 25 to Week 39 Mo 28
Report covers outages commencing/returning/spanning the period: 14/09/2026 - 27/09/2026
Outages commencing/returning in Week 39
OUTAGE ID | PLANT | Week 38 Mo 14: Week 38; Week 39 Mo 21: Week 39
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
TO-26-220 kV B1 @ FLA-01 | FLAGFORD 220 kV B1
TO-26-GGO-RAF-1-01 | GLANAGOW RAFFEEN
TO-26-220 kV A1 @ RAF-02 | RAFFEEN 220 kV A1
TO-26-220 kV B1 @ RAF-02 | RAFFEEN 220 kV B1
TO-26-CBT-INC-1-02 | CASTLEBAGOT INCHICORE 1
TO-26-DOO-CAP1-04 | DOON CAP1
TO-26-MAY-TH-1-04 | MAYNOOTH TURLOUGH HILL
TO-26-110 kV A1 @ PLS-02 | PORTLAOISE 110 kV A1
TO-26-110 kV B1 @ PLS-02 | PORTLAOISE 110 kV B1
TO-26-SHL-D1/CB1-01 | SHELLYBANKS D1/CB1
TO-26-SHL-D1/CB2-06 | SHELLYBANKS D1/CB2
TO-26-FIN-SHL-1-02 | FINGLAS SHELLYBANKS
Outages spanning Weeks 38-39
OUTAGE ID | PLANT | Week 38 Mo 14: Week 38; Week 39 Mo 21: Week 39
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
TO-26-ATH-M/CAP1-03 | ATHLONE M/CAP1
TO-26-ATY-PLS-1-01 | ATHY PORTLAOISE
TO-26-CLW-KLS-2-01 | CARLOW KELLIS 2
TO-26-CD-KBY-1-03 | CARRIGADROHID KILBARRY
TO-26-CSH-SAL-1-01 | CASHLA SALTHILL
TO-26-CBR-SVC-02 | CASTLEBAR SVC
TO-26-CBR-SVC-01
TO-26-CTN-KLN-1-01 | CAUTEEN KILLONAN
TO-26-DND-T121-01 | DARNDALE T121
TO-26-DRY-LOU-1-01 | DRYBRIDGE LOUTH
TO-26-DRY-T141-01 | DRYBRIDGE T141
TO-26-DSN-MP GIS-1-10 | DUNSTOWN MONEYPOINT GIS
TO-26-DSN-T4201-03 | DUNSTOWN T4201
TO-26-FIN-FIN GIS-2-01 | FINGLAS FINGLAS GIS 2
TO-26-FIN-T2104-01 | FINGLAS T2104
TO-26-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-26-GI GIS-220SA1-2CB-02 | GREAT ISLAND GIS 220SA1-2CB
TO-26-GI-T141-01 | GREAT ISLAND T141
TO-26-INC-220K10-01 | INCHICORE 220K10
TO-26-INC-SA6-8CB-03 | INCHICORE 220SA6-8CB
TO-26-INC-SA8-10CB-01 | INCHICORE 220SA8-10CB
TO-26-INC-SB6-8CB-03 | INCHICORE 220SB6-8CB
TO-26-INC-SB8-10CB-01 | INCHICORE 220SB8-10CB
TO-26-INC-PB-2-01 | INCHICORE POOLBEG 2
TO-26-INC-T2101-01 | INCHICORE T2101
TO-26-KBY-KRA-2-03 | KILBARRY KNOCKRAHA 2
TO-26-KKY-CAP2-03 | KILKENNY CAP2
TO-26-KLN-SNG-1-01 | KILLONAN SINGLAND
TO-26-220 kV A4 @ KRA-01 | KNOCKRAHA 220 kV A4
TO-26-220 kV B4 @ KRA-01 | KNOCKRAHA 220 kV B4
TO-26-KRA-220K4-01 | KNOCKRAHA 220K4
TO-26-KRA-220SA2-4CB-03 | KNOCKRAHA 220SA2-4CB
TO-26-KRA-220SB2-4CB-03 | KNOCKRAHA 220SB2-4CB
TO-26-LET-M/CAP1-02 | LETTERKENNY M/CAP1
TO-26-LET-SVC-02 | LETTERKENNY SVC
TO-26-110 kV A1 @ LOU-01 | LOUTH 110 kV A1
TO-26-110 kV B1 @ LOU-01 | LOUTH 110 kV B1
TO-26-MR-T107-01 | MARINA T107
TO-26-NAV-M/CAP1-01 | NAVAN M/CAP1
TO-26-NEW-T141-04 | NEWBRIDGE T141
TO-26-PB-R2001-02 | POOLBEG R2001
TO-26-PB-R2001-03
TO-26-110 kV A2 @ RAF-01 | RAFFEEN 110 kV A2
TO-26-110 kV B2 @ RAF-01 | RAFFEEN 110 kV B2
Report covers outages commencing/returning/spanning the period: 14/09/2026 - 27/09/2026
Outages spanning Weeks 38-39
OUTAGE ID | PLANT | Week 38 Mo 14: Week 38; Week 39 Mo 21: Week 39
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
TO-26-220 kV A1 @ TB-02 | TARBERT 220 kV A1
TO-26-220 kV B1 @ TB-02 | TARBERT 220 kV B1
TO-26-TB-T2003-01 | TARBERT T2003
TO-26-TAW-T1/T2-01 | TAWNAGHMORE T1/T2
TO-26-TAW-T3-02 | TAWNAGHMORE T3
TO-26-TRL-CAP2-01 | TRALEE CAP2
TO-26-WEX-CAP4-06 | WEXFORD CAP4
TO-26-WOO-220K1-2-01 | WOODLAND 220K1-2