## Wks 4 - 5
Report covers outages commencing/returning/spanning the period: 19/01/2026 - 01/02/2026
Outages commencing/returning in Week 4
OUTAGE ID | PLANT |  | Week 4 | [6 empty] | Week 5
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2
TO-26-CDU-CRU-2-01 | CORDUFF CRUISERATH 2
TO-26-LYT-T132-01 | LYSAGHTSTOWN T132
TO-26-BAR-T141-03 | BARRYMORE T141 | bar: Week 4 We 21 to Week 4 Th 22
TO-26-BAR,T-BAR-1-03 | BARRYMORE tee BARRYMORE | bar: Week 4 We 21 to Week 4 Th 22
TO-26-BAR,T-CAH-1-03 | BARRYMORE tee CAHIR | bar: Week 4 We 21 to Week 4 Th 22
TO-26-BAR,T-KRA-1-03 | BARRYMORE tee KNOCKRAHA | bar: Week 4 We 21 to Week 4 Th 22
TO-26-220 kV A1 @ FIN-02 | FINGLAS 220 kV A1 | bar: Week 4 We 21 to Week 4 Th 22
TO-26-220 kV B1 @ FIN-02 | FINGLAS 220 kV B1 | bar: Week 4 We 21 to Week 4 Th 22
TO-26-FIN-220K1-02 | FINGLAS 220K1 | bar: Week 4 We 21 to Week 4 Th 22
TO-26-FIN-220SA1-2CB-07 | FINGLAS 220SA1-2CB | bar: Week 4 We 21 to Week 4 Th 22
TO-26-FIN-220SB1-2CB-06 | FINGLAS 220SB1-2CB | bar: Week 4 We 21 to Week 4 Th 22
TO-26-BLU-CDU-1-02 | BLUNDELSTOWN CORDUFF | bar: Week 4 We 21 to Week 4 Fr 23
TO-26-110 kV A2 @ CBT-01 | CASTLEBAGOT 110 kV A2 | bar: Week 4 We 21 to Week 4 Fr 23
TO-26-110 kV A4 @ CBT-02 | CASTLEBAGOT 110 kV A4 | bar: Week 4 We 21 to Week 4 Fr 23
TO-26-CBT-110K4-03 | CASTLEBAGOT 110K4 | bar: Week 4 We 21 to Week 4 Fr 23
TO-26-CBT-110SA2-4CB-02 | CASTLEBAGOT 110SA2-4CB | bar: Week 4 We 21 to Week 4 Fr 23
TO-26-110 kV A2 @ MR-01 | MARINA 110 kV A2 | bar: Week 4 We 21 to Week 5 Th 29
TO-26-110 kV B2 @ MR-01 | MARINA 110 kV B2 | bar: Week 4 We 21 to Week 5 Th 29
TO-26-MR-TBG-2-02 | MARINA TRABEG 2 | bar: Week 4 We 21 to Week 5 Th 29
TO-26-110 kV A2 @ TBG-01 | TRABEG 110 kV A2 | bar: Week 4 We 21 to Week 5 Th 29
TO-26-110 kV B2 @ TBG-01 | TRABEG 110 kV B2 | bar: Week 4 We 21 to Week 5 Th 29
TO-26-AGL-ENN-1-03 | AGANNYGAL ENNIS | bar: Week 4 We 21 to Week 5 Fr 30
TO-26-SH-T2102-02 | SHANNONBRIDGE T2102 | bar: Week 4 We 21 to Week 5 Mo 2
TO-26-BNK-110SA1-2CB-01 | BARNAKYLE 110SA1-2CB | bar: Su 18
TO-26-BNK-CBT-2-02 | BARNAKYLE CASTLEBAGOT 2 | bar: Su 18
TO-26-BNK-T122-01 | BARNAKYLE T122 | bar: Su 18
TO-26-CRU-220K1-01 | CRUISERATH 220K1
TO-26-NEW-PLS-1-01 | NEWBRIDGE PORTLAOISE | bar: Week 4 We 21 to Week 5 Mo 2
TO-26-220 kV A2 @ CRU-01 | CRUISERATH 220 kV A2 | bar: Su 18
TO-26-220 kV B2 @ CRU-01 | CRUISERATH 220 kV B2 | bar: Su 18
TO-26-CRU-220K2-02 | CRUISERATH 220K2 | bar: Su 18
TO-26-CRU-SA1-2CB-02 | CRUISERATH 220SA1-2CB | bar: Su 18
TO-26-CRU-SB1-2CB-02 | CRUISERATH 220SB1-2CB | bar: Su 18
TO-26-CRU-T224-01 | CRUISERATH T224 | bar: Su 18
TO-26-PRO-TB-1-02 | PROSPECT TARBERT | bar: Su 18
TO-26-220 kV A2 @ TB-01 | TARBERT 220 kV A2 | bar: Su 18
TO-26-220 kV B2 @ TB-01 | TARBERT 220 kV B2 | bar: Su 18
TO-26-TTU-131-01 | TULLABEG T131 | bar: Su 18
TO-26-CRU-220K2-01 | CRUISERATH 220K2 | bar: Week 4 We 21
TO-26-KPG-TRL-1-01 | KILPADDOGE TRALEE 1 | bar: Week 4 We 21 to Week 4 Fr 23
TO-26-LIS-LSA-1-04 | LISDRUM LISLEA | bar: Su 18; Week 4 We 21
TO-26-110 kV A1 @ SNU-01 | SNUGBOROUGH 110 kV A1 | bar: Su 18; Week 4 We 21
TO-26-110 kV A2 @ SNU-01 | SNUGBOROUGH 110 kV A2 | bar: Su 18; Week 4 We 21
TO-26-110 kV B1 @ SNU-01 | SNUGBOROUGH 110 kV B1 | bar: Su 18; Week 4 We 21
TO-26-110 kV B2 @ SNU-01 | SNUGBOROUGH 110 kV B2 | bar: Su 18; Week 4 We 21
TO-26-SNU-110K1-01 | SNUGBOROUGH 110K1 | bar: Su 18; Week 4 We 21
TO-26-CRU-SA1-2CB-01 | CRUISERATH 220SA1-2CB | bar: Week 4 Th 22
TO-26-110 kV B1 @ CSH-04 | CASHLA 110 kV B1 | bar: Week 4 Th 22 to Week 4 Fr 23
TO-26-CRU-SB1-2CB-01 | CRUISERATH 220SB1-2CB | bar: Week 4 Fr 23
TO-26-PHT-PLS-1-02 | PHILIPSTOWN PORTLAOISE | bar: Week 4 Fr 23 to Week 4 Su 25
TO-26-CDU-FIN-2-03 | CORDUFF FINGLAS 2 | bar: Week 4 Fr 23 to Week 5 Mo 2
TO-26-220 kV A2 @ FIN-04 | FINGLAS 220 kV A2 | bar: Week 4 Fr 23 to Week 5 Mo 2
TO-26-220 kV B2 @ FIN-02 | FINGLAS 220 kV B2 | bar: Week 4 Fr 23 to Week 5 Mo 2
TO-26-FIN-220K2-04 | FINGLAS 220K2 | bar: Week 4 Fr 23 to Week 5 Mo 2
TO-26-FIN-220SA1-2CB-04 | FINGLAS 220SA1-2CB | bar: Week 4 Fr 23 to Week 5 Mo 2
TO-26-FIN-220SB1-2CB-03 | FINGLAS 220SB1-2CB | bar: Week 4 Fr 23 to Week 5 Mo 2
TO-26-LOU-AT1-01 | LOUTH AT1 | bar: Su 18; Week 4 We 21 to Week 4 Fr 23
TO-26-SNU-110K2-01 | SNUGBOROUGH 110K2 | bar: Su 18; Week 4 We 21 to Week 4 Fr 23
TO-26-SNU-110SA1-2CB-01 | SNUGBOROUGH 110SA1-2CB | bar: Su 18; Week 4 We 21 to Week 4 Fr 23
TO-26-SNU-110SB1-2CB-01 | SNUGBOROUGH 110SB1-2CB | bar: Su 18; Week 4 We 21 to Week 4 Fr 23
Report covers outages commencing/returning/spanning the period: 19/01/2026 - 01/02/2026
Outages commencing/returning in Week 5
OUTAGE ID | PLANT | Week 4 Mo 19: Week 4; Week 5 Mo 26: Week 5
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2
TO-26-110 kV B1 @ CSH-05 | CASHLA 110 kV B1 | bar: Week 5 Mo 26 to Week 5 Tu 27
TO-26-ARV-SKL-2-01 | ARVA SHANKILL 2 | bar: Week 5 Mo 26 to Week 5 We 28
TO-26-CSH-T2101-03 | CASHLA T2101 | bar: Week 5 Mo 26 to Week 5 Th 29
TO-26-110 kV B1 @ CBT-01 | CASTLEBAGOT 110 kV B1 | bar: Week 5 Mo 26 to Week 5 Fr 30
TO-26-110 kV B2 @ CBT-02 | CASTLEBAGOT 110 kV B2 | bar: Week 5 Mo 26 to Week 5 Fr 30
TO-26-CBT-110K1-02 | CASTLEBAGOT 110K1 | bar: Week 5 Mo 26 to Week 5 Fr 30
TO-26-CBT-110SB1-2CB-01 | CASTLEBAGOT 110SB1-2CB | bar: Week 5 Mo 26 to Week 5 Fr 30
TO-26-GI-110K1-2-01 | GREAT ISLAND 110K1-2 | bar: Week 5 Mo 26 to Week 5 Fr 30
TO-26-PB-R2002-01 | POOLBEG R2002 | bar: Week 5 Mo 26 to Week 5 Fr 30
TO-26-LIS-LOU-1-03 | LISDRUM LOUTH | bar: Week 5 Mo 26 to Week 5 Mo 2
TO-26-LOU-T2102-01 | LOUTH T2102 | bar: Week 5 Tu 27 to Week 5 Th 29
TO-26-OBE-110K1-01 | OLDBRIDGE 110K1 | bar: Week 5 Tu 27 to Week 5 Th 29
TO-26-OBE-110K2-01 | OLDBRIDGE 110K2 | bar: Week 5 Tu 27 to Week 5 Th 29
TO-26-OBE-110SA1-2CB-01 | OLDBRIDGE 110SA1-2CB | bar: Week 5 Tu 27 to Week 5 Th 29
TO-26-OBE-110SB1-2CB-01 | OLDBRIDGE 110SB1-2CB | bar: Week 5 Tu 27 to Week 5 Th 29
TO-26-110 kV A1 @ CSH-03 | CASHLA 110 kV A1 | bar: Week 5 We 28 to Week 5 Th 29
TO-26-CDU-110K1-3-01 | CORDUFF 110K1-3 | bar: Week 5 We 28 to Week 5 Th 29
Outages spanning Weeks 4-5
OUTAGE ID | PLANT | Week 4 Mo 19: Week 4; Week 5 Mo 26: Week 5
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2
TO-26-ATH-M/CAP1-03 | ATHLONE M/CAP1
TO-26-CBR-SVC-01 | CASTLEBAR SVC
TO-26-DND-T121-01 | DARNDALE T121
TO-26-DEN-T132-01 | DEENES T132
TO-26-220 kV A2 @ FLA-01 | FLAGFORD 220 kV A2
TO-26-220 kV B2 @ FLA-01 | FLAGFORD 220 kV B2
TO-26-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-26-GI GIS-220SA1-2CB-02 | GREAT ISLAND GIS 220SA1-2CB
TO-26-GI-T141-01 | GREAT ISLAND T141
TO-26-KLN-T2102-01 | KILLONAN T2102
TO-26-220 kV A2 @ LOU-01 | LOUTH 220 kV A2
TO-26-220 kV B2 @ LOU-01 | LOUTH 220 kV B2
TO-26-MR-T107-01 | MARINA T107
TO-26-MUL-CAP2-01 | MULLINGAR CAP2
TO-26-PB-R2001-03 | POOLBEG R2001
TO-26-SKL-M/CAP2-01 | SHANKILL M/CAP2
TO-26-TB-T2003-01 | TARBERT T2003
TO-26-TRL-CAP2-01 | TRALEE CAP2