## Wks 8 - 9
Report covers outages commencing/returning/spanning the period: 16/02/2026 - 01/03/2026
Outages commencing/returning in Week 8
OUTAGE ID | PLANT |  | Week 8 | [6 empty] | Week 9
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2
TO-26-110 kV A2 @ LOU-04 | LOUTH 110 kV A2 | bar: Week 8 Mo 16 to Week 8 Tu 17
TO-26-RAF-110K1-2-02 | RAFFEEN 110K1-2 | bar: Week 8 Mo 16 to Week 8 Tu 17
TO-26-LOU-T2104-02 | LOUTH T2104 | bar: Week 8 Mo 16 to Week 8 Tu 17
TO-26-BK-CBR-1-01 | BELLACORICK CASTLEBAR | bar: Week 8 Mo 16 to Week 8 Tu 17; Week 8 Fr 20
TO-26-DSN-T4201-01 | DUNSTOWN T4201 | bar: Week 8 Mo 16 to Week 8 Tu 17; Week 8 Fr 20
TO-26-110 kV A2 @ CLG-01 | CLOGHRAN 110 kV A2 | bar: Week 8 Mo 16 to Week 8 Tu 17; Week 8 Fr 20 to Week 9 Fr 27
TO-26-110 kV B2 @ CLG-01 | CLOGHRAN 110 kV B2 | bar: Week 8 Mo 16 to Week 8 Tu 17; Week 8 Fr 20 to Week 9 Fr 27
TO-26-CLG-110K2-05 | CLOGHRAN 110K2 | bar: Week 8 Mo 16 to Week 8 Tu 17; Week 8 Fr 20 to Week 9 Fr 27
TO-26-CLG-110SA1-2CB-01 | CLOGHRAN 110SA1-2CB | bar: Week 8 Mo 16 to Week 8 Tu 17; Week 8 Fr 20 to Week 9 Fr 27
TO-26-CLG-110SB1-2CB-01 | CLOGHRAN 110SB1-2CB | bar: Week 8 Mo 16 to Week 8 Tu 17; Week 8 Fr 20 to Week 9 Fr 27
TO-26-CLG-CDU-1-01 | CLOGHRAN CORDUFF | bar: Week 8 Mo 16 to Week 8 Tu 17; Week 8 Fr 20 to Week 9 Fr 27
TO-26-110 kV A2 @ CDU-02 | CORDUFF 110 kV A2 | bar: Week 8 Mo 16 to Week 8 Tu 17; Week 8 Fr 20 to Week 9 Fr 27
TO-26-110 kV A4 @ CDU-03 | CORDUFF 110 kV A4 | bar: Week 8 Mo 16 to Week 8 Tu 17; Week 8 Fr 20 to Week 9 Fr 27
TO-26-110 kV B2 @ CDU-02 | CORDUFF 110 kV B2 | bar: Week 8 Mo 16 to Week 8 Tu 17; Week 8 Fr 20 to Week 9 Fr 27
TO-26-110 kV B4 @ CDU-02 | CORDUFF 110 kV B4 | bar: Week 8 Mo 16 to Week 8 Tu 17; Week 8 Fr 20 to Week 9 Fr 27
TO-26-CDU-110SA2-4CB-02 | CORDUFF 110SA2-4CB | bar: Week 8 Mo 16 to Week 8 Tu 17; Week 8 Fr 20 to Week 9 Fr 27
TO-26-CDU-110SB2-4CB-02 | CORDUFF 110SB2-4CB | bar: Week 8 Mo 16 to Week 8 Tu 17; Week 8 Fr 20 to Week 9 Fr 27
TO-26-CDU-FIN-1-01 | CORDUFF FINGLAS 1 | bar: Week 8 Mo 16 to Week 8 Tu 17; Week 8 Fr 20 to Week 9 Mo 2
TO-26-220 kV A1 @ FIN-01 | FINGLAS 220 kV A1 | bar: Week 8 Mo 16 to Week 8 Tu 17; Week 8 Fr 20 to Week 9 Mo 2
TO-26-220 kV B1 @ FIN-01 | FINGLAS 220 kV B1 | bar: Week 8 Mo 16 to Week 8 Tu 17; Week 8 Fr 20 to Week 9 Mo 2
TO-26-FIN-220K1-01 | FINGLAS 220K1 | bar: Week 8 Mo 16 to Week 8 Tu 17; Week 8 Fr 20 to Week 9 Mo 2
TO-26-FIN-220SA1-2CB-05 | FINGLAS 220SA1-2CB | bar: Week 8 Mo 16 to Week 8 Tu 17; Week 8 Fr 20 to Week 9 Mo 2
TO-26-FIN-220SB1-2CB-02 | FINGLAS 220SB1-2CB | bar: Week 8 Mo 16 to Week 8 Tu 17; Week 8 Fr 20 to Week 9 Mo 2
TO-26-110 kV A1 @ GLN-01 | GALLANSTOWN 110 kV A1 | bar: Week 8 Mo 16 to Week 8 Tu 17; Week 8 Fr 20 to Week 9 Mo 2
TO-26-110 kV B1 @ GLN-01 | GALLANSTOWN 110 kV B1 | bar: Week 8 Mo 16 to Week 8 Tu 17; Week 8 Fr 20 to Week 9 Mo 2
TO-26-GLN-PLA-1-01 | GALLANSTOWN PLATIN | bar: Week 8 Mo 16 to Week 8 Tu 17; Week 8 Fr 20 to Week 9 Mo 2
TO-26-GAR-PLA-1-02 | GARBALLAGH PLATIN | bar: Week 8 Mo 16 to Week 8 Tu 17; Week 8 Fr 20 to Week 9 Mo 2
TO-26-PLA-110SA1-02 | PLATIN 110SA1 | bar: Week 8 Mo 16 to Week 8 Tu 17; Week 8 Fr 20 to Week 9 Mo 2
TO-26-PLA-110SA2-02 | PLATIN 110SA2 | bar: Week 8 Mo 16 to Week 8 Tu 17; Week 8 Fr 20 to Week 9 Mo 2
TO-26-PLA-T105-01 | PLATIN T105 | bar: Week 8 Mo 16 to Week 8 Tu 17; Week 8 Fr 20 to Week 9 Mo 2
TO-26-AUN-T121-01 | AUNGIERSTOWN T121 | bar: Week 8 Tu 17
TO-26-110 kV A2 @ CKG-01 | CORKAGH 110 kV A2 | bar: Su 15 to Week 8 Tu 17
TO-26-110 kV B2 @ CKG-01 | CORKAGH 110 kV B2 | bar: Su 15 to Week 8 Tu 17
TO-26-CKG-110K2-01 | CORKAGH 110K2 | bar: Su 15 to Week 8 Tu 17
TO-26-CKG-110SA1-2CB-01 | CORKAGH 110SA1-2CB | bar: Su 15 to Week 8 Tu 17
TO-26-CKG-110SB1-2CB-01 | CORKAGH 110SB1-2CB | bar: Su 15 to Week 8 Tu 17
TO-26-LSN-T131-01 | LISHEEN T131 | bar: Su 15 to Week 8 Tu 17
TO-26-BYH-STATCOM-03 | BALLYNAHULLA STATCOM
TO-26-CBT-CKG-2-01 | CASTLEBAGOT CORKAGH 2
TO-26-110 kV A1 @ CKG-01 | CORKAGH 110 kV A1
TO-26-110 kV A2 @ CKG-02 | CORKAGH 110 kV A2
TO-26-110 kV B1 @ CKG-01 | CORKAGH 110 kV B1
TO-26-110 kV B2 @ CKG-02 | CORKAGH 110 kV B2
TO-26-CKG-110K2-03 | CORKAGH 110K2
TO-26-CKG-110SA1-2CB-02 | CORKAGH 110SA1-2CB
TO-26-CKG-110SA1-3CB-01 | CORKAGH 110SA1-3CB
TO-26-CKG-110SB1-2CB-02 | CORKAGH 110SB1-2CB
TO-26-CKG-110SB1-3CB-01 | CORKAGH 110SB1-3CB
TO-26-110 kV B2 @ LOU-04 | LOUTH 110 kV B2
TO-26-DJG-TRL-1-01 | DROMBEG TRALEE | bar: Su 15 to Week 8 Tu 17
TO-26-AUN-T123-01 | AUNGIERSTOWN T123 | bar: Week 8 Fr 20
TO-26-ROP-T131-01 | ROSSPILE T131 | bar: Week 8 Fr 20
TO-26-110 kV A2 @ KRA-03 | KNOCKRAHA 110 kV A2 | bar: Su 15 to Week 8 Tu 17; Week 8 Fr 20
TO-26-110 kV B2 @ KRA-03 | KNOCKRAHA 110 kV B2 | bar: Su 15 to Week 8 Tu 17; Week 8 Fr 20
TO-26-KRA-WOH-1-05 | KNOCKRAHA WOODHOUSE | bar: Su 15 to Week 8 Tu 17; Week 8 Fr 20
Outages commencing/returning in Week 9
OUTAGE ID | PLANT | Week 8 Mo 16: Week 8; Week 9 Mo 23: Week 9
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2
TO-26-AUN-CBT-1-01 | AUNGIERSTOWN CASTLEBAGOT | bar: Week 9 Mo 23 to Week 9 Tu 24
TO-26-KBY-KRA-1-01 | KILBARRY KNOCKRAHA 1 | bar: Week 9 Mo 23 to Week 9 Fr 27
TO-26-DDK-110SA1-01 | DUNDALK 110SA1 | bar: Week 9 Mo 23 to Week 9 Sa 28
Report covers outages commencing/returning/spanning the period: 16/02/2026 - 01/03/2026
Outages commencing/returning in Week 9
OUTAGE ID | PLANT | Week 8 Mo 16: Week 8; Week 9 Mo 23: Week 9
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2
TO-26-DDK-110SA2-01 | DUNDALK 110SA2
TO-26-DDK-MLN-1-01 | DUNDALK MULLAGHARLIN
TO-26-DDK-T141-01 | DUNDALK T141
TO-26-220 kV A2 @ ARK-01 | ARKLOW 220 kV A2
TO-26-220 kV B2 @ ARK-01 | ARKLOW 220 kV B2
TO-26-ARK-CKM GIS-1-01 | ARKLOW CARRICKMINES GIS
TO-26-BEG-CKM GIS-1-01 | BALLYBEG CARRICKMINES GIS
TO-26-220 kV A3 @ CKM GIS-01 | CARRICKMINES GIS 220 kV A3
TO-26-220 kV B3 @ CKM GIS-01 | CARRICKMINES GIS 220 kV B3
TO-26-CKM GIS-220K3-02 | CARRICKMINES GIS 220K3
TO-26-CKM GIS-220SA1-3CB-05 | CARRICKMINES GIS 220SA1-3CB
TO-26-CKM GIS-220SB1-3CB-03 | CARRICKMINES GIS 220SB1-3CB
TO-26-CTN-TIP-1-01 | CAUTEEN TIPPERARY
TO-26-CUL-RTH-1-01 | CULLENAGH RATHNASKILLOGE
TO-26-KLS-110K1-2-01 | KELLIS 110K1-2
TO-26-KLS-110K1-2-04
TO-26-PB-R2001-02 | POOLBEG R2001
TO-26-AUN-KSG-1-01 | AUNGIERSTOWN KISHOGE
TO-26-110 kV A1 @ PLS-05 | PORTLAOISE 110 kV A1
TO-26-220 kV A2 @ FLA-01 | FLAGFORD 220 kV A2
TO-26-220 kV B2 @ FLA-01 | FLAGFORD 220 kV B2
TO-26-LET-PST-04 | LETTERKENNY STRABANE PST
TO-26-220 kV A2 @ LOU-01 | LOUTH 220 kV A2
TO-26-220 kV B2 @ LOU-01 | LOUTH 220 kV B2
TO-26-AD-T2014-01 | AGHADA T2014
TO-26-AD-T2014-02 | bar: Su 15 to Week 9 Sa 28
TO-26-LET-SVC-02 | LETTERKENNY SVC | bar: Su 15 to Week 9 Sa 28
TO-26-ATH-M/CAP1-03 | ATHLONE M/CAP1
Outages spanning Weeks 8-9
OUTAGE ID | PLANT | Week 8 Mo 16: Week 8; Week 9 Mo 23: Week 9
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2
TO-26-BVK-T2102-04 | BALLYVOUSKILL T2102
TO-26-CBR-SVC-01 | CASTLEBAR SVC
TO-26-CLT-MAY-1-01 | CASTLELOST MAYNOOTH
TO-26-CLT-SH-1-02 | CASTLELOST SHANNONBRIDGE
TO-26-DND-T121-01 | DARNDALE T121
TO-26-DEN-T132-01 | DEENES T132
TO-26-DJG-110K2-01 | DROMBEG 110K2
TO-26-DMY-MAC-1-04 | DUNMANWAY MACROOM
TO-26-DSN-MP GIS-1-03 | DUNSTOWN MONEYPOINT GIS
TO-26-GGO-220K1-2-01 | GLANAGOW 220K1-2
TO-26-GI GIS-220SA1-2CB-02 | GREAT ISLAND GIS 220SA1-2CB
TO-26-GI-T141-01 | GREAT ISLAND T141
TO-26-220 kV A2 @ INC-01 | INCHICORE 220 kV A2
TO-26-220 kV B2 @ INC-01 | INCHICORE 220 kV B2
TO-26-INC-PB-2-02 | INCHICORE POOLBEG 2
TO-26-KLN-T2102-01 | KILLONAN T2102
TO-26-220 kV A4 @ KRA-01 | KNOCKRAHA 220 kV A4
TO-26-220 kV B4 @ KRA-01 | KNOCKRAHA 220 kV B4
TO-26-KRA-220K4-01 | KNOCKRAHA 220K4
TO-26-KRA-220SA2-4CB-03 | KNOCKRAHA 220SA2-4CB
TO-26-KRA-220SB2-4CB-03 | KNOCKRAHA 220SB2-4CB
TO-26-MR-T107-01 | MARINA T107
TO-26-MID-110SA1-01 | MIDLETON 110SA1
TO-26-MID-110SA2-01 | MIDLETON 110SA2
TO-26-MID-T102-01 | MIDLETON T102
TO-26-MID-WHI-1-01 | MIDLETON WHITEGATE
TO-26-NEW-PLS-1-01 | NEWBRIDGE PORTLAOISE
TO-26-220 kV A3 @ PB-01 | POOLBEG 220 kV A3
TO-26-220 kV B3 @ PB-01 | POOLBEG 220 kV B3
TO-26-PB-R2001-03 | POOLBEG R2001
TO-26-RAF-110K1-2-03 | RAFFEEN 110K1-2
Report covers outages commencing/returning/spanning the period: 16/02/2026 - 01/03/2026
Outages spanning Weeks 8-9
OUTAGE ID | PLANT | Week 8 Mo 16: Week 8; Week 9 Mo 23: Week 9
|  | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2
TO-26-SKL-M/CAP2-01 | SHANKILL M/CAP2
TO-26-SH-T2102-02 | SHANNONBRIDGE T2102
TO-26-220 kV A1 @ TB-01 | TARBERT 220 kV A1
TO-26-220 kV B1 @ TB-01 | TARBERT 220 kV B1
TO-26-TB-T2003-01 | TARBERT T2003
TO-26-TRL-CAP2-01 | TRALEE CAP2
TO-26-400 kV A1 @ WOO-02 | WOODLAND 400 kV A1
TO-26-400 kV B1 @ WOO-02 | WOODLAND 400 kV B1